## Sheet1
Customer | Site Name | Project Name | Go to Market Project # | Alpha ERP # | Gas Power WBS Element | FieldCore WBS Element | Manual language | Course language | Project Type | Project Manager | Course Number | Course Title | Technology | Duration (days) | # of Prep Days | # of Travel Days | Contractual # of Students | Group # | Unique Identifier | Class Name | Delivery Location | Delivery Country | Country TAS Status | Delivery City | Location | Start Weekday | Local Holidays | Room Number at Learning Center | Start Want Date | Latest Finish Date | Prep Start Latest | Prep Start Date | Prep End Date | Delivery Start Date | Delivery End Date | Reason for Start Date Variance | Agreed Start Date | Delivery Date | PM Notes | Please Resource | Imported Status | Imported Date | Calendar | Lead Instructor | Class Status | Project Year | What-If Project
SONELGAZ | SKIKDA | GEAT SPA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 2 | 2 | 0 | 8 |  | 26-1250 | 26-1250 - SONELGAZ - SKIKDA - GEAT SPA - Gas Turbine - LM2500 Borescope Inspection | Learning Center | KUWAIT | TAS-S | Kuwait | Kuwait Learning Center | Sunday |  |  | 2026-09-27 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-23 01:00 |  |  |  | 2026.0
SONELGAZ | SKIKDA | GEAT SPA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-AER10106 | Gas Turbine - LM2500 Level 2 Hot Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1249 | 26-1249 - SONELGAZ - SKIKDA - GEAT SPA - Gas Turbine - LM2500 Level 2 Hot Maintenance | Learning Center | KUWAIT | TAS-S | Kuwait | Kuwait Learning Center | Sunday |  |  | 2026-09-27 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-23 01:00 |  |  |  | 2026.0
SONELGAZ | SKIKDA | GEAT SPA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-AER10105 | Gas Turbine - LM2500 Level 2 Cold Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1248 | 26-1248 - SONELGAZ - SKIKDA - GEAT SPA - Gas Turbine - LM2500 Level 2 Cold Maintenance | Learning Center | KUWAIT | TAS-S | Kuwait | Kuwait Learning Center | Sunday |  |  | 2026-09-27 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-23 01:00 |  |  |  | 2026.0
SONELGAZ | SKIKDA | GEAT SPA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1247 | 26-1247 - SONELGAZ - SKIKDA - GEAT SPA - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | KUWAIT | TAS-S | Kuwait | Kuwait Learning Center | Sunday |  |  | 2026-09-27 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-23 01:00 |  |  |  | 2026.0
SONELGAZ | SKIKDA | GEAT SPA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-1246 | 26-1246 - SONELGAZ - SKIKDA - GEAT SPA - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | ALGERIA | TAS-S | Algiers | Customer Site | Sunday |  |  | 2026-09-27 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-23 01:00 |  |  |  | 2026.0
SONELGAZ | SKIKDA | GEAT SPA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13602 | Control System - Woodward Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-1245 | 26-1245 - SONELGAZ - SKIKDA - GEAT SPA - Control System - Woodward Operation, Maintenance & Troubleshooting | Customer Site | ALGERIA | TAS-S | Algiers | Customer Site | Sunday |  |  | 2026-09-27 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-23 01:00 |  |  |  | 2026.0
IEC | Orot Rabin | 9HA Tooling |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | Craft HA ITS Roll In-Out & TRACC Scan Alignment (ICGAS31602) | General | 10 |  | 0 | 8 |  | 27-489 | 27-489 - IEC - Orot Rabin - 9HA Tooling - Craft HA ITS Roll In-Out & TRACC Scan Alignment (ICGAS31602) | Learning Center | UNITED STATES | TAS-N | Huston | Houston Learning Center | Monday |  |  | 2027-02-22 | 2027-05-03 01:00 | 0 | [7 empty] | resourcing needs coordination with Andrew and Harry since internal instructors are involved | Yes | Imported | 2026-07-21 01:00 |  |  |  | 2027.0
IEC | Orot Rabin | 9HA Tooling |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | Craft Gas Turbine - Craft HA Combustion Training including EHS (ICGAS31601) | Gas Turbine | 15 |  | 0 | 8 |  | 07-1 | 07-1 - IEC - Orot Rabin - 9HA Tooling - Craft Gas Turbine - Craft HA Combustion Training including EHS (ICGAS31601) | Learning Center | UNITED STATES | TAS-N | Huston | Houston Learning Center | Monday |  |  | -618324.4935 | 2027-02-19 | 0 | [7 empty] | resourcing needs coordination with Andrew and Sherif since internal instructors are involved | Yes | Imported | 2026-07-21 01:00 |  |  |  | 207.0
TPC | Hsinta | 2026 |  |  |  |  | English | Mandarin Chinese | IB | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 26-1244 | 26-1244 - TPC - Hsinta - 2026 - Electrical - Electrical Control System (ECS) Training | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaoshiung | Customer Site | Monday |  |  | 2026-12-16 |  | 0 | [7 empty] | Placeholder for GEGA, please assign dates Dec 16 -18, 2026 | No | Imported | 2026-07-21 01:00 |  |  |  | 2026.0
Space Exploration Technologies Inc | SpaceX Anderson TX | TX 7E.03 Phased SC to CC : GTGs Tranche 1 |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-488 | 27-488 - Space Exploration Technologies Inc - SpaceX Anderson TX - TX 7E.03 Phased SC to CC : GTGs Tranche 1 - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Anderson TX | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | March 2027 dates | Yes | Imported | 2026-07-20 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | SpaceX Anderson TX | TX 7E.03 Phased SC to CC : GTGs Tranche 1 |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-487 | 27-487 - Space Exploration Technologies Inc - SpaceX Anderson TX - TX 7E.03 Phased SC to CC : GTGs Tranche 1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Anderson TX | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | March 2027 dates | Yes | Imported | 2026-07-20 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | SpaceX Anderson TX | TX 7E.03 Phased SC to CC : GTGs Tranche 1 |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-486 | 27-486 - Space Exploration Technologies Inc - SpaceX Anderson TX - TX 7E.03 Phased SC to CC : GTGs Tranche 1 - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Anderson TX | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | March 2027 dates | Yes | Imported | 2026-07-20 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | SpaceX Anderson TX | TX 7E.03 Phased SC to CC : GTGs Tranche 1 |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-485 | 27-485 - Space Exploration Technologies Inc - SpaceX Anderson TX - TX 7E.03 Phased SC to CC : GTGs Tranche 1 - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Anderson TX | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | March 2027 dates | Yes | Imported | 2026-07-20 01:00 |  |  |  | 2027.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 28-1097 | 28-1097 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 28-1096 | 28-1096 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-1095 | 28-1095 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS22101 | Gas Turbine - Operation E-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-1094 | 28-1094 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Gas Turbine - Operation E-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-1093 | 28-1093 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13412 | Control System - Mark VIe Distributed Control System Operation | Controls | 5 | 5 | 0 | 12 |  | 28-1092 | 28-1092 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Control System - Mark VIe Distributed Control System Operation | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-1091 | 28-1091 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 28-1090 | 28-1090 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 28-1089 | 28-1089 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 28-1088 | 28-1088 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Venture Global LNG | VGL Calcasieu Pass 2 | Expansion |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-1087 | 28-1087 - Venture Global LNG - VGL Calcasieu Pass 2 - Expansion - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Cameron Parish LA | Customer Site | Monday | Std US Hols |  | 2028-06-12 01:00 |  | 0 | [7 empty] | Start program in June 2028 | No | Imported | 2026-07-17 01:00 |  |  |  | 2028.0
Lafayette Utilities Systems | LUS Bonin Redevelopment Project | 1x7F.05 |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 28-1086 | 28-1086 - Lafayette Utilities Systems - LUS Bonin Redevelopment Project - 1x7F.05 - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Lafayette LA | Customer Site | Monday | Std US Hols |  | 2028-02-16 |  | 0 | [7 empty] | Start in Feb 2028October dates | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Lafayette Utilities Systems | LUS Bonin Redevelopment Project | 1x7F.05 |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-1085 | 28-1085 - Lafayette Utilities Systems - LUS Bonin Redevelopment Project - 1x7F.05 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Lafayette LA | Customer Site | Monday | Std US Hols |  | 2028-02-16 |  | 0 | [7 empty] | Start in Feb 2028October dates | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Lafayette Utilities Systems | LUS Bonin Redevelopment Project | 1x7F.05 |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1084 | 28-1084 - Lafayette Utilities Systems - LUS Bonin Redevelopment Project - 1x7F.05 - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Lafayette LA | Customer Site | Monday | Std US Hols |  | 2028-02-16 |  | 0 | [7 empty] | Start in Feb 2028October dates | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Lafayette Utilities Systems | LUS Bonin Redevelopment Project | 1x7F.05 |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1083 | 28-1083 - Lafayette Utilities Systems - LUS Bonin Redevelopment Project - 1x7F.05 - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Lafayette LA | Customer Site | Monday | Std US Hols |  | 2028-02-16 |  | 0 | [7 empty] | Start in Feb 2028October dates | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 | 2 | 28-1082 | 28-1082 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 | 2 | 28-1081 | 28-1081 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 | 2 | 28-1080 | 28-1080 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Gas Turbine - Maintenance - G2 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 | 2 | 28-1079 | 28-1079 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Gas Turbine - Operation - G2 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 | 1 | 28-1078 | 28-1078 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 | 1 | 28-1077 | 28-1077 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 | 1 | 28-1076 | 28-1076 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Gas Turbine - Maintenance - G1 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Dow Chemical Canada | Dow Path2Zero Project | 3x7E.03 Hydrogen CC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 | 1 | 28-1075 | 28-1075 - Dow Chemical Canada - Dow Path2Zero Project - 3x7E.03 Hydrogen CC - Gas Turbine - Operation - G1 | Customer Site | CANADA | TAS-N | AB | Customer Site | Monday | Std CA Hols |  | 2028-06-05 01:00 |  | 0 | [7 empty] | Start in June 2028 | No | Imported | 2026-07-16 01:00 |  |  |  | 2028.0
Space Exploration Technologies Inc | Bastrop Starlink | 5 x LM2500+G5 Xpress |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13603 | Control System - RX3i Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 27-484 | 27-484 - Space Exploration Technologies Inc - Bastrop Starlink - 5 x LM2500+G5 Xpress - Control System - RX3i Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Bastrop TX | Customer Site | Monday | Std US Hols |  | 2027-05-10 01:00 |  | 0 | [7 empty] | 1Q2027 | Yes | Imported | 2026-07-16 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | Bastrop Starlink | 5 x LM2500+G5 Xpress |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10602 | Gas Turbine - TM2500+ Aero Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 27-483 | 27-483 - Space Exploration Technologies Inc - Bastrop Starlink - 5 x LM2500+G5 Xpress - Gas Turbine - TM2500+ Aero Package Maintenance | Customer Site | UNITED STATES | TAS-N | Bastrop TX | Customer Site | Monday | Std US Hols |  | 2027-05-10 01:00 |  | 0 | [7 empty] | 1Q2027 | Yes | Imported | 2026-07-16 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | Bastrop Starlink | 5 x LM2500+G5 Xpress |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10601 | Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 27-482 | 27-482 - Space Exploration Technologies Inc - Bastrop Starlink - 5 x LM2500+G5 Xpress - Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Bastrop TX | Customer Site | Monday | Std US Hols |  | 2027-05-10 01:00 |  | 0 | [7 empty] | 1Q2027 | Yes | Imported | 2026-07-16 01:00 |  |  |  | 2027.0
Valara Holdings | Valara Holdings Data Center | 2 x LM6000PF1 - Phase Three - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10701 | Gas Turbine - Aero MKVIe Operations | Aeroderivative | 6 | 0 | 0 | 12 |  | 29-88 | 29-88 - Valara Holdings - Valara Holdings Data Center - 2 x LM6000PF1 - Phase Three - RA - Gas Turbine - Aero MKVIe Operations | Customer Site | UNITED STATES | TAS-N | SC | Customer Site | Monday | Std US Hols |  | 2029-04-09 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-14 01:00 |  |  |  | 2029.0
Valara Holdings | Valara Holdings Data Center | 2 x LM6000PF1 - Phase Three - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 29-87 | 29-87 - Valara Holdings - Valara Holdings Data Center - 2 x LM6000PF1 - Phase Three - RA - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | SC | Customer Site | Monday | Std US Hols |  | 2029-04-09 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-14 01:00 |  |  |  | 2029.0
Valara Holdings | Valara Holdings Data Center | 2 x LM6000PF1 - Phase Three - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 29-86 | 29-86 - Valara Holdings - Valara Holdings Data Center - 2 x LM6000PF1 - Phase Three - RA - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | SC | Customer Site | Monday | Std US Hols |  | 2029-04-09 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-14 01:00 |  |  |  | 2029.0
Valara Holdings | Valara Holdings Data Center | 2 x LM6000PF1 - Phase Three - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 29-85 | 29-85 - Valara Holdings - Valara Holdings Data Center - 2 x LM6000PF1 - Phase Three - RA - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | SC | Customer Site | Monday | Std US Hols |  | 2029-04-09 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-14 01:00 |  |  |  | 2029.0
NLH | Holyrood | 3xLM6000PC, Liquid Fuel, Sync Condensing |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 28-1074 | 28-1074 - NLH - Holyrood - 3xLM6000PC, Liquid Fuel, Sync Condensing - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | CANADA | TAS-N | NL | Customer Site | Monday | Std CA Hols |  | 2028-11-13 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
NLH | Holyrood | 3xLM6000PC, Liquid Fuel, Sync Condensing |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 28-1073 | 28-1073 - NLH - Holyrood - 3xLM6000PC, Liquid Fuel, Sync Condensing - Gas Turbine - LM6000 Package Maintenance | Customer Site | CANADA | TAS-N | NL | Customer Site | Monday | Std CA Hols |  | 2028-11-13 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
NLH | Holyrood | 3xLM6000PC, Liquid Fuel, Sync Condensing |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 28-1072 | 28-1072 - NLH - Holyrood - 3xLM6000PC, Liquid Fuel, Sync Condensing - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | CANADA | TAS-N | NL | Customer Site | Monday | Std CA Hols |  | 2028-11-13 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 28-1071 | 28-1071 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 20 | 0 | 0 | 12 |  | 28-1070 | 28-1070 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 28-1069 | 28-1069 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 28-1068 | 28-1068 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 5 | 28-1067 | 28-1067 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G5 | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 4 | 28-1066 | 28-1066 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G4 | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 3 | 28-1065 | 28-1065 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G3 | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 2 | 28-1064 | 28-1064 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G2 | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
Platte River Power Authority | Platte River Power Authority | 5x LM6000PF+ w/SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 1 | 28-1063 | 28-1063 - Platte River Power Authority - Platte River Power Authority - 5x LM6000PF+ w/SCR - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G1 | Customer Site | UNITED STATES | TAS-N | CO | Customer Site | Monday | Std US Hols |  | 2028-01-10 |  | 0 | [8 empty] | No | Imported | 2026-07-13 01:00 |  |  |  | 2028.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 | 3 | 29-84 | 29-84 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting - G3 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 | 3 | 29-83 | 29-83 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Gas Turbine - LM6000 Package Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 3 | 29-82 | 29-82 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G3 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 | 2 | 29-81 | 29-81 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting - G2 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 | 2 | 29-80 | 29-80 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Gas Turbine - LM6000 Package Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 2 | 29-79 | 29-79 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G2 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 | 1 | 29-78 | 29-78 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting - G1 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 | 1 | 29-77 | 29-77 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Gas Turbine - LM6000 Package Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
HECO | Waiau Unit 11 & 12 | 2 x LM6000PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 | 1 | 29-76 | 29-76 - HECO - Waiau Unit 11 & 12 - 2 x LM6000PC - Gas Turbine - LM6000 Aero Package Operation/Familiarization - G1 | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2029-03-01 |  | 0 | [7 empty] | 1Q2029 | No | Imported | 2026-07-13 01:00 |  |  |  | 2029.0
Space Exploration Technologies Inc | Southaven xAI | 3 x TM2500 Gen 8 (SAC) |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13603 | Control System - RX3i Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 27-481 | 27-481 - Space Exploration Technologies Inc - Southaven xAI - 3 x TM2500 Gen 8 (SAC) - Control System - RX3i Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | 1Q2027 | Yes | Imported | 2026-07-13 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | Southaven xAI | 3 x TM2500 Gen 8 (SAC) |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10602 | Gas Turbine - TM2500+ Aero Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 27-480 | 27-480 - Space Exploration Technologies Inc - Southaven xAI - 3 x TM2500 Gen 8 (SAC) - Gas Turbine - TM2500+ Aero Package Maintenance | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | 1Q2027 | Yes | Imported | 2026-07-13 01:00 |  |  |  | 2027.0
Space Exploration Technologies Inc | Southaven xAI | 3 x TM2500 Gen 8 (SAC) |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10601 | Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 27-479 | 27-479 - Space Exploration Technologies Inc - Southaven xAI - 3 x TM2500 Gen 8 (SAC) - Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | [7 empty] | 1Q2027 | Yes | Imported | 2026-07-13 01:00 |  |  |  | 2027.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 29-75 | 29-75 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 29-74 | 29-74 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 |  | 29-73 | 29-73 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 |  | 29-72 | 29-72 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 10 | 0 | 0 | 12 |  | 29-71 | 29-71 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Maintenance On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 10 | 0 | 0 | 12 |  | 29-70 | 29-70 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Maintenance On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 20 | 0 | 0 | 12 |  | 29-69 | 29-69 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Operation - On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 20 | 0 | 0 | 12 |  | 29-68 | 29-68 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Operation - On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 10 | 0 | 0 | 12 |  | 29-67 | 29-67 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 10 | 0 | 0 | 12 |  | 29-66 | 29-66 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 20 | 0 | 0 | 12 |  | 29-65 | 29-65 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 20 | 0 | 0 | 12 |  | 29-64 | 29-64 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 10 | 0 | 0 | 12 |  | 29-63 | 29-63 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 10 | 0 | 0 | 12 |  | 29-62 | 29-62 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 29-61 | 29-61 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 29-60 | 29-60 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 29-59 | 29-59 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 29-58 | 29-58 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 10 | 0 | 0 | 12 |  | 29-57 | 29-57 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Operation H-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 10 | 0 | 0 | 12 |  | 29-56 | 29-56 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Operation H-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 |  | 29-55 | 29-55 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 |  | 29-54 | 29-54 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2029-01-08 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2029.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-1062 | 28-1062 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-1061 | 28-1061 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-1060 | 28-1060 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-1059 | 28-1059 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1058 | 28-1058 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1057 | 28-1057 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1056 | 28-1056 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
LG&E | EW Brown 12 | 1x1 7HA.03 SS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1055 | 28-1055 - LG&E - EW Brown 12 - 1x1 7HA.03 SS EEP - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Mercer Co KY | Customer Site | Monday | Std US |  | 2028-09-25 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-09 01:00 |  |  |  | 2028.0
Volta River Authority | Kpone | GT11N2 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GEN10301 | Generator - Mechanical Systems & Components | Generator | 5 | 5 | 0 | 8 | 2 | 27-476 | 27-476 - Volta River Authority - Kpone - GT11N2 - Generator - Mechanical Systems & Components - G2 | Customer Site | GHANA | TAS-M | Tema | Customer Site | Monday |  |  | 2027-03-15 01:00 | 2027-03-19 01:00 | 0 | 2027-02-22 | 2027-02-26 | 2027-03-15 01:00 | 2027-03-19 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 | only capable instructor is Vito Franco | Yes | Created | 2026-07-09 01:00 | US Workweek and Holidays | Vito Franco | Tentative | 2027.0
Volta River Authority | Kpone | GT11N2 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 0 | 0 | 11 | 2 | 26-1223 | 26-1223 - Volta River Authority - Kpone - GT11N2 - Gas Turbine - Operation - G2 | Customer Site | GHANA | TAS-M | Tema | Customer Site | Monday |  |  | 2026-12-07 | 2026-12-18 | 0 |  |  | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 | BLC Borrowed instructor will be arranged by Anna | Yes | Created | 2026-07-09 01:00 | US Workweek and Holidays | Gas Turbine Instructor 1 | Tentative | 2026.0
Volta River Authority | Kpone | GT11N2 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 0 | 0 | 11 | 1 | 26-1222 | 26-1222 - Volta River Authority - Kpone - GT11N2 - Gas Turbine - Operation - G1 | Customer Site | GHANA | TAS-M | Tema | Customer Site | Monday |  |  | 2026-11-23 | 2026-12-03 | 0 |  |  | 2026-11-23 | 2026-12-04 |  | 2026-11-23 | 2026-11-23 | BLC Borrowed instructor will be arranged by Anna | Yes | Created | 2026-07-09 01:00 | US Workweek and Holidays | Gas Turbine Instructor 1 | Tentative | 2026.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 10 | 0 | 0 | 12 |  | 28-1054 | 28-1054 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 28-1053 | 28-1053 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-1052 | 28-1052 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1051 | 28-1051 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Gas Turbine - Operation H-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 |  | 28-1050 | 28-1050 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 12 |  | 28-1049 | 28-1049 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-1048 | 28-1048 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-1047 | 28-1047 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1046 | 28-1046 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Energy Forge One | Energy Forge - Units 6 & 7 | 2x1x1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1045 | 28-1045 - Energy Forge One - Energy Forge - Units 6 & 7 - 2x1x1 7HA.02 MS EEP - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | TX | Customer Site | Monday | Std US |  | 2028-08-13 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Xcel Energy | Lyon County Generating Station | 2x7F.05(H) SC w/Synch Condenser |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 28-1044 | 28-1044 - Xcel Energy - Lyon County Generating Station - 2x7F.05(H) SC w/Synch Condenser - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Garvin MN | Customer Site | Monday | Std US |  | 2028-04-10 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Xcel Energy | Lyon County Generating Station | 2x7F.05(H) SC w/Synch Condenser |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-1043 | 28-1043 - Xcel Energy - Lyon County Generating Station - 2x7F.05(H) SC w/Synch Condenser - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Garvin MN | Customer Site | Monday | Std US |  | 2028-04-10 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Xcel Energy | Lyon County Generating Station | 2x7F.05(H) SC w/Synch Condenser |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1042 | 28-1042 - Xcel Energy - Lyon County Generating Station - 2x7F.05(H) SC w/Synch Condenser - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Garvin MN | Customer Site | Monday | Std US |  | 2028-04-10 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Xcel Energy | Lyon County Generating Station | 2x7F.05(H) SC w/Synch Condenser |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1041 | 28-1041 - Xcel Energy - Lyon County Generating Station - 2x7F.05(H) SC w/Synch Condenser - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Garvin MN | Customer Site | Monday | Std US |  | 2028-04-10 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
Xcel Energy | Lyon County Generating Station | 2x7F.05(H) SC w/Synch Condenser |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1040 | 28-1040 - Xcel Energy - Lyon County Generating Station - 2x7F.05(H) SC w/Synch Condenser - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Garvin MN | Customer Site | Monday | Std US |  | 2028-04-10 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-08 01:00 |  |  |  | 2028.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 4 | 0 | 0 | 4 | 2 | 29-53 | 29-53 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Control System - Mark Vle Foundation Fieldbus - G2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 4 | 0 | 0 | 4 | 1 | 29-52 | 29-52 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Control System - Mark Vle Foundation Fieldbus - G1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 15 | 2 Week 2 | 29-51 | 29-51 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Control System - Mark VIe Maintenance (Extended) - G2 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G2 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 15 | 1 Week 2 | 29-50 | 29-50 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Control System - Mark VIe Maintenance (Extended) - G1 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G2 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 15 | 2 Week 1 | 29-49 | 29-49 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Control System - Mark VIe Maintenance (Extended) - G2 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G2 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 15 | 1 Week 1 | 29-48 | 29-48 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Control System - Mark VIe Maintenance (Extended) - G1 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G2 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 15 | 2 | 29-47 | 29-47 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 15 | 1 | 29-46 | 29-46 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 15 | 5 | 29-45 | 29-45 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Maintenance - G5 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 15 | 4 | 29-44 | 29-44 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Maintenance - G4 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 15 | 3 | 29-43 | 29-43 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 15 | 2 | 29-42 | 29-42 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 15 | 1 | 29-41 | 29-41 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 5 Week 2 | 29-40 | 29-40 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G5 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 4 Week 2 | 29-39 | 29-39 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G4 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 3 Week 2 | 29-38 | 29-38 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G3 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 2 Week 2 | 29-37 | 29-37 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G2 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 1 Week 2 | 29-36 | 29-36 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G1 Week 2 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 5 Week 1 | 29-35 | 29-35 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G5 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 4 Week 1 | 29-34 | 29-34 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G4 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 3 Week 1 | 29-33 | 29-33 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G3 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 2 Week 1 | 29-32 | 29-32 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G2 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
TECO | Big Bend 4 | Station Expansion_2x 7HA.02_SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 | 1 Week 1 | 29-31 | 29-31 - TECO - Big Bend 4 - Station Expansion_2x 7HA.02_SC - Gas Turbine - Operation - G1 Week 1 | Customer Site | UNITED STATES | TAS-N | Tampa FL | Customer Site | Monday | Std US Hols |  | 2029-10-08 01:00 |  | 0 | [7 empty] | 4x10s and non-standard sequencing for eight day courses,:G1 Week 1 thro G5 Week 1 ……….followed by G1 Week 2 etc, | Yes | Imported | 2026-07-08 01:00 |  |  |  | 2029.0
Calik / TURKMENENERGO | - | KIYANLY |  |  |  |  | Russian | Russian | NU | Anna Petrella | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 27-475 | 27-475 - Calik / TURKMENENERGO - - - KIYANLY - OTS Post-COD Refresh - CC Sim | Remote | TURKMENISTAN | TAS-N | Remote | Distance Learning | Monday |  |  | 2027-05-24 01:00 |  | 0 |  |  | 2027-05-24 01:00 | 2027-06-22 01:00 |  | 2027-05-24 01:00 | 2027-05-24 01:00 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required | Yes | Created | 2026-07-08 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2027.0
Calik / TURKMENENERGO | - | KIYANLY |  |  |  |  | Russian | Russian | NU | Anna Petrella | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 27-474 | 27-474 - Calik / TURKMENENERGO - - - KIYANLY - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday |  |  | 2027-01-11 |  | 0 |  |  | 2027-01-11 | 2027-01-20 |  | 2027-01-11 | 2027-01-11 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng | Yes | Created | 2026-07-08 01:00 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2027.0
Calik / TURKMENENERGO | - | KIYANLY |  |  |  |  | Russian | Russian | NU | Anna Petrella | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 26-1221 | 26-1221 - Calik / TURKMENENERGO - - - KIYANLY - OTS Simulator Development & Testing - CC Sim | Remote | TURKMENISTAN | TAS-N | Remote | Distance Learning | Monday |  |  | 2026-08-29 01:00 |  | 0 |  |  | 2026-08-29 01:00 | 2026-10-28 01:00 |  | 2026-08-29 01:00 | 2026-08-29 01:00 | Request Charles Wal. No additional prep required | Yes | Created | 2026-07-08 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2026.0
GB II New York LLC | BEC | 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON11902 | Control System - DLN 2.6+ Flex Combustor | Controls | 2 | 0 | 0 | 12 |  | 26-1220 | 26-1220 - GB II New York LLC - BEC - 7FA.04 - Control System - DLN 2.6+ Flex Combustor | Customer Site | UNITED STATES | TAS-N | Glenmont NY | Customer Site | Monday | Std US Hols |  | 2026-10-12 01:00 |  | 0 | [7 empty] | October dates | Yes | Imported | 2026-07-07 01:00 |  |  |  | 2026.0
NIPSCO | NIPSCO Schahfer Gas Peaker | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevENG | OTS Simulator Development & Testing-Engineering Scope (no resource) | Simulator | 0 | 0 | 0 | 0 |  | 27-473 | 27-473 - NIPSCO - NIPSCO Schahfer Gas Peaker - - - OTS Simulator Development & Testing-Engineering Scope (no resource) | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday | Std US Hols |  | 2027-06-29 01:00 |  | 0 | [8 empty] | No | Imported | 2026-07-02 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 10 | 0 | 0 | 12 | 2 | 27-472 | 27-472 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Control System - Mark VIe Distributed Control System Maintenance - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-09-20 01:00 | 2027-09-24 01:00 | 0 | [8 empty] | No | Imported | 2026-07-02 01:00 |  |  |  | 2027.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10307 | Gas Turbine - LM6000 Borescope Inspection | Aeroderivative | 4 | 0 | 0 | 8 |  | 27-471 | 27-471 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM6000 Borescope Inspection | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-07-01 01:00 |  |  |  | 2027.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 4 | 0 | 0 | 8 |  | 27-470 | 27-470 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM2500 Borescope Inspection | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-07-01 01:00 |  |  |  | 2027.0
GECOL | Benghazi North GT14 | - |  |  |  |  | English | English | IB | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 10 |  | 27-469 | 27-469 - GECOL - Benghazi North GT14 - - - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-02-08 | 2027-02-19 | 0 | 2026-11-23 | 2027-02-05 | 2027-02-08 | 2027-02-19 |  | 2027-02-08 | 2027-02-08 | capable instructor to deliver this Training is S. Kumar, prep 5 days at least 4 weeks prior to training start and 5 days right before training start | Yes | Created | 2026-06-28 01:00 | Birr Workweek and Holidays | Santosh Kumar | Tentative | 2027.0
GECOL | Benghazi North GT14 | - |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | Excitation - Combisystem Excitation & Static Starting Device Maintenance | Excitation | 10 | 0 | 0 | 10 |  | 27-468 | 27-468 - GECOL - Benghazi North GT14 - - - Excitation - Combisystem Excitation & Static Starting Device Maintenance | Learning Center | GERMANY | TAS-N | Berlin | Other Learning Center | Monday |  |  | 2027-01-18 | 2027-01-29 | 0 | [7 empty] | no action required from Nelsa, Anna will take care for resourcing with GE Converteam | No | Imported | 2026-07-01 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Generator Hands-On Mechanical Training Program | Generator | 35 | 0 | 0 | 12 |  | 28-1035 | 28-1035 - SONELGAZ - Oumache III - GEAT-01 - Generator Hands-On Mechanical Training Program | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2028-01-17 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Excitation Generator Controls Hands-On Training Program | Excitation | 30 | 0 | 0 | 12 |  | 28-1034 | 28-1034 - SONELGAZ - Oumache III - GEAT-01 - Excitation Generator Controls Hands-On Training Program | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2028-01-17 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | MKVIe Controls Hands-On Training Program | Controls | 32 | 0 | 0 | 12 |  | 28-1033 | 28-1033 - SONELGAZ - Oumache III - GEAT-01 - MKVIe Controls Hands-On Training Program | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2028-01-17 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Steam Turbine Hands-On Mechanical Training Program | Steam Turbine | 62 | 0 | 0 | 12 |  | 28-1032 | 28-1032 - SONELGAZ - Oumache III - GEAT-01 - Steam Turbine Hands-On Mechanical Training Program | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2028-01-17 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Gas Turbine Hands-On Mechanical Training Program | Gas Turbine | 62 | 0 | 0 | 12 |  | 27-467 | 27-467 - SONELGAZ - Oumache III - GEAT-01 - Gas Turbine Hands-On Mechanical Training Program | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2027-11-10 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2027.0
SONELGAZ | Hassi R'Mel1 | Hassi R'Mel1 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Gas Turbine Mechanical – Customer Training program | Gas Turbine | 35 | 0 | 0 | 12 |  | 27-466 | 27-466 - SONELGAZ - Hassi R'Mel1 - Hassi R'Mel1 - Gas Turbine Mechanical – Customer Training program | Learning Center | KUWAIT | TAS-S | Kuwait | Kuwait Learning Center | Sunday |  |  | 2026-10-01 01:00 |  | 0 | [7 empty] | the request is for Q4 in 2026; need of 2 instructors; Sherif to send details of schedule |  | Imported | 2026-06-30 01:00 |  |  |  | 2027.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 28-1031 | 28-1031 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 |  | 28-1030 | 28-1030 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1029 | 28-1029 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1028 | 28-1028 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 14 | 0 | 0 | 12 |  | 28-1027 | 28-1027 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 12 |  | 28-1026 | 28-1026 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Electrical - Electrical Control System (ECS) Training | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 28-1025 | 28-1025 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Control System - Mark VIe Maintenance (Extended) | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-1024 | 28-1024 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1023 | 28-1023 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Gas Turbine - Maintenance | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
ENEVA | Sergipe Expansion | 4x7F.05 SC EO |  |  |  |  | Portugese | Portugese | NU | Alejandra Saldana | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1022 | 28-1022 - ENEVA - Sergipe Expansion - 4x7F.05 SC EO - Gas Turbine - Operation | Customer Site | BRAZIL | TAS-M | Barra dos Coqueiros, Sergipe | Customer Site | Monday |  |  | 2028-03-12 |  | 0 | [8 empty] | No | Imported | 2026-06-30 01:00 |  |  |  | 2028.0
CFE | El Sauz | GT24 |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | Customer-Project Specific | Gas Turbine – Maintenance (GT24) | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-465 | 27-465 - CFE - El Sauz - GT24 - Gas Turbine – Maintenance (GT24) | Customer Site | MEXICO | TAS-M | Pedro Escobedo | Customer Site | Monday |  |  | 2027-10-11 01:00 |  | 0 | [8 empty] | Yes | Created | 2026-06-29 01:00 | US Workweek and Holidays |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Performance Test | Gas Turbine | 3 | 0 | 0 | 15 |  | 27-464 | 27-464 - SONELGAZ - Oumache III - GEAT-01 - Performance Test | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | BN 3500 System1 | Gas Turbine | 6 | 0 | 0 | 15 |  | 27-463 | 27-463 - SONELGAZ - Oumache III - GEAT-01 - BN 3500 System1 | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Commissioning Familiarization | Combined Cycle | 5 | 0 | 0 | 15 |  | 27-462 | 27-462 - SONELGAZ - Oumache III - GEAT-01 - Commissioning Familiarization | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-30 01:00 |  |  |  | 2027.0
SPS Berlin | - | - |  |  |  |  | German | German | IB | Anna Petrella | Customer-Project Specific | Blading Support incl room and equipment rental | Generator | 10 | 0 | 0 | 0 |  | 26-1217 | 26-1217 - SPS Berlin - - - - - Blading Support incl room and equipment rental | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-07-30 01:00 | 2026-06-30 01:00 | 0 |  |  | 2026-07-30 01:00 | 2026-08-12 01:00 |  | 2026-07-30 01:00 | 2026-07-30 01:00 |  | Yes | Created | 2026-06-30 01:00 | Birr Workweek and Holidays |  | Tentative | 2026.0
GP SCS | - | Migration Alspa to MarkVIe |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | Delivery - Legacy ALSTOM Control System to Mark VIe Upgrade - Option 2 | Controls | 10 | 0 | 0 | 12 |  | 26-1216 | 26-1216 - GP SCS - - - Migration Alspa to MarkVIe - Delivery - Legacy ALSTOM Control System to Mark VIe Upgrade - Option 2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-10-19 01:00 | 2026-10-30 01:00 | 0 | [7 empty] | Internal customer is fine with October dates, therefore as agreed in previous escalation meeting if internal customer agrees OE classes can be pulled | Yes | Imported | 2026-06-30 01:00 |  |  | Cancelled | 2026.0
GP SCS | - | Migration Alspa to MarkVIe |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | Delivery - Legacy ALSTOM Control System to Mark VIe Upgrade - Option 1 | Controls | 10 | 0 | 0 | 12 |  | 26-1215 | 26-1215 - GP SCS - - - Migration Alspa to MarkVIe - Delivery - Legacy ALSTOM Control System to Mark VIe Upgrade - Option 1 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-10-12 01:00 | 2026-10-23 01:00 | 0 | [7 empty] | Internal customer is fine with October dates, therefore as agreed in previous escalation meeting if internal customer agrees OE classes can be pulled | Yes | Imported | 2026-06-30 01:00 |  |  |  | 2026.0
ExxonMobil | ExxonMobil Low Carbon Data Center (LCDC) | 6X 6F03 Simple Cycle- RA |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 27-461 | 27-461 - ExxonMobil - ExxonMobil Low Carbon Data Center (LCDC) - 6X 6F03 Simple Cycle- RA - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US |  | 2027-06-07 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  | Cancelled | 2027.0
ExxonMobil | ExxonMobil Low Carbon Data Center (LCDC) | 6X 6F03 Simple Cycle- RA |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 27-460 | 27-460 - ExxonMobil - ExxonMobil Low Carbon Data Center (LCDC) - 6X 6F03 Simple Cycle- RA - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US |  | 2027-06-07 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  | Cancelled | 2027.0
ExxonMobil | ExxonMobil Low Carbon Data Center (LCDC) | 6X 6F03 Simple Cycle- RA |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 27-459 | 27-459 - ExxonMobil - ExxonMobil Low Carbon Data Center (LCDC) - 6X 6F03 Simple Cycle- RA - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US |  | 2027-06-07 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  | Cancelled | 2027.0
ExxonMobil | ExxonMobil Low Carbon Data Center (LCDC) | 6X 6F03 Simple Cycle- RA |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 27-458 | 27-458 - ExxonMobil - ExxonMobil Low Carbon Data Center (LCDC) - 6X 6F03 Simple Cycle- RA - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | MS | Customer Site | Monday | Std US |  | 2027-06-07 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  | Cancelled | 2027.0
Homer City | Homer City | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevENG | OTS Simulator Development & Testing-Engineering Scope (no resource) | Simulator | 0 | 0 | 0 | 15 |  | 27-457 | 27-457 - Homer City - Homer City - - - OTS Simulator Development & Testing-Engineering Scope (no resource) | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday | Std US Hols |  | 2027-11-01 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2027.0
LG&E | Mill Creek | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevENG | OTS Simulator Development & Testing-Engineering Scope (no resource) | Simulator | 0 | 0 | 0 | 15 |  | 26-1214 | 26-1214 - LG&E - Mill Creek - - - OTS Simulator Development & Testing-Engineering Scope (no resource) | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday | Std US Hols |  | 2026-01-01 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2026.0
Ameren | Castle Bluff | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevENG | OTS Simulator Development & Testing-Engineering Scope (no resource) | Simulator | 0 | 0 | 0 | 15 |  | 27-456 | 27-456 - Ameren - Castle Bluff - - - OTS Simulator Development & Testing-Engineering Scope (no resource) | Remote | UNITED STATES | TAS-N | St. Louis | Distance Learning | Monday | Std US Hols |  | 2027-01-01 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2027.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 10 | 0 | 0 | 12 |  | 28-1021 | 28-1021 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Balance of Plant - Operation (GE Integrated Systems) | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 12 |  | 28-1020 | 28-1020 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 |  | 28-1019 | 28-1019 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 28-1018 | 28-1018 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Control System - Mark VIe Maintenance (Extended) | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 10 | 0 | 0 | 12 |  | 28-1017 | 28-1017 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-1016 | 28-1016 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-1015 | 28-1015 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Steam Turbine - Maintenance | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-1014 | 28-1014 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Steam Turbine - Operation | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 28-1013 | 28-1013 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Gas Turbine - Maintenance | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GENERADORA FENIX | Tula I | 1X1 7HA.03 EEP CHUNG CHIA OPTION |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 28-1012 | 28-1012 - GENERADORA FENIX - Tula I - 1X1 7HA.03 EEP CHUNG CHIA OPTION - Gas Turbine - Operation | Customer Site | MEXICO | TAS-M | Tula de Allende | Customer Site | Monday |  |  | 2028-05-30 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2028.0
GEV UTE | Porto de Sergipe | 7HA.02 | IFF-008178-CC-101-TRX |  | IFF-008178-CC-101-TRX |  | English | English | IB | Alejandra Saldana | SIM-RemoteAccess | Remote-Hosted Simulator Access (no resource) | Simulator | 0 | 0 | 0 | 0 |  | 26-1212 | 26-1212 - GEV UTE - Porto de Sergipe - 7HA.02 - Remote-Hosted Simulator Access (no resource) | Remote | BRAZIL | TAS-N | NA | Distance Learning | Monday |  |  | 2026-07-20 01:00 |  | 0 | [8 empty] | No | Imported | 2026-06-29 01:00 |  |  |  | 2026.0
Ingredion | San Juan | LM2500 |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10102 | Gas Turbine - LM2500 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 27-455 | 27-455 - Ingredion - San Juan - LM2500 - Gas Turbine - LM2500 Package Maintenance | Customer Site | MEXICO | TAS-M | San Juan del Rio | Customer Site | Monday |  |  | 2027-02-08 |  | 0 | [7 empty] | This is the final annual training session required under the current contract for this site | Yes | Imported | 2026-06-29 01:00 |  |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 14 | 0 | 0 | 12 |  | 28-1011 | 28-1011 - SEC - Ghazlan - Expansion 1 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 12 |  | 28-1010 | 28-1010 - SEC - Ghazlan - Expansion 1 - Electrical - Electrical Control System (ECS) Training | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 10 | 0 | 0 | 12 |  | 28-1009 | 28-1009 - SEC - Ghazlan - Expansion 1 - Control System - Mark VIe Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-1008 | 28-1008 - SEC - Ghazlan - Expansion 1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-1007 | 28-1007 - SEC - Ghazlan - Expansion 1 - Steam Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-1006 | 28-1006 - SEC - Ghazlan - Expansion 1 - Steam Turbine - Operation | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 28-1005 | 28-1005 - SEC - Ghazlan - Expansion 1 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 |  | 28-1004 | 28-1004 - SEC - Ghazlan - Expansion 1 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-1003 | 28-1003 - SEC - Ghazlan - Expansion 1 - Steam Turbine - Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-1002 | 28-1002 - SEC - Ghazlan - Expansion 1 - Steam Turbine - Operation - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 14 | 0 | 0 | 12 |  | 28-1001 | 28-1001 - SEC - Ghazlan - Expansion 1 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 12 |  | 28-1000 | 28-1000 - SEC - Ghazlan - Expansion 1 - Electrical - Electrical Control System (ECS) Training | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 10 | 0 | 0 | 12 |  | 28-999 | 28-999 - SEC - Ghazlan - Expansion 1 - Control System - Mark VIe Maintenance | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 28-998 | 28-998 - SEC - Ghazlan - Expansion 1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 |  | 28-997 | 28-997 - SEC - Ghazlan - Expansion 1 - Steam Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 |  | 28-996 | 28-996 - SEC - Ghazlan - Expansion 1 - Steam Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2028-03-15 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2028.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 15 |  | 27-454 | 27-454 - SONELGAZ - Oumache III - GEAT-01 - Steam Turbine - Maintenance | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 15 |  | 27-453 | 27-453 - SONELGAZ - Oumache III - GEAT-01 - Steam Turbine - Operation | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-CCP10201 | Combined Cycle - Power Plant Familiarization | Combined Cycle | 10 | 0 | 0 | 15 |  | 27-452 | 27-452 - SONELGAZ - Oumache III - GEAT-01 - Combined Cycle - Power Plant Familiarization | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 15 |  | 27-451 | 27-451 - SONELGAZ - Oumache III - GEAT-01 - Control System - Mark VIe Maintenance (Extended) | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 15 |  | 27-450 | 27-450 - SONELGAZ - Oumache III - GEAT-01 - Excitation - EX2100e Operation & Maintenance | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 15 |  | 27-449 | 27-449 - SONELGAZ - Oumache III - GEAT-01 - Gas Turbine - Maintenance | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SONELGAZ | Oumache III | GEAT-01 |  |  |  |  | French | French | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 15 |  | 27-448 | 27-448 - SONELGAZ - Oumache III - GEAT-01 - Gas Turbine - Operation | Customer Site | ALGERIA | TAS-S | Oumache | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 27-447 | 27-447 - SEC - Ghazlan - Expansion 1 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-10-04 01:00 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | Birr Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 27-446 | 27-446 - SEC - Ghazlan - Expansion 1 - Electrical - Electrical Control System (ECS) Training | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-10-04 01:00 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | Birr Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-445 | 27-445 - SEC - Ghazlan - Expansion 1 - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-05-24 01:00 | 2027-06-04 01:00 | 2027-07-12 01:00 | 2027-07-23 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  |  | Created | 2026-06-27 01:00 | Birr Workweek and Holidays | Rafael Venancio | Resourcing In Progress | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-444 | 27-444 - SEC - Ghazlan - Expansion 1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-05-03 01:00 | 2027-05-10 01:00 | 2027-07-12 01:00 | 2027-07-19 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  |  | Created | 2026-06-25 01:00 | Birr Workweek and Holidays | Joe Mcandrews | Resourcing In Progress | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-443 | 27-443 - SEC - Ghazlan - Expansion 1 - Gas Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-06-14 01:00 | 2027-06-18 01:00 | 2027-07-12 01:00 | 2027-07-19 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  |  | Created | 2026-06-25 01:00 | Birr Workweek and Holidays | Tim Taylor | Resourcing In Progress | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-442 | 27-442 - SEC - Ghazlan - Expansion 1 - Gas Turbine - Operation | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-06-07 01:00 | 2027-06-18 01:00 | 2027-07-12 01:00 | 2027-07-23 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  |  | Created | 2026-06-26 01:00 | Birr Workweek and Holidays | Hichem Mesli | Resourcing In Progress | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 27-441 | 27-441 - SEC - Ghazlan - Expansion 1 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 |  | 27-440 | 27-440 - SEC - Ghazlan - Expansion 1 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-439 | 27-439 - SEC - Ghazlan - Expansion 1 - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-438 | 27-438 - SEC - Ghazlan - Expansion 1 - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 27-437 | 27-437 - SEC - Ghazlan - Expansion 1 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-436 | 27-436 - SEC - Ghazlan - Expansion 1 - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-435 | 27-435 - SEC - Ghazlan - Expansion 1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | [9 empty] | Created | 2026-06-27 01:00 | US Workweek and Holidays |  |  | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-434 | 27-434 - SEC - Ghazlan - Expansion 1 - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | 2027-09-07 01:00 | 2027-09-13 01:00 | 2027-11-14 | 2027-11-18 |  | 2027-11-14 | 2027-11-14 |  |  | Created | 2026-06-27 01:00 | US Workweek and Holidays | Hichem Mesli | Resourcing In Progress | 2027.0
SEC | Ghazlan | Expansion 1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-433 | 27-433 - SEC - Ghazlan - Expansion 1 - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-S | Ras Tanura | Customer Site | Sunday |  |  | 2027-11-14 |  | 0 | 2027-09-13 01:00 | 2027-09-24 01:00 | 2027-11-14 | 2027-11-25 |  | 2027-11-14 | 2027-11-14 |  |  | Created | 2026-06-24 01:00 | US Workweek and Holidays | Tim Taylor | Resourcing In Progress | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 27-432 | 27-432 - SEC - Qurayyah - Hajir2 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 |  | 27-431 | 27-431 - SEC - Qurayyah - Hajir2 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 10 | 0 | 0 | 12 |  | 27-430 | 27-430 - SEC - Qurayyah - Hajir2 - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 20 | 0 | 0 | 12 |  | 27-429 | 27-429 - SEC - Qurayyah - Hajir2 - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 14 | 0 | 0 | 12 |  | 27-428 | 27-428 - SEC - Qurayyah - Hajir2 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 12 |  | 27-427 | 27-427 - SEC - Qurayyah - Hajir2 - Electrical - Electrical Control System (ECS) Training | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 27-426 | 27-426 - SEC - Qurayyah - Hajir2 - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 27-425 | 27-425 - SEC - Qurayyah - Hajir2 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 27-424 | 27-424 - SEC - Qurayyah - Hajir2 - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir2 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 27-423 | 27-423 - SEC - Qurayyah - Hajir2 - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-05-16 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 |  | 27-422 | 27-422 - SEC - Qurayyah - Hajir1 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 |  | 27-421 | 27-421 - SEC - Qurayyah - Hajir1 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 10 | 0 | 0 | 12 |  | 27-420 | 27-420 - SEC - Qurayyah - Hajir1 - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 20 | 0 | 0 | 12 |  | 27-419 | 27-419 - SEC - Qurayyah - Hajir1 - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 14 | 0 | 0 | 12 |  | 27-418 | 27-418 - SEC - Qurayyah - Hajir1 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 12 |  | 27-417 | 27-417 - SEC - Qurayyah - Hajir1 - Electrical - Electrical Control System (ECS) Training | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 |  | 27-416 | 27-416 - SEC - Qurayyah - Hajir1 - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 |  | 27-415 | 27-415 - SEC - Qurayyah - Hajir1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 27-414 | 27-414 - SEC - Qurayyah - Hajir1 - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
SEC | Qurayyah | Hajir1 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 27-413 | 27-413 - SEC - Qurayyah - Hajir1 - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-S | Qurayyah | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | [9 empty] | Imported | 2026-06-28 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 10 | 0 | 0 | 12 | 1 | 28-995 | 28-995 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2028-02-14 | 2028-02-18 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 20 | 0 | 0 | 12 | 1 | 28-994 | 28-994 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Operation - On-the-Job Training (OJT) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2028-01-31 | 2028-02-11 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 10 | 0 | 0 | 12 | 1 | 28-993 | 28-993 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2028-01-24 | 2028-01-28 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 20 | 0 | 0 | 12 | 1 | 28-992 | 28-992 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Operation-On-the-Job Training (OJT) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2028-01-10 | 2028-01-21 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 20 | 0 | 0 | 12 | 1 | 27-412 | 27-412 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-12-06 | 2027-12-17 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 20 | 0 | 0 | 12 | 1 | 27-411 | 27-411 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-11-22 | 2027-12-03 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | Customer-Project Specific | EGR System Maintenance | Gas Turbine | 4 | 0 | 0 | 12 | 2 | 27-410 | 27-410 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - EGR System Maintenance - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-11-08 | 2027-11-11 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | Customer-Project Specific | EGR System Maintenance | Gas Turbine | 4 | 0 | 0 | 12 | 1 | 27-409 | 27-409 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - EGR System Maintenance - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-11-01 01:00 | 2027-11-04 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | Customer-Project Specific | EGR System operation | Gas Turbine | 4 | 0 | 0 | 12 | 2 | 27-408 | 27-408 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - EGR System operation - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-10-25 01:00 | 2027-10-28 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | Customer-Project Specific | EGR System operation | Gas Turbine | 4 | 0 | 0 | 12 | 1 | 27-407 | 27-407 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - EGR System operation - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-10-18 01:00 | 2027-10-21 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 10 | 0 | 0 | 12 | 3 | 27-406 | 27-406 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Balance of Plant - Operation (GE Integrated Systems) - G3 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-10-11 01:00 | 2027-10-15 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 10 | 0 | 0 | 12 | 2 | 27-405 | 27-405 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Balance of Plant - Operation (GE Integrated Systems) - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-10-04 01:00 | 2027-10-08 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 10 | 0 | 0 | 12 | 1 | 27-404 | 27-404 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Balance of Plant - Operation (GE Integrated Systems) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-09-27 01:00 | 2027-10-01 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 | 2 | 27-403 | 27-403 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-09-06 01:00 | 2027-09-17 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 10 | 0 | 0 | 12 | 1 | 27-402 | 27-402 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Control System - Mark VIe Distributed Control System Maintenance - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-08-30 01:00 | 2027-09-03 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 12 | 1 | 27-401 | 27-401 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-08-16 01:00 | 2027-08-27 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 | 2 | 27-400 | 27-400 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-08-09 01:00 | 2027-08-13 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 12 | 1 | 27-399 | 27-399 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-08-02 01:00 | 2027-08-06 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 | 2 | 27-398 | 27-398 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Maintenance - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-07-26 01:00 | 2027-07-30 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 12 | 1 | 27-397 | 27-397 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Maintenance - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-07-19 01:00 | 2027-07-23 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 | 2 | 27-396 | 27-396 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Maintenance - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-07-12 01:00 | 2027-07-16 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 | 1 | 27-395 | 27-395 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Maintenance - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-06-28 01:00 | 2027-07-09 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 | 3 | 27-394 | 27-394 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Combined Cycle - Operation (GE Integrated Systems) - G3 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-06-21 01:00 | 2027-06-25 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 | 3 | 27-393 | 27-393 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Operation - G3 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-06-07 01:00 | 2027-06-18 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 12 | 3 | 27-392 | 27-392 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G3 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Wednesday |  |  | 2027-06-02 01:00 | 2027-06-04 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 | 3 | 27-391 | 27-391 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Operation - G3 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-05-17 01:00 | 2027-05-28 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 | 2 | 27-390 | 27-390 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Combined Cycle - Operation (GE Integrated Systems) - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-05-10 01:00 | 2027-05-14 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 | 2 | 27-389 | 27-389 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Operation - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-04-26 01:00 | 2027-05-07 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 12 | 2 | 27-388 | 27-388 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Wednesday |  |  | 2027-04-21 01:00 | 2027-04-23 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 | 2 | 27-387 | 27-387 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Operation - G2 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-04-05 01:00 | 2027-04-16 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 | 1 | 27-386 | 27-386 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Combined Cycle - Operation (GE Integrated Systems) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-03-15 01:00 | 2027-03-19 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 12 | 1 | 27-385 | 27-385 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Steam Turbine - Operation - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-03-01 | 2027-03-12 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 12 | 1 | 27-384 | 27-384 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Wednesday |  |  | 2027-02-24 | 2027-02-26 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
NET ZERO TEESSIDE POWER LIMITED | Teesside | CCGT |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 | 1 | 27-383 | 27-383 - NET ZERO TEESSIDE POWER LIMITED - Teesside - CCGT - Gas Turbine - Operation - G1 | Customer Site | UNITED KINGDOM | TAS-N | Teesside | Customer Site | Monday |  |  | 2027-02-08 | 2027-02-19 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
UNIPER | Enter Site | UNIPER MYA Grain/Enfield - |  |  |  |  | English | English | IB | Anna Petrella | E-CON10501 | Control System - AC800M with IIT800xA | Controls | 10 | 0 | 0 | 6 |  | 31-5 | 31-5 - UNIPER - Enter Site - UNIPER MYA Grain/Enfield - - Control System - AC800M with IIT800xA | Customer Site | UNITED KINGDOM | TAS-N | Grain | Customer Site | Monday |  |  | 2031-10-06 01:00 | 2031-10-10 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2031.0
UNIPER | Enter Site | UNIPER MYA Grain/Enfield - |  |  |  |  | English | English | IB | Anna Petrella | E-CON10501 | Control System - AC800M with IIT800xA | Controls | 10 | 0 | 0 | 6 |  | 30-17 | 30-17 - UNIPER - Enter Site - UNIPER MYA Grain/Enfield - - Control System - AC800M with IIT800xA | Customer Site | UNITED KINGDOM | TAS-N | Grain | Customer Site | Monday |  |  | 2030-10-07 01:00 | 2030-10-11 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2030.0
UNIPER | Enter Site | UNIPER MYA Grain/Enfield - |  |  |  |  | English | English | IB | Anna Petrella | E-CON10501 | Control System - AC800M with IIT800xA | Controls | 10 | 0 | 0 | 6 |  | 29-30 | 29-30 - UNIPER - Enter Site - UNIPER MYA Grain/Enfield - - Control System - AC800M with IIT800xA | Customer Site | UNITED KINGDOM | TAS-N | Grain | Customer Site | Monday |  |  | 2029-10-08 01:00 | 2029-10-12 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2029.0
UNIPER | Enter Site | UNIPER MYA Grain/Enfield - |  |  |  |  | English | English | IB | Anna Petrella | E-CON10501 | Control System - AC800M with IIT800xA | Controls | 10 | 0 | 0 | 6 |  | 28-991 | 28-991 - UNIPER - Enter Site - UNIPER MYA Grain/Enfield - - Control System - AC800M with IIT800xA | Customer Site | UNITED KINGDOM | TAS-N | Grain | Customer Site | Monday |  |  | 2028-10-09 01:00 | 2028-10-13 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
UNIPER | Enter Site | UNIPER MYA Grain/Enfield - |  |  |  |  | English | English | IB | Anna Petrella | E-CON10501 | Control System - AC800M with IIT800xA | Controls | 10 | 0 | 0 | 6 |  | 27-368 | 27-368 - UNIPER - Enter Site - UNIPER MYA Grain/Enfield - - Control System - AC800M with IIT800xA | Customer Site | UNITED KINGDOM | TAS-N | Grain | Customer Site | Monday |  |  | 2027-10-04 01:00 | 2027-10-08 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | MYA PPC Megalopolis - Online Remote Access Operation Simulator | Simulator | 10 | 10 | 0 | 0 |  | 27-367 | 27-367 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - MYA PPC Megalopolis - Online Remote Access Operation Simulator | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2031-05-05 01:00 | 2031-05-09 01:00 | 0 | [8 empty] | No | Created | 2026-06-24 01:00 | US Workweek and Holidays |  |  | 2027.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 12 |  | 31-4 | 31-4 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - Excitation - EX2100e Operation & Maintenance | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2031-05-05 01:00 | 2031-05-09 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2031.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | MYA PPC Megalopolis - Online Remote Access Operation Simulator | Simulator | 20 | 0 | 0 | 0 |  | 30-16 | 30-16 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - MYA PPC Megalopolis - Online Remote Access Operation Simulator | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2030-05-06 01:00 | 2030-05-10 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2030.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 12 |  | 30-15 | 30-15 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - Excitation - EX2100e Operation & Maintenance | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2030-05-06 01:00 | 2030-05-10 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2030.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | MYA PPC Megalopolis - Online Remote Access Operation Simulator | Simulator | 20 | 0 | 0 | 0 |  | 29-29 | 29-29 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - MYA PPC Megalopolis - Online Remote Access Operation Simulator | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2029-05-07 01:00 | 2029-05-11 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2029.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 12 |  | 29-28 | 29-28 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - Excitation - EX2100e Operation & Maintenance | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2029-05-07 01:00 | 2029-05-11 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2029.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | MYA PPC Megalopolis - Online Remote Access Operation Simulator | Simulator | 20 | 0 | 0 | 0 |  | 28-990 | 28-990 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - MYA PPC Megalopolis - Online Remote Access Operation Simulator | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2028-05-08 01:00 | 2028-05-12 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 12 |  | 28-989 | 28-989 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - Excitation - EX2100e Operation & Maintenance | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2028-05-08 01:00 | 2028-05-12 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2028.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | MYA PPC Megalopolis - Online Remote Access Operation Simulator | Simulator | 20 | 0 | 0 | 0 |  | 27-366 | 27-366 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - MYA PPC Megalopolis - Online Remote Access Operation Simulator | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2027-05-10 01:00 | 2027-05-14 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis |  |  |  |  | English | English | IB | Anna Petrella | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 12 |  | 27-365 | 27-365 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - Excitation - EX2100e Operation & Maintenance | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2027-05-10 01:00 | 2027-05-14 01:00 | 0 | [8 empty] | No | Imported | 2026-06-26 01:00 |  |  |  | 2027.0
TPC | Hsinta | 2027 | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 12 | 3 | 26-1211 | 26-1211 - TPC - Hsinta - 2027 - Electrical - Electrical Control System (ECS) Training - G3 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaoshiung | Customer Site | Monday |  |  | 2026-12-16 |  | 0 | [7 empty] | Delivered by GE Grid | No | Imported | 2026-06-25 01:00 |  |  |  | 2026.0
TPC | Hsinta | 2026 | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 0 | 0 | 12 | 3 | 26-1210 | 26-1210 - TPC - Hsinta - 2026 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control - G3 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaoshiung | Customer Site | Monday |  |  | 2026-07-12 01:00 |  | 0 |  |  | 2026-12-07 | 2026-12-15 |  | 2026-12-07 | 2026-12-07 | Delivered by GE Grid | No | Created | 2026-06-24 01:00 | US Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2026.0
Volta River Authority | Kpone | GT11N2 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GEN10301 | Generator - Mechanical Systems & Components | Generator | 5 | 5 | 0 | 8 | 1 | 26-1209 | 26-1209 - Volta River Authority - Kpone - GT11N2 - Generator - Mechanical Systems & Components - G1 | Customer Site | GHANA | TAS-M | Tema | Customer Site | Monday |  |  | 2026-10-26 01:00 | 2026-10-29 01:00 | 0 | 2026-06-30 01:00 | 2026-07-23 01:00 | 2026-10-19 01:00 | 2026-10-23 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 | Development/Prep June 30th / July 1st and July 21st – 23rd ( 5 days) |  | Created | 2026-06-25 01:00 | US Workweek and Holidays | Vito Franco | Tentative | 2026.0
KGEN | Hot Spring | MkVIe Upgrade w/Autotune |  |  |  |  | English | English | IB | Patrick Molumby | E-CON23407 | Control System - OpFlex Enhanced Transient Stability with AutoTune DX Operation | Controls | 1 | 1 | 0 | 12 |  | 27-358 | 27-358 - KGEN - Hot Spring - MkVIe Upgrade w/Autotune - Control System - OpFlex Enhanced Transient Stability with AutoTune DX Operation | Customer Site | UNITED STATES | TAS-N | Malvern AR | Customer Site | Monday | Std US Hols |  | 2027-08-17 01:00 |  | 0 | 2027-07-19 01:00 | 2027-07-19 01:00 | 2027-08-23 01:00 | 2027-08-23 01:00 |  | 2027-08-23 01:00 | 2027-08-23 01:00 |  | Yes | Created | 2026-06-22 01:00 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2027.0
Luminant | Odessa | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 30-14 | 30-14 - Luminant - Odessa - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Odessa TX | Customer Site | Monday | Std US Hols |  | 2030-11-18 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2030.0
Luminant | Odessa | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 29-27 | 29-27 - Luminant - Odessa - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Odessa TX | Customer Site | Monday | Std US Hols |  | 2029-11-19 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2029.0
Luminant | Odessa | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 28-988 | 28-988 - Luminant - Odessa - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Odessa TX | Customer Site | Monday | Std US Hols |  | 2028-11-13 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2028.0
Luminant | Odessa | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 27-357 | 27-357 - Luminant - Odessa - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Odessa TX | Customer Site | Monday | Std US Hols |  | 2027-11-15 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2027.0
Luminant | Odessa | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 26-1208 | 26-1208 - Luminant - Odessa - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Odessa TX | Customer Site | Monday | Std US Hols |  | 2026-11-16 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2026.0
Luminant | Lamar | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 30-13 | 30-13 - Luminant - Lamar - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Paris TX | Customer Site | Monday | Std US Hols |  | 2030-11-18 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2030.0
Luminant | Lamar | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 29-26 | 29-26 - Luminant - Lamar - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Paris TX | Customer Site | Monday | Std US Hols |  | 2029-11-19 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2029.0
Luminant | Lamar | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 28-987 | 28-987 - Luminant - Lamar - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Paris TX | Customer Site | Monday | Std US Hols |  | 2028-11-13 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2028.0
Luminant | Lamar | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 27-356 | 27-356 - Luminant - Lamar - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Paris TX | Customer Site | Monday | Std US Hols |  | 2027-11-15 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2027.0
Luminant | Lamar | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 10 | 0 | 0 | 12 |  | 26-1207 | 26-1207 - Luminant - Lamar - MYA - 7FA.04 - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Paris TX | Customer Site | Monday | Std US Hols |  | 2026-11-16 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2026.0
Luminant | Forney | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13306 | Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Controls | 10 | 0 | 0 | 12 |  | 30-12 | 30-12 - Luminant - Forney - MYA - 7FA.04 - Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Customer Site | UNITED STATES | TAS-N | Forney TX | Customer Site | Monday | Std US Hols |  | 2030-11-18 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2030.0
Luminant | Forney | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13306 | Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Controls | 10 | 0 | 0 | 12 |  | 29-25 | 29-25 - Luminant - Forney - MYA - 7FA.04 - Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Customer Site | UNITED STATES | TAS-N | Forney TX | Customer Site | Monday | Std US Hols |  | 2029-11-19 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2029.0
Luminant | Forney | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13306 | Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Controls | 10 | 0 | 0 | 12 |  | 28-986 | 28-986 - Luminant - Forney - MYA - 7FA.04 - Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Customer Site | UNITED STATES | TAS-N | Forney TX | Customer Site | Monday | Std US Hols |  | 2028-11-13 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2028.0
Luminant | Forney | MYA - 7FA.04 |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13306 | Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Controls | 10 | 0 | 0 | 12 |  | 27-355 | 27-355 - Luminant - Forney - MYA - 7FA.04 - Control System - Mark VI to Mark VIe Platform Upgrade Maintenance | Customer Site | UNITED STATES | TAS-N | Forney TX | Customer Site | Monday | Std US Hols |  | 2027-11-15 |  | 0 | [7 empty] | MYA - listed course is a placeholder only, customer can choose any course from the catalog | No | Imported | 2026-06-24 01:00 |  |  |  | 2027.0
SAMRA ELECTRIC POWER CO | Samra | Samra CSA |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-CON30401 | Control System - ALSPA Control System Advanced | Controls | 5 | 5 | 0 | 6 |  | 26-1197 | 26-1197 - SAMRA ELECTRIC POWER CO - Samra - Samra CSA - Control System - ALSPA Control System Advanced | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-08-24 01:00 |  | 0 | 2026-08-10 01:00 | 2026-09-02 01:00 | 2026-09-07 01:00 | 2026-09-11 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2026-06-22 01:00 | US Workweek and Holidays | Santosh Kumar | Tentative | 2026.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 27-352 | 27-352 - TPC - Talin - Job Site - Steam Turbine - Maintenance - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Friday | 5/2/ 2031 |  | 2027-01-05 |  | 0 | 2027-02-08 | 2027-02-12 | 2027-04-26 01:00 | 2027-04-30 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Amin Houidi | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-351 | 27-351 - TPC - Talin - Job Site - Gas Turbine - Maintenance - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Thursday | 5/2/ 2030 |  | 2027-01-04 |  | 0 | 2027-04-05 01:00 | 2027-04-09 01:00 | 2027-06-07 01:00 | 2027-06-11 01:00 |  | 2027-06-07 01:00 | 2027-06-07 01:00 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Tim Taylor | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13701 | Control System - Control Server and Thin Client Familiarization | Controls | 2 | 2 | 0 | 12 | 1 | 27-350 | 27-350 - TPC - Talin - Job Site - Control System - Control Server and Thin Client Familiarization - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Wednesday | 5/2/ 2029 |  | 2027-01-03 |  | 0 | 2027-04-02 01:00 | 2027-04-05 01:00 | 2027-04-30 01:00 | 2027-05-03 01:00 |  | 2027-04-30 01:00 | 2027-04-30 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 2 | 2 | 0 | 12 | 1 | 27-349 | 27-349 - TPC - Talin - Job Site - Control System - Mark Vle Foundation Fieldbus - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Tuesday | 5/2/ 2028 |  | 2027-01-02 |  | 0 | 2027-03-31 01:00 | 2027-04-01 01:00 | 2027-04-28 01:00 | 2027-04-29 01:00 |  | 2027-04-28 01:00 | 2027-04-28 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 12 | 1 | 27-348 | 27-348 - TPC - Talin - Job Site - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 2 | 2 | 0 | 12 | 1 | 27-347 | 27-347 - TPC - Talin - Job Site - Control System - Mark Vle Foundation Fieldbus - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2027-03-29 01:00 | 2027-03-30 01:00 | 2027-04-26 01:00 | 2027-04-27 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON10801 | Control System - ActivePoint HMI Operation Familiarization | Controls | 6 | 0 | 0 | 12 | 1 | 27-346 | 27-346 - TPC - Talin - Job Site - Control System - ActivePoint HMI Operation Familiarization - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON23404 | Control System - Mark VIe Troubleshooting (Advanced) | Controls | 5 | 5 | 0 | 12 | 1 | 27-345 | 27-345 - TPC - Talin - Job Site - Control System - Mark VIe Troubleshooting (Advanced) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2026-10-05 01:00 | 2026-10-09 01:00 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-344 | 27-344 - TPC - Talin - Job Site - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2026-12-31 |  | 0 | 2027-01-04 | 2027-01-15 | 2027-02-08 | 2027-02-19 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Nasreddine Laroussi | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 | 1 | 27-343 | 27-343 - TPC - Talin - Job Site - Balance of Plant - Operation (GE Integrated Systems) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2026-12-31 |  | 0 | 2027-03-29 01:00 | 2027-04-02 01:00 | 2027-05-03 01:00 | 2027-05-07 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Amin Houidi | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 | 1 | 27-342 | 27-342 - TPC - Talin - Job Site - Combined Cycle - Operation (GE Integrated Systems) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2027-01-22 | 2027-02-10 | 2027-04-12 01:00 | 2027-04-16 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CCP10204 | Combined Cycle - Fundamentals | Combined Cycle | 10 | 0 | 0 | 12 | 1 | 27-341 | 27-341 - TPC - Talin - Job Site - Combined Cycle - Fundamentals - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 | 1 | 27-340 | 27-340 - TPC - Talin - Job Site - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2027-01-19 | 2027-01-21 | 2027-04-07 01:00 | 2027-04-09 01:00 |  | 2027-04-07 01:00 | 2027-04-07 01:00 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 | 1 | 27-339 | 27-339 - TPC - Talin - Job Site - Steam Turbine - Operation - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2026-10-22 01:00 | 2026-12-23 | 2027-01-04 | 2027-01-15 |  | 2027-01-04 | 2027-01-04 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-338 | 27-338 - TPC - Talin - Job Site - Gas Turbine - Operation - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2027-03-22 01:00 | 2027-04-02 01:00 | 2027-05-24 01:00 | 2027-06-04 01:00 |  | 2027-05-24 01:00 | 2027-05-24 01:00 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Tim Taylor | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 0 | 12 | 1 | 27-337 | 27-337 - TPC - Talin - Job Site - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2026-11-23 | 2026-11-27 | 2027-02-08 | 2027-02-12 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
TPC | Talin | Job Site | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 27-336 | 27-336 - TPC - Talin - Job Site - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2026-10-14 01:00 | 2026-12-23 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 |  |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
TPC | Talin | Local Office | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-335 | 27-335 - TPC - Talin - Local Office - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2026-09-14 01:00 | 2026-09-25 01:00 | 2027-03-01 | 2027-03-12 |  | 2027-03-01 | 2027-03-01 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
TPC | Talin | Local Office | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 | 1 | 27-334 | 27-334 - TPC - Talin - Local Office - Balance of Plant - Operation (GE Integrated Systems) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-01-01 |  | 0 | 2026-12-30 | 2027-02-12 | 2027-03-08 | 2027-03-12 |  | 2027-03-08 | 2027-03-08 |  | Yes | Created | 2026-06-18 01:00 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2027.0
TPC | Talin | Local Office | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 10 | 0 | 0 | 12 | 1 | 27-333 | 27-333 - TPC - Talin - Local Office - Combined Cycle - Operation (GE Integrated Systems) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Local Office | EGM-00590-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CCP10204 | Combined Cycle - Fundamentals | Combined Cycle | 10 | 0 | 0 | 12 | 1 | 27-332 | 27-332 - TPC - Talin - Local Office - Combined Cycle - Fundamentals - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [8 empty] | Yes | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas HRSG | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 10 | 0 | 0 | 3 | 2 | 27-331 | 27-331 - TPC - Talin - Overseas HRSG - Balance of Plant - Operation (GE Integrated Systems) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas HRSG | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 6 | 0 | 0 | 3 | 2 | 27-330 | 27-330 - TPC - Talin - Overseas HRSG - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Geno-Exc | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 0 | 0 | 3 | 1 | 27-329 | 27-329 - TPC - Talin - Overseas Geno-Exc - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Geno Excitation' |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Geno-Exc | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-ELX30501 | Excitation - LS2100e LCI for Turbine Static Start | Excitation | 4 | 0 | 0 | 3 | 1 | 27-328 | 27-328 - TPC - Talin - Overseas Geno-Exc - Excitation - LS2100e LCI for Turbine Static Start - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Geno Excitation' |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Geno-Exc | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-GEN10901 | Generator - Hydrogen Cooling System Operation & Maintenance | Generator | 6 | 0 | 0 | 3 | 1 | 27-327 | 27-327 - TPC - Talin - Overseas Geno-Exc - Generator - Hydrogen Cooling System Operation & Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Geno Excitation' |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Geno-Exc | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-GEN10301 | Generator - Mechanical Systems & Components | Generator | 10 | 0 | 0 | 3 | 1 | 27-326 | 27-326 - TPC - Talin - Overseas Geno-Exc - Generator - Mechanical Systems & Components - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Geno Excitation' |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Steam Turbine | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 3 | 2 | 27-325 | 27-325 - TPC - Talin - Overseas Steam Turbine - Steam Turbine - Operation - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Steam Turbine | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 3 | 2 | 27-324 | 27-324 - TPC - Talin - Overseas Steam Turbine - Steam Turbine - Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Gas Turbine | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 10 | 0 | 0 | 3 | 1 | 27-323 | 27-323 - TPC - Talin - Overseas Gas Turbine - Gas Turbine - Operation H-Class (Advanced) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Gas Turbine | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 3 | 2 | 27-322 | 27-322 - TPC - Talin - Overseas Gas Turbine - Gas Turbine - Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Gas Turbine | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 3 | 2 | 27-321 | 27-321 - TPC - Talin - Overseas Gas Turbine - Gas Turbine - Operation - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Prot-Inter | EGM-00590-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 14 | 0 | 0 | 3 | 1 | 27-320 | 27-320 - TPC - Talin - Overseas Prot-Inter - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Protection Interlock) |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Prot-Inter | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 6 | 0 | 0 | 3 | 1 | 27-319 | 27-319 - TPC - Talin - Overseas Prot-Inter - Electrical - Electrical Control System (ECS) Training - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Protection Interlock) |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas Prot-Inter | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 10 | 0 | 0 | 3 | 1 | 27-318 | 27-318 - TPC - Talin - Overseas Prot-Inter - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [7 empty] | Please group this as 'Protection Interlock) |  | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas DCDAS | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON13701 | Control System - Control Server and Thin Client Familiarization | Controls | 4 | 0 | 0 | 3 | 1 | 27-317 | 27-317 - TPC - Talin - Overseas DCDAS - Control System - Control Server and Thin Client Familiarization - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas DCDAS | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 4 | 0 | 0 | 3 | 1 | 27-316 | 27-316 - TPC - Talin - Overseas DCDAS - Control System - Mark Vle Foundation Fieldbus - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas DCDAS | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON10801 | Control System - ActivePoint HMI Operation Familiarization | Controls | 6 | 0 | 0 | 3 | 1 | 27-315 | 27-315 - TPC - Talin - Overseas DCDAS - Control System - ActivePoint HMI Operation Familiarization - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas DCDAS | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON23404 | Control System - Mark VIe Troubleshooting (Advanced) | Controls | 10 | 0 | 0 | 3 | 1 | 27-314 | 27-314 - TPC - Talin - Overseas DCDAS - Control System - Mark VIe Troubleshooting (Advanced) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
TPC | Talin | Overseas DCDAS | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 20 | 0 | 0 | 3 | 1 | 27-313 | 27-313 - TPC - Talin - Overseas DCDAS - Control System - Mark VIe Maintenance (Extended) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | 5/2/ 2027 |  | 2027-04-01 01:00 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  | Resourcing In Progress | 2027.0
Petrovietnam | Long Phu 1 | Steam Turbine | EGM-00727-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-GEN10901 | Generator - Hydrogen Cooling System Operation & Maintenance | Generator | 6 | 0 | 0 | 15 | 1 | 27-312 | 27-312 - Petrovietnam - Long Phu 1 - Steam Turbine - Generator - Hydrogen Cooling System Operation & Maintenance - G1 | Customer Site | VIETNAM | TAS-M | Can Tho | Customer Site | Monday | Feb 5 -11 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  |  | 2027.0
Petrovietnam | Long Phu 1 | Steam Turbine | EGM-00727-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 20 | 0 | 0 | 15 | 1 | 27-311 | 27-311 - Petrovietnam - Long Phu 1 - Steam Turbine - Steam Turbine - Operation - G1 | Customer Site | VIETNAM | TAS-M | Can Tho | Customer Site | Monday | Feb 5 -11 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  |  | 2027.0
Petrovietnam | Long Phu 1 | Steam Turbine | EGM-00727-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 10 | 0 | 0 | 15 | 1 | 27-310 | 27-310 - Petrovietnam - Long Phu 1 - Steam Turbine - Steam Turbine - Maintenance - G1 | Customer Site | VIETNAM | TAS-M | Can Tho | Customer Site | Monday | Feb 5 -11 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  |  | 2027.0
Petrovietnam | Long Phu 1 | Steam Turbine | EGM-00727-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 10 | 0 | 0 | 15 | 1 | 27-309 | 27-309 - Petrovietnam - Long Phu 1 - Steam Turbine - Excitation - EX2100e Operation & Maintenance - G1 | Customer Site | VIETNAM | TAS-M | Can Tho | Customer Site | Monday | Feb 5 -11 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  |  | 2027.0
Petrovietnam | Long Phu 1 | Steam Turbine | EGM-00727-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-CON13302 | Control System - Mark VI Maintenance (HMI on 1st Day) | Controls | 10 | 0 | 0 | 15 | 1 | 27-308 | 27-308 - Petrovietnam - Long Phu 1 - Steam Turbine - Control System - Mark VI Maintenance (HMI on 1st Day) - G1 | Customer Site | VIETNAM | TAS-M | Can Tho | Customer Site | Monday | Feb 5 -11 |  | 2027-01-01 |  | 0 | [9 empty] | Imported | 2026-06-18 01:00 |  |  |  | 2027.0
Vistra | Forney | - | IFF-008000-GT-101-TRX |  | IFF-008000-GT-101-TRX |  | English | English | IB | Patrick Molumby | SIM-RemoteTrng | Remote-Hosted Simulator Introductory Training | Simulator | 1 | 0 | 0 | 6 |  | 26-1193 | 26-1193 - Vistra - Forney - - - Remote-Hosted Simulator Introductory Training | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2026-07-27 01:00 |  | 0 |  |  | 2026-07-27 01:00 | 2026-07-27 01:00 |  | 2026-07-27 01:00 | 2026-07-27 01:00 | Request Aaron Hayes. 4 hours delivery & 4 hours prep |  | Created | 2026-06-18 01:00 | US Workweek and Holidays | Aaron Hayes | Tentative | 2026.0
Vistra | Forney | - | IFF-008000-GT-101-TRX |  | IFF-008000-GT-101-TRX |  | English | English | IB | Patrick Molumby | SIM-RemotePrep | Remote-Hosted Simulator Preparation | Simulator | 3 | 0 | 0 | 0 |  | 26-1192 | 26-1192 - Vistra - Forney - - - Remote-Hosted Simulator Preparation | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2026-07-13 01:00 |  | 0 |  |  | 2026-07-13 01:00 | 2026-07-15 01:00 |  | 2026-07-13 01:00 | 2026-07-13 01:00 | Request Aaron Hayes. No additional prep required |  | Created | 2026-06-16 01:00 | US Workweek and Holidays | Aaron Hayes | Tentative | 2026.0
CORPOELEC | Head quarter | 7F |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 0 | 0 | 12 |  | 26-1191 | 26-1191 - CORPOELEC - Head quarter - 7F - Gas Turbine - Maintenance | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Gas Turbine - Familiarization for Power Plant Management may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | 7F |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 20 | 0 | 0 | 12 |  | 26-1190 | 26-1190 - CORPOELEC - Head quarter - 7F - Gas Turbine - Operation | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Gas Turbine - Familiarization for Power Plant Management may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | 7F |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-GAS10401 | Gas Turbine - Familiarization for Power Plant Management | Gas Turbine | 10 | 0 | 0 | 12 |  | 26-1189 | 26-1189 - CORPOELEC - Head quarter - 7F - Gas Turbine - Familiarization for Power Plant Management | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Gas Turbine - Familiarization for Power Plant Management may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | Aero |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-CON13602 | Control System - Woodward Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 26-1188 | 26-1188 - CORPOELEC - Head quarter - Aero - Control System - Woodward Operation, Maintenance & Troubleshooting | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Controls courses may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | Aero |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 10 | 0 | 0 | 12 |  | 26-1187 | 26-1187 - CORPOELEC - Head quarter - Aero - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Controls courses may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | Aero |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10102 | Gas Turbine - LM2500 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 26-1186 | 26-1186 - CORPOELEC - Head quarter - Aero - Gas Turbine - LM2500 Package Maintenance | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Controls courses may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | Aero |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10101 | Gas Turbine - LM2500 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 26-1185 | 26-1185 - CORPOELEC - Head quarter - Aero - Gas Turbine - LM2500 Aero Package Operation/Familiarization | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Controls courses may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | Aero |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 10 | 0 | 0 | 12 |  | 26-1184 | 26-1184 - CORPOELEC - Head quarter - Aero - Gas Turbine - LM6000 Package Maintenance | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Controls courses may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
CORPOELEC | Head quarter | Aero |  |  |  |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 26-1183 | 26-1183 - CORPOELEC - Head quarter - Aero - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | VENEZUELA BOLIVARIAN REPUBLIC OF | TAS-S | CARACAS | Customer Site | Monday |  |  | 2026-09-01 01:00 |  | 0 | [7 empty] | Next available date, training to be completed before 31 December 2026. Back to back. Controls courses may require prep 3 months before start date to consider translation time, since material is required in Spanish |  | Imported | 2026-06-16 01:00 |  |  | Resourcing In Progress | 2026.0
Nippon Steel Corporation | Wakayama | - | EGM-00375-1CSTO-TRAINALL |  | EGM-00375-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 26-1182 | 26-1182 - Nippon Steel Corporation - Wakayama - - - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | JAPAN | TAS-M | Wakayama | Customer Site | Monday |  |  | 2026-06-30 01:00 |  | 0 | 2026-09-28 01:00 | 2026-10-09 01:00 | 2026-11-09 | 2026-11-20 |  | 2026-11-09 | 2026-11-09 | Short notice |  | Created | 2026-06-14 01:00 | US Workweek and Holidays | Margaret Baluyut | Tentative | 2026.0
Nippon Steel Corporation | Wakayama | - | EGM-00375-1CSTO-TRAINALL |  | EGM-00375-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 26-1181 | 26-1181 - Nippon Steel Corporation - Wakayama - - - Gas Turbine - Maintenance - G1 | Customer Site | JAPAN | TAS-M | Wakayama | Customer Site | Monday |  |  | 2026-07-01 01:00 |  | 0 | 2026-09-18 01:00 | 2026-10-01 01:00 | 2026-12-14 | 2026-12-18 |  | 2026-12-14 | 2026-12-14 | Short notice |  | Created | 2026-06-14 01:00 | US Workweek and Holidays | Agustin Collado | Tentative | 2026.0
Nippon Steel Corporation | Wakayama | - | EGM-00375-1CSTO-TRAINALL |  | EGM-00375-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 26-1180 | 26-1180 - Nippon Steel Corporation - Wakayama - - - Gas Turbine - Operation - G1 | Customer Site | JAPAN | TAS-M | Wakayama | Customer Site | Monday |  |  | 2026-07-01 01:00 |  | 0 | 2026-08-20 01:00 | 2026-09-02 01:00 | 2026-11-30 | 2026-12-11 |  | 2026-11-30 | 2026-11-30 | Short notice |  | Created | 2026-06-14 01:00 | US Workweek and Holidays | Agustin Collado | Tentative | 2026.0
Crystal Terrain LLC | Crystal Terrain | HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-985 | 28-985 - Crystal Terrain LLC - Crystal Terrain - HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2028-06-12 01:00 |  | 0 | 2028-05-08 01:00 | 2028-05-19 01:00 | 2028-07-17 01:00 | 2028-07-28 01:00 |  | 2028-07-17 01:00 | 2028-07-17 01:00 | Jun-Aug 2028 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Rafael Venancio | Tentative | 2028.0
Crystal Terrain LLC | Crystal Terrain | HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-984 | 28-984 - Crystal Terrain LLC - Crystal Terrain - HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2028-06-12 01:00 |  | 0 | 2028-05-29 01:00 | 2028-06-02 01:00 | 2028-07-10 01:00 | 2028-07-14 01:00 |  | 2028-07-10 01:00 | 2028-07-10 01:00 | Jun-Aug 2028 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
Crystal Terrain LLC | Crystal Terrain | HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-983 | 28-983 - Crystal Terrain LLC - Crystal Terrain - HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2028-06-12 01:00 |  | 0 | 2028-04-17 01:00 | 2028-04-21 01:00 | 2028-06-26 01:00 | 2028-06-30 01:00 |  | 2028-06-26 01:00 | 2028-06-26 01:00 | Jun-Aug 2028 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
Crystal Terrain LLC | Crystal Terrain | HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-982 | 28-982 - Crystal Terrain LLC - Crystal Terrain - HDGT Block 1: 10x6F.03 SC EO w/ Hot SCRs - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2028-06-12 01:00 |  | 0 | 2028-04-03 01:00 | 2028-04-14 01:00 | 2028-06-12 01:00 | 2028-06-23 01:00 |  | 2028-06-12 01:00 | 2028-06-12 01:00 | Jun-Aug 2028 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
Crystal Terrain LLC | Crystal Terrain | Aero Block 1 - 12 x LM6000 PC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-307 | 27-307 - Crystal Terrain LLC - Crystal Terrain - Aero Block 1 - 12 x LM6000 PC - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2027-10-17 01:00 |  | 0 | 2027-11-01 01:00 | 2027-11-05 01:00 | 2027-12-13 | 2027-12-17 |  | 2027-12-13 | 2027-12-13 | sent over to mark as of 24Jun26 / 4Q2027 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Crystal Terrain LLC | Crystal Terrain | Aero Block 1 - 12 x LM6000 PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-306 | 27-306 - Crystal Terrain LLC - Crystal Terrain - Aero Block 1 - 12 x LM6000 PC - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2027-10-17 01:00 |  | 0 | 2027-11-08 | 2027-11-12 | 2027-12-06 | 2027-12-10 |  | 2027-12-06 | 2027-12-06 | sent over to mark as of 24Jun26 / 4Q2027 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Crystal Terrain LLC | Crystal Terrain | Aero Block 1 - 12 x LM6000 PC |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-305 | 27-305 - Crystal Terrain LLC - Crystal Terrain - Aero Block 1 - 12 x LM6000 PC - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2027-10-17 01:00 |  | 0 | 2027-10-18 01:00 | 2027-10-22 01:00 | 2027-11-29 | 2027-12-03 |  | 2027-11-29 | 2027-11-29 | sent over to mark as of 24Jun26 / 4Q2027 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Crystal Terrain LLC | Crystal Terrain | Aero Block 1 - 20 x LM2500+G4 Xpress |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-304 | 27-304 - Crystal Terrain LLC - Crystal Terrain - Aero Block 1 - 20 x LM2500+G4 Xpress - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2027-09-12 01:00 |  | 0 | 2027-08-16 01:00 | 2027-08-20 01:00 | 2027-09-27 01:00 | 2027-10-01 01:00 |  | 2027-09-27 01:00 | 2027-09-27 01:00 | Sent over to mark as of 24Jun26 / 3Q-4Q2027 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Crystal Terrain LLC | Crystal Terrain | Aero Block 1 - 20 x LM2500+G4 Xpress |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10202 | Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-303 | 27-303 - Crystal Terrain LLC - Crystal Terrain - Aero Block 1 - 20 x LM2500+G4 Xpress - Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2027-09-12 01:00 |  | 0 | 2027-08-02 01:00 | 2027-08-06 01:00 | 2027-09-20 01:00 | 2027-09-24 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 | Sent over to mark as of 24Jun26 / 3Q-4Q2027 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Elias Benedi | Tentative | 2027.0
Crystal Terrain LLC | Crystal Terrain | Aero Block 1 - 20 x LM2500+G4 Xpress |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-302 | 27-302 - Crystal Terrain LLC - Crystal Terrain - Aero Block 1 - 20 x LM2500+G4 Xpress - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | AZ | Customer Site | Monday | Std US |  | 2027-09-12 01:00 |  | 0 | 2027-07-26 01:00 | 2027-07-30 01:00 | 2027-09-13 01:00 | 2027-09-17 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 | Sent over to mark as of 24Jun26 / 3Q-4Q2027 |  | Created | 2026-06-12 01:00 | US Workweek and Holidays | Elias Benedi | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | Customer-Project Specific | GT Simulator Introductory Remote Training | General | 10 | 10 | 0 | 6 |  | 29-24 | 29-24 - NIPSCO - NIPSCO Schahfer - - - GT Simulator Introductory Remote Training | Customer Site | UNITED STATES | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2029-01-22 |  | 0 |  |  | 2029-01-22 | 2029-01-23 |  | 2029-01-22 | 2029-01-22 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity 2 days Intro Trng |  | Created | 2026-06-11 01:00 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2029.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | Customer-Project Specific | OTS Simulator Development & Testing - GT Remote Sim | General | 20 | 0 | 0 | 0 |  | 28-981 | 28-981 - NIPSCO - NIPSCO Schahfer - - - OTS Simulator Development & Testing - GT Remote Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2028-11-27 |  | 0 |  |  | 2028-11-27 | 2028-12-22 |  | 2028-11-27 | 2028-11-27 | Request Charles Wal. No additional prep required 28-941 pushing out to 2029. Duration may be 20 days once in OTR, but scheduling 40 days per cost model |  | Created | 2026-06-11 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Sonelgaz | Djelfa | - |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Performance Test | Gas Turbine | 3 | 0 | 0 | 22 |  | 26-1179 | 26-1179 - Sonelgaz - Djelfa - - - Performance Test | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | [7 empty] | To be scheduled by region - No action for Scheduler |  | Imported | 2026-06-10 01:00 |  |  |  | 2026.0
Sonelgaz | Djelfa | - |  |  |  |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | BN 3500 System1 | Gas Turbine | 6 | 0 | 0 | 22 |  | 26-1178 | 26-1178 - Sonelgaz - Djelfa - - - BN 3500 System1 | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | [7 empty] | To be scheduled by region - No action for Scheduler |  | Imported | 2026-06-10 01:00 |  |  |  | 2026.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10306 | Gas Turbine - LM6000 Level 2 Hot Maintenance | Aeroderivative | 7 | 7 | 0 | 8 |  | 26-1177 | 26-1177 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM6000 Level 2 Hot Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2027-01-07 | 2027-01-15 | 2027-02-11 | 2027-02-22 |  | 2027-02-11 | 2027-02-11 | Sent to Mark as of 16June26 -NB |  | Created | 2026-06-08 01:00 | US Workweek and Holidays | Douglas Salazar | Tentative | 2026.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10305 | Gas Turbine - LM6000 Level 2 Cold Maintenance | Aeroderivative | 7 | 7 | 0 | 8 |  | 26-1176 | 26-1176 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM6000 Level 2 Cold Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-12-28 | 2027-01-06 | 2027-02-02 | 2027-02-10 |  | 2027-02-02 | 2027-02-02 | Sent to Mark as of 16June26 -NB |  | Created | 2026-06-08 01:00 | US Workweek and Holidays | Douglas Salazar | Tentative | 2026.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10304 | Gas Turbine - LM6000 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1175 | 26-1175 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM6000 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-12-14 | 2026-12-18 | 2027-01-26 | 2027-02-01 |  | 2027-01-26 | 2027-01-26 | Sent to Mark as of 16June26 -NB |  | Created | 2026-06-08 01:00 | US Workweek and Holidays | Douglas Salazar | Tentative | 2026.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10106 | Gas Turbine - LM2500 Level 2 Hot Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1174 | 26-1174 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM2500 Level 2 Hot Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-11-09 | 2026-11-13 | 2027-01-19 | 2027-01-25 |  | 2027-01-19 | 2027-01-19 | Sent to Mark as of 16June26 -NB |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Richard Fisher | Tentative | 2026.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10105 | Gas Turbine - LM2500 Level 2 Cold Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1173 | 26-1173 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM2500 Level 2 Cold Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-10-21 01:00 | 2026-10-23 01:00 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 | Sent to Mark as of 16June26 -NB |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Richard Fisher | Tentative | 2026.0
TANESCO | Ubungo III | Ubungo III |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-1172 | 26-1172 - TANESCO - Ubungo III - Ubungo III - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-09-28 01:00 | 2026-10-02 01:00 | 2027-01-04 | 2027-01-08 |  | 2027-01-04 | 2027-01-04 | Sent to Mark as of 16June26 -NB |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Richard Fisher | Tentative | 2026.0
SEC | PP13 | PP13 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GEN10901 | Generator - Hydrogen Cooling System Operation & Maintenance | Generator | 3 | 3 | 1 | 12 |  | 26-1171 | 26-1171 - SEC - PP13 - PP13 - Generator - Hydrogen Cooling System Operation & Maintenance | Customer Site | SAUDI ARABIA | TAS-S | Riyadh | Customer Site | Sunday |  |  | 2026-08-23 01:00 |  | 0 | 2026-07-24 01:00 | 2026-09-04 01:00 | 2026-09-22 01:00 | 2026-09-24 01:00 |  | 2026-09-22 01:00 | 2026-09-22 01:00 |  |  | Created | 2026-06-08 01:00 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Confirmed | 2026.0
SEC | PP13 | PP13 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS22201 | Gas Turbine - Operation F-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-1170 | 26-1170 - SEC - PP13 - PP13 - Gas Turbine - Operation F-Class (Advanced) | Customer Site | SAUDI ARABIA | TAS-S | Riyadh | Customer Site | Sunday |  |  | 2026-08-23 01:00 |  | 0 | 2026-08-03 01:00 | 2026-08-07 01:00 | 2026-09-06 01:00 | 2026-09-10 01:00 |  | 2026-09-06 01:00 | 2026-09-06 01:00 |  |  | Created | 2026-06-06 01:00 | Sun - Thurs Middle East 5 Day Workweek | Salvatore Genovese | Confirmed | 2026.0
SEC | PP13 | PP13 |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 26-1169 | 26-1169 - SEC - PP13 - PP13 - Gas Turbine - Operation - G1 | Customer Site | SAUDI ARABIA | TAS-S | Riyadh | Customer Site | Sunday |  |  | 2026-08-23 01:00 |  | 0 | 2026-07-20 01:00 | 2026-08-21 01:00 | 2026-08-23 01:00 | 2026-09-03 01:00 |  | 2026-08-23 01:00 | 2026-08-23 01:00 |  |  | Created | 2026-06-06 01:00 | Sun - Thurs Middle East 5 Day Workweek | Salvatore Genovese | Confirmed | 2026.0
SCPPA | Magnolia | - |  |  | IFF-006750-GT-101-TRX | 4102902151 | English | English | IB | Patrick Molumby | E-GAS22201 | Gas Turbine - Operation F-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-301 | 27-301 - SCPPA - Magnolia - - - Gas Turbine - Operation F-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Burbank CA | Customer Site | Monday | Std US |  | 2027-03-29 01:00 |  | 0 | 2027-02-22 | 2027-02-26 | 2027-03-29 01:00 | 2027-04-02 01:00 |  | 2027-03-29 01:00 | 2027-03-29 01:00 |  | Yes | Created | 2026-06-08 01:00 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
Invenergy | Red Oak Ridge Energy Center | 5x7F.05 H35 GEN-EO |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 29-23 | 29-23 - Invenergy - Red Oak Ridge Energy Center - 5x7F.05 H35 GEN-EO - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Paris WI | Customer Site | Monday | Standard US Holidays |  | 2029-03-05 |  | 0 | 2029-02-05 | 2029-02-16 | 2029-04-02 01:00 | 2029-04-13 01:00 |  | 2029-04-02 01:00 | 2029-04-02 01:00 | Customer asking us to provide dates starting in March 2029 |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2029.0
Invenergy | Red Oak Ridge Energy Center | 5x7F.05 H35 GEN-EO |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 29-22 | 29-22 - Invenergy - Red Oak Ridge Energy Center - 5x7F.05 H35 GEN-EO - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Paris WI | Customer Site | Monday | Standard US Holidays |  | 2029-03-05 |  | 0 | 2029-01-15 | 2029-01-19 | 2029-03-26 01:00 | 2029-03-30 01:00 |  | 2029-03-26 01:00 | 2029-03-26 01:00 | Customer asking us to provide dates starting in March 2029 |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2029.0
Invenergy | Red Oak Ridge Energy Center | 5x7F.05 H35 GEN-EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 29-21 | 29-21 - Invenergy - Red Oak Ridge Energy Center - 5x7F.05 H35 GEN-EO - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Paris WI | Customer Site | Monday | Standard US Holidays |  | 2029-03-05 |  | 0 | 2029-01-22 | 2029-01-26 | 2029-03-19 01:00 | 2029-03-23 01:00 |  | 2029-03-19 01:00 | 2029-03-19 01:00 | Customer asking us to provide dates starting in March 2029 |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Tim Taylor | Confirmed | 2029.0
Invenergy | Red Oak Ridge Energy Center | 5x7F.05 H35 GEN-EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 29-20 | 29-20 - Invenergy - Red Oak Ridge Energy Center - 5x7F.05 H35 GEN-EO - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Paris WI | Customer Site | Monday | Standard US Holidays |  | 2029-03-05 |  | 0 | 2029-01-08 | 2029-01-19 | 2029-03-05 | 2029-03-16 01:00 |  | 2029-03-05 | 2029-03-05 | Customer asking us to provide dates starting in March 2029 |  | Created | 2026-06-07 01:00 | US Workweek and Holidays | Tim Taylor | Confirmed | 2029.0
Rauma Marine Constructions Oy | Rauma | - |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 5 |  | 26-1168 | 26-1168 - Rauma Marine Constructions Oy - Rauma - - - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-09-14 01:00 | 2026-09-24 01:00 | 0 | 2026-08-12 01:00 | 2026-08-25 01:00 | 2026-09-21 01:00 | 2026-09-25 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 | Short Notice Request |  | Created | 2026-06-04 01:00 | US Workweek and Holidays | Richard Fisher | Tentative | 2026.0
Rauma Marine Constructions Oy | Rauma | - |  |  |  |  | English | English | IB | Anna Petrella | E-AER10103 | Gas Turbine - LM2500 Engine Familiarization | Aeroderivative | 3 | 3 | 0 | 5 |  | 26-1167 | 26-1167 - Rauma Marine Constructions Oy - Rauma - - - Gas Turbine - LM2500 Engine Familiarization | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-09-14 01:00 | 2026-09-24 01:00 | 0 | 2026-07-29 01:00 | 2026-07-31 01:00 | 2026-09-14 01:00 | 2026-09-16 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 | Short Notice Request |  | Created | 2026-06-04 01:00 | US Workweek and Holidays | Richard Fisher | Cancelled | 2026.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 | 5 | 27-300 | 27-300 - TPC - Taichung - 2027 - Balance of Plant - Operation (GE Integrated Systems) - G5 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Distance Learning | Tuesday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2027-01-05 | 2027-01-08 | 2027-02-08 | 2027-02-12 |  | 2027-02-08 | 2027-02-08 | Avoid overlaps, only 1 interpreter, |  | Created | 2026-06-02 01:00 | US Workweek and Holidays | Donald Hopkins | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | Customer-Project Specific | HRSG - Operation & Maintenance (GE Engineered) & SCR | HRSG | 3 | 3 | 0 | 12 | 5 | 27-299 | 27-299 - TPC - Taichung - 2027 - HRSG - Operation & Maintenance (GE Engineered) & SCR - G5 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Distance Learning | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-12-30 | 2027-01-04 | 2027-02-03 | 2027-02-05 |  | 2027-02-03 | 2027-02-03 | Avoid overlaps, only 1 interpreter, |  | Created | 2026-06-02 01:00 | US Workweek and Holidays | Donald Hopkins | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 5 | 27-298 | 27-298 - TPC - Taichung - 2027 - Excitation - Generator Excitation, Protection and Static Starter Introduction - G5 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-02 | 2026-11-06 | 2027-01-18 | 2027-01-22 |  | 2027-01-18 | 2027-01-18 | Avoid overlaps, only 1 interpreter, |  | Created | 2026-06-02 01:00 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 0 | 12 | 5 | 27-297 | 27-297 - TPC - Taichung - 2027 - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G5 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-08-17 01:00 | 2026-08-21 01:00 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 | Avoid overlaps, only 1 interpreter, |  | Created | 2026-06-02 01:00 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
BUDAPESTI EROMU ZRT | Veolia | LM6000PD Repair & Upgrade to PF |  |  |  |  | English | English | IB | Anna Petrella | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 10 | 0 | 0 | 12 |  | 26-1166 | 26-1166 - BUDAPESTI EROMU ZRT - Veolia - LM6000PD Repair & Upgrade to PF - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | HUNGARY | TAS-N | Veolia | Customer Site | Monday |  |  | 2026-10-20 01:00 | 2026-10-23 01:00 | 0 | [7 empty] | Please do not yet schedule - I will notify you when I have customer feedback | No | Imported | 2026-05-29 01:00 |  |  |  | 2026.0
NIPSCO | NIPSCO Schahfer Gas Peaker | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-980 | 28-980 - NIPSCO - NIPSCO Schahfer Gas Peaker - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2028-02-07 |  | 0 |  |  | 2028-02-07 | 2028-03-03 |  | 2028-02-07 | 2028-02-07 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required |  | Created | 2026-05-28 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
NIPSCO | NIPSCO Schahfer Gas Peaker | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 2 | 6 |  | 28-979 | 28-979 - NIPSCO - NIPSCO Schahfer Gas Peaker - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2028-02-07 |  | 0 |  |  | 2028-02-07 | 2028-02-15 |  | 2028-02-07 | 2028-02-07 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng | Yes | Created | 2026-05-28 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2028.0
NIPSCO | NIPSCO Schahfer Gas Peaker | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 27-296 | 27-296 - NIPSCO - NIPSCO Schahfer Gas Peaker - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2027-07-26 01:00 |  | 0 |  |  | 2027-07-26 01:00 | 2027-09-24 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 | Request Charles Wal. No additional prep required |  | Created | 2026-05-28 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2027.0
Chevron | Kilby | 3 x 7HA.02 Simple Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-978 | 28-978 - Chevron - Kilby - 3 x 7HA.02 Simple Cycle - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-01-10 |  | 0 | 2027-10-25 01:00 | 2027-10-29 01:00 | 2028-01-10 | 2028-01-21 |  | 2028-01-10 | 2028-01-10 | Sometime in Jan |  | Created | 2026-05-22 01:00 | US Workweek and Holidays | Rafael Venancio | Tentative | 2028.0
Chevron | Kilby | 3 x 7HA.02 Simple Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 27-295 | 27-295 - Chevron - Kilby - 3 x 7HA.02 Simple Cycle - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2027-12-13 |  | 0 | 2027-10-18 01:00 | 2027-10-22 01:00 | 2027-12-13 | 2027-12-17 |  | 2027-12-13 | 2027-12-13 | To follow 27-141, addition to same project |  | Created | 2026-05-22 01:00 | US Workweek and Holidays | Rafael Venancio | Tentative | 2027.0
GS Power | Bucheon #2 | - |  |  |  |  | English | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 20 | 1 | 26-1163 | 26-1163 - GS Power - Bucheon #2 - - - Gas Turbine - Operation - G1 | Customer Site | KOREA REPUBLIC OF | TAS-M | Bucheon | Customer Site | Monday |  |  | 2026-07-01 01:00 | 2026-11-30 | 0 | 2026-08-31 01:00 | 2026-09-14 01:00 | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 | Any time in 2nd half 2026 |  | Created | 2026-05-21 01:00 | US Workweek and Holidays | Ihsan Rakha | Tentative | 2026.0
GS Power | Bucheon #2 | - |  |  |  |  | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 26-1162 | 26-1162 - GS Power - Bucheon #2 - - - Control System - Mark VIe Maintenance (Extended) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-07-01 01:00 | 2026-12-01 | 0 | 2026-09-08 01:00 | 2026-09-18 01:00 | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 | Any time in 2nd half 2026 |  | Created | 2026-05-21 01:00 | US Workweek and Holidays | Isaiah Mason | Tentative | 2026.0
GS Power | Bucheon #2 | - |  |  |  |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 26-1161 | 26-1161 - GS Power - Bucheon #2 - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-07-01 01:00 | 2026-12-01 | 0 | 2026-08-10 01:00 | 2026-08-14 01:00 | 2026-12-07 | 2026-12-11 |  | 2026-12-07 | 2026-12-07 | Any time in 2nd half 2026 |  | Created | 2026-05-21 01:00 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2026.0
GS Power | Bucheon #2 | - |  |  |  |  | English | English | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 26-1160 | 26-1160 - GS Power - Bucheon #2 - - - Gas Turbine - Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-07-01 01:00 | 2026-11-30 | 0 | 2026-08-24 01:00 | 2026-08-28 01:00 | 2026-11-30 | 2026-12-04 |  | 2026-11-30 | 2026-11-30 | Any time in 2nd half 2026 |  | Created | 2026-05-21 01:00 | US Workweek and Holidays | Coy Jackson | Tentative | 2026.0
TPC | Talin | 2026 | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL | I01-120623 / PO 4102884708 | English | Mandarin Chinese | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 1 | 1 | 26-1159 | 26-1159 - TPC - Talin - 2026 - Balance of Plant - Operation (GE Integrated Systems) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-10-01 01:00 |  | 0 | 2026-07-23 01:00 | 2026-08-26 01:00 | 2026-11-23 | 2026-12-01 |  | 2026-11-23 | 2026-11-23 | Must be back to back with HRSG , customer course duration per contract requireent, anytime in Q4 |  | Created | 2026-05-13 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2026.0
TPC | Talin | 2026 | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL | I01-120623 / PO 4102884708 | English | Mandarin Chinese | NU | Gavin Yoong | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 5 | 3 | 0 | 1 | 1 | 26-1158 | 26-1158 - TPC - Talin - 2026 - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-10-01 01:00 |  | 0 | 2026-07-20 01:00 | 2026-07-22 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 | Must be back to back with BOP , customer course duration per contract requireent, anytime in Q4 |  | Created | 2026-05-13 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2026.0
TPC | Talin | 2026 | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL | I01-120623 / PO 4102884708 | English | Mandarin Chinese | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 13 | 10 | 0 | 1 | 1 | 26-1157 | 26-1157 - TPC - Talin - 2026 - Steam Turbine - Operation - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-10-01 01:00 |  | 0 | 2026-08-27 01:00 | 2026-10-21 01:00 | 2026-12-02 | 2026-12-18 |  | 2026-12-02 | 2026-12-02 | Must be back to back with ST Mnt, custom course duration per contract requirement, anytime in Q4 |  | Created | 2026-05-13 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2026.0
TPC | Talin | 2026 | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | Mandarin Chinese | NU | Gavin Yoong | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 7 | 5 | 0 | 1 | 1 | 26-1156 | 26-1156 - TPC - Talin - 2026 - Steam Turbine - Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-10-01 01:00 |  | 0 | 2026-10-05 01:00 | 2026-10-09 01:00 | 2026-12-21 | 2026-12-31 |  | 2026-12-21 | 2026-12-21 | Must be back to back with ST Opt, custom course duration per contract requirement, anytime in Q4 |  | Created | 2026-05-13 01:00 | US Workweek and Holidays |  | Tentative | 2026.0
TPC | Talin | 2026 | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | Mandarin Chinese | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 7 | 5 | 0 | 3 | 1 | 26-1155 | 26-1155 - TPC - Talin - 2026 - Gas Turbine - Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-09-30 01:00 |  | 0 |  |  | 2026-09-24 01:00 | 2026-10-02 01:00 |  | 2026-09-24 01:00 | 2026-09-24 01:00 | Must be back to back with GT Opt, custom course duration per contract requirement, anytime in Q4 | Yes | Created | 2026-05-13 01:00 | US Workweek and Holidays | Tim Taylor | Tentative | 2026.0
TPC | Talin | 2026 | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | English | Mandarin Chinese | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 13 | 10 | 0 | 3 | 1 | 26-1154 | 26-1154 - TPC - Talin - 2026 - Gas Turbine - Operation - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-09-30 01:00 |  | 0 |  |  | 2026-09-08 01:00 | 2026-09-23 01:00 |  | 2026-09-08 01:00 | 2026-09-08 01:00 | Must be back to back with GT Mnt, custom course duration per contract requirement, anytime in Q4 | Yes | Created | 2026-05-13 01:00 | US Workweek and Holidays | Tim Taylor | Tentative | 2026.0
GECOL | - | Tripoli South GT12 |  |  |  |  | English | English | IB | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 10 |  | 26-1150 | 26-1150 - GECOL - - - Tripoli South GT12 - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-10-19 01:00 | 2026-10-28 01:00 | 0 | 2026-07-13 01:00 | 2026-08-07 01:00 | 2026-09-28 01:00 | 2026-10-09 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 | Customer Want date Q3/2026 however we will propose our next best availability, capable instructor to deliver this Training is S. Kumar or A. Kitanovic |  | Created | 2026-05-07 01:00 | Birr Workweek and Holidays | Santosh Kumar | Tentative | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-1149 | 26-1149 - DAMCO ENERGY S.A. - - - Alexandroupolis - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Friday |  |  | 2027-07-19 01:00 | 2027-07-23 01:00 | 0 |  |  | 2027-07-19 01:00 | 2027-07-23 01:00 |  | 2027-07-19 01:00 | 2027-07-19 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-1148 | 26-1148 - DAMCO ENERGY S.A. - - - Alexandroupolis - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Saturday |  |  | 2027-07-12 01:00 | 2027-07-16 01:00 | 0 |  |  | 2027-07-12 01:00 | 2027-07-16 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-1147 | 26-1147 - DAMCO ENERGY S.A. - - - Alexandroupolis - Control System - Mark VIe Maintenance (Extended) | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Sunday |  |  | 2027-06-28 01:00 | 2027-07-09 01:00 | 0 |  |  | 2027-06-28 01:00 | 2027-07-09 01:00 |  | 2027-06-28 01:00 | 2027-06-28 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 26-1146 | 26-1146 - DAMCO ENERGY S.A. - - - Alexandroupolis - Steam Turbine - Maintenance | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Thursday |  |  | 2027-06-14 01:00 | 2027-06-18 01:00 | 0 |  |  | 2027-06-14 01:00 | 2027-06-18 01:00 |  | 2027-06-14 01:00 | 2027-06-14 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-1145 | 26-1145 - DAMCO ENERGY S.A. - - - Alexandroupolis - Gas Turbine - Maintenance | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Tuesday | 15-Aug-2027 |  | 2027-06-07 01:00 | 2027-06-11 01:00 | 0 |  |  | 2027-06-07 01:00 | 2027-06-11 01:00 |  | 2027-06-07 01:00 | 2027-06-07 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 26-1144 | 26-1144 - DAMCO ENERGY S.A. - - - Alexandroupolis - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Monday | 1-May-2027 |  | 2027-05-31 01:00 | 2027-06-04 01:00 | 0 |  |  | 2027-05-31 01:00 | 2027-06-04 01:00 |  | 2027-05-31 01:00 | 2027-05-31 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 26-1143 | 26-1143 - DAMCO ENERGY S.A. - - - Alexandroupolis - Steam Turbine - Operation | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Wednesday | 06-Jan-2027 |  | 2027-05-17 01:00 | 2027-05-28 01:00 | 0 |  |  | 2027-05-17 01:00 | 2027-05-28 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 26-1142 | 26-1142 - DAMCO ENERGY S.A. - - - Alexandroupolis - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Tuesday | 25-Mar-2027 |  | 2027-05-12 01:00 | 2027-05-14 01:00 | 0 |  |  | 2027-05-12 01:00 | 2027-05-14 01:00 |  | 2027-05-12 01:00 | 2027-05-12 01:00 | **DO NOT SCHEDULE PER ANNA** | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
DAMCO ENERGY S.A. | - | Alexandroupolis |  |  |  |  | English | English | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-1141 | 26-1141 - DAMCO ENERGY S.A. - - - Alexandroupolis - Gas Turbine - Operation | Customer Site | GREECE | TAS-N | Alexandropoulis | Customer Site | Monday | 28-Oct-2026 |  | 2027-04-12 01:00 | 2027-04-23 01:00 | 0 |  |  | 2027-04-12 01:00 | 2027-04-23 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 | **DO NOT SCHEDULE PER ANNA** Please check availability in Q4 latest as possible but ending no later than 11-Dec-2026, also please keep sequence | No | Created | 2026-05-05 01:00 | Birr Workweek and Holidays |  |  | 2026.0
GECOL | - | Tripoli South GT12 | EG0-007248-PE04GPGT01TR |  | IG0-002869-12 |  | English | English | IB | Anna Petrella | Customer-Project Specific | Excitation - Combisystem Excitation & Static Starting Device Maintenance | Excitation | 10 | 10 | 0 | 10 |  | 26-1140 | 26-1140 - GECOL - - - Tripoli South GT12 - Excitation - Combisystem Excitation & Static Starting Device Maintenance | Learning Center | GERMANY | TAS-N | Berlin | Other Learning Center | Monday |  |  | 2026-08-10 01:00 | 2026-08-19 01:00 | 0 |  |  | 2026-08-10 01:00 | 2026-08-21 01:00 |  | 2026-08-10 01:00 | 2026-08-10 01:00 | no action required from Nelsa, Anna will take care for resourcing with GE Converteam |  | Created | 2026-05-07 01:00 | US Workweek and Holidays |  | Confirmed | 2026.0
CSS - GP Scherer | Plant Scherer | MkVI |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13302 | Control System - Mark VI Maintenance (HMI on 1st Day) | Controls | 5 | 5 | 0 | 12 |  | 26-1139 | 26-1139 - CSS - GP Scherer - Plant Scherer - MkVI - Control System - Mark VI Maintenance (HMI on 1st Day) | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | std US holidays |  | 2026-08-17 01:00 | 2026-08-20 01:00 | 0 | 2026-10-05 01:00 | 2026-10-09 01:00 | 2026-10-26 01:00 | 2026-10-30 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 | Please note legacy MkVI controls training for a G3 Steam Turbine @ HLC |  | Created | 2026-05-05 01:00 | US Workweek and Holidays | Martin Acosta | Cancelled | 2026.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 2 | 0 | 12 | 4 | 27-294 | 27-294 - TPC - Taichung - 2027 - Balance of Plant - Operation (GE Integrated Systems) - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Distance Learning | Tuesday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-12-21 | 2026-12-22 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | Customer-Project Specific | HRSG - Operation & Maintenance (GE Engineered) & SCR | HRSG | 4 | 2 | 0 | 12 | 4 | 27-293 | 27-293 - TPC - Taichung - 2027 - HRSG - Operation & Maintenance (GE Engineered) & SCR - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Distance Learning | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-10-15 01:00 | 2026-10-16 01:00 | 2027-01-04 | 2027-01-07 |  | 2027-01-04 | 2027-01-04 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 3 | 0 | 12 | 4 | 27-292 | 27-292 - TPC - Taichung - 2027 - Gas Turbine - Operation - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Distance Learning | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-10-26 01:00 | 2026-10-28 01:00 | 2027-01-18 | 2027-01-29 |  | 2027-01-18 | 2027-01-18 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 4 | 27-291 | 27-291 - TPC - Taichung - 2027 - Excitation - Generator Excitation, Protection and Static Starter Introduction - G4 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-12 | 2026-11-13 | 2027-02-01 | 2027-02-05 |  | 2027-02-01 | 2027-02-01 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 0 | 12 | 4 | 27-290 | 27-290 - TPC - Taichung - 2027 - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G4 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-09 | 2026-11-11 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13701 | Control System - Control Server and Thin Client Familiarization | Controls | 3 | 1 | 0 | 12 | 5 | 27-289 | 27-289 - TPC - Taichung - 2027 - Control System - Control Server and Thin Client Familiarization - G5 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-05 | 2026-11-05 | 2027-03-18 01:00 | 2027-03-22 01:00 |  | 2027-03-18 01:00 | 2027-03-18 01:00 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13701 | Control System - Control Server and Thin Client Familiarization | Controls | 3 | 1 | 0 | 12 | 4 | 27-288 | 27-288 - TPC - Taichung - 2027 - Control System - Control Server and Thin Client Familiarization - G4 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-04 | 2026-11-04 | 2027-03-15 01:00 | 2027-03-17 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 2 | 1 | 0 | 12 | 5 | 27-287 | 27-287 - TPC - Taichung - 2027 - Control System - Mark Vle Foundation Fieldbus - G5 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-03 | 2026-11-03 | 2027-03-25 01:00 | 2027-03-26 01:00 |  | 2027-03-25 01:00 | 2027-03-25 01:00 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 2 | 1 | 0 | 12 | 4 | 27-286 | 27-286 - TPC - Taichung - 2027 - Control System - Mark Vle Foundation Fieldbus - G4 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2026-11-02 | 2026-11-02 | 2027-03-23 01:00 | 2027-03-24 01:00 |  | 2027-03-23 01:00 | 2027-03-23 01:00 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
TPC | Taichung | 2027 |  |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 | 4 | 27-285 | 27-285 - TPC - Taichung - 2027 - Control System - Mark VIe Distributed Control System Maintenance - G4 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2027-01-25 | 2027-01-27 | 2027-03-08 | 2027-03-12 |  | 2027-03-08 | 2027-03-08 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-27 01:00 | US Workweek and Holidays | Gerardo Gonzalez | Cancelled | 2027.0
TPC | Taichung | 2027 | EGM-00166-1CSTO-TRAINALL |  |  |  | English | Mandarin Chinese | NU | Gavin Yoong | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 4 | 0 | 12 | 4 | 27-284 | 27-284 - TPC - Taichung - 2027 - Control System - Mark VIe Maintenance - G4 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday | Feb 5 -10 , Lunar New Year |  | 2027-01-04 |  | 0 | 2027-01-04 | 2027-01-07 | 2027-02-22 | 2027-02-26 |  | 2027-02-22 | 2027-02-22 | Avoid overlaps, only 1 interpreter, Q1 2027 |  | Created | 2026-04-26 01:00 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
EVM | EVM II | - |  |  |  | I01-118157 | Spanish | Spanish | IB | Alejandra Saldana | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-1138 | 26-1138 - EVM - EVM II - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | MEXICO | TAS-M | Pachuca | Customer Site | Monday |  |  | 2026-07-12 01:00 |  | 0 | 2026-05-04 01:00 | 2026-09-04 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 | Please assign Gerardo, as the customer is requesting a Spanish speaker. The 5-day prep is scheduled to start on April 27. Can Nasreddine help with the next 5-day prep on June 22? For the delivery piece, since prep for 26-1055 is being pushed out, this clears the week of July 6 to make space for the other prep work Gerardo has for 26-1056, 26-1057, and 26-196, and to accommodate the 20-day Mark VIe course. The week of August 10 is also available for prep rescheduling. |  | Created | 2026-04-24 01:00 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2026.0
DTL | Livingston | 7HA.03 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 31-3 | 31-3 - DTL - Livingston - 7HA.03 - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2031-03-10 01:00 |  | 0 |  |  | 2031-03-10 01:00 | 2031-04-04 01:00 |  | 2031-03-10 01:00 | 2031-03-10 01:00 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required |  | Created | 2026-04-24 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2031.0
DTL | Livingston | 7HA.03 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 30-11 | 30-11 - DTL - Livingston - 7HA.03 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2030-11-28 |  | 0 |  |  | 2030-11-28 | 2030-12-06 |  | 2030-11-28 | 2030-11-28 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng |  | Created | 2026-04-24 01:00 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2030.0
DTL | Livingston | 7HA.03 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 30-10 | 30-10 - DTL - Livingston - 7HA.03 - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2030-08-12 01:00 |  | 0 |  |  | 2030-08-12 01:00 | 2030-10-10 01:00 |  | 2030-08-12 01:00 | 2030-08-12 01:00 | Request Charles Wal. No additional prep required. Move 29-13 - LG&E - EW Brown - 12 - OTS Post-COD Refresh - CC Sim to start 11-Oct-2030. There should be no conflict, as DTE Milan should been removed from the schedule |  | Created | 2026-04-24 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2030.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00085-1CSTO-TRAINALL |  | English | Mandarin Chinese | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 3 | 26-1132 | 26-1132 - TPC - Datan - 8&9 Local Training - Gas Turbine - Operation - G3 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Taoyuan | Distance Learning | Monday |  |  | 2026-12-07 |  | 0 | 2026-07-27 01:00 | 2026-07-31 01:00 | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 |  |  | Created | 2026-04-21 01:00 | US Workweek and Holidays | Coy Jackson | Cancelled | 2026.0
YTL Power | Seraya | CCP50 |  |  |  |  | English | English | NU | Gavin Yoong | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 27-281 | 27-281 - YTL Power - Seraya - CCP50 - OTS Post-COD Refresh - CC Sim | Remote | SINGAPORE | TAS-N | Remote | Distance Learning | Monday |  |  | 2027-10-14 01:00 |  | 0 |  |  | 2027-10-14 01:00 | 2027-11-10 |  | 2027-10-14 01:00 | 2027-10-14 01:00 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required |  | Created | 2026-04-16 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2027.0
YTL Power | Seraya | CCP50 |  |  |  |  | English | English | NU | Gavin Yoong | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 2 | 6 |  | 27-280 | 27-280 - YTL Power - Seraya - CCP50 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | SINGAPORE | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2027-08-12 01:00 |  | 0 |  |  | 2027-08-12 01:00 | 2027-08-20 01:00 |  | 2027-08-12 01:00 | 2027-08-12 01:00 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng | Yes | Created | 2026-04-17 01:00 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
YTL Power | Seraya | CCP50 |  |  |  |  | English | English | NU | Gavin Yoong | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 26-1130 | 26-1130 - YTL Power - Seraya - CCP50 - OTS Simulator Development & Testing - CC Sim | Remote | SINGAPORE | TAS-N | Remote | Distance Learning | Monday |  |  | 2026-12-30 |  | 0 |  |  | 2026-12-30 | 2027-03-04 |  | 2026-12-30 | 2026-12-30 | Request Charles Wal. No additional prep required |  | Created | 2026-04-17 01:00 | US Workweek and Holidays | Charles Wall | Tentative | 2026.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 3 | 27-279 | 27-279 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2028-01-31 | 2028-02-04 | 2028-03-13 01:00 | 2028-03-24 01:00 |  | 2028-03-13 01:00 | 2028-03-13 01:00 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-07 01:00 | US Workweek and Holidays | Rafael Venancio | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 3 | 27-278 | 27-278 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-12-27 | 2027-12-31 | 2028-01-31 | 2028-02-11 |  | 2028-01-31 | 2028-01-31 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 | 3 | 27-277 | 27-277 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-13 01:00 | 2027-05-14 01:00 | 2027-12-13 | 2027-12-17 |  | 2027-12-13 | 2027-12-13 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 5 | 0 | 12 | 3 | 27-276 | 27-276 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Operation-On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-08-16 01:00 | 2027-08-20 01:00 | 2027-11-08 | 2027-11-19 |  | 2027-11-08 | 2027-11-08 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 3 | 27-275 | 27-275 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Control System - Mark VIe Maintenance (Extended) - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-10 01:00 | 2027-05-14 01:00 | 2027-06-28 01:00 | 2027-07-09 01:00 |  | 2027-06-28 01:00 | 2027-06-28 01:00 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 3 | 27-274 | 27-274 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Excitation - Generator Excitation, Protection and Static Starter Introduction - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-04-29 01:00 | 2027-04-30 01:00 | 2027-06-07 01:00 | 2027-06-11 01:00 |  | 2027-06-07 01:00 | 2027-06-07 01:00 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 3 | 27-273 | 27-273 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-02-25 | 2027-02-26 | 2027-05-24 01:00 | 2027-05-28 01:00 |  | 2027-05-24 01:00 | 2027-05-24 01:00 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 3 | 27-272 | 27-272 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-08 | 2027-03-12 | 2027-05-03 01:00 | 2027-05-14 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 | To be added to Marshall Groups 1 and 2 as discussed |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Mohamed Abdelaziz | Tentative | 2027.0
GRE | Lakefield | - | IFF-007927-GT-101-TRX |  |  | I01-120564 / PO 4102885362 | English | English | IB | Patrick Molumby | E-GAS22101 | Gas Turbine - Operation E-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-1129 | 26-1129 - GRE - Lakefield - - - Gas Turbine - Operation E-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Trimont | Customer Site | Monday | Std US Hols |  | 2026-09-28 01:00 |  | 0 | 2026-07-20 01:00 | 2026-08-18 01:00 | 2026-10-05 01:00 | 2026-10-09 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 | Asking for a Fall 2026, does not have to be sequential with the other GRE course, but not in parallel |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Tim Taylor | Confirmed | 2026.0
GRE | Lakefield | - | IFF-007927-GT-101-TRX |  |  | I01-120108 / PO 4102885363 | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 5 | 5 | 0 | 12 |  | 26-1128 | 26-1128 - GRE - Lakefield - - - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | UNITED STATES | TAS-N | Trimont | Customer Site | Monday | Std US Hols |  | 2026-09-14 01:00 |  | 0 | 2026-07-06 01:00 | 2026-07-10 01:00 | 2026-09-28 01:00 | 2026-10-02 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 | Asking for a Fall 2026, does not have to be sequential with the other GRE course, but not in parallel |  | Created | 2026-04-09 01:00 | US Workweek and Holidays | Gerardo Gonzalez;Nasreddine Laroussi | Confirmed | 2026.0
OGE | Redbud | - | IFF-007765-GT-101-TRX |  | IFF-007765-GT-101-TRX | I01-120111 / PO 4102871298 | English | English | IB | Patrick Molumby | Customer-Project Specific | Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation / DLN 2.6+/ Aspirated Haz Gas | Controls | 5 | 10 | 0 | 15 | 2 | 26-1127 | 26-1127 - OGE - Redbud - - - Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation / DLN 2.6+/ Aspirated Haz Gas - G2 | Customer Site | UNITED STATES | TAS-N | Luther | Customer Site | Monday | Std US Holidays |  | 2026-10-12 01:00 |  | 0 | 2026-06-25 01:00 | 2026-09-03 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 | Week of Week of October 12th, 2026 or Week of October 19th, 2026 (Outage ends in September), 3 days prep |  | Created | 2026-04-08 01:00 | US Workweek and Holidays | Martin Acosta | Confirmed | 2026.0
OGE | Redbud | - | IFF-007765-GT-101-TRX |  | IFF-007765-GT-101-TRX | I01-118533 | English | English | IB | Patrick Molumby | Customer-Project Specific | Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation / DLN 2.6+/ Aspirated Haz Gas | Controls | 5 | 10 | 0 | 15 | 1 | 26-1126 | 26-1126 - OGE - Redbud - - - Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation / DLN 2.6+/ Aspirated Haz Gas - G1 | Customer Site | UNITED STATES | TAS-N | Luther | Customer Site | Monday | Std US Holidays |  | 2026-08-03 01:00 |  | 0 | 2026-05-11 01:00 | 2026-05-29 01:00 | 2026-08-03 01:00 | 2026-08-07 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 | Week of August 3rd, 2026 or Week of August 10th, 2026 (Outage starts in September), 10 days prep |  | Created | 2026-04-08 01:00 | US Workweek and Holidays | Martin Acosta | Confirmed | 2026.0
Dominion | Possum Point | AGP Tech -DLN 2.6+ - AFS | PO 4102851145 |  |  | I01-118270 / PO 4102851145 | English | English | IB | Patrick Molumby | E-CON11902 | Control System - DLN 2.6+ Flex Combustor | Controls | 1 | 1 | 1 | 12 |  | 26-1125 | 26-1125 - Dominion - Possum Point - AGP Tech -DLN 2.6+ - AFS - Control System - DLN 2.6+ Flex Combustor | Customer Site | UNITED STATES | TAS-N | Dumfries | Customer Site | Monday | Std US Holidays |  | 2026-04-21 01:00 |  | 0 |  |  | 2026-04-23 01:00 | 2026-04-23 01:00 |  | 2026-04-23 01:00 | 2026-04-23 01:00 | Second session, in addition to 26-1053 |  | Created | 2026-03-31 01:00 | US Workweek and Holidays | Doug Wadsworth | Confirmed | 2026.0
GECOL | - | ZAWIA GT13 | EG0-007248-PE04GPGT01TR |  | IG0-002860-12 |  | English | English | IB | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 10 |  | 26-1124 | 26-1124 - GECOL - - - ZAWIA GT13 - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  | Athene | 2026-06-29 01:00 | 2026-10-05 01:00 | 0 | 2026-04-20 01:00 | 2026-06-03 01:00 | 2026-06-29 01:00 | 2026-07-10 01:00 |  | 2026-06-29 01:00 | 2026-06-29 01:00 | Customer Want date End May but due to CH-Public holidays best start from week 24, capable instructor to deliver this Training is A. Kitanovic or S. Kumar |  | Created | 2026-03-30 01:00 | Birr Workweek and Holidays | Santosh Kumar | Confirmed | 2026.0
RGE | Genera PR | LM2500 XPRESS |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 10 | 10 | 0 | 12 |  | 27-271 | 27-271 - RGE - Genera PR - LM2500 XPRESS - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | PUERTO RICO | TAS-M | San Juan | Customer Site | Monday |  |  | 2027-01-04 |  | 0 |  |  | 2027-07-05 01:00 | 2027-07-16 01:00 |  | 2027-07-05 01:00 | 2027-07-05 01:00 | Greg to resource / Prep 3 months before start date to consider translation time, since material is required in Spanish. Commission until at least March of 2027 |  | Created | 2026-03-27 01:00 | US Workweek and Holidays |  | Resourcing In Progress | 2027.0
RGE | Genera PR | LM2500 XPRESS |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 27-270 | 27-270 - RGE - Genera PR - LM2500 XPRESS - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | PUERTO RICO | TAS-M | San Juan | Customer Site | Monday |  |  | 2027-01-04 |  | 0 |  |  | 2027-07-19 01:00 | 2027-07-30 01:00 |  | 2027-07-19 01:00 | 2027-07-19 01:00 | Greg to resource / Prep 3 months before start date to consider translation time, since material is required in Spanish. Commission until at least March of 2027 |  | Created | 2026-03-27 01:00 | US Workweek and Holidays |  | Resourcing In Progress | 2027.0
RGE | Genera PR | LM2500 XPRESS |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-269 | 27-269 - RGE - Genera PR - LM2500 XPRESS - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | PUERTO RICO | TAS-M | San Juan | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2027-04-26 01:00 | 2027-04-30 01:00 | 2027-06-28 01:00 | 2027-07-02 01:00 |  | 2027-06-28 01:00 | 2027-06-28 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish. Commission until at least March of 2027 |  | Created | 2026-03-27 01:00 | US Workweek and Holidays | John Selman | Tentative | 2027.0
RGE | Genera PR | LM2500 XPRESS |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10202 | Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Aeroderivative | 5 | 3 | 0 | 12 |  | 27-268 | 27-268 - RGE - Genera PR - LM2500 XPRESS - Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Customer Site | PUERTO RICO | TAS-M | San Juan | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2027-04-19 01:00 | 2027-04-21 01:00 | 2027-06-21 01:00 | 2027-06-25 01:00 |  | 2027-06-21 01:00 | 2027-06-21 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish. Commission until at least March of 2027 |  | Created | 2026-03-27 01:00 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
RGE | Genera PR | LM2500 XPRESS |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-267 | 27-267 - RGE - Genera PR - LM2500 XPRESS - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | PUERTO RICO | TAS-M | San Juan | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2026-10-05 01:00 | 2026-10-09 01:00 | 2027-06-14 01:00 | 2027-06-18 01:00 |  | 2027-06-14 01:00 | 2027-06-14 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish. Commission until at least March of 2027 |  | Created | 2026-03-27 01:00 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Oneta Power LLC | - | - |  |  |  |  | English | English | IB | Patrick Molumby | Customer-Project Specific | Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation & Aspirated Hazardous Gas System | Controls | 3 | 3 | 1 | 12 | 2 | 27-266 | 27-266 - Oneta Power LLC - - - - - Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation & Aspirated Hazardous Gas System - G2 | Customer Site | UNITED STATES | TAS-N | Broken Arrow | Customer Site | Monday | Std US Hols |  | 2027-03-08 |  | 0 | 2027-12-27 | 2027-12-29 | 2027-02-01 | 2027-02-03 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Oneta Power LLC | - | - | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | IB | Patrick Molumby | Customer-Project Specific | Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation & Aspirated Hazardous Gas System | Controls | 3 | 5 | 2 | 12 | 1 | 26-1102 | 26-1102 - Oneta Power LLC - - - - - Control System - OpFlex Enhanced Transient Stability with AutoTune DX and Cold Day Performance Operation & Aspirated Hazardous Gas System - G1 | Customer Site | UNITED STATES | TAS-N | Broken Arrow | Customer Site | Monday | Std US Hols |  | 2026-06-08 01:00 |  | 0 | 2027-03-15 01:00 | 2027-03-19 01:00 | 2027-06-15 01:00 | 2027-06-17 01:00 |  | 2027-06-15 01:00 | 2027-06-15 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2026.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 27-265 | 27-265 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-08-09 01:00 | 2027-08-13 01:00 | 2027-09-20 01:00 | 2027-09-24 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 15 |  | 27-264 | 27-264 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-08-02 01:00 | 2027-08-06 01:00 | 2027-09-13 01:00 | 2027-09-17 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 15 |  | 27-263 | 27-263 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-06-21 01:00 | 2027-06-25 01:00 | 2027-09-06 01:00 | 2027-09-10 01:00 |  | 2027-09-06 01:00 | 2027-09-06 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS22101 | Gas Turbine - Operation E-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 15 |  | 27-262 | 27-262 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Gas Turbine - Operation E-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-06-14 01:00 | 2027-06-17 01:00 | 2027-08-30 01:00 | 2027-09-03 01:00 |  | 2027-08-30 01:00 | 2027-08-30 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 15 |  | 27-261 | 27-261 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-07-05 01:00 | 2027-07-09 01:00 | 2027-08-23 01:00 | 2027-08-27 01:00 |  | 2027-08-23 01:00 | 2027-08-23 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Khaled Al Behiri | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13412 | Control System - Mark VIe Distributed Control System Operation | Controls | 5 | 5 | 0 | 12 |  | 27-260 | 27-260 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Control System - Mark VIe Distributed Control System Operation | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-07-12 01:00 | 2027-07-16 01:00 | 2027-08-16 01:00 | 2027-08-20 01:00 |  | 2027-08-16 01:00 | 2027-08-16 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Bharat Vispara | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-259 | 27-259 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-06-28 01:00 | 2027-07-09 01:00 | 2027-08-02 01:00 | 2027-08-13 01:00 |  | 2027-08-02 01:00 | 2027-08-02 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Bharat Vispara | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 15 |  | 27-258 | 27-258 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-06-10 01:00 | 2027-06-16 01:00 | 2027-07-26 01:00 | 2027-07-30 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 15 |  | 27-257 | 27-257 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-06-07 01:00 | 2027-06-09 01:00 | 2027-07-19 01:00 | 2027-07-21 01:00 |  | 2027-07-19 01:00 | 2027-07-19 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 15 |  | 27-256 | 27-256 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-05-24 01:00 | 2027-06-07 01:00 | 2027-07-05 01:00 | 2027-07-16 01:00 |  | 2027-07-05 01:00 | 2027-07-05 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2027.0
Venture Global LNG | Calcasieu Pass 2 | Ph 2 | EGM-00412-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 |  | 27-255 | 27-255 - Venture Global LNG - Calcasieu Pass 2 - Ph 2 - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Calcasieu | Customer Site | Monday | Std US Hols |  | 2027-08-16 01:00 |  | 0 | 2027-05-03 01:00 | 2027-05-14 01:00 | 2027-06-21 01:00 | 2027-07-02 01:00 |  | 2027-06-21 01:00 | 2027-06-21 01:00 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Tim Taylor | Tentative | 2027.0
PUBLIC POWER CORPORATION SA | - | Megalopolis | IFF-007322-CC-101-TRX |  | IFF-007322-CC-101-TRX |  | English | English | IB | Anna Petrella | E-CON10801 | Control System - ActivePoint HMI Operation Familiarization | Controls | 3 | 3 | 0 | 12 |  | 26-1101 | 26-1101 - PUBLIC POWER CORPORATION SA - - - Megalopolis - Control System - ActivePoint HMI Operation Familiarization | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday |  |  | 2026-10-28 01:00 | 2026-10-28 01:00 | 0 | 2026-09-09 01:00 | 2026-09-11 01:00 | 2026-11-04 | 2026-11-06 |  | 2026-11-04 | 2026-11-04 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Martin Acosta | Confirmed | 2026.0
PUBLIC POWER CORPORATION SA | - | Megalopolis | IFF-007322-CC-101-TRX |  | IFF-007322-CC-101-TRX |  | English | English | IB | Anna Petrella | E-CON23409 | Control System - OpFlex Enhanced Transient Stability with AutoTune MX & Variable Load Path Operation | Controls | 2 | 2 | 0 | 12 |  | 26-1100 | 26-1100 - PUBLIC POWER CORPORATION SA - - - Megalopolis - Control System - OpFlex Enhanced Transient Stability with AutoTune MX & Variable Load Path Operation | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday |  |  | 2026-10-26 01:00 | 2026-10-25 01:00 | 0 | 2026-09-04 01:00 | 2026-09-08 01:00 | 2026-11-02 | 2026-11-03 |  | 2026-11-02 | 2026-11-02 |  |  | Created | 2026-03-24 01:00 | US Workweek and Holidays | Martin Acosta | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | English | Mandarin Chinese | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 | 3 | 26-1099 | 26-1099 - TPC - Datan - 8&9 Local Training - Balance of Plant - Operation (GE Integrated Systems) - G3 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Datan | Distance Learning | Monday |  |  | 2026-11-01 01:00 |  | 0 | 2026-06-17 01:00 | 2026-06-18 01:00 | 2026-07-13 01:00 | 2026-07-17 01:00 |  | 2026-07-13 01:00 | 2026-07-13 01:00 | Customer request this course to replace 26-266 ST Opt |  | Created | 2026-03-18 01:00 | US Workweek and Holidays | Jeff Ogletree | Cancelled | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | I01-109845 / PO 4102695663 | English | Mandarin Chinese | NU | Gavin Yoong | Customer-Project Specific | HRSG- Operation & Maintenance (GE Engineered) with SCR | HRSG | 5 | 2 | 0 | 12 | 3 | 26-1098 | 26-1098 - TPC - Datan - 8&9 Local Training - HRSG- Operation & Maintenance (GE Engineered) with SCR - G3 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Datan | Distance Learning | Monday |  |  | 2026-10-26 01:00 |  | 0 | 2026-06-15 01:00 | 2026-06-16 01:00 | 2026-07-13 01:00 | 2026-07-17 01:00 |  |  | 2026-07-13 01:00 | Customer request this course to replace 26-266 ST Opt |  | Created | 2026-03-17 01:00 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
GP SCS | - | Migration Alspa to MarkVIe | IG0-002859-12 |  | IG0-002859-12 |  | English | English | IB | Anna Petrella | Customer-Project Specific | Development Legacy ALSTOM Control System to Mark Vie Ugrade | Controls | 10 | 23 | 0 | 12 |  | 26-1097 | 26-1097 - GP SCS - - - Migration Alspa to MarkVIe - Development Legacy ALSTOM Control System to Mark Vie Ugrade | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-01-04 |  | 0 | 2026-05-15 01:00 | 2026-09-25 01:00 | 2026-10-19 01:00 | 2026-10-30 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 | For Prep please consider total 33 days (including development, delivery and close out). Please connect with Pablo to schedule this request. Santosh Kumar and Aleksandar Kitanovic are the only instructors capabel for this request. Development is 23 days and Delivery is 10 days | Yes | Created | 2026-03-13 01:00 | Birr Workweek and Holidays | Aleksandar Kitanovic | Confirmed | 2026.0
TAIS Turkish Navi - MIL | - | MILGEM |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 | 4 | 26-1095 | 26-1095 - TAIS Turkish Navi - MIL - - - MILGEM - Gas Turbine - LM2500 Level 1 Maintenance - G4 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-12-14 | 2026-12-17 | 0 | 2027-02-01 | 2027-02-03 | 2027-04-05 01:00 | 2027-04-09 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2026-03-13 01:00 | US Workweek and Holidays | Elias Benedi | Tentative | 2026.0
TAIS Turkish Navi - MIL | - | MILGEM |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 | 3 | 26-1094 | 26-1094 - TAIS Turkish Navi - MIL - - - MILGEM - Gas Turbine - LM2500 Level 1 Maintenance - G3 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-12-07 | 2026-11-11 | 0 |  |  | 2026-12-07 | 2026-12-11 |  | 2026-12-07 | 2026-12-07 |  |  | Created | 2026-03-13 01:00 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
TAIS Turkish Navi - MIL | - | MILGEM |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 | 2 | 26-1093 | 26-1093 - TAIS Turkish Navi - MIL - - - MILGEM - Gas Turbine - LM2500 Level 1 Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-30 | 2026-04-11 01:00 | 0 |  |  | 2026-11-30 | 2026-12-04 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2026-03-13 01:00 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
TAIS Turkish Navi - MIL | - | MILGEM |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 | 1 | 26-1092 | 26-1092 - TAIS Turkish Navi - MIL - - - MILGEM - Gas Turbine - LM2500 Level 1 Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-11-23 | 2026-11-25 | 0 | 2026-09-08 01:00 | 2026-09-11 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 |  |  | Created | 2026-03-13 01:00 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
TVA | - | Cumberland | EGM-00329-1CSTO-TRAINALL |  | EGM-00329-1CSTO-TRAINALL | I01-117856 / PO 4102841700 | English | English | IB | Patrick Molumby | Customer-Project Specific | 7HA.03 AutoTune | Controls | 1 | 5 | 2 | 12 |  | 26-1091 | 26-1091 - TVA - - - Cumberland - 7HA.03 AutoTune | Customer Site | UNITED STATES | TAS-N | Cumberland | Customer Site | Monday |  |  | 2026-03-27 01:00 | 2026-03-29 01:00 | 0 | 2026-03-17 01:00 | 2026-03-20 01:00 | 2026-03-26 01:00 | 2026-03-26 01:00 |  | 2026-03-26 01:00 | 2026-03-26 01:00 | Short Notice Request |  | Created | 2026-03-13 01:00 | US Workweek and Holidays | Martin Acosta | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 26-1089 | 26-1089 - YTL - Power Seraya - 1 x 9HA.01 SS - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 |  |  | 2026-08-24 01:00 | 2026-09-01 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 26-1088 | 26-1088 - YTL - Power Seraya - 1 x 9HA.01 SS - Electrical - Electrical Control System (ECS) Training | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 |  |  | 2026-09-02 01:00 | 2026-09-04 01:00 |  | 2026-09-02 01:00 | 2026-09-02 01:00 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 |  | 26-1087 | 26-1087 - YTL - Power Seraya - 1 x 9HA.01 SS - Balance of Plant - Operation (GE Integrated Systems) | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-11-04 | 2026-11-10 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 26-1086 | 26-1086 - YTL - Power Seraya - 1 x 9HA.01 SS - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-11-02 | 2026-11-03 | 2027-01-19 | 2027-01-21 |  | 2027-01-19 | 2027-01-19 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 26-1085 | 26-1085 - YTL - Power Seraya - 1 x 9HA.01 SS - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-09-28 01:00 | 2026-10-23 01:00 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL | I01-120520 / PO 4102863257 | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-1084 | 26-1084 - YTL - Power Seraya - 1 x 9HA.01 SS - Control System - Mark VIe Maintenance (Extended) | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-07-13 01:00 | 2026-08-07 01:00 | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-1083 | 26-1083 - YTL - Power Seraya - 1 x 9HA.01 SS - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-10-19 01:00 | 2026-10-23 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-1082 | 26-1082 - YTL - Power Seraya - 1 x 9HA.01 SS - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-09-07 01:00 | 2026-09-11 01:00 | 2026-11-09 | 2026-11-13 |  | 2026-11-09 | 2026-11-09 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL | PO 4102863257 | English | English | NU | Gavin Yoong | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 26-1081 | 26-1081 - YTL - Power Seraya - 1 x 9HA.01 SS - Steam Turbine - Maintenance | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-08-06 01:00 | 2026-08-12 01:00 | 2026-12-14 | 2026-12-18 |  | 2026-12-14 | 2026-12-14 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL | PO 4102863257 | English | English | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 26-1080 | 26-1080 - YTL - Power Seraya - 1 x 9HA.01 SS - Steam Turbine - Operation | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-07-09 01:00 | 2026-08-05 01:00 | 2026-11-30 | 2026-12-11 |  | 2026-11-30 | 2026-11-30 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-1079 | 26-1079 - YTL - Power Seraya - 1 x 9HA.01 SS - Gas Turbine - Maintenance | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-09-28 01:00 | 2026-10-02 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Mohamed Abdelaziz | Confirmed | 2026.0
YTL | Power Seraya | 1 x 9HA.01 SS | EGM-00493-1CSTO-TRAINALL |  | EGM-00493-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-1078 | 26-1078 - YTL - Power Seraya - 1 x 9HA.01 SS - Gas Turbine - Operation | Customer Site | SINGAPORE | TAS-N | Jurong Island | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-09-14 01:00 | 2026-09-25 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 | Q3-Q4 2026 into 2027 |  | Created | 2026-03-09 01:00 | US Workweek and Holidays | Mohamed Abdelaziz | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin | NU | Gavin Yoong | E-GEN10403 | Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Generator | 5 | 5 | 0 | 12 |  | 26-1077 | 26-1077 - TPC - Hsinta - - - Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Distance Learning | Monday |  |  | 2026-12-15 |  | 0 | 2027-01-12 | 2027-01-15 | 2027-02-22 | 2027-02-26 |  | 2027-02-22 | 2027-02-22 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  |  | English | Mandarin | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 |  | 27-254 | 27-254 - TPC - Hsinta - - - Balance of Plant - Operation (GE Integrated Systems) | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Distance Learning | Monday | Feb 5 - 10 |  | 2027-01-01 |  | 0 | 2026-12-23 | 2026-12-29 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2027.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  |  | English | Mandarin | NU | Gavin Yoong | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 |  | 27-253 | 27-253 - TPC - Hsinta - - - Balance of Plant - Operation (GE Integrated Systems) | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Distance Learning | Monday | Feb 5 - 10 |  | 2027-01-01 |  | 0 | 2027-01-25 | 2027-01-29 | 2027-02-15 | 2027-02-19 |  | 2027-02-15 | 2027-02-15 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Dave Miller | Tentative | 2027.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  | I01-115476 / PO 4102794272 | English | Mandarin | NU | Gavin Yoong | Customer-Project Specific | HRSG - Operation & Maintenance (GE Engineered) & SCR | HRSG | 5 | 10 | 0 | 12 |  | 26-1076 | 26-1076 - TPC - Hsinta - - - HRSG - Operation & Maintenance (GE Engineered) & SCR | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Distance Learning | Monday | June 19 |  | 2026-06-29 01:00 |  | 0 |  |  | 2026-06-29 01:00 | 2026-07-03 01:00 |  | 2026-06-29 01:00 | 2026-06-29 01:00 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  | I01-115476 / PO 4102794272 | English | Mandarin | NU | Gavin Yoong | Customer-Project Specific | HRSG - Operation & Maintenance (GE Engineered) & SCR | HRSG | 5 | 10 | 0 | 12 |  | 26-1075 | 26-1075 - TPC - Hsinta - - - HRSG - Operation & Maintenance (GE Engineered) & SCR | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Distance Learning | Monday | June 19 |  | 2026-06-01 01:00 |  | 0 | 2026-04-20 01:00 | 2026-04-24 01:00 | 2026-06-01 01:00 | 2026-06-09 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  | I01-115476 / PO 4102794272 | English | Mandarin | NU | Gavin Yoong | E-CON33402 | Control System - Proficy CIMPLICITY for Turbine Controls (Advanced) | Controls | 5 | 5 | 0 | 12 |  | 26-1074 | 26-1074 - TPC - Hsinta - - - Control System - Proficy CIMPLICITY for Turbine Controls (Advanced) | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Distance Learning | Monday |  |  | 2026-11-30 |  | 0 | 2026-10-12 01:00 | 2026-10-16 01:00 | 2026-11-30 | 2026-12-04 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Rafael Venancio | Cancelled | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL | I01-115476 / PO 4102794272 | English | Mandarin | NU | Gavin Yoong | E-CON33402 | Control System - Proficy CIMPLICITY for Turbine Controls (Advanced) | Controls | 5 | 9 | 0 | 12 |  | 26-1073 | 26-1073 - TPC - Hsinta - - - Control System - Proficy CIMPLICITY for Turbine Controls (Advanced) | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday |  |  | 2026-08-03 01:00 |  | 0 | 2026-05-26 01:00 | 2026-07-24 01:00 | 2026-09-07 01:00 | 2026-09-11 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 6 | 5 | 0 | 12 |  | 26-1072 | 26-1072 - TPC - Hsinta - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday | Oct 9, 10 |  | 2026-10-02 01:00 |  | 0 | 2026-05-11 01:00 | 2026-05-15 01:00 | 2026-08-28 01:00 | 2026-09-04 01:00 |  | 2026-08-28 01:00 | 2026-08-28 01:00 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 2 | 12 |  | 26-1071 | 26-1071 - TPC - Hsinta - - - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday |  |  | 2026-12-07 |  | 0 | 2026-07-06 01:00 | 2026-07-10 01:00 | 2026-08-21 01:00 | 2026-08-27 01:00 |  | 2026-08-21 01:00 | 2026-08-21 01:00 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-252 | 27-252 - TPC - Hsinta - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday | Feb 5 - 10 |  | 2027-01-01 |  | 0 | 2027-01-07 | 2027-01-11 | 2027-01-18 | 2027-01-22 |  | 2027-01-18 | 2027-01-18 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | Mandarin | NU | Gavin Yoong | E-GEN10403 | Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Generator | 5 | 5 | 0 | 12 |  | 27-251 | 27-251 - TPC - Hsinta - - - Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday | Feb 5 - 10 |  | 2027-01-01 |  | 0 |  |  | 2027-03-08 | 2027-03-12 |  | 2027-03-08 | 2027-03-08 |  |  | Created | 2026-03-11 01:00 | US Workweek and Holidays | Hichem Mesli | Tentative | 2027.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  |  | English | Mandarin | NU | Gavin Yoong | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 27-250 | 27-250 - TPC - Hsinta - - - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday | Feb 5 - 10 |  | 2027-01-01 |  | 0 |  |  | 2027-01-07 | 2027-01-15 |  | 2027-01-07 | 2027-01-07 |  | No | Created | 2026-03-10 01:00 | US Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2027.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  |  | English | Mandarin | NU | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 27-249 | 27-249 - TPC - Hsinta - - - Electrical - Electrical Control System (ECS) Training | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Hsinta | Customer Site | Monday | Feb 5 - 10 |  | 2027-01-01 |  | 0 |  |  | 2027-01-04 | 2027-01-06 |  | 2027-01-04 | 2027-01-04 |  | No | Created | 2026-03-10 01:00 | US Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2027.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  | IFF-007458-GT-101-TRX |  | English | English | IB | Abuobaida El Mansoor | O-ELX20201 | Excitation - EX2100 Generator Excitation Maintenance (Advanced) | Excitation | 5 | 0 | 0 | 8 |  | 26-1070 | 26-1070 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Excitation - EX2100 Generator Excitation Maintenance (Advanced) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-12-07 | 2026-12-11 |  | 2026-12-07 | 2026-12-07 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Zakaria Al-Qawasmeh | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  | IFF-007458-GT-101-TRX |  | English | English | IB | Abuobaida El Mansoor | Customer-Project Specific | Excitation - EX2100 Generator Operation | Excitation | 1 | 0 | 0 | 8 |  | 26-1069 | 26-1069 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Excitation - EX2100 Generator Operation | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-12-04 | 2026-12-04 |  | 2026-12-04 | 2026-12-04 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Zakaria Al-Qawasmeh | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  | IFF-007458-GT-101-TRX |  | English | English | IB | Abuobaida El Mansoor | Customer-Project Specific | Excitation - EX2100 Maintenance | Excitation | 4 | 2 | 0 | 8 |  | 26-1068 | 26-1068 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Excitation - EX2100 Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-05-07 01:00 | 2026-05-08 01:00 | 2026-11-30 | 2026-12-03 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Zakaria Al-Qawasmeh | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS22101 | Gas Turbine - Operation E-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 8 |  | 26-1067 | 26-1067 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Gas Turbine - Operation E-Class (Advanced) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-09-07 01:00 | 2026-09-11 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Salvatore Genovese | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS10401 | Gas Turbine - Familiarization for Power Plant Management | Gas Turbine | 5 | 5 | 0 | 8 | 2 | 26-1066 | 26-1066 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Gas Turbine - Familiarization for Power Plant Management - G2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-09-14 01:00 | 2026-09-18 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Salvatore Genovese | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  |  |  | English | English | IB | Abuobaida El Mansoor | E-CON23404 | Control System - Mark VIe Troubleshooting (Advanced) | Controls | 5 | 1 | 0 | 8 |  | 26-1065 | 26-1065 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Control System - Mark VIe Troubleshooting (Advanced) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-07-28 01:00 | 2026-07-28 01:00 | 2026-09-21 01:00 | 2026-09-25 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Khaled Al Behiri | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  | IFF-007458-GT-101-TRX | I01-120151 / PO 4102886869 | English | English | IB | Abuobaida El Mansoor | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 5 | 0 | 8 |  | 26-1064 | 26-1064 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Control System - Mark VIe Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-06-15 01:00 | 2026-07-27 01:00 | 2026-09-14 01:00 | 2026-09-18 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Khaled Al Behiri | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 8 |  | 26-1063 | 26-1063 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Gas Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-09-21 01:00 | 2026-09-25 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Salvatore Genovese | Cancelled | 2026.0
UPPER EGYPT ELECTRICITY PRODUCTION COMPANY | Assyut | CSA | IFF-007458-GT-101-TRX |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GAS10401 | Gas Turbine - Familiarization for Power Plant Management | Gas Turbine | 5 | 5 | 0 | 8 | 1 | 26-1062 | 26-1062 - UPPER EGYPT ELECTRICITY PRODUCTION COMPANY - Assyut - CSA - Gas Turbine - Familiarization for Power Plant Management - G1 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-08-31 01:00 | 2026-09-04 01:00 |  | 2026-08-31 01:00 | 2026-08-31 01:00 |  |  | Created | 2026-02-25 | Birr Workweek and Holidays | Salvatore Genovese | Cancelled | 2026.0
SENELEC | SAINT LOUIS | 250MW CCGT AKSA | EGM-00438-1CSTO-TRAINALL |  | IFF-007632-CC-101-TRX | I01-120606 / PO 4200331964 | French | French | IB | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 1 | 12 |  | 26-1061 | 26-1061 - SENELEC - SAINT LOUIS - 250MW CCGT AKSA - Control System - Mark VIe Maintenance (Extended) | Customer Site | SENEGAL | TAS-M | DAKAR | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-07-20 01:00 | 2026-08-21 01:00 | 2026-10-19 01:00 | 2026-10-30 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Nasreddine Laroussi | Tentative | 2026.0
SENELEC | SAINT LOUIS | 250MW CCGT AKSA | EGM-00438-1CSTO-TRAINALL |  | IFF-007632-CC-101-TRX |  | French | French | IB | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-1060 | 26-1060 - SENELEC - SAINT LOUIS - 250MW CCGT AKSA - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SENEGAL | TAS-M | DAKAR | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-05-25 01:00 | 2026-05-29 01:00 | 2026-10-26 01:00 | 2026-10-30 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2026.0
SENELEC | SAINT LOUIS | 250MW CCGT AKSA | EGM-00438-1CSTO-TRAINALL |  | IFF-007632-CC-101-TRX |  | French | French | IB | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 3 | 26-1059 | 26-1059 - SENELEC - SAINT LOUIS - 250MW CCGT AKSA - Gas Turbine - Maintenance - G3 | Customer Site | SENEGAL | TAS-M | DAKAR | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Salvatore Genovese | Tentative | 2026.0
SENELEC | SAINT LOUIS | 250MW CCGT AKSA | EGM-00438-1CSTO-TRAINALL |  | IFF-007632-CC-101-TRX |  | French | French | IB | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 26-1058 | 26-1058 - SENELEC - SAINT LOUIS - 250MW CCGT AKSA - Gas Turbine - Operation - G1 | Customer Site | SENEGAL | TAS-M | DAKAR | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 |  |  | 2026-09-28 01:00 | 2026-10-09 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Salvatore Genovese | Tentative | 2026.0
AL-KHAFJI JOINT OPERATIONS | KJO | KJO |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 5 | 2 | 0 | 12 | 3 | 26-1057 | 26-1057 - AL-KHAFJI JOINT OPERATIONS - KJO - KJO - Control System - Mark VIe Migration from Mark V (HMI on 1st day) - G3 | Learning Center | UNITED STATES | TAS-M | Houston | Houston Learning Center | Sunday |  |  | 2027-06-07 01:00 |  | 0 | 2026-11-19 | 2026-11-20 | 2027-02-08 | 2027-02-12 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2026.0
AL-KHAFJI JOINT OPERATIONS | KJO | KJO |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 5 | 3 | 0 | 12 | 2 | 26-1056 | 26-1056 - AL-KHAFJI JOINT OPERATIONS - KJO - KJO - Control System - Mark VIe Migration from Mark V (HMI on 1st day) - G2 | Learning Center | UNITED STATES | TAS-M | Houston | Houston Learning Center | Sunday |  |  | 2027-06-07 01:00 |  | 0 | 2026-11-16 | 2026-11-18 | 2027-02-01 | 2027-02-05 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2026.0
AL-KHAFJI JOINT OPERATIONS | KJO | KJO |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 5 | 5 | 0 | 12 | 1 | 26-1055 | 26-1055 - AL-KHAFJI JOINT OPERATIONS - KJO - KJO - Control System - Mark VIe Migration from Mark V (HMI on 1st day) - G1 | Learning Center | UNITED STATES | TAS-M | Houston | Houston Learning Center | Sunday |  |  | 2027-06-07 01:00 |  | 0 | 2026-10-26 01:00 | 2026-10-30 01:00 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 |  |  | Created | 2026-02-25 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2026.0
Dominion | Possum Point | AGP Tech -DLN 2.6+ - AFS |  |  |  |  | English | English | IB | Patrick Molumby | E-GAS22201 | Gas Turbine - Operation F-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-1054 | 26-1054 - Dominion - Possum Point - AGP Tech -DLN 2.6+ - AFS - Gas Turbine - Operation F-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Dumfries | Customer Site | Monday | Std US Holidays |  | 2026-04-13 01:00 |  | 0 | 2026-03-09 01:00 | 2026-03-13 01:00 | 2026-04-06 01:00 | 2026-04-10 01:00 |  | 2026-04-06 01:00 | 2026-04-06 01:00 | From requestor…"outage beginning in March and ending May 19th. Would it be possible to have an onsite training for the 26+ Flex course by May, and possibly the advanced class in same time frame or later? " |  | Created | 2026-02-17 | US Workweek and Holidays | Tom Walsh | Cancelled | 2026.0
Dominion | Possum Point | AGP Tech -DLN 2.6+ - AFS | PO 4102851145 |  |  | I01-118270 / PO 4102851145 | English | English | IB | Patrick Molumby | E-CON11902 | Control System - DLN 2.6+ Flex Combustor | Controls | 1 | 1 | 1 | 12 |  | 26-1053 | 26-1053 - Dominion - Possum Point - AGP Tech -DLN 2.6+ - AFS - Control System - DLN 2.6+ Flex Combustor | Customer Site | UNITED STATES | TAS-N | Dumfries | Customer Site | Monday | Std US Holidays |  | 2026-04-07 01:00 |  | 0 | 2026-04-06 01:00 | 2026-04-06 01:00 | 2026-04-22 01:00 | 2026-04-22 01:00 |  | 2026-04-22 01:00 | 2026-04-22 01:00 | From requestor…"outage beginning in March and ending May 19th. Would it be possible to have an onsite training for the 26+ Flex course by May, and possibly the advanced class in same time frame or later? " |  | Created | 2026-02-17 | US Workweek and Holidays | Doug Wadsworth | Confirmed | 2026.0
NRG | Jewett | Phase 2 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 31-2 | 31-2 - NRG - Jewett - Phase 2 - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2031-01-06 |  | 0 |  |  | 2031-01-06 | 2031-01-31 |  | 2031-01-06 | 2031-01-06 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required |  | Created | 2026-02-12 | US Workweek and Holidays | Charles Wall | Tentative | 2031.0
NRG | Jewett | Phase 2 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 30-9 | 30-9 - NRG - Jewett - Phase 2 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2030-01-07 |  | 0 |  |  | 2030-01-07 | 2030-01-15 |  | 2030-01-07 | 2030-01-07 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng |  | Created | 2026-02-12 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2030.0
NRG | Jewett | Phase 2 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 29-19 | 29-19 - NRG - Jewett - Phase 2 - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2029-07-16 01:00 |  | 0 |  |  | 2029-07-16 01:00 | 2029-09-13 01:00 |  | 2029-07-16 01:00 | 2029-07-16 01:00 | Request Charles Wal. No additional prep required This will likely have the same scope as 29-14 NRG Jewett Phase 1, so scheduling both at the same time |  | Created | 2026-02-12 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
TPC | Hsinta | 2026 | EGM-00165-1CSTO-TRAINALL |  |  | I01-115476 | English | English | NU | Gavin Yoong | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 | 2 | 26-1050 | 26-1050 - TPC - Hsinta - 2026 - Combined Cycle - Operation (GE Integrated Systems) - G2 | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2026-03-02 |  | 0 | 2026-02-17 | 2026-02-20 | 2026-03-02 | 2026-03-06 |  | 2026-03-02 | 2026-03-02 | Short Notice request |  | Created | 2026-02-04 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
Arabelle Solutions | Cernavoda | - |  |  |  |  | English | English | IB | Anna Petrella | E-GEN10901 | Generator - Hydrogen Cooling System Operation & Maintenance | Generator | 3 | 3 | 0 | 6 |  | 26-1049 | 26-1049 - Arabelle Solutions - Cernavoda - - - Generator - Hydrogen Cooling System Operation & Maintenance | Customer Site | ROMANIA | TAS-N | Cernavoda | Customer Site | Monday | - |  | 2026-08-10 01:00 | 2026-08-11 01:00 | 0 | 2025-12-01 | 2025-12-03 | 2026-01-05 | 2026-01-07 |  | 2026-01-05 | 2026-01-05 | Customer needs training in second half of 2026 |  | Created | 2026-01-30 | US Workweek and Holidays |  | Cancelled | 2026.0
Arabelle Solutions | Cernavoda | - |  |  |  |  | English | English | IB | Anna Petrella | E-GEN10301 | Generator - Mechanical Systems & Components | Generator | 5 | 5 | 0 | 6 |  | 26-1048 | 26-1048 - Arabelle Solutions - Cernavoda - - - Generator - Mechanical Systems & Components | Customer Site | ROMANIA | TAS-N | Cernavoda | Customer Site | Monday | - |  | 2026-08-03 01:00 | 2026-08-06 01:00 | 0 | 2025-12-01 | 2025-12-05 | 2026-01-05 | 2026-01-09 |  | 2026-01-05 | 2026-01-05 | Customer needs training in second half of 2026 |  | Created | 2026-01-30 | US Workweek and Holidays | Vito Franco | Cancelled | 2026.0
Arabelle Solutions | Cernavoda | - |  |  |  |  | English | English | IB | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 6 |  | 26-1047 | 26-1047 - Arabelle Solutions - Cernavoda - - - Steam Turbine - Maintenance | Customer Site | ROMANIA | TAS-N | Cernavoda | Customer Site | Monday | - |  | 2026-04-27 01:00 | 2026-04-30 01:00 | 0 | 2025-12-01 | 2025-12-05 | 2026-01-05 | 2026-01-09 |  | 2026-01-05 | 2026-01-05 | Customer needs training before May 2026 |  | Created | 2026-01-30 | US Workweek and Holidays |  | Cancelled | 2026.0
Arabelle Solutions | Cernavoda | - |  |  |  |  | English | English | IB | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 6 |  | 26-1046 | 26-1046 - Arabelle Solutions - Cernavoda - - - Steam Turbine - Operation | Customer Site | ROMANIA | TAS-N | Cernavoda | Customer Site | Monday | - |  | 2026-04-13 01:00 | 2026-04-22 01:00 | 0 | 2025-12-01 | 2025-12-12 | 2026-01-05 | 2026-01-16 |  | 2026-01-05 | 2026-01-05 | Customer needs training before May 2026 |  | Created | 2026-01-30 | US Workweek and Holidays |  | Cancelled | 2026.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.03 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 27-248 | 27-248 - ACWA - Quarayah IPP - Hajr Expansion 7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2027-02-01 |  | 0 |  |  | 2026-10-22 01:00 | 2026-10-30 01:00 |  | 2026-10-22 01:00 | 2026-10-22 01:00 |  |  | Created | 2026-01-24 | Birr Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2027.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.03 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 27-247 | 27-247 - ACWA - Quarayah IPP - Hajr Expansion 7HA.03 - Electrical - Electrical Control System (ECS) Training | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2027-02-01 |  | 0 |  |  | 2026-10-19 01:00 | 2026-10-21 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2026-01-24 | Birr Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2027.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.03 | IFF-007958-CC-101-FSX |  |  | I01-120553 / PO 4200331966 | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-246 | 27-246 - ACWA - Quarayah IPP - Hajr Expansion 7HA.03 - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2027-02-01 |  | 0 | 2026-07-13 01:00 | 2026-07-31 01:00 | 2026-10-05 01:00 | 2026-10-16 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2026-01-24 | Birr Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.03 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-245 | 27-245 - ACWA - Quarayah IPP - Hajr Expansion 7HA.03 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2027-02-01 |  | 0 | 2026-07-27 01:00 | 2026-07-31 01:00 | 2026-09-28 01:00 | 2026-10-02 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2026-01-24 | Birr Workweek and Holidays | Joe Mcandrews | Tentative | 2027.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.03 | IFF-007958-CC-101-FSX |  |  | I01-120552 / PO 4200331965 | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-244 | 27-244 - ACWA - Quarayah IPP - Hajr Expansion 7HA.03 - Gas Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2027-02-01 |  | 0 | 2026-07-13 01:00 | 2026-07-17 01:00 | 2026-09-21 01:00 | 2026-09-25 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2026-01-24 | Birr Workweek and Holidays | Agustin Collado | Tentative | 2027.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.03 | IFF-007958-CC-101-FSX |  | IFF-007958-CC-101-FSX |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 7 | 0 | 12 |  | 27-243 | 27-243 - ACWA - Quarayah IPP - Hajr Expansion 7HA.03 - Gas Turbine - Operation | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2027-02-01 |  | 0 | 2026-06-08 01:00 | 2026-07-03 01:00 | 2026-09-07 01:00 | 2026-09-18 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2026-01-24 | Birr Workweek and Holidays | Hichem Mesli | Tentative | 2027.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.02 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 26-1045 | 26-1045 - ACWA - Quarayah IPP - Hajr Expansion 7HA.02 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2026-07-06 01:00 |  | 0 |  |  | 2027-06-03 01:00 | 2027-06-11 01:00 |  | 2027-06-03 01:00 | 2027-06-03 01:00 |  | Yes | Created | 2026-01-24 | Birr Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2026.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.02 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 26-1044 | 26-1044 - ACWA - Quarayah IPP - Hajr Expansion 7HA.02 - Electrical - Electrical Control System (ECS) Training | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2026-07-06 01:00 |  | 0 |  |  | 2027-05-31 01:00 | 2027-06-02 01:00 |  | 2027-05-31 01:00 | 2027-05-31 01:00 |  | Yes | Created | 2026-01-24 | Birr Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2026.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.02 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 |  | 26-1043 | 26-1043 - ACWA - Quarayah IPP - Hajr Expansion 7HA.02 - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2027-03-29 01:00 | 2027-04-02 01:00 | 2027-05-17 01:00 | 2027-05-28 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 |  | Yes | Created | 2026-01-24 | Birr Workweek and Holidays | Gerardo Gonzalez | Tentative | 2026.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.02 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 |  | 26-1042 | 26-1042 - ACWA - Quarayah IPP - Hajr Expansion 7HA.02 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2027-03-08 | 2027-03-10 | 2027-05-10 01:00 | 2027-05-14 01:00 |  | 2027-05-10 01:00 | 2027-05-10 01:00 |  | Yes | Created | 2026-01-24 | Birr Workweek and Holidays | Joe Mcandrews | Tentative | 2026.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.02 |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 |  | 26-1041 | 26-1041 - ACWA - Quarayah IPP - Hajr Expansion 7HA.02 - Gas Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2027-03-08 | 2027-03-10 | 2027-05-03 01:00 | 2027-05-07 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 |  | Yes | Created | 2026-01-24 | Birr Workweek and Holidays | Dave Miller | Tentative | 2026.0
ACWA | Quarayah IPP | Hajr Expansion 7HA.02 | EGM-00489-1CSTO-TRAINALL |  | EGM-00489-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 |  | 26-1040 | 26-1040 - ACWA - Quarayah IPP - Hajr Expansion 7HA.02 - Gas Turbine - Operation | Learning Center | SWITZERLAND | TAS-M | Birr | Birr Learning Center | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-19 01:00 | 2027-04-30 01:00 |  | 2027-04-19 01:00 | 2027-04-19 01:00 |  | Yes | Created | 2026-01-24 | Birr Workweek and Holidays | Dave Miller | Tentative | 2026.0
IEC | Orot Rabin | n/a |  |  |  |  | English | English | NU | Anna Petrella | Customer-Project Specific | Feedwater pump MV VFD System | Generator | 5 | 5 | 0 | 4 |  | 26-1039 | 26-1039 - IEC - Orot Rabin - n/a - Feedwater pump MV VFD System | Learning Center | FRANCE | TAS-N | Massy | Other Learning Center | Monday |  |  | 2026-12-01 | 2026-01-13 | 0 |  |  | 2026-01-12 | 2026-01-16 |  | 2026-01-12 | 2026-01-12 | added to UDC as of 23Jan26 |  | Created | 2026-01-22 | US Workweek and Holidays |  | Confirmed | 2026.0
ONEE | Mohammedia | CSA extension + Upgrades | IFF-006121-GT-101-TRX |  | IFF-006121-GT-101-TRX |  | French | French | IB | Abuobaida El Mansoor | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 10 | 0 | 12 |  | 26-1038 | 26-1038 - ONEE - Mohammedia - CSA extension + Upgrades - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | MOROCCO | TAS-M | Mohammedia | Customer Site | Monday |  |  | 2026-06-15 01:00 |  | 0 | 2026-03-23 01:00 | 2026-04-24 01:00 | 2026-05-11 01:00 | 2026-05-15 01:00 |  | 2026-05-11 01:00 | 2026-05-11 01:00 |  |  | Created | 2026-01-21 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
VOLTA RIVER AUTHORITY | KPONE | KPONE |  |  |  |  | English | English | IB | Abuobaida El Mansoor | Customer-Project Specific | Gas Turbine - GT11N2 Inspection | Gas Turbine | 10 | 15 | 0 | 12 |  | 26-1037 | 26-1037 - VOLTA RIVER AUTHORITY - KPONE - KPONE - Gas Turbine - GT11N2 Inspection | Customer Site | GHANA | TAS-M | Tema | Customer Site | Monday |  |  | 2026-01-04 |  | 0 | 2026-09-28 01:00 | 2026-10-16 01:00 | 2026-10-26 01:00 | 2026-11-06 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2026-01-21 | US Workweek and Holidays | Gaetan Kofmel | Tentative | 2026.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 15 | 2 | 28-973 | 28-973 - Duke Energy - Cayuga - CC Power Block 1 - GT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-07-24 01:00 | 2028-07-28 01:00 | 2028-11-27 | 2028-12-08 |  | 2028-11-27 | 2028-11-27 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 5 | 0 | 15 | 2 | 28-972 | 28-972 - Duke Energy - Cayuga - CC Power Block 1 - GT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-07-17 01:00 | 2028-07-21 01:00 | 2028-10-30 01:00 | 2028-11-10 |  | 2028-10-30 01:00 | 2028-10-30 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 15 | 2 | 28-971 | 28-971 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-09-05 01:00 | 2028-09-11 01:00 | 2028-10-23 01:00 | 2028-10-27 01:00 |  | 2028-10-23 01:00 | 2028-10-23 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Donald Hopkins | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 15 | 2 | 28-970 | 28-970 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-08-28 01:00 | 2028-09-01 01:00 | 2028-10-09 01:00 | 2028-10-20 01:00 |  | 2028-10-09 01:00 | 2028-10-09 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Donald Hopkins | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 15 | 2 | 28-969 | 28-969 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-08-21 01:00 | 2028-08-23 01:00 | 2028-10-02 01:00 | 2028-10-06 01:00 |  | 2028-10-02 01:00 | 2028-10-02 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 15 | 2 | 28-968 | 28-968 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Operation-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-07-10 01:00 | 2028-07-14 01:00 | 2028-09-18 01:00 | 2028-09-29 01:00 |  | 2028-09-18 01:00 | 2028-09-18 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Hichem Mesli | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 15 | 2 | 28-967 | 28-967 - Duke Energy - Cayuga - CC Power Block 1 - GT - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-07-17 01:00 | 2028-07-21 01:00 | 2028-09-04 01:00 | 2028-09-15 01:00 |  | 2028-09-04 01:00 | 2028-09-04 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 15 | 2 | 28-966 | 28-966 - Duke Energy - Cayuga - CC Power Block 1 - GT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-07-05 01:00 | 2028-07-07 01:00 | 2028-08-28 01:00 | 2028-09-01 01:00 |  | 2028-08-28 01:00 | 2028-08-28 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 15 | 2 | 28-965 | 28-965 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-06-20 01:00 | 2028-06-26 01:00 | 2028-08-21 01:00 | 2028-08-25 01:00 |  | 2028-08-21 01:00 | 2028-08-21 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Donald Hopkins | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 15 | 2 | 28-964 | 28-964 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-06-12 01:00 | 2028-06-16 01:00 | 2028-08-07 01:00 | 2028-08-18 01:00 |  | 2028-08-07 01:00 | 2028-08-07 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Donald Hopkins | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 15 | 2 | 28-963 | 28-963 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-06-26 01:00 | 2028-06-28 01:00 | 2028-07-31 01:00 | 2028-08-04 01:00 |  | 2028-07-31 01:00 | 2028-07-31 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 | 2 | 28-962 | 28-962 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 | 2028-12-14 | 0 | 2028-05-29 01:00 | 2028-06-02 01:00 | 2028-07-17 01:00 | 2028-07-28 01:00 |  | 2028-07-17 01:00 | 2028-07-17 01:00 | Q3-Q4 (Sep-Dec) in 2028 |  | Created | 2026-01-14 | US Workweek and Holidays | Hichem Mesli | Tentative | 2028.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 15 | 1 | 27-239 | 27-239 - Duke Energy - Cayuga - CC Power Block 1 - GT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-08-30 01:00 | 2027-09-10 01:00 | 2027-11-29 | 2027-12-10 |  | 2027-11-29 | 2027-11-29 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 15 | 1 | 27-238 | 27-238 - Duke Energy - Cayuga - CC Power Block 1 - GT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-09-06 01:00 | 2027-09-17 01:00 | 2027-11-08 | 2027-11-19 |  | 2027-11-08 | 2027-11-08 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 15 | 1 | 27-237 | 27-237 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-08-16 01:00 | 2027-08-20 01:00 | 2027-11-01 01:00 | 2027-11-05 01:00 |  | 2027-11-01 01:00 | 2027-11-01 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Domingo Aleman | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 15 | 1 | 27-236 | 27-236 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-08-02 01:00 | 2027-08-13 01:00 | 2027-10-18 01:00 | 2027-10-29 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Domingo Aleman | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 15 | 1 | 27-235 | 27-235 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-07-12 01:00 | 2027-07-16 01:00 | 2027-10-11 01:00 | 2027-10-15 01:00 |  | 2027-10-11 01:00 | 2027-10-11 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 15 | 1 | 27-234 | 27-234 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Operation-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-08-09 01:00 | 2027-08-20 01:00 | 2027-09-27 01:00 | 2027-10-08 01:00 |  | 2027-09-27 01:00 | 2027-09-27 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Hichem Mesli | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 15 | 1 | 27-233 | 27-233 - Duke Energy - Cayuga - CC Power Block 1 - GT - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-07-19 01:00 | 2027-07-30 01:00 | 2027-09-13 01:00 | 2027-09-24 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Bharat Vispara | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 15 | 1 | 27-232 | 27-232 - Duke Energy - Cayuga - CC Power Block 1 - GT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-07-12 01:00 | 2027-07-16 01:00 | 2027-09-06 01:00 | 2027-09-10 01:00 |  | 2027-09-06 01:00 | 2027-09-06 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 15 | 1 | 27-231 | 27-231 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-06-28 01:00 | 2027-07-02 01:00 | 2027-08-30 01:00 | 2027-09-03 01:00 |  | 2027-08-30 01:00 | 2027-08-30 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - ST |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 15 | 1 | 27-230 | 27-230 - Duke Energy - Cayuga - CC Power Block 1 - ST - Steam Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-06-14 01:00 | 2027-06-25 01:00 | 2027-08-16 01:00 | 2027-08-27 01:00 |  | 2027-08-16 01:00 | 2027-08-16 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 15 | 1 | 27-229 | 27-229 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-06-14 01:00 | 2027-06-17 01:00 | 2027-08-09 01:00 | 2027-08-13 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Tim Taylor | Tentative | 2027.0
Duke Energy | Cayuga | CC Power Block 1 - GT |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 | 1 | 27-228 | 27-228 - Duke Energy - Cayuga - CC Power Block 1 - GT - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Cayuga, Indiana | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 | 2027-12-16 | 0 | 2027-05-17 01:00 | 2027-05-28 01:00 | 2027-07-26 01:00 | 2027-08-06 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 | Q3-Q4 (Sep-Dec) in 2027 |  | Created | 2026-01-14 | US Workweek and Holidays | Hichem Mesli | Tentative | 2027.0
Xcel | Xcel Energy Fort St Vrain | - | EGM-00480-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-227 | 27-227 - Xcel - Xcel Energy Fort St Vrain - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Fort St Vrain | Customer Site | Monday |  |  | 2027-02-15 |  | 0 | 2026-12-16 | 2026-12-31 | 2027-02-15 | 2027-02-26 |  | 2027-02-15 | 2027-02-15 | This course should precede 27-39, it's the same project |  | Created | 2026-01-14 | US Workweek and Holidays | Tim Taylor | Tentative | 2027.0
CFE | CUAUTITLAN POWER SUBSTATION | LM600 | IFF-007081-CC-101-TRX | 203768 | IFF-007081-CC-101-TRX |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-1033 | 26-1033 - CFE - CUAUTITLAN POWER SUBSTATION - LM600 - Gas Turbine - LM6000 Package Maintenance | Customer Site | MEXICO | TAS-M | TLALNEPANTLA | Customer Site | Monday |  |  | 2026-04-20 01:00 |  | 0 | 2026-02-09 | 2026-02-13 | 2026-06-15 01:00 | 2026-06-19 01:00 |  | 2026-06-15 01:00 | 2026-06-15 01:00 | Next available date. Back to back. Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2026-01-12 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
CFE | CUAUTITLAN POWER SUBSTATION | LM600 | IFF-007081-CC-101-TRX | 203768 | IFF-007081-CC-101-TRX |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-1032 | 26-1032 - CFE - CUAUTITLAN POWER SUBSTATION - LM600 - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | MEXICO | TAS-M | TLALNEPANTLA | Customer Site | Monday |  |  | 2026-04-20 01:00 |  | 0 | 2026-02-02 | 2026-02-06 | 2026-06-08 01:00 | 2026-06-12 01:00 |  | 2026-06-08 01:00 | 2026-06-08 01:00 | Next available date. Back to back. Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2026-01-12 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
AEP | Northeastern | 2 x 7F.05 SC |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-961 | 28-961 - AEP - Northeastern - 2 x 7F.05 SC - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Oologah | Customer Site | Monday | Std US Holidays |  | 2028-04-03 01:00 |  | 0 | 2028-03-13 01:00 | 2028-03-24 01:00 | 2028-05-01 01:00 | 2028-05-12 01:00 |  | 2028-05-01 01:00 | 2028-05-01 01:00 |  |  | Created | 2026-01-09 | US Workweek and Holidays | Isaiah Mason | Tentative | 2028.0
AEP | Northeastern | 2 x 7F.05 SC |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-960 | 28-960 - AEP - Northeastern - 2 x 7F.05 SC - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Oologah | Customer Site | Monday | Std US Holidays |  | 2028-04-03 01:00 |  | 0 | 2028-02-07 | 2028-02-11 | 2028-04-24 01:00 | 2028-04-28 01:00 |  | 2028-04-24 01:00 | 2028-04-24 01:00 |  |  | Created | 2026-01-09 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
AEP | Northeastern | 2 x 7F.05 SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-959 | 28-959 - AEP - Northeastern - 2 x 7F.05 SC - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Oologah | Customer Site | Monday | Std US Holidays |  | 2028-04-03 01:00 |  | 0 | 2028-03-13 01:00 | 2028-03-17 01:00 | 2028-04-17 01:00 | 2028-04-21 01:00 |  | 2028-04-17 01:00 | 2028-04-17 01:00 |  |  | Created | 2026-01-09 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
AEP | Northeastern | 2 x 7F.05 SC |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-958 | 28-958 - AEP - Northeastern - 2 x 7F.05 SC - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Oologah | Customer Site | Monday | Std US Holidays |  | 2028-04-03 01:00 |  | 0 | 2028-02-28 | 2028-03-10 | 2028-04-03 01:00 | 2028-04-14 01:00 |  | 2028-04-03 01:00 | 2028-04-03 01:00 |  |  | Created | 2026-01-09 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
National Grid | Port Jefferson | LM6000 |  |  |  |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-1030 | 26-1030 - National Grid - Port Jefferson - LM6000 - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Port Jefferson | Customer Site | Monday |  |  | 2026-07-27 01:00 |  | 0 | 2026-07-20 01:00 | 2026-07-24 01:00 | 2026-08-17 01:00 | 2026-08-21 01:00 |  | 2026-08-17 01:00 | 2026-08-17 01:00 |  |  | Created | 2026-01-08 | US Workweek and Holidays | Mark Girling | Cancelled | 2026.0
Hindustan Aeronautics Ltd. | - | Indian Navy | G10-US-0001075-001-00241 |  | G10-US-0001075-001-00241 |  | English | English | NU | Gavin Yoong | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 2 | 1 | 0 | 8 | 4 | 26-1029 | 26-1029 - Hindustan Aeronautics Ltd. - - - Indian Navy - Gas Turbine - LM2500 Borescope Inspection - G4 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-08-17 01:00 |  | 0 | 2026-07-01 01:00 | 2026-07-01 01:00 | 2026-09-21 01:00 | 2026-09-22 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 | Back to back with Level 1 | Yes | Created | 2026-01-08 | US Workweek and Holidays | Elias Benedi | Confirmed | 2026.0
Hindustan Aeronautics Ltd. | - | Indian Navy | G10-US-0001075-001-00241 |  | G10-US-0001075-001-00241 |  | English | English | NU | Gavin Yoong | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 1 | 0 | 8 | 4 | 26-1028 | 26-1028 - Hindustan Aeronautics Ltd. - - - Indian Navy - Gas Turbine - LM2500 Level 1 Maintenance - G4 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-08-10 01:00 |  | 0 | 2026-06-18 01:00 | 2026-06-18 01:00 | 2026-09-14 01:00 | 2026-09-18 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 | Back to back with Borescope | Yes | Created | 2026-01-08 | US Workweek and Holidays | Elias Benedi | Confirmed | 2026.0
Hindustan Aeronautics Ltd. | - | Indian Navy | G10-US-0001075-001-00241 |  | G10-US-0001075-001-00241 |  | English | English | NU | Gavin Yoong | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 2 | 2 | 0 | 4 | 3 | 26-1027 | 26-1027 - Hindustan Aeronautics Ltd. - - - Indian Navy - Gas Turbine - LM2500 Borescope Inspection - G3 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-05-18 01:00 |  | 0 | 2026-06-01 01:00 | 2026-06-02 01:00 | 2026-10-19 01:00 | 2026-10-20 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 | Back to back with Level 1 |  | Created | 2026-01-08 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
Hindustan Aeronautics Ltd. | - | Indian Navy | G10-US-0001075-001-00241 |  | G10-US-0001075-001-00241 |  | English | English | NU | Gavin Yoong | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 4 | 3 | 26-1026 | 26-1026 - Hindustan Aeronautics Ltd. - - - Indian Navy - Gas Turbine - LM2500 Level 1 Maintenance - G3 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-05-11 01:00 |  | 0 | 2026-05-04 01:00 | 2026-05-08 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 | Back to back with Borescope |  | Created | 2026-01-08 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
ACWA POWER INTERNATIONAL | Taiba-1 | IPP Project_1.8GW_7E.03 SC | EGM-00489-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 26-1025 | 26-1025 - ACWA POWER INTERNATIONAL - Taiba-1 - IPP Project_1.8GW_7E.03 SC - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-08-02 01:00 | 2026-08-09 01:00 | 0 |  |  | 2026-09-06 01:00 | 2026-09-14 01:00 |  | 2026-09-06 01:00 | 2026-09-06 01:00 |  | Yes | Created | 2026-01-04 | Sun - Thurs Middle East 5 Day Workweek | Grid Solution Excitation Instructor | Confirmed | 2026.0
ACWA POWER INTERNATIONAL | Taiba-1 | IPP Project_1.8GW_7E.03 SC | EGM-00489-1CSTO-TRAINALL |  |  | I01-117920 / PO 4102842310 | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-1024 | 26-1024 - ACWA POWER INTERNATIONAL - Taiba-1 - IPP Project_1.8GW_7E.03 SC - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-07-19 01:00 | 2026-07-26 01:00 | 0 | 2026-03-16 01:00 | 2026-04-24 01:00 | 2026-07-19 01:00 | 2026-07-30 01:00 |  | 2026-07-19 01:00 | 2026-07-19 01:00 |  | Yes | Created | 2026-01-04 | Sun - Thurs Middle East 5 Day Workweek | Rafael Venancio | Confirmed | 2026.0
ACWA POWER INTERNATIONAL | Taiba-1 | IPP Project_1.8GW_7E.03 SC | EGM-00489-1CSTO-TRAINALL |  | EGM-00489-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-1023 | 26-1023 - ACWA POWER INTERNATIONAL - Taiba-1 - IPP Project_1.8GW_7E.03 SC - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-07-12 01:00 | 2026-07-14 01:00 | 0 | 2026-05-18 01:00 | 2026-05-22 01:00 | 2026-07-12 01:00 | 2026-07-16 01:00 |  | 2026-07-12 01:00 | 2026-07-12 01:00 |  | Yes | Created | 2026-01-04 | Sun - Thurs Middle East 5 Day Workweek | Zakaria Al-Qawasmeh | Confirmed | 2026.0
ACWA POWER INTERNATIONAL | Taiba-1 | IPP Project_1.8GW_7E.03 SC | EGM-00489-1CSTO-TRAINALL |  |  | I01-119546 / PO 4102869572 | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 1 | 12 |  | 26-1022 | 26-1022 - ACWA POWER INTERNATIONAL - Taiba-1 - IPP Project_1.8GW_7E.03 SC - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-07-05 01:00 | 2026-07-06 01:00 | 0 | 2026-06-01 01:00 | 2026-06-05 01:00 | 2026-07-05 01:00 | 2026-07-09 01:00 |  | 2026-07-05 01:00 | 2026-07-05 01:00 |  | Yes | Created | 2026-01-03 | Sun - Thurs Middle East 5 Day Workweek | Agustin Collado;Mohamed Abdelaziz | Confirmed | 2026.0
ACWA POWER INTERNATIONAL | Taiba-1 | IPP Project_1.8GW_7E.03 SC | EGM-00489-1CSTO-TRAINALL |  |  | I01-117921 / PO 4102842309 | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 1 | 12 |  | 26-1021 | 26-1021 - ACWA POWER INTERNATIONAL - Taiba-1 - IPP Project_1.8GW_7E.03 SC - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-07-05 01:00 | 2026-07-12 01:00 | 0 | 2026-04-20 01:00 | 2026-05-29 01:00 | 2026-07-05 01:00 | 2026-07-16 01:00 |  | 2026-07-05 01:00 | 2026-07-05 01:00 |  | Yes | Created | 2026-01-04 | Sun - Thurs Middle East 5 Day Workweek | Tim Taylor | Confirmed | 2026.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 2 | 27-214 | 27-214 - TVA - New Caledonia - - - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday | Std US Holidays |  | 2027-09-20 01:00 | 2027-10-01 01:00 | 0 | 2027-07-26 01:00 | 2027-08-06 01:00 | 2027-09-20 01:00 | 2027-10-01 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 | This course timing to follow 27-57 (replaces pulled 27-58) |  | Created | 2026-01-05 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-213 | 27-213 - TVA - New Caledonia - - - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday | Std US Holidays |  | 2027-08-09 01:00 | 2027-08-20 01:00 | 0 | 2027-06-21 01:00 | 2027-07-02 01:00 | 2027-08-09 01:00 | 2027-08-20 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 | This course timing to follow 27-53 (replaces pulled 27-54) |  | Created | 2026-01-05 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2027.0
Calpine | Gregory | 1x7F.04 |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-945 | 28-945 - Calpine - Gregory - 1x7F.04 - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Gregory | Customer Site | Monday | Standard US Holidays |  | 2028-01-24 |  | 0 | 2028-01-03 | 2028-01-14 | 2028-02-21 | 2028-03-03 |  | 2028-02-21 | 2028-02-21 | Asking to start program in 1Q2028 |  | Created | 2026-01-05 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2028.0
Calpine | Gregory | 1x7F.04 |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-944 | 28-944 - Calpine - Gregory - 1x7F.04 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Gregory | Customer Site | Monday | Standard US Holidays |  | 2028-01-24 |  | 0 | 2027-12-13 | 2027-12-17 | 2028-02-14 | 2028-02-18 |  | 2028-02-14 | 2028-02-14 | Asking to start program in 1Q2028 |  | Created | 2026-01-05 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
Calpine | Gregory | 1x7F.04 |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-943 | 28-943 - Calpine - Gregory - 1x7F.04 - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Gregory | Customer Site | Monday | Standard US Holidays |  | 2028-01-24 |  | 0 | 2027-12-13 | 2027-12-17 | 2028-02-07 | 2028-02-11 |  | 2028-02-07 | 2028-02-07 | Asking to start program in 1Q2028 |  | Created | 2026-01-05 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
Calpine | Gregory | 1x7F.04 |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-942 | 28-942 - Calpine - Gregory - 1x7F.04 - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Gregory | Customer Site | Monday | Standard US Holidays |  | 2028-01-24 |  | 0 | 2027-11-01 01:00 | 2027-11-24 | 2028-01-24 | 2028-02-04 |  | 2028-01-24 | 2028-01-24 | Asking to start program in 1Q2028 |  | Created | 2026-01-05 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL | I01-115476 / PO 4102794272 | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Steam Turbine Maintenance | Steam Turbine | 7 | 5 | 0 | 12 | 2 | 26-1020 | 26-1020 - TPC - Hsinta - - - Steam Turbine Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1236 Parsons Room | 2026-06-01 01:00 |  | 0 | 2026-03-16 01:00 | 2026-05-27 01:00 | 2026-06-18 01:00 | 2026-06-26 01:00 |  | 2026-06-18 01:00 | 2026-06-18 01:00 |  |  | Created | 2026-01-05 | US Workweek and Holidays | Tom Walsh | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL | I01-115476 / PO 4102794272 | English | English | NU | Gavin Yoong | Customer-Project Specific | Steam Turbine Operation | Steam Turbine | 13 | 8 | 0 | 12 | 2 | 26-1019 | 26-1019 - TPC - Hsinta - - - Steam Turbine Operation - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3203 Allen Parkway Room | 2026-06-01 01:00 |  | 0 | 2026-03-09 01:00 | 2026-05-22 01:00 | 2026-06-01 01:00 | 2026-06-17 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 |  |  | Created | 2026-01-05 | US Workweek and Holidays | Tom Walsh | Confirmed | 2026.0
Public Power Coorporation (PPC) | Megalopolis | MYA PPC Megalopolis | IFF-006716-CC-101-TRX |  | IFF-006716-CC-101-TRX |  | English | English | IB | Anna Petrella | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 5 | 5 | 0 | 12 |  | 26-1018 | 26-1018 - Public Power Coorporation (PPC) - Megalopolis - MYA PPC Megalopolis - Excitation - EX2100e Operation & Maintenance | Customer Site | GREECE | TAS-N | Megalopolis | Customer Site | Monday | -- |  | 2026-03-09 01:00 | 2026-03-11 01:00 | 0 | 2026-03-02 | 2026-03-06 | 2026-05-18 01:00 | 2026-05-22 01:00 |  | 2026-05-18 01:00 | 2026-05-18 01:00 | Customer has following available windows: 9-13 March 16-20 March 30 March - 3 April 20-24 April 4-8 May 11-15 May 18-22 May 25-29 May |  | Created | 2025-12-19 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 30-8 | 30-8 - NIPSCO - NIPSCO Schahfer - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2030-04-08 01:00 |  | 0 |  |  | 2030-04-08 01:00 | 2030-05-03 01:00 |  | 2030-04-08 01:00 | 2030-04-08 01:00 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required Wanted date is 8-Apr-2030, but find the earliest timeslot possible |  | Created | 2025-12-18 | US Workweek and Holidays | Charles Wall | Tentative | 2030.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 29-18 | 29-18 - NIPSCO - NIPSCO Schahfer - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2029-06-10 01:00 |  | 0 |  |  | 2029-08-02 01:00 | 2029-08-10 01:00 |  | 2029-08-02 01:00 | 2029-08-02 01:00 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng |  | Created | 2025-12-18 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2029.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-941 | 28-941 - NIPSCO - NIPSCO Schahfer - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2028-11-27 |  | 0 |  |  | 2029-01-29 | 2029-03-29 01:00 |  | 2029-01-29 | 2029-01-29 | Request Charles Wal. No additional prep required Wanted date is 27-Nov-2028, but find the earliest timeslot possible |  | Created | 2025-12-18 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Consumers Energy Company | Jackson Generating Station | - | IFF-008091-CC-101-TRX |  | IFF-008091-CC-101-TRX |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 4 | 5 | 1 | 12 |  | 26-1017 | 26-1017 - Consumers Energy Company - Jackson Generating Station - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | NYC | Customer Site | Monday |  |  | 2026-07-19 01:00 |  | 0 | 2026-07-20 01:00 | 2026-07-24 01:00 | 2026-08-24 01:00 | 2026-08-27 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 | New request, no change to 26-240 |  | Created | 2025-12-18 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
Petro Vietnam Corporation | Nhon Trach | 3&4 |  |  |  |  | English | English | IB | Gavin Yoong | Customer-Project Specific | Gas Turbine - Maintenance | Gas Turbine | 5 | 0 | 0 | 15 |  | 25-914 | 25-914 - Petro Vietnam Corporation - Nhon Trach - 3&4 - Gas Turbine - Maintenance | Customer Site | VIETNAM | TAS-M | Ho Chi Minh | Customer Site | Monday |  |  | 2025-04-20 01:00 |  | 0 | [7 empty] | Short Notice Request |  | Imported | 2025-12-15 |  |  | Cancelled | 2025.0
Petro Vietnam Corporation | Nhon Trach | 3&4 |  |  |  |  | English | English | IB | Gavin Yoong | Customer-Project Specific | Control System - Mark VIe Maintenance (HMI on 1st Day) | Controls | 5 | 0 | 0 | 15 |  | 25-913 | 25-913 - Petro Vietnam Corporation - Nhon Trach - 3&4 - Control System - Mark VIe Maintenance (HMI on 1st Day) | Customer Site | VIETNAM | TAS-M | Ho Chi Minh | Customer Site | Monday |  |  | 2025-04-06 01:00 |  | 0 | [7 empty] | Short Notice Request |  | Imported | 2025-12-15 |  |  | Cancelled | 2025.0
Petro Vietnam Corporation | Nhon Trach | 3&4 | IFF-005837-GT-101-TRX |  | IFF-005837-GT-101-TRX | I01-116475 / PO 7903057095 | English | English | IB | Gavin Yoong | Customer-Project Specific | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 15 |  | 25-912 | 25-912 - Petro Vietnam Corporation - Nhon Trach - 3&4 - Gas Turbine - Maintenance | Customer Site | VIETNAM | TAS-M | Ho Chi Minh | Customer Site | Monday |  |  | 2025-04-20 01:00 |  | 0 | 2026-03-02 | 2026-03-06 | 2026-05-04 01:00 | 2026-05-08 01:00 |  | 2026-05-04 01:00 | 2026-05-04 01:00 | Short Notice Request | Yes | Created | 2025-12-15 | US Workweek and Holidays | Agustin Collado;Mohamed Abdelaziz | Confirmed | 2025.0
Petro Vietnam Corporation | Nhon Trach | 3&4 | IFF-005837-GT-101-TRX |  |  | I01-116475 / PO 7903057095 | English | English | IB | Gavin Yoong | Customer-Project Specific | Control System - Mark VIe Maintenance (HMI on 1st Day) | Controls | 5 | 5 | 1 | 15 |  | 25-911 | 25-911 - Petro Vietnam Corporation - Nhon Trach - 3&4 - Control System - Mark VIe Maintenance (HMI on 1st Day) | Customer Site | VIETNAM | TAS-M | Ho Chi Minh | Customer Site | Monday |  |  | 2025-04-06 01:00 |  | 0 | 2026-02-23 | 2026-02-27 | 2026-04-20 01:00 | 2026-04-24 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 | Short Notice Request | Yes | Created | 2025-12-15 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2025.0
Xcel | Fort Lupton | 1x7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-940 | 28-940 - Xcel - Fort Lupton - 1x7F.05 EO - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Fort Lupton | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-01-03 | 2028-01-14 | 2028-02-21 | 2028-03-03 |  | 2028-02-21 | 2028-02-21 | Asking to start program in May 2028 |  | Created | 2025-12-12 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2028.0
Xcel | Fort Lupton | 1x7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-939 | 28-939 - Xcel - Fort Lupton - 1x7F.05 EO - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Fort Lupton | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2027-12-13 | 2027-12-17 | 2028-02-14 | 2028-02-18 |  | 2028-02-14 | 2028-02-14 | Asking to start program in May 2028 |  | Created | 2025-12-12 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2028.0
Xcel | Fort Lupton | 1x7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-938 | 28-938 - Xcel - Fort Lupton - 1x7F.05 EO - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Fort Lupton | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2027-11-29 | 2027-12-03 | 2028-02-07 | 2028-02-11 |  | 2028-02-07 | 2028-02-07 | Asking to start program in May 2028 |  | Created | 2025-12-12 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Xcel | Fort Lupton | 1x7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-937 | 28-937 - Xcel - Fort Lupton - 1x7F.05 EO - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Fort Lupton | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2027-11-15 | 2027-11-19 | 2028-01-24 | 2028-02-04 |  | 2028-01-24 | 2028-01-24 | Asking to start program in May 2028 |  | Created | 2025-12-12 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Xcel | Fort Lupton | 1x7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-936 | 28-936 - Xcel - Fort Lupton - 1x7F.05 EO - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Fort Lupton | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2027-10-25 01:00 | 2027-11-19 | 2028-01-10 | 2028-01-21 |  | 2028-01-10 | 2028-01-10 | Asking to start program in May 2028 |  | Created | 2025-12-12 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2028.0
ENEA ELKOGAZ | Kozienice | 1x9HA.01 |  |  |  |  | Polish | Polish | NU | Anna Petrella | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 29-17 | 29-17 - ENEA ELKOGAZ - Kozienice - 1x9HA.01 - OTS Post-COD Refresh - CC Sim | Remote | POLAND | TAS-N | Remote | Distance Learning | Monday |  |  | 2029-08-13 01:00 |  | 0 |  |  | 2029-08-13 01:00 | 2029-09-07 01:00 |  | 2029-08-13 01:00 | 2029-08-13 01:00 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. No additional prep required OLD UNIQUE ID: 28-14 |  | Created | 2025-12-11 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
ENEA ELKOGAZ | Kozienice | 1x9HA.01 |  |  |  |  | Polish | Polish | NU | Anna Petrella | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 29-16 | 29-16 - ENEA ELKOGAZ - Kozienice - 1x9HA.01 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | POLAND | TAS-N | Świerże Górne | Customer Site | Monday |  |  | 2029-02-05 |  | 0 |  |  | 2029-02-05 | 2029-02-13 |  | 2029-02-05 | 2029-02-05 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng OLD UNIQUE ID: 28-13 |  | Created | 2025-12-11 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2029.0
ENEA ELKOGAZ | Kozienice | 1x9HA.01 |  |  |  |  | Polish | Polish | NU | Anna Petrella | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-935 | 28-935 - ENEA ELKOGAZ - Kozienice - 1x9HA.01 - OTS Simulator Development & Testing - CC Sim | Remote | POLAND | TAS-N | Remote | Distance Learning | Monday |  |  | 2028-07-31 01:00 |  | 0 |  |  | 2028-07-31 01:00 | 2028-09-28 01:00 |  | 2028-07-31 01:00 | 2028-07-31 01:00 | Request Charles Wal. No additional prep required OLD UNIQUE ID: 28-12 |  | Created | 2025-12-11 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | I01-109845 / PO 4102695663 | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Mark VIe DCS Maintenance | Controls | 7 | 5 | 0 | 12 | 2 | 26-1016 | 26-1016 - TPC - Datan - 8&9 Local Training - Mark VIe DCS Maintenance - G2 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-N | - | Distance Learning | Monday | Feb 16 - 22 |  | 2026-02-01 |  | 0 | 2026-05-26 01:00 | 2026-05-29 01:00 | 2026-08-10 01:00 | 2026-08-18 01:00 |  | 2026-08-10 01:00 | 2026-08-10 01:00 | Formerly 25-497 moved to 2026, customer request reschedule in February onwards. Lunar new year week of 17 Feb to be avoided. Can be on-site delivery if requested |  | Created | 2025-12-10 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
GS Caltex Corporation | Yeosu Captive | - | IFF-007349-CC-101-TRX |  | IFF-007349-CC-101-TRX |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-1015 | 26-1015 - GS Caltex Corporation - Yeosu Captive - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-11-16 |  | 0 | 2026-09-21 01:00 | 2026-09-25 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 |  |  | Created | 2025-12-11 | Birr Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
GS Caltex Corporation | Yeosu Captive | - | IFF-007349-CC-101-TRX |  | IFF-007349-CC-101-TRX |  | English | English | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-1014 | 26-1014 - GS Caltex Corporation - Yeosu Captive - - - Gas Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-11-16 |  | 0 | 2026-09-28 01:00 | 2026-10-02 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 | Overlap with Electricals requested by customer |  | Created | 2025-12-11 | Birr Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
GS Caltex Corporation | Yeosu Captive | - | IFF-007349-CC-101-TRX |  | IFF-007349-CC-101-TRX |  | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-1013 | 26-1013 - GS Caltex Corporation - Yeosu Captive - - - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-02-12 | 2026-08-17 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 | Room in Birr is only availble only Nov 16 - 27 ; look at Aleksandar |  | Created | 2025-12-11 | Birr Workweek and Holidays | Aleksandar Kitanovic | Confirmed | 2026.0
GS Caltex Corporation | Yeosu Captive | - | IFF-007349-CC-101-TRX |  | IFF-007349-CC-101-TRX |  | English | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-1012 | 26-1012 - GS Caltex Corporation - Yeosu Captive - - - Gas Turbine - Operation | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-11-02 |  | 0 | 2026-07-13 01:00 | 2026-07-23 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 | Overlap with Controls requested by customer |  | Created | 2025-12-11 | Birr Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Simulator - Maintenance Training Simulator (OTS) For OTS Maintenance Team | Simulator | 5 | 5 | 0 | 6 |  | 26-1011 | 26-1011 - TPC - Datan - 8&9 Local Training - Simulator - Maintenance Training Simulator (OTS) For OTS Maintenance Team | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Taoyuan | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-04-28 01:00 | 2026-04-30 01:00 | 2026-07-20 01:00 | 2026-07-24 01:00 |  | 2026-07-20 01:00 | 2026-07-20 01:00 | Formerly 22-326 moved to 2026 |  | Created | 2025-12-10 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL |  | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Simulator - Operator Training Course | Simulator | 5 | 4 | 2 | 6 |  | 26-1010 | 26-1010 - TPC - Datan - 8&9 Local Training - Simulator - Operator Training Course | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Taoyuan | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 | 2026-06-29 01:00 | 2026-07-02 01:00 | 2026-07-27 01:00 | 2026-07-31 01:00 |  | 2026-07-27 01:00 | 2026-07-27 01:00 | Formerly 22-324 moved to 2026 |  | Created | 2025-12-10 | US Workweek and Holidays | Santosh Kumar;Tom Walsh | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Steam Turbine - Maintenance | Steam Turbine | 7 | 5 | 0 | 12 | 1 | 26-1009 | 26-1009 - TPC - Datan - 8&9 Local Training - Steam Turbine - Maintenance - G1 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-N | - | Distance Learning | Monday |  |  | 2026-04-01 01:00 |  | 0 | 2026-06-29 01:00 | 2026-07-02 01:00 | 2026-09-18 01:00 | 2026-09-30 01:00 |  | 2026-09-18 01:00 | 2026-09-18 01:00 | Formerly 25-495 moved to 2026 |  | Created | 2025-12-11 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
OGE 2 | Horseshoe Lake 13 & 14 | 2 x 7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-934 | 28-934 - OGE 2 - Horseshoe Lake 13 & 14 - 2 x 7F.05 EO - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday | Standard US holidays |  | 2028-10-01 01:00 |  | 0 | 2028-06-19 01:00 | 2028-06-30 01:00 | 2028-08-21 01:00 | 2028-09-01 01:00 |  | 2028-08-21 01:00 | 2028-08-21 01:00 | Asking 4Q2028 |  | Created | 2025-12-09 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2028.0
OGE 2 | Horseshoe Lake 13 & 14 | 2 x 7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-933 | 28-933 - OGE 2 - Horseshoe Lake 13 & 14 - 2 x 7F.05 EO - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday | Standard US holidays |  | 2028-10-01 01:00 |  | 0 | 2028-06-26 01:00 | 2028-06-30 01:00 | 2028-08-14 01:00 | 2028-08-18 01:00 |  | 2028-08-14 01:00 | 2028-08-14 01:00 | Asking 4Q2028 |  | Created | 2025-12-09 | US Workweek and Holidays | Willy Bueno | Confirmed | 2028.0
OGE 2 | Horseshoe Lake 13 & 14 | 2 x 7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-932 | 28-932 - OGE 2 - Horseshoe Lake 13 & 14 - 2 x 7F.05 EO - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday | Standard US holidays |  | 2028-10-01 01:00 |  | 0 | 2028-05-22 01:00 | 2028-05-26 01:00 | 2028-08-07 01:00 | 2028-08-11 01:00 |  | 2028-08-07 01:00 | 2028-08-07 01:00 | Asking 4Q2028 |  | Created | 2025-12-09 | US Workweek and Holidays | Dave Miller | Confirmed | 2028.0
OGE 2 | Horseshoe Lake 13 & 14 | 2 x 7F.05 EO |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-931 | 28-931 - OGE 2 - Horseshoe Lake 13 & 14 - 2 x 7F.05 EO - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday | Standard US holidays |  | 2028-10-01 01:00 |  | 0 | 2028-05-08 01:00 | 2028-05-19 01:00 | 2028-07-24 01:00 | 2028-08-04 01:00 |  |  | 2028-07-24 01:00 | Asking 4Q2028 |  | Created | 2025-12-09 | US Workweek and Holidays | Dave Miller | Confirmed | 2028.0
SEC | PP14 | PP14 | 7903062757 |  |  | I01-119176 / PO 7903062757 | English | English | IB | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-1005 | 26-1005 - SEC - PP14 - PP14 - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | Riyadh | Customer Site | Sunday |  |  | 2026-01-14 |  | 0 | 2026-06-01 01:00 | 2026-06-12 01:00 | 2026-09-06 01:00 | 2026-09-17 01:00 |  | 2026-09-06 01:00 | 2026-09-06 01:00 |  | Yes | Created | 2025-12-07 | Sun - Thurs Middle East 5 Day Workweek | Tim Taylor | Resourcing In Progress | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IG0-002835-12 |  | Russian | English | NU | Anna Petrella | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 15 | G2 | 26-1004 | 26-1004 - Calik / TURKMENENERGO - - - KIYANLY - Control System - Mark VIe Distributed Control System Maintenance - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-12-14 | 2026-12-16 | 0 | 2026-09-21 01:00 | 2026-09-25 01:00 | 2026-12-14 | 2026-12-18 |  | 2026-12-14 | 2026-12-14 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Aleksandar Kitanovic | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IG0-002835-12 |  | Russian | English | NU | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 15 | G2 | 26-1003 | 26-1003 - Calik / TURKMENENERGO - - - KIYANLY - Control System - Mark VIe Maintenance (Extended) - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-11-30 | 2026-12-09 | 0 | 2026-01-29 | 2026-02-11 | 2026-11-30 | 2026-12-11 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Aleksandar Kitanovic | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IFF-007026-CC-101-TRX |  | Russian | English | NU | Anna Petrella | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 3 | 2 | 15 | G2 | 26-1002 | 26-1002 - Calik / TURKMENENERGO - - - KIYANLY - Balance of Plant - Operation (GE Integrated Systems) - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-11-09 | 2026-11-10 | 0 |  |  | 2026-11-09 | 2026-11-13 |  | 2026-11-09 | 2026-11-09 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118610 / PO 4102839249 | Russian | English | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 15 | G2 | 26-1001 | 26-1001 - Calik / TURKMENENERGO - - - KIYANLY - Combined Cycle - Operation (GE Integrated Systems) - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-10-12 01:00 | 2026-10-13 01:00 | 0 | 2026-06-02 01:00 | 2026-06-03 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118610 / PO 4102839249 | Russian | English | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 15 | G2 | 26-1000 | 26-1000 - Calik / TURKMENENERGO - - - KIYANLY - Steam Turbine - Operation - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-09-28 01:00 | 2026-10-06 01:00 | 0 | 2026-05-26 01:00 | 2026-06-01 01:00 | 2026-09-28 01:00 | 2026-10-09 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118610 / PO 4102839249 | Russian | English | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 2 | 15 | G2 | 26-999 | 26-999 - Calik / TURKMENENERGO - - - KIYANLY - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-09-23 01:00 | 2026-09-22 01:00 | 0 | 2026-05-21 01:00 | 2026-05-22 01:00 | 2026-09-23 01:00 | 2026-09-25 01:00 |  | 2026-09-23 01:00 | 2026-09-23 01:00 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IFF-007026-CC-101-TRX |  | Russian | English | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 2 | 15 | G2 | 26-998 | 26-998 - Calik / TURKMENENERGO - - - KIYANLY - Steam Turbine - Maintenance - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- | Kronos | 2026-08-24 01:00 | 2026-08-25 01:00 | 0 | 2026-06-01 01:00 | 2026-06-05 01:00 | 2026-08-24 01:00 | 2026-08-28 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IFF-007026-CC-101-TRX |  | IFF-007026-CC-101-TRX |  | Russian | English | NU | Anna Petrella | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 15 | G2 | 26-997 | 26-997 - Calik / TURKMENENERGO - - - KIYANLY - Excitation - Generator Excitation, Protection and Static Starter Introduction - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-04-20 01:00 | 2026-04-22 01:00 | 0 | 2026-03-18 01:00 | 2026-03-20 01:00 | 2026-04-20 01:00 | 2026-04-24 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IG0-002835-12 | I01-116481 / PO 4102813466 | Russian | English | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 15 | G2 | 26-996 | 26-996 - Calik / TURKMENENERGO - - - KIYANLY - Gas Turbine - Maintenance - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-04-13 01:00 | 2026-04-12 01:00 | 0 | 2026-01-05 | 2026-01-07 | 2026-04-20 01:00 | 2026-04-24 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 | 01-05-26 publich holiday at BLC |  | Created | 2025-12-08 | Birr Workweek and Holidays | Agustin Collado;Hichem Mesli | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  |  | English | English | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 | G2 | 26-995 | 26-995 - Calik / TURKMENENERGO - - - KIYANLY - Gas Turbine - Operation - GG2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday | -- |  | 2026-04-12 01:00 | 2026-04-21 01:00 | 0 |  |  | 2026-04-13 01:00 | 2026-04-24 01:00 |  | 2026-04-13 01:00 | 2026-04-13 01:00 |  |  | Created | 2025-12-08 | Birr Workweek and Holidays | Salvatore Genovese | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118958 / PO 4102839264 | Russian | English | NU | Anna Petrella | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 15 | G1 | 26-994 | 26-994 - Calik / TURKMENENERGO - - - KIYANLY - Control System - Mark VIe Distributed Control System Maintenance - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-11-16 | 2026-11-17 | 0 | 2026-08-24 01:00 | 2026-08-28 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118958 / PO 4102839264 | Russian | English | NU | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 15 | G1 | 26-993 | 26-993 - Calik / TURKMENENERGO - - - KIYANLY - Control System - Mark VIe Maintenance (Extended) - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-11-02 | 2026-11-10 | 0 | 2026-07-20 01:00 | 2026-08-07 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IFF-007027-CC-101-TRX |  | Russian | English | NU | Anna Petrella | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 4 | 15 | G1 | 26-992 | 26-992 - Calik / TURKMENENERGO - - - KIYANLY - Balance of Plant - Operation (GE Integrated Systems) - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-10-05 01:00 | 2026-10-06 01:00 | 0 | 2026-07-13 01:00 | 2026-07-17 01:00 | 2026-10-05 01:00 | 2026-10-09 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  | IFF-007027-CC-101-TRX |  | Russian | English | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 4 | 15 | G1 | 26-991 | 26-991 - Calik / TURKMENENERGO - - - KIYANLY - Steam Turbine - Maintenance - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-09-14 01:00 | 2026-09-15 01:00 | 0 | 2026-06-08 01:00 | 2026-06-12 01:00 | 2026-09-14 01:00 | 2026-09-18 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118049 / PO 4102839258 | Russian | English | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 15 | G1 | 26-990 | 26-990 - Calik / TURKMENENERGO - - - KIYANLY - Combined Cycle - Operation (GE Integrated Systems) - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-08-17 01:00 | 2026-08-18 01:00 | 0 | 2026-05-14 01:00 | 2026-05-20 01:00 | 2026-08-17 01:00 | 2026-08-21 01:00 |  | 2026-08-17 01:00 | 2026-08-17 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118049 / PO 4102839258 | Russian | English | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 15 | G1 | 26-989 | 26-989 - Calik / TURKMENENERGO - - - KIYANLY - Steam Turbine - Operation - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-08-03 01:00 | 2026-08-11 01:00 | 0 | 2026-04-30 01:00 | 2026-05-13 01:00 | 2026-08-03 01:00 | 2026-08-14 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-118049 / PO 4102839258 | Russian | English | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 2 | 15 | G1 | 26-988 | 26-988 - Calik / TURKMENENERGO - - - KIYANLY - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-07-29 01:00 | 2026-07-28 01:00 | 0 | 2026-04-27 01:00 | 2026-04-29 01:00 | 2026-07-31 01:00 | 2026-08-02 01:00 |  | 2026-07-29 01:00 | 2026-07-31 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IFF-007027-CC-101-TRX |  | IFF-007027-CC-101-TRX |  | English | English | NU | Anna Petrella | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 7 | 1 | 15 | G1 | 26-987 | 26-987 - Calik / TURKMENENERGO - - - KIYANLY - Excitation - Generator Excitation, Protection and Static Starter Introduction - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-03-30 01:00 | 2026-04-01 01:00 | 0 | 2026-02-17 | 2026-02-20 | 2026-03-25 01:00 | 2026-03-29 01:00 |  | 2026-03-25 01:00 | 2026-03-25 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IFF-007027-CC-101-TRX |  | IFF-007027-CC-101-TRX |  | English | English | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 6 | 5 | 1 | 15 | G1 | 26-986 | 26-986 - Calik / TURKMENENERGO - - - KIYANLY - Gas Turbine - Maintenance - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Monday | -- |  | 2026-03-23 01:00 | 2026-03-25 01:00 | 0 | 2026-02-02 | 2026-02-06 | 2026-03-30 01:00 | 2026-04-04 01:00 |  | 2026-03-30 01:00 | 2026-03-30 01:00 |  |  | Created | 2025-12-08 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2026.0
Calik / TURKMENENERGO | - | KIYANLY | IG0-002835-12 |  |  | I01-116333 / PO 4102813042 | English | English | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 | G1 | 26-985 | 26-985 - Calik / TURKMENENERGO - - - KIYANLY - Gas Turbine - Operation - GG1 | Customer Site | TURKMENISTAN | TAS-M | KIYANLY | Customer Site | Sunday | -- |  | 2026-03-08 | 2026-03-15 01:00 | 0 | 2025-12-01 | 2025-12-19 | 2026-03-09 01:00 | 2026-03-20 01:00 |  | 2026-03-09 01:00 | 2026-03-09 01:00 | exception start on Sunday |  | Created | 2025-12-08 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
Nghi Son Refinery | Nghi Son | Nghi Son | IFF-006635-GT-101-TRX |  | IFF-006635-GT-101-TRX | I01-115459 / PO 7903055407 | English | English | IB | Gavin Yoong | Customer-Project Specific | GT Maintenance custom content | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-984 | 26-984 - Nghi Son Refinery - Nghi Son - Nghi Son - GT Maintenance custom content | Customer Site | VIETNAM | TAS-N | Nghe An | Customer Site | Monday |  |  | 2026-01-26 |  | 0 |  |  | 2026-01-26 | 2026-01-30 |  | 2026-01-26 | 2026-01-26 | Previously 25-667 |  | Created | 2025-12-08 | US Workweek and Holidays | Agustin Collado | Cancelled | 2026.0
Crusoe Energy | Crusoe Energy | 4th Project |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 | 3 | 27-212 | 27-212 - Crusoe Energy - Crusoe Energy - 4th Project - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization - G3 | Customer Site | UNITED STATES | TAS-N | Abilene | Customer Site | Monday | Std US Holidays |  | 2027-01-11 |  | 0 | 2027-10-11 01:00 | 2027-10-15 01:00 | 2027-11-15 | 2027-11-19 |  | 2027-11-15 | 2027-11-15 | 1/1/2027 12:00:00 AM |  | Created | 2025-12-05 | US Workweek and Holidays | Elias Benedi | Tentative | 2027.0
Crusoe Energy | Crusoe Energy | 4th Project |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 | 2 | 27-211 | 27-211 - Crusoe Energy - Crusoe Energy - 4th Project - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization - G2 | Customer Site | UNITED STATES | TAS-N | Abilene | Customer Site | Monday | Std US Holidays |  | 2027-01-11 |  | 0 | 2027-10-04 01:00 | 2027-10-08 01:00 | 2027-11-08 | 2027-11-12 |  | 2027-11-08 | 2027-11-08 | 1/1/2027 12:00:00 AM |  | Created | 2025-12-05 | US Workweek and Holidays | Elias Benedi | Tentative | 2027.0
Crusoe Energy | Crusoe Energy | 4th Project |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 | 1 | 27-210 | 27-210 - Crusoe Energy - Crusoe Energy - 4th Project - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization - G1 | Customer Site | UNITED STATES | TAS-N | Abilene | Customer Site | Monday | Std US Holidays |  | 2027-01-11 |  | 0 | 2027-09-27 01:00 | 2027-10-01 01:00 | 2027-11-01 01:00 | 2027-11-05 01:00 |  | 2027-11-01 01:00 | 2027-11-01 01:00 | 1/1/2027 12:00:00 AM |  | Created | 2025-12-05 | US Workweek and Holidays | Elias Benedi | Tentative | 2027.0
NRG | Jewett | Phase 1 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 30-7 | 30-7 - NRG - Jewett - Phase 1 - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2030-11-11 |  | 0 |  |  | 2030-11-11 | 2030-12-06 |  | 2030-11-11 | 2030-11-11 | Request Charles Wall. Only requires about 80 hours over 4 weeks, not full time. Please move out 29-7 - JEA - Jacksonville - OTS Post-COD Refresh as needed to accommodate this new request. No additional prep required |  | Created | 2025-12-03 | US Workweek and Holidays | Charles Wall | Tentative | 2030.0
NRG | Jewett | Phase 1 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 29-15 | 29-15 - NRG - Jewett - Phase 1 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | PM to confirm | Customer Site | Monday |  |  | 2029-10-29 01:00 |  | 0 |  |  | 2029-10-29 01:00 | 2029-11-06 |  | 2029-10-29 01:00 | 2029-10-29 01:00 | Request Doug Wadsworth. No additional prep required. Cannot take place sooner than 4 months after the completion of above activity Includes 5 days SAT + 2 days Intro Trng |  | Created | 2025-12-03 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2029.0
NRG | Jewett | Phase 1 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 29-14 | 29-14 - NRG - Jewett - Phase 1 - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | Remote | Distance Learning | Monday |  |  | 2029-07-16 01:00 |  | 0 |  |  | 2029-07-16 01:00 | 2029-09-13 01:00 |  | 2029-07-16 01:00 | 2029-07-16 01:00 | Request Charles Wal. No additional prep required |  | Created | 2025-12-03 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 | 2 | 27-207 | 27-207 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Combined Cycle - Operation (GE Integrated Systems) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-06-01 01:00 | 2027-06-03 01:00 | 2027-08-02 01:00 | 2027-08-06 01:00 |  | 2027-08-02 01:00 | 2027-08-02 01:00 | Sequence to follow Combined Cycle G1 (which follows directly after 27-205) |  | Created | 2025-12-02 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 | 1 | 27-206 | 27-206 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Combined Cycle - Operation (GE Integrated Systems) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-24 01:00 | 2027-05-28 01:00 | 2027-07-26 01:00 | 2027-07-30 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 | Sequence to follow directly after 27-205 |  | Created | 2025-12-02 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 | 2 | 27-205 | 27-205 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-06 01:00 | 2027-05-07 01:00 | 2027-07-19 01:00 | 2027-07-21 01:00 |  | 2027-07-19 01:00 | 2027-07-19 01:00 | Sequence to follow directly after 27-182 |  | Created | 2025-12-02 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 2 | 27-204 | 27-204 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2028-01-31 | 2028-02-04 | 2028-04-10 01:00 | 2028-04-21 01:00 |  | 2028-04-10 01:00 | 2028-04-10 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 1 | 27-203 | 27-203 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2028-01-17 | 2028-01-28 | 2028-03-27 01:00 | 2028-04-07 01:00 |  | 2028-03-27 01:00 | 2028-03-27 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 2 | 27-202 | 27-202 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2028-01-31 | 2028-02-04 | 2028-03-13 01:00 | 2028-03-24 01:00 |  | 2028-03-13 01:00 | 2028-03-13 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Willy Bueno | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 1 | 27-201 | 27-201 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2028-01-10 | 2028-01-21 | 2028-02-28 | 2028-03-10 |  | 2028-02-28 | 2028-02-28 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 12 | 2 | 27-200 | 27-200 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2028-01-03 | 2028-01-07 | 2028-02-21 | 2028-02-25 |  | 2028-02-21 | 2028-02-21 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 27-199 | 27-199 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-11-29 | 2027-12-03 | 2028-02-14 | 2028-02-18 |  | 2028-02-14 | 2028-02-14 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 12 | 2 | 27-198 | 27-198 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Operation - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-11-15 | 2027-11-19 | 2028-01-31 | 2028-02-11 |  | 2028-01-31 | 2028-01-31 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 12 | 1 | 27-197 | 27-197 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Operation - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-10-11 01:00 | 2027-11-12 | 2028-01-17 | 2028-01-28 |  | 2028-01-17 | 2028-01-17 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 | 2 | 27-196 | 27-196 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-10-04 01:00 | 2027-10-06 01:00 | 2028-01-10 | 2028-01-14 |  | 2028-01-10 | 2028-01-10 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-195 | 27-195 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-09-27 01:00 | 2027-10-01 01:00 | 2028-01-03 | 2028-01-07 |  | 2028-01-03 | 2028-01-03 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 27-194 | 27-194 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Operation-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-09-20 01:00 | 2027-09-24 01:00 | 2027-11-29 | 2027-12-10 |  | 2027-11-29 | 2027-11-29 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-193 | 27-193 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Operation-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-09-13 01:00 | 2027-09-24 01:00 | 2027-11-01 01:00 | 2027-11-12 |  | 2027-11-01 01:00 | 2027-11-01 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 | 2 | 27-192 | 27-192 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Control System - Mark VIe Distributed Control System Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-08-16 01:00 | 2027-08-18 01:00 | 2027-10-25 01:00 | 2027-10-29 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 | 1 | 27-191 | 27-191 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Control System - Mark VIe Distributed Control System Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-08-09 01:00 | 2027-08-13 01:00 | 2027-10-18 01:00 | 2027-10-22 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 2 | 27-190 | 27-190 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-08-02 01:00 | 2027-08-06 01:00 | 2027-10-04 01:00 | 2027-10-15 01:00 |  | 2027-10-04 01:00 | 2027-10-04 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-189 | 27-189 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-07-19 01:00 | 2027-07-30 01:00 | 2027-09-20 01:00 | 2027-10-01 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 | 2 | 27-188 | 27-188 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 |  |  | 2027-09-06 01:00 | 2027-09-14 01:00 |  | 2027-09-06 01:00 | 2027-09-06 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 | 1 | 27-187 | 27-187 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 |  |  | 2027-08-23 01:00 | 2027-08-31 01:00 |  | 2027-08-23 01:00 | 2027-08-23 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 2 | 27-186 | 27-186 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-06-21 01:00 | 2027-06-23 01:00 | 2027-08-16 01:00 | 2027-08-20 01:00 |  | 2027-08-16 01:00 | 2027-08-16 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 27-185 | 27-185 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-06-14 01:00 | 2027-06-17 01:00 | 2027-08-09 01:00 | 2027-08-13 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 | 1 | 27-182 | 27-182 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-03 01:00 | 2027-05-05 01:00 | 2027-07-12 01:00 | 2027-07-14 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 3 | 0 | 12 | 2 | 27-181 | 27-181 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-17 01:00 | 2027-05-19 01:00 | 2027-07-05 01:00 | 2027-07-09 01:00 |  | 2027-07-05 01:00 | 2027-07-05 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 27-180 | 27-180 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-04-05 01:00 | 2027-04-09 01:00 | 2027-06-28 01:00 | 2027-07-02 01:00 |  | 2027-06-28 01:00 | 2027-06-28 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 5 | 0 | 12 | 2 | 27-179 | 27-179 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-29 01:00 | 2027-04-02 01:00 | 2027-06-14 01:00 | 2027-06-25 01:00 |  | 2027-06-14 01:00 | 2027-06-14 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 | 1 | 27-178 | 27-178 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Steam Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-29 01:00 | 2027-04-09 01:00 | 2027-05-31 01:00 | 2027-06-11 01:00 |  | 2027-05-31 01:00 | 2027-05-31 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 | 2 | 27-177 | 27-177 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-15 01:00 | 2027-03-17 01:00 | 2027-05-24 01:00 | 2027-05-28 01:00 |  | 2027-05-24 01:00 | 2027-05-24 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-176 | 27-176 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-08 | 2027-03-12 | 2027-05-17 01:00 | 2027-05-21 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 2 | 27-175 | 27-175 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-05-03 01:00 | 2027-05-14 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
Kiewit | Homer City | 1 x 1 7HA.02 MS EEP |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-174 | 27-174 - Kiewit - Homer City - 1 x 1 7HA.02 MS EEP - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Homer City | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-15 01:00 | 2027-03-25 01:00 | 2027-04-19 01:00 | 2027-04-30 01:00 |  | 2027-04-19 01:00 | 2027-04-19 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2027.0
Invenergy | Sycamore Riverside Energy Project | 4 x 7F.05 H35 - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-930 | 28-930 - Invenergy - Sycamore Riverside Energy Project - 4 x 7F.05 H35 - RA - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Shelburn | Customer Site | Monday | Standard US Holidays |  | 2028-04-10 01:00 |  | 0 | 2028-08-21 01:00 | 2028-09-01 01:00 | 2028-10-09 01:00 | 2028-10-20 01:00 |  | 2028-10-09 01:00 | 2028-10-09 01:00 | 2Q-3Q2028, customer asking to have dates by 09-Jan-2026. |  | Created | 2025-12-02 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2028.0
Invenergy | Sycamore Riverside Energy Project | 4 x 7F.05 H35 - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-929 | 28-929 - Invenergy - Sycamore Riverside Energy Project - 4 x 7F.05 H35 - RA - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Shelburn | Customer Site | Monday | Standard US Holidays |  | 2028-04-10 01:00 |  | 0 | 2028-08-07 01:00 | 2028-08-11 01:00 | 2028-10-02 01:00 | 2028-10-06 01:00 |  | 2028-10-02 01:00 | 2028-10-02 01:00 | 2Q-3Q2028, customer asking to have dates by 09-Jan-2026. |  | Created | 2025-12-02 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2028.0
Invenergy | Sycamore Riverside Energy Project | 4 x 7F.05 H35 - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-928 | 28-928 - Invenergy - Sycamore Riverside Energy Project - 4 x 7F.05 H35 - RA - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Shelburn | Customer Site | Monday | Standard US Holidays |  | 2028-04-10 01:00 |  | 0 | 2028-08-14 01:00 | 2028-08-18 01:00 | 2028-09-25 01:00 | 2028-09-29 01:00 |  | 2028-09-25 01:00 | 2028-09-25 01:00 | 2Q-3Q2028, customer asking to have dates by 09-Jan-2026. |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2028.0
Invenergy | Sycamore Riverside Energy Project | 4 x 7F.05 H35 - RA |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-927 | 28-927 - Invenergy - Sycamore Riverside Energy Project - 4 x 7F.05 H35 - RA - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Shelburn | Customer Site | Monday | Standard US Holidays |  | 2028-04-10 01:00 |  | 0 | 2028-07-31 01:00 | 2028-08-11 01:00 | 2028-09-11 01:00 | 2028-09-22 01:00 |  | 2028-09-11 01:00 | 2028-09-11 01:00 | 2Q-3Q2028, customer asking to have dates by 09-Jan-2026. |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Confirmed | 2028.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 2 | 27-173 | 27-173 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-12-20 | 2027-12-27 | 2028-02-28 | 2028-03-10 |  | 2028-02-28 | 2028-02-28 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 1 | 27-172 | 27-172 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-12-06 | 2027-12-17 | 2028-02-14 | 2028-02-25 |  | 2028-02-14 | 2028-02-14 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 2 | 27-171 | 27-171 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-12-01 | 2027-12-07 | 2028-01-17 | 2028-01-28 |  | 2028-01-17 | 2028-01-17 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 1 | 27-170 | 27-170 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-11-15 | 2027-11-30 | 2028-01-03 | 2028-01-14 |  | 2028-01-03 | 2028-01-03 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 | 2 | 27-169 | 27-169 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-10 01:00 | 2027-05-12 01:00 | 2027-12-06 | 2027-12-10 |  | 2027-12-06 | 2027-12-06 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-168 | 27-168 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-03 01:00 | 2027-05-07 01:00 | 2027-11-29 | 2027-12-03 |  | 2027-11-29 | 2027-11-29 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 27-167 | 27-167 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Operation-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-07-05 01:00 | 2027-07-09 01:00 | 2027-09-27 01:00 | 2027-10-08 01:00 |  | 2027-09-27 01:00 | 2027-09-27 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-166 | 27-166 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Operation-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-29 01:00 | 2027-04-09 01:00 | 2027-07-12 01:00 | 2027-07-23 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 2 | 27-165 | 27-165 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-05-03 01:00 | 2027-05-07 01:00 | 2027-06-14 01:00 | 2027-06-25 01:00 |  | 2027-06-14 01:00 | 2027-06-14 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-164 | 27-164 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-02-22 | 2027-03-05 | 2027-04-05 01:00 | 2027-04-16 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 2 | 27-163 | 27-163 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-04-26 01:00 | 2027-04-28 01:00 | 2027-06-01 01:00 | 2027-06-04 01:00 |  | 2027-06-01 01:00 | 2027-06-01 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 27-162 | 27-162 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-02-16 | 2027-02-19 | 2027-03-29 01:00 | 2027-04-02 01:00 |  | 2027-03-29 01:00 | 2027-03-29 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 2 | 27-161 | 27-161 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-02-22 | 2027-02-24 | 2027-05-17 01:00 | 2027-05-21 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-160 | 27-160 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-01-19 | 2027-01-22 | 2027-03-22 01:00 | 2027-03-26 01:00 |  | 2027-03-22 01:00 | 2027-03-22 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 27-159 | 27-159 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-19 01:00 | 2027-04-30 01:00 |  | 2027-04-19 01:00 | 2027-04-19 01:00 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Mohamed Abdelaziz | Tentative | 2027.0
Duke Energy | Marshall | 2 x 7HA.03 with HT SCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-158 | 27-158 - Duke Energy - Marshall - 2 x 7HA.03 with HT SCR - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Lenoir | Customer Site | Monday | Standard US Holidays |  | 2027-03-29 01:00 |  | 0 | 2027-01-05 | 2027-01-15 | 2027-03-08 | 2027-03-19 01:00 |  | 2027-03-08 | 2027-03-08 | Asking 2Q2027 |  | Created | 2025-12-02 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Shell | Tejas Power | LM6000 | IFF-006825-CC-101-TRX |  | IFF-006825-CC-101-TRX |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-983 | 26-983 - Shell - Tejas Power - LM6000 - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | NYC | Customer Site | Monday |  |  | 2026-01-11 |  | 0 | 2026-01-20 | 2026-01-23 | 2026-06-01 01:00 | 2026-06-05 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 | replaces 25-630, asking 1Q2026. |  | Created | 2025-12-02 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
TVA | Lagoon Creek | - | IFF-005921-GT-101-TRX |  | IFF-005921-GT-101-TRX | I01-116787 / PO 4102802558 | English | English | IB | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-982 | 26-982 - TVA - Lagoon Creek - - - Control System - Mark VIe Maintenance | Customer Site | UNITED STATES | TAS-N | Brownsville | Customer Site | Monday |  |  | 2026-01-11 |  | 0 | 2026-03-04 | 2026-03-10 01:00 | 2026-04-06 01:00 | 2026-04-10 01:00 |  | 2026-04-06 01:00 | 2026-04-06 01:00 | replaces 26-658, asking 1Q2026. |  | Created | 2025-12-02 | US Workweek and Holidays | Bharat Vispara | Confirmed | 2026.0
CFE | MGVP Nizuc | LM2500 |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10701 | Gas Turbine - Aero MKVIe Operations | Aeroderivative | 3 | 3 | 1 | 12 |  | 26-981 | 26-981 - CFE - MGVP Nizuc - LM2500 - Gas Turbine - Aero MKVIe Operations | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-31 01:00 | 0 | 2026-01-08 | 2026-01-12 | 2026-04-27 01:00 | 2026-04-29 01:00 |  | 2026-04-27 01:00 | 2026-04-27 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Tamilarasan Kannaiyan | Cancelled | 2026.0
CFE | MGVP Nizuc | LM2500 |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 10 | 10 | 0 | 12 |  | 26-980 | 26-980 - CFE - MGVP Nizuc - LM2500 - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-30 01:00 | 0 | [7 empty] | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays |  | Cancelled | 2026.0
CFE | MGVP Nizuc | LM2500 |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 26-979 | 26-979 - CFE - MGVP Nizuc - LM2500 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-30 01:00 | 0 | [7 empty] | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays |  | Cancelled | 2026.0
CFE | MGVP Nizuc | LM2500 |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-978 | 26-978 - CFE - MGVP Nizuc - LM2500 - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-31 01:00 | 0 | 2026-01-20 | 2026-01-23 | 2026-04-20 01:00 | 2026-04-24 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | John Selman | Cancelled | 2026.0
CFE | MGVP Nizuc | LM2500 |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10202 | Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-977 | 26-977 - CFE - MGVP Nizuc - LM2500 - Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-31 01:00 | 0 | 2026-01-20 | 2026-01-23 | 2026-04-13 01:00 | 2026-04-17 01:00 |  | 2026-04-13 01:00 | 2026-04-13 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Cancelled | 2026.0
CFE | MGVP Nizuc | LM2500 |  |  |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-976 | 26-976 - CFE - MGVP Nizuc - LM2500 - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-30 01:00 | 0 | 2026-01-05 | 2026-01-09 | 2026-04-06 01:00 | 2026-04-10 01:00 |  | 2026-04-06 01:00 | 2026-04-06 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Cancelled | 2026.0
CFE | MGVP Cancun | LM2500 | PO 7903058405 | 203742 |  | I01-117367 / PO 7903058405 | Spanish | Spanish | NU | Alejandra Saldana | E-AER10701 | Gas Turbine - Aero MKVIe Operations | Aeroderivative | 3 | 3 | 1 | 12 |  | 26-975 | 26-975 - CFE - MGVP Cancun - LM2500 - Gas Turbine - Aero MKVIe Operations | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2026-03-30 01:00 | 2026-04-01 01:00 | 2026-05-04 01:00 | 2026-05-06 01:00 |  | 2026-05-04 01:00 | 2026-05-04 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Tamilarasan Kannaiyan | Confirmed | 2026.0
CFE | MGVP Cancun | LM2500 | PO 7903062235 | 203742 |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 10 | 10 | 0 | 12 |  | 26-974 | 26-974 - CFE - MGVP Cancun - LM2500 - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-30 01:00 | 0 | [5 empty] | 2026-07-27 01:00 |  | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Aero Instructor 1 | Tentative | 2026.0
CFE | MGVP Cancun | LM2500 | PO 7903065606 | 203742 |  | I01-120596 / PO 7903065606 | Spanish | Spanish | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 26-973 | 26-973 - CFE - MGVP Cancun - LM2500 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 |  |  | 2026-08-17 01:00 | 2026-08-28 01:00 |  | 2026-08-17 01:00 | 2026-08-17 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Diogo Dario | Confirmed | 2026.0
CFE | MGVP Cancun | LM2500 | PO 7903058405 | 203742 |  | I01-117367 / PO 7903058405 | Spanish | Spanish | NU | Alejandra Saldana | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-972 | 26-972 - CFE - MGVP Cancun - LM2500 - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday | 1-May-26 |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2026-02-23 | 2026-02-27 | 2026-04-27 01:00 | 2026-05-01 01:00 |  | 2026-04-27 01:00 | 2026-04-27 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Tamilarasan Kannaiyan | Confirmed | 2026.0
CFE | MGVP Cancun | LM2500 | IFF-007044-CC-101-TRX | 203742 | IFF-007044-CC-101-TRX |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10202 | Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-971 | 26-971 - CFE - MGVP Cancun - LM2500 - Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2026-02-23 | 2026-02-27 | 2026-04-20 01:00 | 2026-04-24 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Elias Benedi | Confirmed | 2026.0
CFE | MGVP Cancun | LM2500 | IFF-007040-CC-101-TRX | 203742 | IFF-007040-CC-101-TRX |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-970 | 26-970 - CFE - MGVP Cancun - LM2500 - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-26 01:00 | 0 | 2026-03-09 01:00 | 2026-03-13 01:00 | 2026-04-13 01:00 | 2026-04-17 01:00 |  | 2026-04-13 01:00 | 2026-04-13 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
CFE | MGVP Cozumel | LM2500 | PO 7903058433 | 203747 |  | I01-117336 / PO 7903058433 | Spanish | Spanish | NU | Alejandra Saldana | E-AER10701 | Gas Turbine - Aero MKVIe Operations | Aeroderivative | 3 | 3 | 1 | 12 |  | 26-969 | 26-969 - CFE - MGVP Cozumel - LM2500 - Gas Turbine - Aero MKVIe Operations | Customer Site | MEXICO | TAS-M | Cozumel | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2026-01-05 | 2026-01-07 | 2026-05-18 01:00 | 2026-05-20 01:00 |  | 2026-05-18 01:00 | 2026-05-18 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Tamilarasan Kannaiyan | Confirmed | 2026.0
CFE | MGVP Cozumel | LM2500 | PO 7903062236 | 203747 |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 10 | 10 | 0 | 12 |  | 26-968 | 26-968 - CFE - MGVP Cozumel - LM2500 - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | MEXICO | TAS-M | Cozumel | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 | [5 empty] | 2026-07-13 01:00 |  | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Aero Instructor 1 | Tentative | 2026.0
CFE | MGVP Cozumel | LM2500 |  | 203747 |  |  | Spanish | Spanish | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 26-967 | 26-967 - CFE - MGVP Cozumel - LM2500 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | MEXICO | TAS-M | Cozumel | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-28 01:00 | 0 |  |  | 2026-07-27 01:00 | 2026-08-07 01:00 |  | 2026-07-27 01:00 | 2026-07-27 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays |  | Confirmed | 2026.0
CFE | MGVP Cozumel | LM2500 | PO 7903058433 | 203747 |  | I01-117336 / PO 7903058433 | Spanish | Spanish | NU | Alejandra Saldana | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-966 | 26-966 - CFE - MGVP Cozumel - LM2500 - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | MEXICO | TAS-M | Cozumel | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2026-03-02 | 2026-03-06 | 2026-05-11 01:00 | 2026-05-15 01:00 |  | 2026-05-11 01:00 | 2026-05-11 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Tamilarasan Kannaiyan | Confirmed | 2026.0
CFE | MGVP Cozumel | LM2500 | IFF-007045-CC-101-TRX | 203747 | IFF-007045-CC-101-TRX |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10202 | Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-965 | 26-965 - CFE - MGVP Cozumel - LM2500 - Gas Turbine - LM2500+ and LM2500+ Xpress Package Maintenance | Customer Site | MEXICO | TAS-M | Cozumel | Customer Site | Monday | 1-May-26 |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2025-12-17 | 2025-12-23 | 2026-04-27 01:00 | 2026-05-01 01:00 |  | 2026-04-27 01:00 | 2026-04-27 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
CFE | MGVP Cozumel | LM2500 | IFF-007045-CC-101-TRX | 203747 | IFF-007045-CC-101-TRX |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-964 | 26-964 - CFE - MGVP Cozumel - LM2500 - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | MEXICO | TAS-M | Cozumel | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-27 01:00 | 0 | 2025-12-08 | 2025-12-16 | 2026-04-20 01:00 | 2026-04-24 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
CFE | MGVP Nizuc | TM2500 | PO 7903062237 | 203722 |  | I01-119021 / PO 7903062237 | Spanish | Spanish | NU | Alejandra Saldana | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 10 | 10 | 0 | 12 |  | 26-963 | 26-963 - CFE - MGVP Nizuc - TM2500 - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-25 01:00 | 0 |  |  | 2026-05-25 01:00 | 2026-06-05 01:00 |  | 2026-05-25 01:00 | 2026-05-25 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Brandon Beirne | Confirmed | 2026.0
CFE | MGVP Nizuc | TM2500 | PO 7903063406 | 203722 |  | I01-119144 / PO 7903063406 | Spanish | Spanish | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 26-962 | 26-962 - CFE - MGVP Nizuc - TM2500 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-27 01:00 | 0 |  |  | 2026-07-13 01:00 | 2026-07-24 01:00 |  | 2026-07-13 01:00 | 2026-07-13 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Diogo Dario | Confirmed | 2026.0
CFE | MGVP Nizuc | TM2500 | PO 7903063406 | 203722 |  | I01-119144 / PO 7903063406 | Spanish | Spanish | NU | Alejandra Saldana | E-CON13603 | Control System - RX3i Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-961 | 26-961 - CFE - MGVP Nizuc - TM2500 - Control System - RX3i Operation, Maintenance & Troubleshooting | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-28 01:00 | 0 | 2026-02-17 | 2026-02-20 | 2026-06-15 01:00 | 2026-06-19 01:00 |  | 2026-06-15 01:00 | 2026-06-15 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Diogo Dario | Confirmed | 2026.0
CFE | MGVP Nizuc | TM2500 | IFF-007021-CC-101-TRX | 203722 | IFF-007021-CC-101-TRX |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10502 | Gas Turbine - TM2500 Aero Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-960 | 26-960 - CFE - MGVP Nizuc - TM2500 - Gas Turbine - TM2500 Aero Package Maintenance | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday |  |  | 2026-03-01 | 2026-05-29 01:00 | 0 | 2026-01-20 | 2026-01-23 | 2026-03-23 01:00 | 2026-03-27 01:00 |  | 2026-03-23 01:00 | 2026-03-23 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
CFE | MGVP Nizuc | TM2500 | IFF-007021-CC-101-TRX | 203722 | IFF-007021-CC-101-TRX |  | Spanish | Spanish | NU | Alejandra Saldana | E-AER10501 | Gas Turbine - TM2500 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-959 | 26-959 - CFE - MGVP Nizuc - TM2500 - Gas Turbine - TM2500 Aero Package Operation/Familiarization | Customer Site | MEXICO | TAS-M | Cancun | Customer Site | Monday | 16-Mar-26 |  | 2026-03-01 | 2026-05-27 01:00 | 0 | 2026-01-05 | 2026-01-09 | 2026-03-16 01:00 | 2026-03-20 01:00 |  | 2026-03-16 01:00 | 2026-03-16 01:00 | Prep 3 months before start date to consider translation time, since material is required in Spanish |  | Created | 2025-12-01 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
Vistra | Permian | 440 MW 2 x 7HA.03 SC w/HTSCR |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-157 | 27-157 - Vistra - Permian - 440 MW 2 x 7HA.03 SC w/HTSCR - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Monahans | Customer Site | Monday | Standard US Holidays |  | 2027-02-01 |  | 0 | 2027-06-14 01:00 | 2027-06-25 01:00 | 2027-08-23 01:00 | 2027-09-03 01:00 |  | 2027-08-23 01:00 | 2027-08-23 01:00 | Asking Q1 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
Vistra | Permian | 440 MW 2 x 7HA.03 SC w/HTSCR |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-156 | 27-156 - Vistra - Permian - 440 MW 2 x 7HA.03 SC w/HTSCR - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Monahans | Customer Site | Monday | Standard US Holidays |  | 2027-02-01 |  | 0 | 2027-07-05 01:00 | 2027-07-09 01:00 | 2027-08-16 01:00 | 2027-08-20 01:00 |  | 2027-08-16 01:00 | 2027-08-16 01:00 | Asking Q1 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Vistra | Permian | 440 MW 2 x 7HA.03 SC w/HTSCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-155 | 27-155 - Vistra - Permian - 440 MW 2 x 7HA.03 SC w/HTSCR - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Monahans | Customer Site | Monday | Standard US Holidays |  | 2027-02-01 |  | 0 | 2027-05-24 01:00 | 2027-05-27 01:00 | 2027-08-09 01:00 | 2027-08-13 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 | Asking Q1 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
Vistra | Permian | 440 MW 2 x 7HA.03 SC w/HTSCR |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-154 | 27-154 - Vistra - Permian - 440 MW 2 x 7HA.03 SC w/HTSCR - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Monahans | Customer Site | Monday | Standard US Holidays |  | 2027-01-31 |  | 0 | 2027-06-14 01:00 | 2027-06-25 01:00 | 2027-07-26 01:00 | 2027-08-06 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 | Asking Q1 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 28-926 | 28-926 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-06-19 01:00 | 2028-06-23 01:00 | 2028-08-14 01:00 | 2028-08-18 01:00 |  | 2028-08-14 01:00 | 2028-08-14 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Isaiah Mason | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-925 | 28-925 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-06-05 01:00 | 2028-06-16 01:00 | 2028-07-31 01:00 | 2028-08-11 01:00 |  | 2028-07-31 01:00 | 2028-07-31 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Isaiah Mason | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-924 | 28-924 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-06-12 01:00 | 2028-06-16 01:00 | 2028-07-24 01:00 | 2028-07-28 01:00 |  | 2028-07-24 01:00 | 2028-07-24 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 28-923 | 28-923 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 |  |  | 2028-07-10 01:00 | 2028-07-18 01:00 |  | 2028-07-10 01:00 | 2028-07-10 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 28-922 | 28-922 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Electrical - Electrical Control System (ECS) Training | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 |  |  | 2028-07-05 01:00 | 2028-07-07 01:00 |  | 2028-07-05 01:00 | 2028-07-05 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-921 | 28-921 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Gas Turbine - Operation H-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-04-10 01:00 | 2028-04-14 01:00 | 2028-06-26 01:00 | 2028-06-30 01:00 |  | 2028-06-26 01:00 | 2028-06-26 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 28-920 | 28-920 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-05-01 01:00 | 2028-05-05 01:00 | 2028-06-19 01:00 | 2028-06-23 01:00 |  | 2028-06-19 01:00 | 2028-06-19 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Dave Miller | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 28-919 | 28-919 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-04-24 01:00 | 2028-04-26 01:00 | 2028-06-12 01:00 | 2028-06-14 01:00 |  | 2028-06-12 01:00 | 2028-06-12 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Dave Miller | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 28-918 | 28-918 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-03-27 01:00 | 2028-03-31 01:00 | 2028-06-05 01:00 | 2028-06-09 01:00 |  | 2028-06-05 01:00 | 2028-06-05 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Donald Hopkins | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 28-917 | 28-917 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-03-13 01:00 | 2028-03-24 01:00 | 2028-05-22 01:00 | 2028-06-02 01:00 |  | 2028-05-22 01:00 | 2028-05-22 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Donald Hopkins | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-916 | 28-916 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-04-03 01:00 | 2028-04-07 01:00 | 2028-05-15 01:00 | 2028-05-19 01:00 |  | 2028-05-15 01:00 | 2028-05-15 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2028.0
CPV | Basin Ranch | 2x1x1 7HA.03 EEP CCS |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-915 | 28-915 - CPV - Basin Ranch - 2x1x1 7HA.03 EEP CCS - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Barstow | Customer Site | Monday | Standard US Holidays |  | 2028-05-01 01:00 |  | 0 | 2028-03-20 01:00 | 2028-03-31 01:00 | 2028-05-01 01:00 | 2028-05-12 01:00 |  | 2028-05-01 01:00 | 2028-05-01 01:00 | Asking Q2 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 28-902 | 28-902 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-09-04 01:00 | 2028-09-08 01:00 | 2028-10-09 01:00 | 2028-10-13 01:00 |  | 2028-10-09 01:00 | 2028-10-09 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Isaiah Mason | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-901 | 28-901 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-08-21 01:00 | 2028-09-01 01:00 | 2028-09-25 01:00 | 2028-10-06 01:00 |  | 2028-09-25 01:00 | 2028-09-25 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Isaiah Mason | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-900 | 28-900 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-07-31 01:00 | 2028-08-04 01:00 | 2028-09-18 01:00 | 2028-09-22 01:00 |  | 2028-09-18 01:00 | 2028-09-18 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-899 | 28-899 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Gas Turbine - Operation H-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-07-31 01:00 | 2028-08-04 01:00 | 2028-09-11 01:00 | 2028-09-15 01:00 |  | 2028-09-11 01:00 | 2028-09-11 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 28-898 | 28-898 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-07-10 01:00 | 2028-07-14 01:00 | 2028-08-28 01:00 | 2028-09-01 01:00 |  | 2028-08-28 01:00 | 2028-08-28 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Dave Miller | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 28-897 | 28-897 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-07-05 01:00 | 2028-07-07 01:00 | 2028-08-21 01:00 | 2028-08-23 01:00 |  | 2028-08-21 01:00 | 2028-08-21 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Dave Miller | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 28-896 | 28-896 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-06-19 01:00 | 2028-06-23 01:00 | 2028-08-14 01:00 | 2028-08-18 01:00 |  | 2028-08-14 01:00 | 2028-08-14 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 28-895 | 28-895 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-06-05 01:00 | 2028-06-16 01:00 | 2028-07-31 01:00 | 2028-08-11 01:00 |  | 2028-07-31 01:00 | 2028-07-31 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 28-894 | 28-894 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-06-19 01:00 | 2028-06-23 01:00 | 2028-07-24 01:00 | 2028-07-28 01:00 |  | 2028-07-24 01:00 | 2028-07-24 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Chevron | Kilby | 2 x 7HA.02 Combined Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 28-893 | 28-893 - Chevron - Kilby - 2 x 7HA.02 Combined Cycle - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2028-07-10 01:00 |  | 0 | 2028-06-05 01:00 | 2028-06-16 01:00 | 2028-07-10 01:00 | 2028-07-21 01:00 |  | 2028-07-10 01:00 | 2028-07-10 01:00 | Asking Q3 2028 |  | Created | 2025-11-25 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Chevron | Kilby | 3 x 7HA.02 Simple Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 15 | 1 | 27-141 | 27-141 - Chevron - Kilby - 3 x 7HA.02 Simple Cycle - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 |  | 0 | 2027-10-04 01:00 | 2027-10-15 01:00 | 2027-11-29 | 2027-12-10 |  | 2027-11-29 | 2027-11-29 | Asking Q3/Q4 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Rafael Venancio | Tentative | 2027.0
Chevron | Kilby | 3 x 7HA.02 Simple Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 15 | 1 | 27-140 | 27-140 - Chevron - Kilby - 3 x 7HA.02 Simple Cycle - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 |  | 0 | 2027-10-04 01:00 | 2027-10-08 01:00 | 2027-11-15 | 2027-11-19 |  | 2027-11-15 | 2027-11-15 | Asking Q3/Q4 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2027.0
Chevron | Kilby | 3 x 7HA.02 Simple Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 15 | 1 | 27-139 | 27-139 - Chevron - Kilby - 3 x 7HA.02 Simple Cycle - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 |  | 0 | 2027-08-23 01:00 | 2027-08-27 01:00 | 2027-11-08 | 2027-11-12 |  | 2027-11-08 | 2027-11-08 | Asking Q3/Q4 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Chevron | Kilby | 3 x 7HA.02 Simple Cycle |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 | 1 | 27-138 | 27-138 - Chevron - Kilby - 3 x 7HA.02 Simple Cycle - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Reeves City | Customer Site | Monday | Standard US Holidays |  | 2027-07-12 01:00 |  | 0 | 2027-08-09 01:00 | 2027-08-20 01:00 | 2027-10-25 01:00 | 2027-11-05 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 | Asking Q3/Q4 2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Santee Cooper | Moncks Corner | 2 x LM6000 PF+ |  |  |  |  | English | English | IB | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-137 | 27-137 - Santee Cooper - Moncks Corner - 2 x LM6000 PF+ - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Moncks Corner | Customer Site | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-10-11 01:00 | 2027-10-15 01:00 | 2027-11-08 | 2027-11-12 |  | 2027-11-08 | 2027-11-08 | 4Q2027 |  | Created | 2025-11-25 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Santee Cooper | Moncks Corner | 2 x LM6000 PF+ |  |  |  |  | English | English | IB | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-136 | 27-136 - Santee Cooper - Moncks Corner - 2 x LM6000 PF+ - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Moncks Corner | Customer Site | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-09-27 01:00 | 2027-10-01 01:00 | 2027-11-01 01:00 | 2027-11-05 01:00 |  | 2027-11-01 01:00 | 2027-11-01 01:00 | 4Q2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Santee Cooper | Moncks Corner | 2 x LM6000 PF+ |  |  |  |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-135 | 27-135 - Santee Cooper - Moncks Corner - 2 x LM6000 PF+ - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Moncks Corner | Customer Site | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-09-07 01:00 | 2027-09-10 01:00 | 2027-10-25 01:00 | 2027-10-29 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 | 4Q2027 |  | Created | 2025-11-25 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
HAL | Indian Navy | P17 | G10-US-0001075-001-00241 |  | G10-US-0001075-001-00241 |  | English | English | NU | Gavin Yoong | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 25-910 | 25-910 - HAL - Indian Navy - P17 - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2025-12-08 | 2025-12-11 | 0 |  |  | 2025-12-08 | 2025-12-12 |  | 2025-12-08 | 2025-12-08 |  | Yes | Created | 2025-11-25 | US Workweek and Holidays | Elias Benedi | Confirmed | 2025.0
HAL | Indian Navy | P17 | G10-US-0001075-001-00241 |  | G10-US-0001075-001-00241 |  | English | English | NU | Gavin Yoong | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 2 | 2 | 0 | 8 |  | 25-909 | 25-909 - HAL - Indian Navy - P17 - Gas Turbine - LM2500 Borescope Inspection | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2025-12-04 | 2025-12-04 | 0 |  |  | 2025-12-04 | 2025-12-05 |  | 2025-12-04 | 2025-12-04 |  | Yes | Created | 2025-11-25 | US Workweek and Holidays | Elias Benedi | Confirmed | 2025.0
Rauma Marine Constructions (RMC) | - | The Finnish Defense Forces Robert Liner SQ2020 | G10-US-0001319-001-00245 |  | G10-US-0001319-001-00245 |  | English | English | IB | Anna Petrella | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 2 | 2 | 0 | 12 |  | 26-958 | 26-958 - Rauma Marine Constructions (RMC) - - - The Finnish Defense Forces Robert Liner SQ2020 - Gas Turbine - LM2500 Borescope Inspection | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | -- | 3202 Astrodome Room | 2026-03-12 01:00 | 2026-03-11 01:00 | 0 | 2026-02-23 | 2026-02-24 | 2026-03-12 01:00 | 2026-03-13 01:00 |  | 2026-03-12 01:00 | 2026-03-12 01:00 |  |  | Created | 2025-11-25 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
Rauma Marine Constructions (RMC) | - | The Finnish Defense Forces Robert Liner SQ2020 | G10-US-0001319-001-00245 |  | G10-US-0001319-001-00245 |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-957 | 26-957 - Rauma Marine Constructions (RMC) - - - The Finnish Defense Forces Robert Liner SQ2020 - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | -- | 3202 Astrodome Room | 2026-03-05 | 2026-03-09 01:00 | 0 | 2026-01-15 | 2026-01-22 | 2026-03-05 | 2026-03-11 01:00 |  | 2026-03-05 | 2026-03-05 |  |  | Created | 2025-11-25 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
Rauma Marine Constructions (RMC) | - | The Finnish Defense Forces Robert Liner SQ2020 | G10-US-0001319-001-00245 |  | G10-US-0001319-001-00245 |  | English | English | IB | Anna Petrella | E-AER10103 | Gas Turbine - LM2500 Engine Familiarization | Aeroderivative | 3 | 3 | 0 | 12 |  | 26-956 | 26-956 - Rauma Marine Constructions (RMC) - - - The Finnish Defense Forces Robert Liner SQ2020 - Gas Turbine - LM2500 Engine Familiarization | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday | -- | 3202 Astrodome Room | 2026-03-02 | 2026-03-01 | 0 | 2026-01-12 | 2026-01-14 | 2026-03-02 | 2026-03-04 |  | 2026-03-02 | 2026-03-02 |  |  | Created | 2025-11-25 | US Workweek and Holidays | Richard Fisher | Confirmed | 2026.0
NYPA | In City | - | IFF-006245-GT-101-TRX |  | IFF-006245-GT-101-TRX |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-953 | 26-953 - NYPA - In City - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | NYC | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2026-01-26 | 2026-01-30 | 2026-06-08 01:00 | 2026-06-12 01:00 |  | 2026-06-08 01:00 | 2026-06-08 01:00 | replaces 26-254 - Calpine King City |  | Created | 2025-11-24 | US Workweek and Holidays | Mark Girling | Cancelled | 2026.0
SEPCOIII | Qassim-1 IPP | Project_1.8GW_7E.03 SC Unit | EGM-00487-1CSTO-TRAINALL |  | EGM-00487-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 15 |  | 26-952 | 26-952 - SEPCOIII - Qassim-1 IPP - Project_1.8GW_7E.03 SC Unit - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-M | Qassim | Customer Site | Sunday |  |  | 2026-09-27 01:00 | 2026-10-03 01:00 | 0 |  |  | 2027-02-14 | 2027-02-22 |  | 2027-02-14 | 2027-02-14 |  |  | Created | 2025-11-21 | Sun - Thurs Middle East 5 Day Workweek | Grid Solution Excitation Instructor | Tentative | 2026.0
SEPCOIII | Qassim-1 IPP | Project_1.8GW_7E.03 SC Unit | EGM-00487-1CSTO-TRAINALL |  | EGM-00487-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 15 |  | 26-951 | 26-951 - SEPCOIII - Qassim-1 IPP - Project_1.8GW_7E.03 SC Unit - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-M | Qassim | Customer Site | Sunday |  |  | 2026-09-06 01:00 | 2026-09-16 01:00 | 0 | 2026-12-14 | 2026-12-29 | 2027-02-07 | 2027-02-18 |  | 2027-02-07 | 2027-02-07 |  |  | Created | 2025-11-24 | Sun - Thurs Middle East 5 Day Workweek | Khaled Al Behiri | Tentative | 2026.0
SEPCOIII | Qassim-1 IPP | Project_1.8GW_7E.03 SC Unit | EGM-00487-1CSTO-TRAINALL |  | EGM-00487-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 15 |  | 26-950 | 26-950 - SEPCOIII - Qassim-1 IPP - Project_1.8GW_7E.03 SC Unit - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-M | Qassim | Customer Site | Sunday |  |  | 2026-08-09 01:00 | 2026-08-11 01:00 | 0 | 2026-11-23 | 2026-11-27 | 2027-01-31 | 2027-02-04 |  | 2027-01-31 | 2027-01-31 |  |  | Created | 2025-11-24 | Sun - Thurs Middle East 5 Day Workweek | Khaled Al Behiri | Tentative | 2026.0
SEPCOIII | Qassim-1 IPP | Project_1.8GW_7E.03 SC Unit | EGM-00487-1CSTO-TRAINALL |  | EGM-00487-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 1 | 15 |  | 26-949 | 26-949 - SEPCOIII - Qassim-1 IPP - Project_1.8GW_7E.03 SC Unit - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-M | Qassim | Customer Site | Sunday |  |  | 2026-07-26 01:00 | 2026-07-28 01:00 | 0 | 2026-05-26 01:00 | 2026-05-29 01:00 | 2027-01-24 | 2027-01-28 |  | 2027-01-24 | 2027-01-24 |  |  | Created | 2025-11-24 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Tentative | 2026.0
SEPCOIII | Qassim-1 IPP | Project_1.8GW_7E.03 SC Unit | EGM-00487-1CSTO-TRAINALL |  | EGM-00487-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 15 |  | 26-948 | 26-948 - SEPCOIII - Qassim-1 IPP - Project_1.8GW_7E.03 SC Unit - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | Qassim | Customer Site | Sunday |  |  | 2026-05-07 01:00 | 2026-07-14 01:00 | 0 | 2026-04-27 01:00 | 2026-05-15 01:00 | 2027-01-10 | 2027-01-21 |  | 2027-01-10 | 2027-01-10 |  |  | Created | 2025-11-24 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Tentative | 2026.0
LG&E | Mill Creek | 6 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 30-6 | 30-6 - LG&E - Mill Creek - 6 - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2031-02-10 |  | 0 |  |  | 2031-02-10 | 2031-03-07 |  | 2031-02-10 | 2031-02-10 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2030.0
LG&E | Mill Creek | 6 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 30-5 | 30-5 - LG&E - Mill Creek - 6 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2030-09-23 01:00 |  | 0 |  |  | 2030-09-23 01:00 | 2030-10-01 01:00 |  | 2030-09-23 01:00 | 2030-09-23 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2030.0
LG&E | Mill Creek | 6 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 30-4 | 30-4 - LG&E - Mill Creek - 6 - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2030-06-10 01:00 |  | 0 |  |  | 2030-06-10 01:00 | 2030-08-08 01:00 |  | 2030-06-10 01:00 | 2030-06-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2030.0
DTE | Milan Township | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 30-3 | 30-3 - DTE - Milan Township - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2031-07-07 01:00 |  | 0 |  |  | 2031-07-07 01:00 | 2031-08-01 01:00 |  | 2031-07-07 01:00 | 2031-07-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Cancelled | 2030.0
DTE | Milan Township | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 30-2 | 30-2 - DTE - Milan Township - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2030-11-11 |  | 0 |  |  | 2030-11-11 | 2030-11-19 |  | 2030-11-11 | 2030-11-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Cancelled | 2030.0
DTE | Milan Township | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 30-1 | 30-1 - DTE - Milan Township - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2030-09-09 01:00 |  | 0 |  |  | 2030-09-09 01:00 | 2030-11-07 |  | 2030-09-09 01:00 | 2030-09-09 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Cancelled | 2030.0
LG&E | EW Brown | 12 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 29-13 | 29-13 - LG&E - EW Brown - 12 - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2030-08-12 01:00 |  | 0 |  |  | 2030-10-14 01:00 | 2030-11-08 |  | 2030-10-14 01:00 | 2030-10-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
LG&E | EW Brown | 12 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 29-12 | 29-12 - LG&E - EW Brown - 12 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2029-08-13 01:00 |  | 0 |  |  | 2029-08-13 01:00 | 2029-08-21 01:00 |  | 2029-08-13 01:00 | 2029-08-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2029.0
LG&E | EW Brown | 12 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 29-11 | 29-11 - LG&E - EW Brown - 12 - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2029-04-09 01:00 |  | 0 |  |  | 2029-03-05 | 2029-05-03 01:00 |  | 2029-03-05 | 2029-03-05 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
JEA | Jacksonville | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 29-7 | 29-7 - JEA - Jacksonville - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2030-11-11 |  | 0 |  |  | 2030-12-09 | 2031-01-03 |  | 2030-12-09 | 2030-12-09 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
JEA | Jacksonville | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 29-6 | 29-6 - JEA - Jacksonville - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2029-12-12 |  | 0 |  |  | 2029-12-12 | 2029-12-20 |  | 2029-12-12 | 2029-12-12 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2029.0
JEA | Jacksonville | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 29-5 | 29-5 - JEA - Jacksonville - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2029-09-14 01:00 |  | 0 |  |  | 2029-09-14 01:00 | 2029-11-14 |  | 2029-09-14 01:00 | 2029-09-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2029.0
Senoko Energy Pte Ltd | Senoko | - |  |  |  |  | English | English | NU | Gavin Yoong | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 29-4 | 29-4 - Senoko Energy Pte Ltd - Senoko - - - OTS Post-COD Refresh - CC Sim | Remote | SINGAPORE | TAS-M | - | Distance Learning | Monday |  |  | 2030-01-14 |  | 0 |  |  | 2030-01-14 | 2030-02-08 |  | 2030-01-14 | 2030-01-14 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Cancelled | 2029.0
Senoko Energy Pte Ltd | Senoko | - |  |  |  |  | English | English | NU | Gavin Yoong | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 29-3 | 29-3 - Senoko Energy Pte Ltd - Senoko - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | SINGAPORE | TAS-M | - | Customer Site | Monday |  |  | 2029-05-22 01:00 |  | 0 |  |  | 2029-05-22 01:00 | 2029-05-30 01:00 |  | 2029-05-22 01:00 | 2029-05-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Cancelled | 2029.0
Senoko Energy Pte Ltd | Senoko | - |  |  |  |  | English | English | NU | Gavin Yoong | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 29-2 | 29-2 - Senoko Energy Pte Ltd - Senoko - - - OTS Simulator Development & Testing - CC Sim | Remote | SINGAPORE | TAS-M | - | Distance Learning | Monday |  |  | 2029-01-22 |  | 0 |  |  | 2029-01-01 | 2029-03-01 |  | 2029-01-01 | 2029-01-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Cancelled | 2029.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 | 4 | 28-69 | 28-69 - Dominion - Chesterfield - - - Control System - Mark VIe Maintenance (Extended) - G4 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-08-07 01:00 | 2028-08-11 01:00 | 2029-01-08 | 2029-01-19 |  | 2029-01-08 | 2029-01-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 | 4 | 28-68 | 28-68 - Dominion - Chesterfield - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G4 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-08-21 01:00 | 2028-08-23 01:00 | 2028-12-18 | 2028-12-22 |  | 2028-12-18 | 2028-12-18 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 | 4 | 28-67 | 28-67 - Dominion - Chesterfield - - - Gas Turbine - Maintenance - G4 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-08-14 01:00 | 2028-08-16 01:00 | 2028-12-11 | 2028-12-15 |  | 2028-12-11 | 2028-12-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 4 | 28-66 | 28-66 - Dominion - Chesterfield - - - Gas Turbine - Operation - G4 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-08-07 01:00 | 2028-08-11 01:00 | 2028-11-27 | 2028-12-08 |  | 2028-11-27 | 2028-11-27 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 | 3 | 28-65 | 28-65 - Dominion - Chesterfield - - - Control System - Mark VIe Maintenance (Extended) - G3 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-07-10 01:00 | 2028-07-14 01:00 | 2028-10-30 01:00 | 2028-11-10 |  | 2028-10-30 01:00 | 2028-10-30 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 | 3 | 28-64 | 28-64 - Dominion - Chesterfield - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G3 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-20 01:00 | 2028-06-22 01:00 | 2028-10-23 01:00 | 2028-10-27 01:00 |  | 2028-10-23 01:00 | 2028-10-23 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 | 3 | 28-63 | 28-63 - Dominion - Chesterfield - - - Gas Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-19 01:00 | 2028-06-21 01:00 | 2028-10-16 01:00 | 2028-10-20 01:00 |  | 2028-10-16 01:00 | 2028-10-16 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 3 | 28-62 | 28-62 - Dominion - Chesterfield - - - Gas Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-12 01:00 | 2028-06-16 01:00 | 2028-10-02 01:00 | 2028-10-13 01:00 |  | 2028-10-02 01:00 | 2028-10-02 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 | 2 | 28-61 | 28-61 - Dominion - Chesterfield - - - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-07-31 01:00 | 2028-08-04 01:00 | 2028-09-18 01:00 | 2028-09-29 01:00 |  | 2028-09-18 01:00 | 2028-09-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 | 2 | 28-60 | 28-60 - Dominion - Chesterfield - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-08-07 01:00 | 2028-08-09 01:00 | 2028-09-11 01:00 | 2028-09-15 01:00 |  | 2028-09-11 01:00 | 2028-09-11 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 | 2 | 28-59 | 28-59 - Dominion - Chesterfield - - - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-07-05 01:00 | 2028-07-07 01:00 | 2028-09-04 01:00 | 2028-09-08 01:00 |  | 2028-09-04 01:00 | 2028-09-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 2 | 28-58 | 28-58 - Dominion - Chesterfield - - - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-26 01:00 | 2028-06-30 01:00 | 2028-08-21 01:00 | 2028-09-01 01:00 |  | 2028-08-21 01:00 | 2028-08-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 28-57 | 28-57 - Dominion - Chesterfield - - - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-26 01:00 | 2028-07-07 01:00 | 2028-08-07 01:00 | 2028-08-18 01:00 |  | 2028-08-07 01:00 | 2028-08-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 28-56 | 28-56 - Dominion - Chesterfield - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-12 01:00 | 2028-06-16 01:00 | 2028-07-31 01:00 | 2028-08-04 01:00 |  | 2028-07-31 01:00 | 2028-07-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 28-55 | 28-55 - Dominion - Chesterfield - - - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-06-05 01:00 | 2028-06-09 01:00 | 2028-07-24 01:00 | 2028-07-28 01:00 |  | 2028-07-24 01:00 | 2028-07-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
Dominion | Chesterfield | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 28-54 | 28-54 - Dominion - Chesterfield - - - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Chester | Customer Site | Monday |  |  | 2028-07-01 01:00 |  | 0 | 2028-05-01 01:00 | 2028-05-12 01:00 | 2028-07-10 01:00 | 2028-07-21 01:00 |  | 2028-07-10 01:00 | 2028-07-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 3 | 0 | 12 | 4 | 28-53 | 28-53 - Duke Energy - Person County - Phase 1 - GT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-10-02 01:00 | 2028-10-04 01:00 | 2028-12-11 | 2028-12-22 |  | 2028-12-11 | 2028-12-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 3 | 0 | 12 | 4 | 28-52 | 28-52 - Duke Energy - Person County - Phase 1 - GT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-10-30 01:00 | 2028-11-01 01:00 | 2028-11-27 | 2028-12-08 |  | 2028-11-27 | 2028-11-27 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 2 | 0 | 12 | 4 | 28-51 | 28-51 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance On-the-Job Training (OJT) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-09-07 01:00 | 2028-09-08 01:00 | 2028-11-06 | 2028-11-10 |  | 2028-11-06 | 2028-11-06 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 3 | 0 | 12 | 4 | 28-50 | 28-50 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-09-04 01:00 | 2028-09-06 01:00 | 2028-10-23 01:00 | 2028-11-03 01:00 |  | 2028-10-23 01:00 | 2028-10-23 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 2 | 0 | 12 | 4 | 28-49 | 28-49 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-08-17 01:00 | 2028-08-18 01:00 | 2028-10-16 01:00 | 2028-10-20 01:00 |  | 2028-10-16 01:00 | 2028-10-16 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 3 | 0 | 12 | 4 | 28-48 | 28-48 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation-On-the-Job Training (OJT) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-08-14 01:00 | 2028-08-16 01:00 | 2028-10-02 01:00 | 2028-10-13 01:00 |  | 2028-10-02 01:00 | 2028-10-02 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 3 | 0 | 12 | 3 | 28-47 | 28-47 - Duke Energy - Person County - Phase 1 - GT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-08-28 01:00 | 2028-08-30 01:00 | 2028-09-18 01:00 | 2028-09-29 01:00 |  | 2028-09-18 01:00 | 2028-09-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 3 | 0 | 12 | 3 | 28-46 | 28-46 - Duke Energy - Person County - Phase 1 - GT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-07-10 01:00 | 2028-07-12 01:00 | 2028-09-04 01:00 | 2028-09-15 01:00 |  | 2028-09-04 01:00 | 2028-09-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 5 | 2 | 0 | 12 | 3 | 28-45 | 28-45 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-06-29 01:00 | 2028-06-30 01:00 | 2028-08-28 01:00 | 2028-09-01 01:00 |  | 2028-08-28 01:00 | 2028-08-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 3 | 0 | 12 | 3 | 28-44 | 28-44 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-06-26 01:00 | 2028-06-28 01:00 | 2028-08-14 01:00 | 2028-08-25 01:00 |  | 2028-08-14 01:00 | 2028-08-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 2 | 0 | 12 | 3 | 28-43 | 28-43 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-05-25 01:00 | 2028-05-26 01:00 | 2028-08-07 01:00 | 2028-08-11 01:00 |  | 2028-08-07 01:00 | 2028-08-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 3 | 0 | 12 | 3 | 28-42 | 28-42 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation-On-the-Job Training (OJT) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2028-05-22 01:00 | 2028-05-24 01:00 | 2028-07-24 01:00 | 2028-08-04 01:00 |  | 2028-07-24 01:00 | 2028-07-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 3 | 0 | 12 | 4 | 28-41 | 28-41 - Duke Energy - Person County - Phase 1 - GT - Control System - Mark VIe Maintenance (Extended) - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2027-08-12 01:00 | 2027-08-16 01:00 | 2028-01-10 | 2028-01-21 |  | 2028-01-10 | 2028-01-10 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 | 4 | 28-40 | 28-40 - Duke Energy - Person County - Phase 1 - GT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2027-10-11 01:00 | 2027-10-13 01:00 | 2028-01-03 | 2028-01-07 |  | 2028-01-03 | 2028-01-03 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 2 | 0 | 12 | 4 | 28-39 | 28-39 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2027-08-19 01:00 | 2027-08-20 01:00 | 2027-12-13 | 2027-12-17 |  | 2027-12-13 | 2027-12-13 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 3 | 0 | 12 | 4 | 28-38 | 28-38 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2027-08-16 01:00 | 2027-08-18 01:00 | 2027-11-29 | 2027-12-10 |  | 2027-11-29 | 2027-11-29 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 2 | 0 | 12 | 4 | 28-37 | 28-37 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2027-09-30 01:00 | 2027-10-01 01:00 | 2027-11-15 | 2027-11-19 |  | 2027-11-15 | 2027-11-15 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 3 | 0 | 12 | 4 | 28-36 | 28-36 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation - G4 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-09-01 01:00 |  | 0 | 2027-09-27 01:00 | 2027-09-29 01:00 | 2027-11-01 01:00 | 2027-11-12 |  | 2027-11-01 01:00 | 2027-11-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 3 | 0 | 12 | 3 | 28-35 | 28-35 - Duke Energy - Person County - Phase 1 - GT - Control System - Mark VIe Maintenance (Extended) - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-03-01 |  | 0 | 2027-08-09 01:00 | 2027-08-11 01:00 | 2027-10-25 01:00 | 2027-11-05 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 | 3 | 28-34 | 28-34 - Duke Energy - Person County - Phase 1 - GT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-03-01 |  | 0 | 2027-09-07 01:00 | 2027-09-09 01:00 | 2027-10-18 01:00 | 2027-10-22 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 2 | 0 | 12 | 3 | 28-33 | 28-33 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-03-01 |  | 0 | 2027-08-12 01:00 | 2027-08-13 01:00 | 2027-10-11 01:00 | 2027-10-15 01:00 |  | 2027-10-11 01:00 | 2027-10-11 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 3 | 0 | 12 | 3 | 28-32 | 28-32 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-03-01 |  | 0 | 2027-08-09 01:00 | 2027-08-11 01:00 | 2027-09-27 01:00 | 2027-10-08 01:00 |  | 2027-09-27 01:00 | 2027-09-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 2 | 0 | 12 | 3 | 28-31 | 28-31 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-03-01 |  | 0 | 2027-06-24 01:00 | 2027-06-25 01:00 | 2027-09-20 01:00 | 2027-09-24 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2028.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 3 | 0 | 12 | 3 | 28-30 | 28-30 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2028-03-01 |  | 0 | 2027-06-21 01:00 | 2027-06-23 01:00 | 2027-09-06 01:00 | 2027-09-17 01:00 |  | 2027-09-06 01:00 | 2027-09-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2028.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 28-29 | 28-29 - NRG - Greens Bayou - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2028-01-07 |  | 0 | 2028-06-26 01:00 | 2028-06-30 01:00 | 2028-08-07 01:00 | 2028-08-18 01:00 |  | 2028-08-07 01:00 | 2028-08-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Tentative | 2028.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 28-28 | 28-28 - NRG - Greens Bayou - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2028-01-07 |  | 0 | 2028-06-20 01:00 | 2028-06-22 01:00 | 2028-07-31 01:00 | 2028-08-04 01:00 |  | 2028-07-31 01:00 | 2028-07-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2028.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 |  | 28-27 | 28-27 - NRG - Greens Bayou - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2028-01-07 |  | 0 | 2028-06-05 01:00 | 2028-06-07 01:00 | 2028-07-24 01:00 | 2028-07-28 01:00 |  | 2028-07-24 01:00 | 2028-07-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 |  | 28-26 | 28-26 - NRG - Greens Bayou - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2028-01-07 |  | 0 | 2028-05-29 01:00 | 2028-06-02 01:00 | 2028-07-10 01:00 | 2028-07-21 01:00 |  | 2028-07-10 01:00 | 2028-07-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2028.0
ENEA ELKOGAZ | Polaniec | - |  |  |  |  | Polish | Polish | NU | Anna Petrella | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-25 | 28-25 - ENEA ELKOGAZ - Polaniec - - - OTS Post-COD Refresh - CC Sim | Remote | POLAND | TAS-N | - | Distance Learning | Monday |  |  | 2030-03-18 01:00 |  | 0 |  |  | 2030-03-18 01:00 | 2030-04-12 01:00 |  | 2030-03-18 01:00 | 2030-03-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
ENEA ELKOGAZ | Polaniec | - |  |  |  |  | Polish | Polish | NU | Anna Petrella | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 28-24 | 28-24 - ENEA ELKOGAZ - Polaniec - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | POLAND | TAS-N | Polaniec | Customer Site | Monday |  |  | 2029-03-12 01:00 |  | 0 |  |  | 2029-03-12 01:00 | 2029-03-20 01:00 |  | 2029-03-12 01:00 | 2029-03-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2028.0
ENEA ELKOGAZ | Polaniec | - |  |  |  |  | Polish | Polish | NU | Anna Petrella | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-23 | 28-23 - ENEA ELKOGAZ - Polaniec - - - OTS Simulator Development & Testing - CC Sim | Remote | POLAND | TAS-N | - | Distance Learning | Monday |  |  | 2028-08-28 01:00 |  | 0 |  |  | 2028-08-28 01:00 | 2028-10-26 01:00 |  | 2028-08-28 01:00 | 2028-08-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Oglethorpe Power Company | SMARR CC | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-22 | 28-22 - Oglethorpe Power Company - SMARR CC - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2029-07-16 01:00 |  | 0 |  |  | 2029-05-07 01:00 | 2029-06-01 01:00 |  | 2029-05-07 01:00 | 2029-05-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Oglethorpe Power Company | SMARR CC | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 28-21 | 28-21 - Oglethorpe Power Company - SMARR CC - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2028-10-23 01:00 |  | 0 |  |  | 2028-10-23 01:00 | 2028-10-31 01:00 |  | 2028-10-23 01:00 | 2028-10-23 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Tentative | 2028.0
Oglethorpe Power Company | SMARR CC | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-20 | 28-20 - Oglethorpe Power Company - SMARR CC - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2028-04-17 01:00 |  | 0 |  |  | 2028-04-17 01:00 | 2028-06-15 01:00 |  | 2028-04-17 01:00 | 2028-04-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Tentative | 2028.0
TPC | Talin | - | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | Chinese | Chinese | NU | Gavin Yoong | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-19 | 28-19 - TPC - Talin - - - OTS Post-COD Refresh - CC Sim | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2030-04-15 01:00 |  | 0 |  |  | 2030-04-15 01:00 | 2030-05-10 01:00 |  | 2030-04-15 01:00 | 2030-04-15 01:00 |  |  | Created | 2025-11-05 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
TPC | Talin | - | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | Chinese | Chinese | NU | Gavin Yoong | Customer-Project Specific | Maintaining the Operator Training Simulator (OTS) For OTS Administrators | Simulator | 6 | 6 | 0 | 6 |  | 28-18 | 28-18 - TPC - Talin - - - Maintaining the Operator Training Simulator (OTS) For OTS Administrators | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Customer Site | Monday |  |  | 2028-10-27 01:00 |  | 0 | 2028-08-07 01:00 | 2028-08-14 01:00 | 2028-10-27 01:00 | 2028-11-03 01:00 |  | 2028-10-27 01:00 | 2028-10-27 01:00 |  | Yes | Created | 2025-11-05 | US Workweek and Holidays | Yegor Spencer | Tentative | 2028.0
TPC | Talin | - | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | Chinese | Chinese | NU | Gavin Yoong | Customer-Project Specific | OTS & Train the Trainer For Instructors & OTS Administrators | Simulator | 14 | 21 | 0 | 6 |  | 28-17 | 28-17 - TPC - Talin - - - OTS & Train the Trainer For Instructors & OTS Administrators | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Customer Site | Monday |  |  | 2028-10-09 01:00 |  | 0 | 2028-06-12 01:00 | 2028-07-10 01:00 | 2028-10-09 01:00 | 2028-10-26 01:00 |  | 2028-10-09 01:00 | 2028-10-09 01:00 |  | Yes | Created | 2025-11-05 | US Workweek and Holidays | Yegor Spencer | Tentative | 2028.0
TPC | Talin | - | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | Chinese | Chinese | NU | Gavin Yoong | Customer-Project Specific | Simulator Site Acceptance Test (SAT) | Simulator | 5 | 0 | 0 | 0 |  | 28-16 | 28-16 - TPC - Talin - - - Simulator Site Acceptance Test (SAT) | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Customer Site | Monday |  |  | 2028-10-02 01:00 |  | 0 |  |  | 2028-10-02 01:00 | 2028-10-06 01:00 |  | 2028-10-02 01:00 | 2028-10-02 01:00 |  | Yes | Created | 2025-11-05 | US Workweek and Holidays | Yegor Spencer | Tentative | 2028.0
TPC | Talin | - | EGM-00590-1CSTO-TRAINALL |  | EGM-00590-1CSTO-TRAINALL |  | Chinese | Chinese | NU | Gavin Yoong | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-15 | 28-15 - TPC - Talin - - - OTS Simulator Development & Testing - CC Sim | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2028-04-03 01:00 |  | 0 |  |  | 2028-04-03 01:00 | 2028-06-01 01:00 |  | 2028-04-03 01:00 | 2028-04-03 01:00 |  |  | Created | 2025-11-05 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Ameren | NGS | 3 |  |  |  |  | English | English | NU | Patrick Molumby | Customer-Project Specific | OTS 6-month Post-COD Tune up – GT Only Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-11 | 28-11 - Ameren - NGS - 3 - OTS 6-month Post-COD Tune up – GT Only Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2029-06-15 01:00 |  | 0 |  |  | 2029-06-15 01:00 | 2029-07-12 01:00 |  | 2029-06-15 01:00 | 2029-06-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Ameren | NGS | 3 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefGT | OTS Post-COD Refresh - GT Only Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-10 | 28-10 - Ameren - NGS - 3 - OTS Post-COD Refresh - GT Only Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2030-05-13 01:00 |  | 0 |  |  | 2030-05-13 01:00 | 2030-06-07 01:00 |  | 2030-05-13 01:00 | 2030-05-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Ameren | NGS | 3 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 1 | 6 |  | 28-9 | 28-9 - Ameren - NGS - 3 - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2028-09-06 01:00 |  | 0 |  |  | 2028-09-06 01:00 | 2028-09-14 01:00 |  | 2028-09-06 01:00 | 2028-09-06 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Tentative | 2028.0
Ameren | NGS | 3 |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevGT | OTS Simulator Development & Testing - GT Only Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-8 | 28-8 - Ameren - NGS - 3 - OTS Simulator Development & Testing - GT Only Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2028-06-05 01:00 |  | 0 |  |  | 2028-06-05 01:00 | 2028-08-03 01:00 |  | 2028-06-05 01:00 | 2028-06-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
RWE | Voerde | - |  |  |  |  | German | German | NU | Anna Petrella | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 28-4 | 28-4 - RWE - Voerde - - - OTS Post-COD Refresh - CC Sim | Remote | GERMANY | TAS-N | - | Distance Learning | Monday |  |  | 2030-02-18 |  | 0 |  |  | 2030-02-18 | 2030-03-15 01:00 |  | 2030-02-18 | 2030-02-18 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
RWE | Voerde | - |  |  |  |  | German | German | NU | Anna Petrella | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 28-3 | 28-3 - RWE - Voerde - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | GERMANY | TAS-N | - | Customer Site | Monday |  |  | 2029-05-11 01:00 |  | 0 |  |  | 2029-05-11 01:00 | 2029-05-21 01:00 |  | 2029-05-11 01:00 | 2029-05-11 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2028.0
RWE | Voerde | - |  |  |  |  | German | German | NU | Anna Petrella | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 28-2 | 28-2 - RWE - Voerde - - - OTS Simulator Development & Testing - CC Sim | Remote | GERMANY | TAS-N | - | Distance Learning | Monday |  |  | 2028-10-30 01:00 |  | 0 |  |  | 2028-10-30 01:00 | 2028-12-28 |  | 2028-10-30 01:00 | 2028-10-30 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2028.0
Invenergy | Foundry Ridge Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-134 | 27-134 - Invenergy - Foundry Ridge Energy Center - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Elkhorn | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-09-13 01:00 | 2027-10-15 01:00 | 2027-11-01 01:00 | 2027-11-12 |  | 2027-11-01 01:00 | 2027-11-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Invenergy | Foundry Ridge Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-133 | 27-133 - Invenergy - Foundry Ridge Energy Center - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Elkhorn | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-08-30 01:00 | 2027-09-03 01:00 | 2027-10-25 01:00 | 2027-10-29 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Khaled Al Behiri | Tentative | 2027.0
Invenergy | Foundry Ridge Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-132 | 27-132 - Invenergy - Foundry Ridge Energy Center - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Elkhorn | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-08-02 01:00 | 2027-08-06 01:00 | 2027-10-18 01:00 | 2027-10-22 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Tentative | 2027.0
Invenergy | Foundry Ridge Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-131 | 27-131 - Invenergy - Foundry Ridge Energy Center - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Elkhorn | Customer Site | Monday |  |  | 2027-06-30 01:00 |  | 0 | 2027-06-28 01:00 | 2027-07-09 01:00 | 2027-10-04 01:00 | 2027-10-15 01:00 |  | 2027-10-04 01:00 | 2027-10-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 5 | 0 | 12 | 2 | 27-130 | 27-130 - Duke Energy - Person County - Phase 1 - GT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-05-15 01:00 | 2028-05-19 01:00 | 2028-07-10 01:00 | 2028-07-21 01:00 |  | 2028-07-10 01:00 | 2028-07-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 5 | 0 | 12 | 2 | 27-129 | 27-129 - Duke Energy - Person County - Phase 1 - GT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-02-07 | 2028-02-11 | 2028-06-26 01:00 | 2028-07-07 01:00 |  | 2028-06-26 01:00 | 2028-06-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 2 | 0 | 12 | 2 | 27-128 | 27-128 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-04-06 01:00 | 2028-04-07 01:00 | 2028-06-19 01:00 | 2028-06-23 01:00 |  | 2028-06-19 01:00 | 2028-06-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 3 | 0 | 12 | 2 | 27-127 | 27-127 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-04-03 01:00 | 2028-04-05 01:00 | 2028-06-05 01:00 | 2028-06-16 01:00 |  | 2028-06-05 01:00 | 2028-06-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 2 | 0 | 12 | 2 | 27-126 | 27-126 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-03-30 01:00 | 2028-03-31 01:00 | 2028-05-29 01:00 | 2028-06-02 01:00 |  | 2028-05-29 01:00 | 2028-05-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 3 | 0 | 12 | 2 | 27-125 | 27-125 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-03-27 01:00 | 2028-03-29 01:00 | 2028-05-15 01:00 | 2028-05-26 01:00 |  | 2028-05-15 01:00 | 2028-05-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 1 | 27-124 | 27-124 - Duke Energy - Person County - Phase 1 - GT - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-01-31 | 2028-02-11 | 2028-04-03 01:00 | 2028-04-14 01:00 |  | 2028-04-03 01:00 | 2028-04-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 1 | 27-123 | 27-123 - Duke Energy - Person County - Phase 1 - GT - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-01-24 | 2028-02-04 | 2028-03-20 01:00 | 2028-03-31 01:00 |  | 2028-03-20 01:00 | 2028-03-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 27-122 | 27-122 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-12-27 | 2027-12-31 | 2028-03-13 01:00 | 2028-03-17 01:00 |  | 2028-03-13 01:00 | 2028-03-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 12 | 1 | 27-121 | 27-121 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-12-06 | 2027-12-17 | 2028-02-28 | 2028-03-10 |  | 2028-02-28 | 2028-02-28 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-120 | 27-120 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-01-17 | 2028-01-21 | 2028-02-21 | 2028-02-25 |  | 2028-02-21 | 2028-02-21 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-119 | 27-119 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2028-01-03 | 2028-01-14 | 2028-02-07 | 2028-02-18 |  | 2028-02-07 | 2028-02-07 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 | 2 | 27-118 | 27-118 - Duke Energy - Person County - Phase 1 - GT - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-04-19 01:00 | 2027-04-23 01:00 | 2027-05-31 01:00 | 2027-06-11 01:00 |  | 2027-05-31 01:00 | 2027-05-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 3 | 0 | 12 | 2 | 27-117 | 27-117 - Duke Energy - Person County - Phase 1 - GT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-03-22 01:00 | 2027-03-24 01:00 | 2027-05-24 01:00 | 2027-05-28 01:00 |  | 2027-05-24 01:00 | 2027-05-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 3 | 0 | 12 | 2 | 27-116 | 27-116 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-04-01 01:00 | 2027-04-05 01:00 | 2027-05-17 01:00 | 2027-05-21 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Raghunath Yeturi | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 5 | 0 | 12 | 2 | 27-115 | 27-115 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-02-11 | 2027-03-31 01:00 | 2027-05-03 01:00 | 2027-05-14 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Raghunath Yeturi | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 | 2 | 27-114 | 27-114 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-03-15 01:00 | 2027-03-17 01:00 | 2027-04-26 01:00 | 2027-04-30 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 2 | 27-113 | 27-113 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-09-01 01:00 |  | 0 | 2027-02-08 | 2027-02-12 | 2027-04-12 01:00 | 2027-04-23 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-112 | 27-112 - Duke Energy - Person County - Phase 1 - GT - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2026-11-23 | 2026-12-22 | 2027-01-11 | 2027-01-22 |  | 2027-01-11 | 2027-01-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 27-111 | 27-111 - Duke Energy - Person County - Phase 1 - GT - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2026-11-09 | 2026-11-13 | 2027-01-04 | 2027-01-08 |  | 2027-01-04 | 2027-01-04 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 27-110 | 27-110 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2026-09-21 01:00 | 2026-09-25 01:00 | 2026-12-14 | 2026-12-18 |  | 2026-12-14 | 2026-12-14 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - ST | EGM-00506-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 | 1 | 27-109 | 27-109 - Duke Energy - Person County - Phase 1 - ST - Steam Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2026-09-08 01:00 | 2026-09-18 01:00 | 2026-11-30 | 2026-12-11 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-108 | 27-108 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2026-09-01 01:00 | 2026-09-04 01:00 | 2026-11-09 | 2026-11-13 |  | 2026-11-09 | 2026-11-09 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
Duke Energy | Person County | Phase 1 - GT | EGM-00481-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-107 | 27-107 - Duke Energy - Person County - Phase 1 - GT - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Person County | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2026-08-19 01:00 | 2026-08-31 01:00 | 2026-10-26 01:00 | 2026-11-06 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
TVA | Kingston | AERO | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-106 | 27-106 - TVA - Kingston - AERO - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2026-12-07 | 2026-12-11 | 2027-02-01 | 2027-02-05 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
TVA | Kingston | AERO | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-105 | 27-105 - TVA - Kingston - AERO - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2026-11-30 | 2026-12-04 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
TVA | Kingston | AERO | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-104 | 27-104 - TVA - Kingston - AERO - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2026-11-04 | 2026-11-24 | 2027-01-19 | 2027-01-22 |  | 2027-01-19 | 2027-01-19 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
TVA | Kingston | AERO | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-103 | 27-103 - TVA - Kingston - AERO - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2026-10-19 01:00 | 2026-10-22 01:00 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
WE Energies | WE Energies | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-102 | 27-102 - WE Energies - WE Energies - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Milwaukee | Customer Site | Monday |  |  | 2027-04-01 01:00 |  | 0 | 2027-04-05 01:00 | 2027-04-16 01:00 | 2027-05-17 01:00 | 2027-05-28 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
WE Energies | WE Energies | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 27-101 | 27-101 - WE Energies - WE Energies - - - Electrical - Electrical Control System (ECS) Training | Customer Site | UNITED STATES | TAS-N | Milwaukee | Customer Site | Monday |  |  | 2027-04-01 01:00 |  | 0 |  |  | 2027-05-10 01:00 | 2027-05-12 01:00 |  | 2027-05-10 01:00 | 2027-05-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Tentative | 2027.0
WE Energies | WE Energies | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-100 | 27-100 - WE Energies - WE Energies - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Milwaukee | Customer Site | Monday |  |  | 2027-04-01 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-05-03 01:00 | 2027-05-07 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
WE Energies | WE Energies | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-99 | 27-99 - WE Energies - WE Energies - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Milwaukee | Customer Site | Monday |  |  | 2027-04-01 01:00 |  | 0 | 2027-02-16 | 2027-02-19 | 2027-04-26 01:00 | 2027-04-30 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
WE Energies | WE Energies | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-98 | 27-98 - WE Energies - WE Energies - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Milwaukee | Customer Site | Monday |  |  | 2027-04-01 01:00 |  | 0 | 2027-02-01 | 2027-02-12 | 2027-04-12 01:00 | 2027-04-23 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 | 3 | 27-97 | 27-97 - Dominion Urquhart - Dominion Urquhart - - - Control System - Mark VIe Maintenance (Extended) - G3 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-06-07 01:00 | 2027-06-11 01:00 | 2027-09-27 01:00 | 2027-10-08 01:00 |  | 2027-09-27 01:00 | 2027-09-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 3 | 27-96 | 27-96 - Dominion Urquhart - Dominion Urquhart - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G3 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-20 01:00 | 2027-05-21 01:00 | 2027-09-20 01:00 | 2027-09-24 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 3 | 27-95 | 27-95 - Dominion Urquhart - Dominion Urquhart - - - Gas Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-06-28 01:00 | 2027-06-30 01:00 | 2027-09-13 01:00 | 2027-09-17 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 3 | 27-94 | 27-94 - Dominion Urquhart - Dominion Urquhart - - - Gas Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-31 01:00 | 2027-06-04 01:00 | 2027-08-30 01:00 | 2027-09-10 01:00 |  | 2027-08-30 01:00 | 2027-08-30 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 | 2 | 27-93 | 27-93 - Dominion Urquhart - Dominion Urquhart - - - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-31 01:00 | 2027-06-04 01:00 | 2027-08-16 01:00 | 2027-08-27 01:00 |  | 2027-08-16 01:00 | 2027-08-16 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 2 | 27-92 | 27-92 - Dominion Urquhart - Dominion Urquhart - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-17 01:00 | 2027-05-19 01:00 | 2027-08-09 01:00 | 2027-08-13 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 2 | 27-91 | 27-91 - Dominion Urquhart - Dominion Urquhart - - - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-24 01:00 | 2027-05-26 01:00 | 2027-08-02 01:00 | 2027-08-06 01:00 |  | 2027-08-02 01:00 | 2027-08-02 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 27-90 | 27-90 - Dominion Urquhart - Dominion Urquhart - - - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-17 01:00 | 2027-05-21 01:00 | 2027-07-19 01:00 | 2027-07-30 01:00 |  | 2027-07-19 01:00 | 2027-07-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 27-89 | 27-89 - Dominion Urquhart - Dominion Urquhart - - - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-04-19 01:00 | 2027-04-30 01:00 | 2027-07-05 01:00 | 2027-07-16 01:00 |  | 2027-07-05 01:00 | 2027-07-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 27-88 | 27-88 - Dominion Urquhart - Dominion Urquhart - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-10 01:00 | 2027-05-14 01:00 | 2027-06-28 01:00 | 2027-07-02 01:00 |  | 2027-06-28 01:00 | 2027-06-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-87 | 27-87 - Dominion Urquhart - Dominion Urquhart - - - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-10 01:00 | 2027-05-14 01:00 | 2027-06-21 01:00 | 2027-06-25 01:00 |  | 2027-06-21 01:00 | 2027-06-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
Dominion Urquhart | Dominion Urquhart | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-86 | 27-86 - Dominion Urquhart - Dominion Urquhart - - - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Aiken | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-04-26 01:00 | 2027-05-07 01:00 | 2027-06-07 01:00 | 2027-06-18 01:00 |  | 2027-06-07 01:00 | 2027-06-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 2 | 27-85 | 27-85 - NVE Valmy - NVE Valmy - - - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-08-23 01:00 | 2027-09-17 01:00 | 2027-11-08 | 2027-11-19 |  | 2027-11-08 | 2027-11-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 2 | 27-84 | 27-84 - NVE Valmy - NVE Valmy - - - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-09-20 01:00 | 2027-10-01 01:00 | 2027-10-25 01:00 | 2027-11-05 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-83 | 27-83 - NVE Valmy - NVE Valmy - - - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-08-16 01:00 | 2027-08-20 01:00 | 2027-10-18 01:00 | 2027-10-22 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-82 | 27-82 - NVE Valmy - NVE Valmy - - - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-07-12 01:00 | 2027-07-23 01:00 | 2027-10-04 01:00 | 2027-10-15 01:00 |  | 2027-10-04 01:00 | 2027-10-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-81 | 27-81 - NVE Valmy - NVE Valmy - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-07-26 01:00 | 2027-08-06 01:00 | 2027-09-20 01:00 | 2027-10-01 01:00 |  | 2027-09-20 01:00 | 2027-09-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-80 | 27-80 - NVE Valmy - NVE Valmy - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-07-19 01:00 | 2027-07-23 01:00 | 2027-09-13 01:00 | 2027-09-17 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-79 | 27-79 - NVE Valmy - NVE Valmy - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-07-05 01:00 | 2027-07-09 01:00 | 2027-09-07 01:00 | 2027-09-10 01:00 |  | 2027-09-06 01:00 | 2027-09-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 2 | 0 | 12 | 4 | 27-78 | 27-78 - NVE Valmy - NVE Valmy - - - Gas Turbine - Operation - G4 | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-20 01:00 | 2027-05-21 01:00 | 2027-08-23 01:00 | 2027-09-03 01:00 |  | 2027-08-23 01:00 | 2027-08-23 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 4 | 0 | 12 | 3 | 27-77 | 27-77 - NVE Valmy - NVE Valmy - - - Gas Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-06-14 01:00 | 2027-06-17 01:00 | 2027-08-09 01:00 | 2027-08-20 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 3 | 0 | 12 | 2 | 27-76 | 27-76 - NVE Valmy - NVE Valmy - - - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-05-17 01:00 | 2027-05-19 01:00 | 2027-07-26 01:00 | 2027-08-06 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2027.0
NVE Valmy | NVE Valmy | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-75 | 27-75 - NVE Valmy - NVE Valmy - - - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Valmy | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-04-19 01:00 | 2027-04-30 01:00 | 2027-07-12 01:00 | 2027-07-23 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-74 | 27-74 - NRG - Greens Bayou - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2027-10-01 01:00 |  | 0 | 2027-09-06 01:00 | 2027-09-17 01:00 | 2027-11-01 01:00 | 2027-11-15 |  | 2027-11-01 01:00 | 2027-11-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Tentative | 2027.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-73 | 27-73 - NRG - Greens Bayou - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2027-10-01 01:00 |  | 0 | 2027-08-30 01:00 | 2027-09-03 01:00 | 2027-10-25 01:00 | 2027-10-29 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-72 | 27-72 - NRG - Greens Bayou - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2027-10-01 01:00 |  | 0 | 2027-08-23 01:00 | 2027-08-27 01:00 | 2027-10-18 01:00 | 2027-10-22 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
NRG | Greens Bayou | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-71 | 27-71 - NRG - Greens Bayou - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Houston | Customer Site | Monday |  |  | 2027-10-01 01:00 |  | 0 | 2027-07-05 01:00 | 2027-07-30 01:00 | 2027-10-04 01:00 | 2027-10-15 01:00 |  | 2027-10-04 01:00 | 2027-10-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-AER31301 | Gas Turbine - Aero Package Operation & Maintenance (OJT) | Aeroderivative | 10 | 10 | 0 | 12 |  | 27-70 | 27-70 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - Aero Package Operation & Maintenance (OJT) | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2028-01-03 |  | 0 |  |  | 2028-04-10 01:00 | 2028-04-21 01:00 |  | 2028-04-10 01:00 | 2028-04-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays |  | Resourcing In Progress | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 27-69 | 27-69 - NIPSCO - NIPSCO Schahfer - - - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2028-01-03 |  | 0 |  |  | 2028-03-27 01:00 | 2028-04-07 01:00 |  | 2028-03-27 01:00 | 2028-03-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays |  | Resourcing In Progress | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-68 | 27-68 - NIPSCO - NIPSCO Schahfer - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-12-06 | 2027-12-10 | 2028-02-07 | 2028-02-11 |  | 2028-02-07 | 2028-02-07 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-67 | 27-67 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-12-13 | 2027-12-17 | 2028-01-31 | 2028-02-04 |  | 2028-01-31 | 2028-01-31 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-66 | 27-66 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-07-01 01:00 |  | 0 | 2027-11-15 | 2027-11-19 | 2028-01-24 | 2028-01-28 |  | 2028-01-24 | 2028-01-24 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Lincoln Electric Terry Bundy Plant | Lincoln Electric Terry Bundy Plant | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-65 | 27-65 - Lincoln Electric Terry Bundy Plant - Lincoln Electric Terry Bundy Plant - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Lincoln | Customer Site | Monday |  |  | 2027-10-25 01:00 |  | 0 | 2027-10-04 01:00 | 2027-10-08 01:00 | 2027-10-25 01:00 | 2027-10-29 01:00 |  | 2027-10-25 01:00 | 2027-10-25 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Lincoln Electric Terry Bundy Plant | Lincoln Electric Terry Bundy Plant | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-64 | 27-64 - Lincoln Electric Terry Bundy Plant - Lincoln Electric Terry Bundy Plant - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Lincoln | Customer Site | Monday |  |  | 2027-10-18 01:00 |  | 0 | 2027-09-20 01:00 | 2027-09-24 01:00 | 2027-10-18 01:00 | 2027-10-22 01:00 |  | 2027-10-18 01:00 | 2027-10-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Lincoln Electric Terry Bundy Plant | Lincoln Electric Terry Bundy Plant | - |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-63 | 27-63 - Lincoln Electric Terry Bundy Plant - Lincoln Electric Terry Bundy Plant - - - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Lincoln | Customer Site | Monday |  |  | 2027-10-11 01:00 |  | 0 | 2027-08-30 01:00 | 2027-09-03 01:00 | 2027-10-11 01:00 | 2027-10-15 01:00 |  | 2027-10-11 01:00 | 2027-10-11 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Lincoln Electric Terry Bundy Plant | Lincoln Electric Terry Bundy Plant | - |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-62 | 27-62 - Lincoln Electric Terry Bundy Plant - Lincoln Electric Terry Bundy Plant - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Lincoln | Customer Site | Monday |  |  | 2027-10-04 01:00 |  | 0 | 2027-08-23 01:00 | 2027-08-27 01:00 | 2027-10-04 01:00 | 2027-10-08 01:00 |  | 2027-10-04 01:00 | 2027-10-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
Cheyenne Prairie Generation Station | Cheyenne Prairie Generation Station | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-61 | 27-61 - Cheyenne Prairie Generation Station - Cheyenne Prairie Generation Station - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Wyoming | Customer Site | Monday |  |  | 2027-04-19 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-19 01:00 | 2027-04-23 01:00 |  | 2027-04-19 01:00 | 2027-04-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Cheyenne Prairie Generation Station | Cheyenne Prairie Generation Station | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 27-60 | 27-60 - Cheyenne Prairie Generation Station - Cheyenne Prairie Generation Station - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Wyoming | Customer Site | Monday |  |  | 2027-04-12 01:00 |  | 0 | 2027-02-22 | 2027-02-26 | 2027-04-12 01:00 | 2027-04-16 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2027.0
Cheyenne Prairie Generation Station | Cheyenne Prairie Generation Station | - |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 27-59 | 27-59 - Cheyenne Prairie Generation Station - Cheyenne Prairie Generation Station - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Wyoming | Customer Site | Monday |  |  | 2027-04-05 01:00 |  | 0 | 2027-03-08 | 2027-03-12 | 2027-04-05 01:00 | 2027-04-09 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 5 | 0 | 12 | 2 | 27-58 | 27-58 - TVA - New Caledonia - - - Control System - Mark VIe Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-09-13 01:00 |  | 0 | 2027-07-26 01:00 | 2027-07-28 01:00 | 2027-09-13 01:00 | 2027-09-17 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Cancelled | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 2 | 27-57 | 27-57 - TVA - New Caledonia - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-09-06 01:00 |  | 0 | 2027-07-26 01:00 | 2027-07-28 01:00 | 2027-09-13 01:00 | 2027-09-17 01:00 |  | 2027-09-13 01:00 | 2027-09-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 3 | 0 | 12 | 2 | 27-56 | 27-56 - TVA - New Caledonia - - - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-08-30 01:00 |  | 0 | 2027-07-07 01:00 | 2027-07-09 01:00 | 2027-09-06 01:00 | 2027-09-10 01:00 |  | 2027-09-06 01:00 | 2027-09-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 5 | 0 | 12 | 2 | 27-55 | 27-55 - TVA - New Caledonia - - - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-08-16 01:00 |  | 0 | 2027-06-29 01:00 | 2027-07-06 01:00 | 2027-08-23 01:00 | 2027-09-03 01:00 |  | 2027-08-23 01:00 | 2027-08-23 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 5 | 0 | 12 | 1 | 27-54 | 27-54 - TVA - New Caledonia - - - Control System - Mark VIe Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-08-09 01:00 |  | 0 | 2027-05-24 01:00 | 2027-05-28 01:00 | 2027-08-09 01:00 | 2027-08-13 01:00 |  | 2027-08-09 01:00 | 2027-08-09 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Cancelled | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 27-53 | 27-53 - TVA - New Caledonia - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-08-02 01:00 |  | 0 | 2027-05-17 01:00 | 2027-05-21 01:00 | 2027-08-02 01:00 | 2027-08-06 01:00 |  | 2027-08-02 01:00 | 2027-08-02 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 1 | 27-52 | 27-52 - TVA - New Caledonia - - - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-07-26 01:00 |  | 0 | 2027-06-01 01:00 | 2027-06-04 01:00 | 2027-07-26 01:00 | 2027-07-30 01:00 |  | 2027-07-26 01:00 | 2027-07-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
TVA | New Caledonia | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 1 | 27-51 | 27-51 - TVA - New Caledonia - - - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Caledonia | Customer Site | Monday |  |  | 2027-07-12 01:00 |  | 0 | 2027-05-10 01:00 | 2027-05-21 01:00 | 2027-07-12 01:00 | 2027-07-23 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 | 2 | 27-50 | 27-50 - NIPSCO - NIPSCO Schahfer - - - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-05-17 01:00 |  | 0 | 2028-03-27 01:00 | 2028-04-07 01:00 | 2028-05-29 01:00 | 2028-06-09 01:00 |  | 2028-05-29 01:00 | 2028-05-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 | 2 | 27-49 | 27-49 - NIPSCO - NIPSCO Schahfer - - - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-05-03 01:00 |  | 0 | 2028-02-21 | 2028-03-03 | 2028-05-15 01:00 | 2028-05-26 01:00 |  | 2028-05-15 01:00 | 2028-05-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-48 | 27-48 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-04-26 01:00 |  | 0 | 2028-02-28 | 2028-03-03 | 2028-05-08 01:00 | 2028-05-12 01:00 |  | 2028-05-08 01:00 | 2028-05-08 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-47 | 27-47 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-04-12 01:00 |  | 0 | 2028-02-14 | 2028-02-25 | 2028-04-24 01:00 | 2028-05-05 01:00 |  | 2028-04-24 01:00 | 2028-04-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-46 | 27-46 - NIPSCO - NIPSCO Schahfer - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-03-29 01:00 |  | 0 | 2028-01-17 | 2028-01-28 | 2028-03-13 01:00 | 2028-03-24 01:00 |  | 2028-03-13 01:00 | 2028-03-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-45 | 27-45 - NIPSCO - NIPSCO Schahfer - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-03-22 01:00 |  | 0 | 2027-12-20 | 2027-12-27 | 2028-03-06 | 2028-03-10 |  | 2028-03-06 | 2028-03-06 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-44 | 27-44 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-03-15 01:00 |  | 0 | 2028-01-03 | 2028-01-07 | 2028-02-28 | 2028-03-03 |  | 2028-02-28 | 2028-02-28 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Tentative | 2027.0
NIPSCO | NIPSCO Schahfer | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-43 | 27-43 - NIPSCO - NIPSCO Schahfer - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Wheatfield | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2027-12-06 | 2027-12-17 | 2028-02-14 | 2028-02-25 |  | 2028-02-14 | 2028-02-14 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Tentative | 2027.0
Xcel | Xcel Energy Fort St Vrain | - | EGM-00480-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-42 | 27-42 - Xcel - Xcel Energy Fort St Vrain - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Fort St Vrain | Customer Site | Monday |  |  | 2027-04-05 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-05 01:00 | 2027-04-09 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2027.0
Xcel | Xcel Energy Fort St Vrain | - | EGM-00480-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-41 | 27-41 - Xcel - Xcel Energy Fort St Vrain - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Fort St Vrain | Customer Site | Monday |  |  | 2027-03-22 01:00 |  | 0 | 2027-01-25 | 2027-02-12 | 2027-03-22 01:00 | 2027-04-02 01:00 |  | 2027-03-22 01:00 | 2027-03-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Tentative | 2027.0
Xcel | Xcel Energy Fort St Vrain | - | EGM-00480-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-40 | 27-40 - Xcel - Xcel Energy Fort St Vrain - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Fort St Vrain | Customer Site | Monday |  |  | 2027-03-15 01:00 |  | 0 | 2027-01-04 | 2027-01-08 | 2027-03-15 01:00 | 2027-03-19 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
Xcel | Xcel Energy Fort St Vrain | - | EGM-00480-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-39 | 27-39 - Xcel - Xcel Energy Fort St Vrain - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Fort St Vrain | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2027-02-01 | 2027-02-05 | 2027-03-01 | 2027-03-12 |  | 2027-03-01 | 2027-03-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-34 | 27-34 - CBEC - Castle Bluff Energy Center - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-03-15 01:00 |  | 0 | 2027-04-19 01:00 | 2027-04-21 01:00 | 2027-06-01 01:00 | 2027-06-04 01:00 |  | 2027-06-01 01:00 | 2027-06-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-33 | 27-33 - CBEC - Castle Bluff Energy Center - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-03-08 |  | 0 | 2027-03-29 01:00 | 2027-04-02 01:00 | 2027-05-24 01:00 | 2027-05-28 01:00 |  | 2027-05-24 01:00 | 2027-05-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 27-32 | 27-32 - CBEC - Castle Bluff Energy Center - - - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2027-03-15 01:00 | 2027-03-17 01:00 | 2027-05-17 01:00 | 2027-05-21 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 27-31 | 27-31 - CBEC - Castle Bluff Energy Center - - - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-02-22 |  | 0 | 2027-03-08 | 2027-03-12 | 2027-05-10 01:00 | 2027-05-14 01:00 |  | 2027-05-10 01:00 | 2027-05-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-30 | 27-30 - CBEC - Castle Bluff Energy Center - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-02-15 |  | 0 | 2027-03-08 | 2027-03-12 | 2027-04-26 01:00 | 2027-05-07 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Nasreddine Laroussi | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-29 | 27-29 - CBEC - Castle Bluff Energy Center - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-02-01 |  | 0 | 2027-02-22 | 2027-03-05 | 2027-04-12 01:00 | 2027-04-23 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Nasreddine Laroussi | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-28 | 27-28 - CBEC - Castle Bluff Energy Center - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-01-25 |  | 0 | 2027-02-22 | 2027-02-24 | 2027-04-05 01:00 | 2027-04-09 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-27 | 27-27 - CBEC - Castle Bluff Energy Center - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-01-18 |  | 0 | 2027-01-25 | 2027-01-29 | 2027-03-29 01:00 | 2027-04-02 01:00 |  | 2027-03-29 01:00 | 2027-03-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2027.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-26 | 27-26 - CBEC - Castle Bluff Energy Center - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2027-01-07 | 2027-01-13 | 2027-03-15 01:00 | 2027-03-26 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2027.0
AEP | AEP Hallsville | - |  |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 27-25 | 27-25 - AEP - AEP Hallsville - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Hallsville | Customer Site | Monday |  |  | 2027-05-03 01:00 |  | 0 | 2027-02-16 | 2027-02-19 | 2027-04-26 01:00 | 2027-04-30 01:00 |  |  | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2027.0
AEP | AEP Hallsville | - |  |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 27-24 | 27-24 - AEP - AEP Hallsville - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Hallsville | Customer Site | Monday |  |  | 2027-04-26 01:00 |  | 0 | 2027-02-16 | 2027-02-26 | 2027-05-03 01:00 | 2027-05-14 01:00 |  | 2027-04-26 01:00 | 2027-05-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2027.0
AEP | AEP Hallsville | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 27-23 | 27-23 - AEP - AEP Hallsville - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Hallsville | Customer Site | Monday |  |  | 2027-04-19 01:00 |  | 0 | 2027-02-22 | 2027-02-26 | 2027-04-19 01:00 | 2027-04-23 01:00 |  | 2027-04-19 01:00 | 2027-04-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2027.0
AEP | AEP Hallsville | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 27-22 | 27-22 - AEP - AEP Hallsville - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Hallsville | Customer Site | Monday |  |  | 2027-04-05 01:00 |  | 0 | 2027-02-08 | 2027-02-19 | 2027-04-05 01:00 | 2027-04-16 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2027.0
Sefine Shipyard | FACM | - |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 27-21 | 27-21 - Sefine Shipyard - FACM - - - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | KUWAIT | TAS-N | KUWAIT | Kuwait Learning Center | Sunday |  |  | 2027-04-19 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-19 01:00 | 2027-04-23 01:00 |  | 2027-04-19 01:00 | 2027-04-19 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Elias Benedi | Tentative | 2027.0
Ameren | Castle Bluff | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefGT | OTS Post-COD Refresh - GT Only Sim | Simulator | 20 | 0 | 0 | 0 |  | 27-9 | 27-9 - Ameren - Castle Bluff - - - OTS Post-COD Refresh - GT Only Sim | Remote | UNITED STATES | TAS-N | St. Louis | Distance Learning | Monday |  |  | 2028-03-06 |  | 0 |  |  | 2028-03-06 | 2028-03-31 01:00 |  | 2028-03-06 | 2028-03-06 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2027.0
Ameren | Castle Bluff | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefGT | OTS Post-COD Refresh - GT Only Sim | Simulator | 20 | 0 | 0 | 0 |  | 27-4 | 27-4 - Ameren - Castle Bluff - - - OTS Post-COD Refresh - GT Only Sim | Remote | UNITED STATES | TAS-N | St. Louis | Distance Learning | Monday |  |  | 2028-01-24 |  | 0 |  |  | 2028-01-24 | 2028-02-18 |  | 2028-01-24 | 2028-01-24 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2027.0
Ameren | Castle Bluff | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 0 | 6 |  | 27-3 | 27-3 - Ameren - Castle Bluff - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | St. Louis | Customer Site | Monday |  |  | 2027-05-17 01:00 |  | 0 |  |  | 2027-05-17 01:00 | 2027-05-25 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Tentative | 2027.0
Ameren | Castle Bluff | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefGT | OTS Post-COD Refresh - GT Only Sim | Simulator | 20 | 0 | 0 | 0 |  | 27-2 | 27-2 - Ameren - Castle Bluff - - - OTS Post-COD Refresh - GT Only Sim | Remote | UNITED STATES | TAS-N | St. Louis | Distance Learning | Monday |  |  | 2027-03-08 |  | 0 |  |  | 2027-03-08 | 2027-04-09 01:00 |  | 2027-03-08 | 2027-03-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2027.0
NYPA | NYPA Brentwood | - |  |  |  |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-270 | 26-270 - NYPA - NYPA Brentwood - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Long Island | Customer Site | Monday |  |  | 2026-03-16 01:00 |  | 0 | 2026-02-17 | 2026-02-19 | 2026-03-16 01:00 | 2026-03-20 01:00 |  | 2026-03-16 01:00 | 2026-03-16 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Cancelled | 2026.0
Rauma Marine Constructions (RMC) | The Finnish Defense Forces Rober Liner SQ2020 | - |  |  |  |  | English | English | IB | Anna Petrella | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 0 | 0 | 8 |  | 26-269 | 26-269 - Rauma Marine Constructions (RMC) - The Finnish Defense Forces Rober Liner SQ2020 - - - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-02-09 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2026.0
Rauma Marine Constructions (RMC) | The Finnish Defense Forces Rober Liner SQ2020 | - |  |  |  |  | English | English | IB | Anna Petrella | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 5 | 0 | 0 | 8 |  | 26-268 | 26-268 - Rauma Marine Constructions (RMC) - The Finnish Defense Forces Rober Liner SQ2020 - - - Gas Turbine - LM2500 Borescope Inspection | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-02-09 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2026.0
Rauma Marine Constructions (RMC) | The Finnish Defense Forces Rober Liner SQ2020 | - |  |  |  |  | English | English | IB | Anna Petrella | E-AER10101 | Gas Turbine - LM2500 Aero Package Operation/Familiarization | Aeroderivative | 5 | 0 | 0 | 12 |  | 26-267 | 26-267 - Rauma Marine Constructions (RMC) - The Finnish Defense Forces Rober Liner SQ2020 - - - Gas Turbine - LM2500 Aero Package Operation/Familiarization | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2026-02-09 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  |  | English | English | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 11 | 10 | 0 | 12 | 4 | 26-266 | 26-266 - TPC - Datan - 8&9 Local Training - Steam Turbine - Operation - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-06-17 01:00 |  | 0 | 2026-07-06 01:00 | 2026-07-17 01:00 | 2026-10-26 01:00 | 2026-11-09 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Cancelled | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | EGM-00084-1CSTO-TRAINALL | Mandarin Chinese | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 4 | 26-265 | 26-265 - TPC - Datan - 8&9 Local Training - Gas Turbine - Operation - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-08-03 01:00 |  | 0 | 2026-02-09 | 2026-06-05 01:00 | 2026-10-26 01:00 | 2026-11-06 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-05 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | English | English | NU | Gavin Yoong | E-CCP10204 | Combined Cycle - Fundamentals | Combined Cycle | 10 | 5 | 0 | 12 | 4 | 26-264 | 26-264 - TPC - Datan - 8&9 Local Training - Combined Cycle - Fundamentals - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2026-03-19 01:00 | 2026-03-25 01:00 | 2026-06-01 01:00 | 2026-06-12 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | English | English | NU | Gavin Yoong | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 12 | 10 | 0 | 12 | 4 | 26-263 | 26-263 - TPC - Datan - 8&9 Local Training - Steam Turbine - Operation - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-06-01 01:00 |  | 0 | 2026-03-09 01:00 | 2026-03-20 01:00 | 2026-05-11 01:00 | 2026-05-26 01:00 |  | 2026-05-11 01:00 | 2026-05-11 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | English | English | NU | Gavin Yoong | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 | 4 | 26-262 | 26-262 - TPC - Datan - 8&9 Local Training - Control System - Mark VIe Distributed Control System Maintenance - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-05-04 01:00 |  | 0 | 2026-03-10 01:00 | 2026-03-13 01:00 | 2026-05-04 01:00 | 2026-05-08 01:00 |  | 2026-05-04 01:00 | 2026-05-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | I01-109845 / PO 4102695663 | Mandarin Chinese | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 4 | 26-261 | 26-261 - TPC - Datan - 8&9 Local Training - Control System - Mark VIe Maintenance (Extended) - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-04-20 01:00 |  | 0 | 2026-01-20 | 2026-09-23 01:00 | 2026-10-12 01:00 | 2026-10-23 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-06 | US Workweek and Holidays | Margaret Baluyut | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | English | English | NU | Gavin Yoong | Customer-Project Specific | Auxiliary Mechanical Systems | General | 2 | 2 | 0 | 12 | 4 | 26-260 | 26-260 - TPC - Datan - 8&9 Local Training - Auxiliary Mechanical Systems - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-03-31 01:00 |  | 0 | 2026-01-20 | 2026-01-21 | 2026-04-07 01:00 | 2026-04-08 01:00 |  | 2026-04-07 01:00 | 2026-04-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  |  | I01-109845 / PO 4102695663 | English | English | NU | Gavin Yoong | Customer-Project Specific | Selective Catalytic Reduction (SCR) | General | 1 | 1 | 0 | 12 | 4 | 26-259 | 26-259 - TPC - Datan - 8&9 Local Training - Selective Catalytic Reduction (SCR) - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-03-30 01:00 |  | 0 | 2026-02-25 | 2026-02-25 | 2026-04-01 01:00 | 2026-04-01 01:00 |  | 2026-04-01 01:00 | 2026-04-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | I01-109845 / PO 4102695663 | Mandarin Chinese | English | NU | Gavin Yoong | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 7 | 5 | 2 | 12 | 4 | 26-258 | 26-258 - TPC - Datan - 8&9 Local Training - Gas Turbine - Operation H-Class (Advanced) - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-03-16 01:00 |  | 0 | 2026-03-02 | 2026-03-06 | 2026-08-03 01:00 | 2026-08-11 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 |  |  | Created | 2025-11-06 | US Workweek and Holidays | Tom Walsh | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | EGM-00084-1CSTO-TRAINALL | Mandarin Chinese | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 7 | 5 | 0 | 12 | 4 | 26-257 | 26-257 - TPC - Datan - 8&9 Local Training - Excitation - Generator Excitation, Protection and Static Starter Introduction - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-03-02 |  | 0 | 2026-04-27 01:00 | 2026-05-01 01:00 | 2026-09-14 01:00 | 2026-09-22 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2025-11-05 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | EGM-00084-1CSTO-TRAINALL | Mandarin Chinese | English | NU | Gavin Yoong | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 8 | 0 | 12 | 4 | 26-256 | 26-256 - TPC - Datan - 8&9 Local Training - Control System - Mark VIe Maintenance - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-02-09 |  | 0 | 2026-01-12 | 2026-07-10 01:00 | 2026-08-31 01:00 | 2026-09-04 01:00 |  | 2026-08-31 01:00 | 2026-08-31 01:00 |  |  | Created | 2025-11-05 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2026.0
TPC | Datan | 8&9 Local Training | EGM-00085-1CSTO-TRAINALL |  | EGM-00084-1CSTO-TRAINALL | EGM-00084-1CSTO-TRAINALL | Mandarin Chinese | English | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 0 | 12 | 4 | 26-255 | 26-255 - TPC - Datan - 8&9 Local Training - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G4 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-02-02 |  | 0 | 2026-06-25 01:00 | 2026-06-29 01:00 | 2026-08-24 01:00 | 2026-08-28 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 |  |  | Created | 2025-11-05 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
Calpine King City | Calpine King City | - |  |  |  |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 0 | 0 | 12 |  | 26-254 | 26-254 - Calpine King City - Calpine King City - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2026-03-02 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays | John Selman | Cancelled | 2026.0
Meta | Williams Aquila 2 | 7 x TM2500 Gen9 (DLE) |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-253 | 26-253 - Meta - Williams Aquila 2 - 7 x TM2500 Gen9 (DLE) - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Eagle Mountain, UT | Customer Site | Monday |  |  | 2026-11-16 |  | 0 | 2027-02-08 | 2027-02-12 | 2027-03-15 01:00 | 2027-03-19 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2026.0
Meta | Williams Aquila 2 | 7 x TM2500 Gen9 (DLE) |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10602 | Gas Turbine - TM2500+ Aero Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-252 | 26-252 - Meta - Williams Aquila 2 - 7 x TM2500 Gen9 (DLE) - Gas Turbine - TM2500+ Aero Package Maintenance | Customer Site | UNITED STATES | TAS-N | Eagle Mountain, UT | Customer Site | Monday |  |  | 2026-11-09 |  | 0 | 2027-01-19 | 2027-01-22 | 2027-03-08 | 2027-03-12 |  | 2027-03-08 | 2027-03-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2026.0
Meta | Williams Aquila 2 | 7 x TM2500 Gen9 (DLE) |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10601 | Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-251 | 26-251 - Meta - Williams Aquila 2 - 7 x TM2500 Gen9 (DLE) - Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Eagle Mountain, UT | Customer Site | Monday |  |  | 2026-11-02 |  | 0 | 2026-12-28 | 2026-12-31 | 2027-03-01 | 2027-03-05 |  | 2027-03-01 | 2027-03-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
Kindle Energy | Canyon Peak Power | - | EGM-00507-1CSTO-TRAINALL |  | EGM-00507-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-250 | 26-250 - Kindle Energy - Canyon Peak Power - - - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Bennett | Customer Site | Monday |  |  | 2026-04-06 01:00 |  | 0 | 2026-03-02 | 2026-03-06 | 2026-05-18 01:00 | 2026-05-22 01:00 |  | 2026-05-18 01:00 | 2026-05-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
NNPC | Abuja IPP | 240MW CC | EGM-00502-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11101 | Excitation - CombiSystem Excitation & Static Starting Device Maintenance | Excitation | 5 | 0 | 0 | 8 |  | 26-249 | 26-249 - NNPC - Abuja IPP - 240MW CC - Excitation - CombiSystem Excitation & Static Starting Device Maintenance | Customer Site | GERMANY | TAS-N | Berlin | Customer Site | Monday |  |  | 2026-10-01 01:00 |  | 0 | [9 empty] | Imported | 2025-11-07 | Birr Workweek and Holidays | Grid Solution Excitation Instructor | Cancelled | 2026.0
UNIPER | MYA Grain/Enfield | - |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | General - Bearing Introdcution - GT26 - Option 2 | General | 3 | 0 | 0 | 12 |  | 26-248 | 26-248 - UNIPER - MYA Grain/Enfield - - - General - Bearing Introdcution - GT26 - Option 2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-11-30 |  | 0 |  |  | 2026-11-30 | 2026-12-02 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Gaetan Kofmel | Cancelled | 2026.0
UNIPER | MYA Grain/Enfield | - |  |  |  |  | English | English | IB | Anna Petrella | Customer-Project Specific | General - Shaft Alignment - GT26 - Option 2 | General | 5 | 9 | 0 | 12 |  | 26-247 | 26-247 - UNIPER - MYA Grain/Enfield - - - General - Shaft Alignment - GT26 - Option 2 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-11-23 |  | 0 | 2026-11-10 | 2026-11-20 | 2026-11-23 | 2026-11-27 |  | 2026-11-23 | 2026-11-23 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Gaetan Kofmel | Cancelled | 2026.0
UNIPER | MYA Grain/Enfield | - | IG0-002842-12 |  | IG0-002842-12 |  | English | English | IB | Anna Petrella | Customer-Project Specific | General - Bearing Introdcution - GT26 | General | 3 | 0 | 0 | 12 |  | 26-246 | 26-246 - UNIPER - MYA Grain/Enfield - - - General - Bearing Introdcution - GT26 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-05-11 01:00 |  | 0 |  |  | 2026-11-30 | 2026-12-02 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Gaetan Kofmel | Confirmed | 2026.0
UNIPER | MYA Grain/Enfield | - | IG0-002842-12 |  | IG0-002842-12 |  | English | English | IB | Anna Petrella | Customer-Project Specific | General - Shaft Alignment - GT26 | General | 5 | 12 | 0 | 12 |  | 26-245 | 26-245 - UNIPER - MYA Grain/Enfield - - - General - Shaft Alignment - GT26 | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-05-04 01:00 |  | 0 | 2026-04-20 01:00 | 2026-11-20 | 2026-11-23 | 2026-11-27 |  | 2026-11-23 | 2026-11-23 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Gaetan Kofmel | Confirmed | 2026.0
Valara Holdings LLC | Valara Holdings LLC | - | EGM-00575-1CSTO-TRAINALL |  | EGM-00575-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10701 | Gas Turbine - Aero MKVIe Operations | Aeroderivative | 3 | 3 | 1 | 12 |  | 26-244 | 26-244 - Valara Holdings LLC - Valara Holdings LLC - - - Gas Turbine - Aero MKVIe Operations | Customer Site | UNITED STATES | TAS-N | Spartanburg | Customer Site | Monday |  |  | 2026-12-07 |  | 0 | 2027-03-29 01:00 | 2027-03-31 01:00 | 2027-05-17 01:00 | 2027-05-19 01:00 |  | 2027-05-17 01:00 | 2027-05-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tamilarasan Kannaiyan | Tentative | 2026.0
Valara Holdings LLC | Valara Holdings LLC | - | EGM-00575-1CSTO-TRAINALL |  | EGM-00575-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-243 | 26-243 - Valara Holdings LLC - Valara Holdings LLC - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Spartanburg | Customer Site | Monday |  |  | 2026-11-30 |  | 0 | 2027-03-22 01:00 | 2027-03-25 01:00 | 2027-05-10 01:00 | 2027-05-14 01:00 |  | 2027-05-10 01:00 | 2027-05-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2026.0
Valara Holdings LLC | Valara Holdings LLC | - | EGM-00575-1CSTO-TRAINALL |  | EGM-00575-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-242 | 26-242 - Valara Holdings LLC - Valara Holdings LLC - - - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Spartanburg | Customer Site | Monday |  |  | 2026-11-16 |  | 0 | 2027-01-25 | 2027-01-29 | 2027-05-03 01:00 | 2027-05-07 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
Valara Holdings LLC | Valara Holdings LLC | - | EGM-00575-1CSTO-TRAINALL |  | EGM-00575-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-241 | 26-241 - Valara Holdings LLC - Valara Holdings LLC - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Spartanburg | Customer Site | Monday |  |  | 2026-11-09 |  | 0 | 2027-01-04 | 2027-01-08 | 2027-04-26 01:00 | 2027-04-30 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
Consumers Energy Company | Jackson Generating Station | - | IFF-007348-CC-101-TRX |  | IFF-007348-CC-101-TRX |  | English | English | IB | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-240 | 26-240 - Consumers Energy Company - Jackson Generating Station - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Jackson | Customer Site | Monday |  |  | 2026-03-23 01:00 |  | 0 | 2026-01-26 | 2026-01-30 | 2026-03-23 01:00 | 2026-03-27 01:00 |  | 2026-03-23 01:00 | 2026-03-23 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Walker | Confirmed | 2026.0
JongShyn Shipbuilding | Su-Ao Naval Base | - |  |  |  |  | Chinese | Chinese | IB | Gavin Yoong | E-AER10203 | Gas Turbine - LM2500+ Borescope Inspection | Aeroderivative | 2 | 2 | 0 | 8 |  | 26-239 | 26-239 - JongShyn Shipbuilding - Su-Ao Naval Base - - - Gas Turbine - LM2500+ Borescope Inspection | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-05-21 01:00 |  | 0 |  |  | 2026-05-21 01:00 | 2026-05-22 01:00 |  | 2026-05-21 01:00 | 2026-05-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Roland De Conceicao | Cancelled | 2026.0
JongShyn Shipbuilding | Su-Ao Naval Base | - |  |  |  |  | Chinese | Chinese | IB | Gavin Yoong | E-AER10107 | Gas Turbine - LM2500+ Level 2 Hot Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-238 | 26-238 - JongShyn Shipbuilding - Su-Ao Naval Base - - - Gas Turbine - LM2500+ Level 2 Hot Maintenance | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-05-14 01:00 |  | 0 |  |  | 2026-05-14 01:00 | 2026-05-20 01:00 |  | 2026-05-14 01:00 | 2026-05-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Roland De Conceicao | Cancelled | 2026.0
JongShyn Shipbuilding | Su-Ao Naval Base | - |  |  |  |  | Chinese | Chinese | IB | Gavin Yoong | E-AER10206 | Gas Turbine - LM2500+ Level 2 Cold Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-237 | 26-237 - JongShyn Shipbuilding - Su-Ao Naval Base - - - Gas Turbine - LM2500+ Level 2 Cold Maintenance | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-05-07 01:00 |  | 0 |  |  | 2026-05-07 01:00 | 2026-05-13 01:00 |  | 2026-05-07 01:00 | 2026-05-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Roland De Conceicao | Cancelled | 2026.0
JongShyn Shipbuilding | Su-Ao Naval Base | - |  |  |  |  | Chinese | Chinese | IB | Gavin Yoong | E-AER10205 | Gas Turbine - LM2500+ Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 26-236 | 26-236 - JongShyn Shipbuilding - Su-Ao Naval Base - - - Gas Turbine - LM2500+ Level 1 Maintenance | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-04-30 01:00 |  | 0 |  |  | 2026-04-30 01:00 | 2026-05-06 01:00 |  | 2026-04-30 01:00 | 2026-04-30 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Roland De Conceicao | Cancelled | 2026.0
JongShyn Shipbuilding | Su-Ao Naval Base | - |  |  |  |  | Chinese | Chinese | IB | Gavin Yoong | E-AER10204 | Gas Turbine - LM2500+/G4 Engine Familiarization | Aeroderivative | 3 | 3 | 0 | 12 |  | 26-235 | 26-235 - JongShyn Shipbuilding - Su-Ao Naval Base - - - Gas Turbine - LM2500+/G4 Engine Familiarization | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-04-27 01:00 |  | 0 |  |  | 2026-04-27 01:00 | 2026-04-29 01:00 |  | 2026-04-27 01:00 | 2026-04-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Roland De Conceicao | Cancelled | 2026.0
JongShyn Shipbuilding | Su-Ao Naval Base | - |  |  |  |  | Chinese | Chinese | IB | Gavin Yoong | Customer-Project Specific | Additional on site preparation sruvey | General | 10 | 10 | 0 | 12 |  | 26-234 | 26-234 - JongShyn Shipbuilding - Su-Ao Naval Base - - - Additional on site preparation sruvey | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2026-01-12 | 2026-01-22 | 2026-03-02 | 2026-03-13 01:00 |  | 2026-03-02 | 2026-03-02 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Roland De Conceicao | Cancelled | 2026.0
Syncrude | Syncrude Aurora | - | IFF-006256-GT-101-TRX |  | IFF-006256-GT-101-TRX | I01-118000 / PO 7903061022 | English | English | IB | Patrick Molumby | E-GAS22101 | Gas Turbine - Operation E-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-233 | 26-233 - Syncrude - Syncrude Aurora - - - Gas Turbine - Operation E-Class (Advanced) | Customer Site | CANADA | TAS-N | Fort McMurray | Customer Site | Monday |  |  | 2026-04-06 01:00 |  | 0 | 2026-02-23 | 2026-02-27 | 2026-04-06 01:00 | 2026-04-10 01:00 |  | 2026-04-06 01:00 | 2026-04-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL |  | Spanish | Spanish | NU | Alejandra Saldana | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 |  | 26-232 | 26-232 - GSF - Andres CCPP - - - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2027-02-04 |  | 0 |  |  | 2026-11-19 | 2026-11-27 |  | 2026-11-19 | 2026-11-19 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL |  | Spanish | Spanish | NU | Alejandra Saldana | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 |  | 26-231 | 26-231 - GSF - Andres CCPP - - - Electrical - Electrical Control System (ECS) Training | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2027-02-01 |  | 0 |  |  | 2026-11-16 | 2026-11-18 |  | 2026-11-16 | 2026-11-16 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | PO 4102872704 | Spanish | Spanish | NU | Alejandra Saldana | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 0 | 12 |  | 26-230 | 26-230 - GSF - Andres CCPP - - - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2027-01-18 |  | 0 | 2027-01-04 | 2027-01-15 | 2027-03-29 01:00 | 2027-04-09 01:00 |  | 2027-03-29 01:00 | 2027-03-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL |  | Spanish | Spanish | NU | Alejandra Saldana | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 |  | 26-229 | 26-229 - GSF - Andres CCPP - - - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2026-12-28 | 2027-01-08 | 2027-03-15 01:00 | 2027-03-26 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL | PO 4102872686 | Spanish | Spanish | NU | Alejandra Saldana | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 12 |  | 26-228 | 26-228 - GSF - Andres CCPP - - - Steam Turbine - Maintenance On-the-Job Training (OJT) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-12-14 |  | 0 | 2026-12-21 | 2026-12-29 | 2027-04-26 01:00 | 2027-04-30 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL | PO 4102872686 | Spanish | Spanish | NU | Alejandra Saldana | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 12 |  | 26-227 | 26-227 - GSF - Andres CCPP - - - Steam Turbine - Operation - On-the-Job Training (OJT) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-11-30 |  | 0 | 2026-11-12 | 2026-11-25 | 2027-04-12 01:00 | 2027-04-23 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | PO 4102872705 | Spanish | Spanish | NU | Alejandra Saldana | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-226 | 26-226 - GSF - Andres CCPP - - - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-11-16 |  | 0 | 2026-10-02 01:00 | 2026-11-03 | 2027-02-15 | 2027-02-19 |  | 2027-02-15 | 2027-02-15 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | PO 4102872705 | Spanish | Spanish | NU | Alejandra Saldana | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-225 | 26-225 - GSF - Andres CCPP - - - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-11-02 |  | 0 | 2026-09-03 01:00 | 2026-09-17 01:00 | 2027-02-01 | 2027-02-12 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118645 / PO 4102872702 | Spanish | Spanish | NU | Alejandra Saldana | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 |  | 26-224 | 26-224 - GSF - Andres CCPP - - - Balance of Plant - Operation (GE Integrated Systems) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-10-26 01:00 |  | 0 | 2026-06-22 01:00 | 2026-06-26 01:00 | 2026-10-26 01:00 | 2026-10-30 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118645 / PO 4102872702 | Spanish | Spanish | NU | Alejandra Saldana | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 26-223 | 26-223 - GSF - Andres CCPP - - - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-10-19 01:00 |  | 0 | 2026-05-27 01:00 | 2026-05-29 01:00 | 2026-10-19 01:00 | 2026-10-21 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118645 / PO 4102872702 | Spanish | Spanish | NU | Alejandra Saldana | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 26-222 | 26-222 - GSF - Andres CCPP - - - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-10-12 01:00 |  | 0 | 2026-05-19 01:00 | 2026-05-26 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118157 / PO 4102872704 | Spanish | Spanish | NU | Alejandra Saldana | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-221 | 26-221 - GSF - Andres CCPP - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-09-28 01:00 |  | 0 | 2026-06-22 01:00 | 2026-07-02 01:00 | 2026-09-28 01:00 | 2026-10-09 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118157 / PO 4102872704 | Spanish | Spanish | NU | Alejandra Saldana | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-220 | 26-220 - GSF - Andres CCPP - - - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-09-21 01:00 |  | 0 | 2026-04-27 01:00 | 2026-05-01 01:00 | 2026-09-21 01:00 | 2026-09-25 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL |  | Spanish | Spanish | NU | Alejandra Saldana | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-219 | 26-219 - GSF - Andres CCPP - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-05-26 01:00 | 2026-05-29 01:00 | 2026-09-14 01:00 | 2026-09-18 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118649 / PO 4102872692 | Spanish | Spanish | NU | Alejandra Saldana | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 8 | 0 | 12 |  | 26-218 | 26-218 - GSF - Andres CCPP - - - Steam Turbine - Maintenance | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-09-07 01:00 |  | 0 | 2026-05-18 01:00 | 2026-08-19 01:00 | 2026-09-07 01:00 | 2026-09-11 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  |  | I01-118156 / PO 4102872686 | Spanish | Spanish | NU | Alejandra Saldana | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 26-217 | 26-217 - GSF - Andres CCPP - - - Steam Turbine - Operation | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-08-24 01:00 |  | 0 | 2026-04-27 01:00 | 2026-05-08 01:00 | 2026-08-24 01:00 | 2026-09-04 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL |  | Spanish | Spanish | NU | Alejandra Saldana | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-216 | 26-216 - GSF - Andres CCPP - - - Gas Turbine - Maintenance | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-08-17 01:00 |  | 0 | 2026-05-26 01:00 | 2026-05-29 01:00 | 2026-08-17 01:00 | 2026-08-21 01:00 |  | 2026-08-17 01:00 | 2026-08-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
GSF | Andres CCPP | - | EGM-00437-1CSTO-TRAINALL |  | EGM-00437-1CSTO-TRAINALL |  | Spanish | Spanish | NU | Alejandra Saldana | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-215 | 26-215 - GSF - Andres CCPP - - - Gas Turbine - Operation | Customer Site | DOMINICAN REPUBLIC | TAS-M | Punta Caucedo, Boca Chica | Customer Site | Monday |  |  | 2026-08-03 01:00 |  | 0 | 2026-04-27 01:00 | 2026-05-08 01:00 | 2026-08-03 01:00 | 2026-08-14 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 7 | 0 | 12 |  | 26-214 | 26-214 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2027-01-28 |  | 0 |  |  | 2026-11-23 | 2026-11-27 |  | 2026-11-23 | 2026-11-23 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 3 | 0 | 12 |  | 26-213 | 26-213 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  |  | 2027-01-25 |  | 0 |  |  | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 5 | 0 | 12 |  | 26-212 | 26-212 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Control System - Mark VIe Maintenance (Extended) | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3208-9 Energy Corridor Room | 2027-01-11 |  | 0 | 2026-09-21 01:00 | 2026-09-25 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Nasreddine Laroussi | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-211 | 26-211 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2027-01-04 |  | 0 | 2026-08-03 01:00 | 2026-08-07 01:00 | 2026-10-26 01:00 | 2026-10-30 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-210 | 26-210 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Gas Turbine - Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | T-103 Trailblazer | 2026-12-14 |  | 0 | 2026-08-17 01:00 | 2026-08-21 01:00 | 2026-10-19 01:00 | 2026-10-23 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-209 | 26-209 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Gas Turbine - Operation | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | T-101 Voyager | 2026-11-30 |  | 0 |  |  | 2026-10-05 01:00 | 2026-10-16 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 2 | 12 |  | 26-208 | 26-208 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2027-05-23 01:00 |  | 0 | 2026-10-19 01:00 | 2026-10-30 01:00 | 2027-01-05 | 2027-01-18 |  | 2027-01-05 | 2027-01-05 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Gopinath Kumar | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 2 | 12 |  | 26-207 | 26-207 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2027-04-25 01:00 |  | 0 | 2026-09-23 01:00 | 2026-10-16 01:00 | 2026-12-22 | 2027-01-04 |  | 2026-12-22 | 2026-12-22 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Zakaria Al-Qawasmeh | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  |  | I01-119542 / PO 4102869573 | English | English | NU | Abuobaida El Mansoor | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-206 | 26-206 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2027-04-18 01:00 |  | 0 | 2026-10-26 01:00 | 2026-10-30 01:00 | 2026-12-15 | 2026-12-21 |  | 2026-12-15 | 2026-12-15 |  |  | Created | 2025-11-06 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL | I01-119542 / PO 4102869573 | English | English | NU | Abuobaida El Mansoor | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-205 | 26-205 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2027-04-04 01:00 |  | 0 | 2026-06-08 01:00 | 2026-06-18 01:00 | 2026-12-01 | 2026-12-14 |  | 2026-12-01 | 2026-12-01 |  |  | Created | 2025-11-06 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 7 | 0 | 12 |  | 26-204 | 26-204 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Wednesday |  |  | 2026-11-11 |  | 0 |  |  | 2026-08-23 01:00 | 2026-08-27 01:00 |  | 2026-08-23 01:00 | 2026-08-23 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Grid Solution Excitation Instructor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 3 | 0 | 12 |  | 26-203 | 26-203 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-11-08 |  | 0 |  |  | 2026-08-30 01:00 | 2026-09-03 01:00 |  | 2026-08-30 01:00 | 2026-08-30 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Grid Solution Excitation Instructor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 2 | 12 |  | 26-202 | 26-202 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-10-25 01:00 |  | 0 | 2026-03-16 01:00 | 2026-03-27 01:00 | 2026-06-07 01:00 | 2026-06-18 01:00 |  | 2026-06-07 01:00 | 2026-06-07 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Khaled Al Behiri | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-201 | 26-201 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-10-18 01:00 |  | 0 | 2026-03-09 01:00 | 2026-03-13 01:00 | 2026-05-10 01:00 | 2026-05-14 01:00 |  | 2026-05-10 01:00 | 2026-05-10 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Zakaria Al-Qawasmeh | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  | EGM-00488-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 1 | 12 |  | 26-200 | 26-200 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-10-11 01:00 |  | 0 | 2026-03-16 01:00 | 2026-03-20 01:00 | 2026-08-30 01:00 | 2026-09-03 01:00 |  | 2026-08-30 01:00 | 2026-08-30 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Coy Jackson | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Taiba-1 | IPP Project_1.8GW_7HA.03 | EGM-00488-1CSTO-TRAINALL |  |  | I01-117919 / PO 4102842308 | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-199 | 26-199 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Taiba-1 - IPP Project_1.8GW_7HA.03 - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | Taiba | Customer Site | Sunday |  |  | 2026-09-27 01:00 |  | 0 | 2026-03-30 01:00 | 2026-04-10 01:00 | 2026-06-21 01:00 | 2026-07-02 01:00 |  | 2026-06-21 01:00 | 2026-06-21 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Tim Taylor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 7 | 0 | 12 |  | 26-198 | 26-198 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-10-29 01:00 |  | 0 |  |  | 2026-11-02 | 2026-11-06 |  | 2026-11-02 | 2026-11-02 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 3 | 0 | 12 |  | 26-197 | 26-197 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-10-26 01:00 |  | 0 |  |  | 2026-10-26 01:00 | 2026-10-30 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-196 | 26-196 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Control System - Mark VIe Maintenance (Extended) | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-10-12 01:00 |  | 0 | 2026-08-10 01:00 | 2026-09-11 01:00 | 2026-10-12 01:00 | 2026-10-23 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-195 | 26-195 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-10-05 01:00 |  | 0 | 2026-07-06 01:00 | 2026-07-21 01:00 | 2026-10-05 01:00 | 2026-10-09 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-194 | 26-194 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Gas Turbine - Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-09-28 01:00 |  | 0 | 2026-07-27 01:00 | 2026-07-31 01:00 | 2026-09-28 01:00 | 2026-10-02 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-193 | 26-193 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Gas Turbine - Operation | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-09-14 01:00 |  | 0 | 2026-06-01 01:00 | 2026-06-12 01:00 | 2026-09-14 01:00 | 2026-09-25 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 10 | 10 | 1 | 12 |  | 26-192 | 26-192 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | 2027-03-22 01:00 | 2027-04-02 01:00 | 2027-05-02 01:00 | 2027-05-13 01:00 |  |  | 2027-05-02 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Khaled Al Behiri | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 10 | 10 | 0 | 12 |  | 26-191 | 26-191 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2027-02-21 |  | 0 | 2027-03-08 | 2027-03-19 01:00 | 2027-04-18 01:00 | 2027-04-29 01:00 |  |  | 2027-04-18 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Zakaria Al-Qawasmeh | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-190 | 26-190 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Gas Turbine - Maintenance-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2027-02-14 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-04 01:00 | 2027-04-08 01:00 |  |  | 2027-04-04 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-189 | 26-189 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2027-01-31 |  | 0 | 2027-02-15 | 2027-02-26 | 2027-03-21 01:00 | 2027-04-01 01:00 |  |  | 2027-03-21 01:00 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Hichem Mesli | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 7 | 0 | 12 |  | 26-188 | 26-188 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2026-08-23 01:00 |  | 0 |  |  | 2027-02-28 | 2027-03-04 |  |  | 2027-02-28 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Grid Solution Excitation Instructor | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 5 | 3 | 0 | 12 |  | 26-187 | 26-187 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2026-08-16 01:00 |  | 0 |  |  | 2027-02-21 | 2027-02-25 |  |  | 2027-02-21 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Grid Solution Excitation Instructor | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  |  | I01-117466 / PO 4102827066 | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-186 | 26-186 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Control System - Mark VIe Maintenance (Extended) | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2026-08-02 01:00 |  | 0 | 2026-11-16 | 2026-12-01 | 2027-02-07 | 2027-02-18 |  |  | 2027-02-07 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Rafael Venancio | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-185 | 26-185 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2026-07-26 01:00 |  | 0 | 2026-03-30 01:00 | 2026-04-03 01:00 | 2027-01-31 | 2027-02-04 |  |  | 2027-01-31 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Joe Mcandrews | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL | I01-117463 / PO 4102827063 | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-184 | 26-184 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Gas Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2026-07-19 01:00 |  | 0 | 2026-12-21 | 2026-12-29 | 2027-01-24 | 2027-01-28 |  |  | 2027-01-24 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Mohamed Abdelaziz | Tentative | 2026.0
SEPCOIII ELECTRIC POWER CONSTRUCTION CO. | Qassim-1 IPP | Project_1.8GW_7HA.03 | EGM-00486-1CSTO-TRAINALL |  | EGM-00486-1CSTO-TRAINALL | I01-117463 / PO 4102827063 | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 20 | 0 | 12 |  | 26-183 | 26-183 - SEPCOIII ELECTRIC POWER CONSTRUCTION CO. - Qassim-1 IPP - Project_1.8GW_7HA.03 - Gas Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | Al-Qassim | Customer Site | Sunday |  |  | 2026-07-05 01:00 |  | 0 | 2026-02-17 | 2026-12-18 | 2027-01-10 | 2027-01-21 |  |  | 2027-01-10 |  |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek | Mohamed Abdelaziz | Tentative | 2026.0
CBEC | Castle Bluff Energy Center | - |  |  |  |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-176 | 26-176 - CBEC - Castle Bluff Energy Center - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Oakville, St Louis | Customer Site | Monday |  |  | 2026-12-07 |  | 0 | 2026-12-21 | 2027-01-06 | 2027-03-01 | 2027-03-12 |  | 2027-03-01 | 2027-03-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Tentative | 2026.0
Hunterstown | Hunterstown Generating Station | - | IFF-006515-ST-101-TRX |  | IFF-006515-ST-101-TRX | I01-115105 / PO 4102793396 | English | English | NU | Patrick Molumby | E-CON33402 | Control System - Proficy CIMPLICITY for Turbine Controls (Advanced) | Controls | 5 | 5 | 0 | 12 |  | 26-175 | 26-175 - Hunterstown - Hunterstown Generating Station - - - Control System - Proficy CIMPLICITY for Turbine Controls (Advanced) | Customer Site | UNITED STATES | TAS-N | Hunterstwon | Customer Site | Monday |  |  | 2026-02-09 |  | 0 | 2025-12-01 | 2025-12-05 | 2026-02-09 | 2026-02-13 |  | 2026-02-09 | 2026-02-09 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Bharat Vispara | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  |  | I01-115476 | English | English | NU | Gavin Yoong | Customer-Project Specific | Combined Cycle Fundamentals / extended | Combined Cycle | 18 | 10 | 0 | 12 | 1 | 26-174 | 26-174 - TPC - Hsinta - - - Combined Cycle Fundamentals / extended - G1 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-03-09 01:00 |  | 0 | 2026-03-02 | 2026-03-06 | 2026-04-01 01:00 | 2026-11-24 |  | 2026-04-01 01:00 | 2026-04-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
Meta | Williams Aquila 1 | 4 x TM DLE |  |  |  |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-173 | 26-173 - Meta - Williams Aquila 1 - 4 x TM DLE - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Eagle Mountain, UT | Customer Site | Monday |  |  | 2026-06-15 01:00 |  | 0 | 2027-01-04 | 2027-01-08 | 2027-02-15 | 2027-02-19 |  | 2027-02-15 | 2027-02-15 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Tentative | 2026.0
Meta | Williams Aquila 1 | 4 x TM DLE |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10602 | Gas Turbine - TM2500+ Aero Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-172 | 26-172 - Meta - Williams Aquila 1 - 4 x TM DLE - Gas Turbine - TM2500+ Aero Package Maintenance | Customer Site | UNITED STATES | TAS-N | Eagle Mountain, UT | Customer Site | Monday |  |  | 2026-06-08 01:00 |  | 0 | 2026-12-14 | 2026-12-18 | 2027-02-08 | 2027-02-12 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
Meta | Williams Aquila 1 | 4 x TM DLE |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10601 | Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-171 | 26-171 - Meta - Williams Aquila 1 - 4 x TM DLE - Gas Turbine - TM2500+ Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Eagle Mountain, UT | Customer Site | Monday |  |  | 2026-06-01 01:00 |  | 0 | 2026-11-16 | 2026-11-20 | 2027-02-01 | 2027-02-05 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 4 | 5 | 1 | 12 | 3 | 26-170 | 26-170 - TVA - Kingston - - - Control System - Mark VIe Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-03-08 |  | 0 | 2026-12-30 | 2026-12-31 | 2027-03-08 | 2027-03-11 |  | 2027-03-08 | 2027-03-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 4 | 5 | 1 | 12 | 3 | 26-169 | 26-169 - TVA - Kingston - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-03-01 |  | 0 | 2027-01-18 | 2027-01-20 | 2027-03-01 | 2027-03-04 |  | 2027-03-01 | 2027-03-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 4 | 5 | 1 | 12 | 3 | 26-168 | 26-168 - TVA - Kingston - - - Combined Cycle - Operation (GE Integrated Systems) - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-02-22 |  | 0 | 2027-02-02 | 2027-02-04 | 2027-02-22 | 2027-02-25 |  | 2027-02-22 | 2027-02-22 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 | 3 | 26-167 | 26-167 - TVA - Kingston - - - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-02-15 |  | 0 | 2027-01-22 | 2027-02-01 | 2027-02-16 | 2027-02-18 |  | 2027-02-16 | 2027-02-16 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 3 | 26-166 | 26-166 - TVA - Kingston - - - Steam Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-02-08 |  | 0 | 2027-01-19 | 2027-01-21 | 2027-02-08 | 2027-02-12 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 9 | 10 | 1 | 12 | 3 | 26-165 | 26-165 - TVA - Kingston - - - Steam Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-01-25 |  | 0 | 2026-12-28 | 2026-12-31 | 2027-01-25 | 2027-02-04 |  | 2027-01-25 | 2027-01-25 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Raghunath Yeturi | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 4 | 5 | 1 | 12 | 3 | 26-164 | 26-164 - TVA - Kingston - - - Gas Turbine - Maintenance - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-01-18 |  | 0 | 2026-11-05 | 2026-11-06 | 2027-01-18 | 2027-01-21 |  | 2027-01-18 | 2027-01-18 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 3 | 26-163 | 26-163 - TVA - Kingston - - - Gas Turbine - Operation - G3 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2026-11-02 | 2026-11-04 | 2027-01-04 | 2027-01-14 |  | 2027-01-04 | 2027-01-04 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 4 | 5 | 1 | 12 | 2 | 26-162 | 26-162 - TVA - Kingston - - - Control System - Mark VIe Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-03-29 01:00 |  | 0 | 2027-02-01 | 2027-02-03 | 2027-03-29 01:00 | 2027-04-01 01:00 |  | 2027-03-29 01:00 | 2027-03-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 4 | 5 | 1 | 12 | 2 | 26-161 | 26-161 - TVA - Kingston - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-10-26 01:00 |  | 0 | 2027-01-25 | 2027-01-27 | 2027-04-05 01:00 | 2027-04-08 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118917 / PO 4102846687 | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 4 | 5 | 1 | 12 | 2 | 26-160 | 26-160 - TVA - Kingston - - - Combined Cycle - Operation (GE Integrated Systems) - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-10-19 01:00 |  | 0 | 2026-08-24 01:00 | 2026-08-26 01:00 | 2026-10-19 01:00 | 2026-10-22 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118917 / PO 4102846687 | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 | 2 | 26-159 | 26-159 - TVA - Kingston - - - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-10-12 01:00 |  | 0 | 2026-07-23 01:00 | 2026-07-24 01:00 | 2026-10-12 01:00 | 2026-10-14 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118917 / PO 4102846687 | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 2 | 26-158 | 26-158 - TVA - Kingston - - - Steam Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-10-05 01:00 |  | 0 | 2026-07-20 01:00 | 2026-07-24 01:00 | 2026-10-05 01:00 | 2026-10-08 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118576 / PO 4102846674 | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 4 | 2 | 1 | 12 | 2 | 26-157 | 26-157 - TVA - Kingston - - - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-09-28 01:00 |  | 0 | 2026-07-30 01:00 | 2026-07-31 01:00 | 2026-09-28 01:00 | 2026-10-01 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118154 / PO 4102846795 | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 9 | 10 | 1 | 12 | 2 | 26-156 | 26-156 - TVA - Kingston - - - Steam Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-06-04 01:00 | 2026-06-12 01:00 | 2026-09-14 01:00 | 2026-09-24 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118917 / PO 4102846687 | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 9 | 8 | 1 | 12 | 2 | 26-155 | 26-155 - TVA - Kingston - - - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-08-31 01:00 |  | 0 | 2026-06-15 01:00 | 2026-08-14 01:00 | 2026-08-31 01:00 | 2026-09-10 01:00 |  | 2026-08-31 01:00 | 2026-08-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 5 | 0 | 12 | 1 | 26-154 | 26-154 - TVA - Kingston - - - Control System - Mark VIe Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-03-22 01:00 |  | 0 | 2027-01-25 | 2027-01-29 | 2027-03-22 01:00 | 2027-03-25 01:00 |  | 2027-03-22 01:00 | 2027-03-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 4 | 5 | 1 | 12 | 1 | 26-153 | 26-153 - TVA - Kingston - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2027-03-15 01:00 |  | 0 | 2027-01-06 | 2027-01-07 | 2027-03-15 01:00 | 2027-03-18 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 4 | 5 | 1 | 12 | 1 | 26-152 | 26-152 - TVA - Kingston - - - Combined Cycle - Operation (GE Integrated Systems) - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-08-24 01:00 |  | 0 | 2027-03-01 | 2027-03-05 | 2027-04-12 01:00 | 2027-04-15 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118576 / PO 4102846674 | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 4 | 1 | 12 | 1 | 26-151 | 26-151 - TVA - Kingston - - - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-08-17 01:00 |  | 0 | 2026-05-13 01:00 | 2026-07-17 01:00 | 2026-08-17 01:00 | 2026-08-19 01:00 |  | 2026-08-17 01:00 | 2026-08-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118576 / PO 4102846674 | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 26-150 | 26-150 - TVA - Kingston - - - Steam Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-08-10 01:00 |  | 0 | 2026-05-04 01:00 | 2026-05-08 01:00 | 2026-08-10 01:00 | 2026-08-13 01:00 |  | 2026-08-10 01:00 | 2026-08-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118570 / PO 4102846808 | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 4 | 8 | 0 | 12 | 1 | 26-149 | 26-149 - TVA - Kingston - - - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-08-03 01:00 |  | 0 | 2026-05-11 01:00 | 2026-07-29 01:00 | 2026-08-03 01:00 | 2026-08-06 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL | I01-118154 / PO 4102846795 | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 9 | 10 | 1 | 12 | 1 | 26-148 | 26-148 - TVA - Kingston - - - Steam Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-07-20 01:00 |  | 0 | 2026-03-30 01:00 | 2026-04-10 01:00 | 2026-07-20 01:00 | 2026-07-30 01:00 |  | 2026-07-20 01:00 | 2026-07-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
TVA | Kingston | - | EGM-00332-1CSTO-TRAINALL |  | EGM-00332-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 9 | 10 | 1 | 12 | 1 | 26-147 | 26-147 - TVA - Kingston - - - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Harriman | Customer Site | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2026-02-17 | 2026-03-27 01:00 | 2026-05-11 01:00 | 2026-05-21 01:00 |  | 2026-05-11 01:00 | 2026-05-11 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Maintaining the Operator Training Simulator (OTS) | Simulator | 6 | 6 | 2 | 6 | 2 | 26-146 | 26-146 - TPC - Hsinta - - - Maintaining the Operator Training Simulator (OTS) - G2 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday |  |  | 2026-05-18 01:00 |  | 0 | 2026-04-15 01:00 | 2026-04-17 01:00 | 2026-05-18 01:00 | 2026-05-25 01:00 |  | 2026-05-18 01:00 | 2026-05-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Operator Training Simulator (OTS) & Train the Trainer | Simulator | 10 | 9 | 1 | 6 |  | 26-145 | 26-145 - TPC - Hsinta - - - Operator Training Simulator (OTS) & Train the Trainer | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-N | Kaohsiung | Customer Site | Monday | test |  | 2026-05-04 01:00 |  | 0 | 2026-04-02 01:00 | 2026-04-14 01:00 | 2026-05-04 01:00 | 2026-05-15 01:00 |  | 2026-05-04 01:00 | 2026-05-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Combined cycle Ops using OTS cloud simulator | Combined Cycle | 10 | 10 | 0 | 12 | 2 | 26-144 | 26-144 - TPC - Hsinta - - - Combined cycle Ops using OTS cloud simulator - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1231 Rickover Room | 2026-04-20 01:00 |  | 0 | 2026-02-17 | 2026-02-20 | 2026-04-20 01:00 | 2026-05-01 01:00 |  | 2026-04-20 01:00 | 2026-04-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tom Walsh | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX30501 | Excitation - LS2100e LCI for Turbine Static Start | Excitation | 2 | 2 | 1 | 12 | 1 | 26-143 | 26-143 - TPC - Hsinta - - - Excitation - LS2100e LCI for Turbine Static Start - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1225 Turing Room | 2026-04-06 01:00 |  | 0 | 2026-06-22 01:00 | 2026-06-23 01:00 | 2026-10-01 01:00 | 2026-10-02 01:00 |  | 2026-07-23 01:00 | 2026-10-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL | I01-115476 | English | English | NU | Gavin Yoong | E-GEN10403 | Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Generator | 5 | 5 | 0 | 12 | 1 | 26-142 | 26-142 - TPC - Hsinta - - - Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3201 Minute Maid Room | 2026-03-30 01:00 |  | 0 | 2026-02-04 | 2026-02-10 | 2026-10-22 01:00 | 2026-10-28 01:00 |  | 2026-08-13 01:00 | 2026-10-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL | I01-115476 | English | English | NU | Gavin Yoong | Customer-Project Specific | Generator - Hydrogen Cooled Auxiliaries Maintenance | Generator | 3 | 2 | 0 | 12 | 1 | 26-141 | 26-141 - TPC - Hsinta - - - Generator - Hydrogen Cooled Auxiliaries Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3201 Minute Maid Room | 2026-03-23 01:00 |  | 0 | 2026-02-02 | 2026-02-03 | 2026-10-19 01:00 | 2026-10-21 01:00 |  | 2026-08-10 01:00 | 2026-10-19 01:00 | Formerly E-GEN10903 |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 8 | 0 | 12 | 1 | 26-140 | 26-140 - TPC - Hsinta - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1225 Turing Room | 2026-03-09 01:00 |  | 0 | 2026-01-12 | 2026-06-26 01:00 | 2026-10-05 01:00 | 2026-10-16 01:00 |  | 2026-07-27 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 | 2 | 26-139 | 26-139 - TPC - Hsinta - - - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | T-102 Nomad | 2026-05-14 01:00 |  | 0 |  |  | 2026-10-08 01:00 | 2026-10-16 01:00 |  | 2026-10-08 01:00 | 2026-10-08 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 | 2 | 26-138 | 26-138 - TPC - Hsinta - - - Electrical - Electrical Control System (ECS) Training - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | T-102 Nomad | 2026-05-10 01:00 |  | 0 |  |  | 2026-10-05 01:00 | 2026-10-07 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Confirmed | 2026.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 10 | 5 | 0 | 12 | 2 | 26-137 | 26-137 - TPC - Hsinta - - - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3203 Allen Parkway Room | 2026-04-27 01:00 |  | 0 | 2026-01-26 | 2026-01-30 | 2026-09-21 01:00 | 2026-10-02 01:00 |  | 2026-09-28 01:00 | 2026-09-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
Crusoe Energy | Crusoe Energy | Goodnight Pkg 2 |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-136 | 26-136 - Crusoe Energy - Crusoe Energy - Goodnight Pkg 2 - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Abiline | Customer Site | Monday |  |  | 2026-05-11 01:00 |  | 0 | 2027-02-22 | 2027-02-26 | 2027-03-22 01:00 | 2027-03-26 01:00 |  | 2027-03-22 01:00 | 2027-03-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
Crusoe Energy | Crusoe Energy | Goodnight Pkg 2 |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-135 | 26-135 - Crusoe Energy - Crusoe Energy - Goodnight Pkg 2 - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Abiline | Customer Site | Monday |  |  | 2026-05-04 01:00 |  | 0 | 2027-02-16 | 2027-02-19 | 2027-03-15 01:00 | 2027-03-19 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
Crusoe Energy | Crusoe Energy 2 | Long Horn |  |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-134 | 26-134 - Crusoe Energy - Crusoe Energy 2 - Long Horn - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Abiline | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2027-01-18 | 2027-01-22 | 2027-03-08 | 2027-03-12 |  | 2027-03-08 | 2027-03-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Elias Benedi | Tentative | 2026.0
City Utilities | City Utilities of Springfield MO | - | EGM-00504-1CSTO-TRAINALL |  | EGM-00504-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON23401 | Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 26-133 | 26-133 - City Utilities - City Utilities of Springfield MO - - - Control System - Mark VIe (Aero) Operation, Maintenance & Troubleshooting | Customer Site | UNITED STATES | TAS-N | Springfield | Customer Site | Monday |  |  | 2026-09-28 01:00 |  | 0 | 2026-08-03 01:00 | 2026-08-07 01:00 | 2026-12-14 | 2026-12-18 |  | 2026-12-14 | 2026-12-14 |  |  | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Confirmed | 2026.0
City Utilities | City Utilities of Springfield MO | - | EGM-00504-1CSTO-TRAINALL |  | EGM-00504-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-132 | 26-132 - City Utilities - City Utilities of Springfield MO - - - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Springfield | Customer Site | Monday |  |  | 2026-09-21 01:00 |  | 0 | 2026-11-02 | 2026-11-03 | 2026-12-07 | 2026-12-11 |  | 2026-12-07 | 2026-12-07 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
City Utilities | City Utilities of Springfield MO | - | EGM-00504-1CSTO-TRAINALL |  | EGM-00504-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-131 | 26-131 - City Utilities - City Utilities of Springfield MO - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Springfield | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-05-26 01:00 | 2026-05-29 01:00 | 2026-11-30 | 2026-12-04 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
TVA | Allen | - |  |  | EGM-00392-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10101 | Gas Turbine - LM2500 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-129 | 26-129 - TVA - Allen - - - Gas Turbine - LM2500 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Memphis | Customer Site | Monday |  |  | 2026-10-05 01:00 |  | 0 | 2026-09-21 01:00 | 2026-09-25 01:00 | 2026-11-09 | 2026-11-13 |  | 2026-11-09 | 2026-11-09 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Tentative | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-118245 / PO 4102705601 | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Maintaining the Operator Training Simulator (OTS) | Simulator | 8 | 10 | 1 | 6 | 2 | 26-128 | 26-128 - TPC - Taichung - 2026 - Maintaining the Operator Training Simulator (OTS) - G2 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday |  |  | 2026-09-21 01:00 |  | 0 | 2026-06-01 01:00 | 2026-06-05 01:00 | 2026-09-22 01:00 | 2026-10-01 01:00 |  | 2026-09-22 01:00 | 2026-09-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-118245 / PO 4102705601 | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Operator Training Simulator (OTS) & Train the Trainer | Simulator | 10 | 10 | 1 | 6 | 2 | 26-127 | 26-127 - TPC - Taichung - 2026 - Operator Training Simulator (OTS) & Train the Trainer - G2 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday |  |  | 2026-09-07 01:00 |  | 0 | 2026-05-11 01:00 | 2026-05-22 01:00 | 2026-09-08 01:00 | 2026-09-21 01:00 |  | 2026-09-08 01:00 | 2026-09-08 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-112984 | English | English | NU | Gavin Yoong | Customer-Project Specific | Maintaining the Operator Training Simulator (OTS) | Simulator | 5 | 10 | 0 | 6 | 1 | 26-126 | 26-126 - TPC - Taichung - 2026 - Maintaining the Operator Training Simulator (OTS) - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday |  |  | 2026-06-23 01:00 |  | 0 |  |  | 2025-11-24 | 2025-11-28 |  | 2025-11-24 | 2025-11-24 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | OTS Training - OTS & Train the Trainer | Simulator | 11 | 7 | 3 | 6 | 1 | 26-125 | 26-125 - TPC - Taichung - 2026 - OTS Training - OTS & Train the Trainer - G1 | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Taichung | Customer Site | Monday |  |  | 2026-06-08 01:00 |  | 0 | 2026-02-23 | 2026-03-03 | 2027-01-11 | 2027-01-25 |  | 2027-01-11 | 2027-01-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Tentative | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | Mandarin Chinese | English | NU | Gavin Yoong | E-ELX30501 | Excitation - LS2100e LCI for Turbine Static Start | Excitation | 2 | 2 | 0 | 12 | 2 | 26-124 | 26-124 - TPC - Taichung - 2026 - Excitation - LS2100e LCI for Turbine Static Start - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2026-06-15 01:00 |  | 0 | 2026-05-06 01:00 | 2026-05-06 01:00 | 2026-06-15 01:00 | 2026-06-16 01:00 |  | 2026-06-15 01:00 | 2026-06-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GEN10403 | Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Generator | 5 | 5 | 0 | 12 | 2 | 26-123 | 26-123 - TPC - Taichung - 2026 - Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2026-06-22 01:00 |  | 0 | 2026-04-08 01:00 | 2026-04-10 01:00 | 2026-06-22 01:00 | 2026-06-26 01:00 |  | 2026-06-22 01:00 | 2026-06-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Generator - Hydrogen Cooled Auxiliaries Maintenance | Generator | 3 | 3 | 4 | 12 | 2 | 26-122 | 26-122 - TPC - Taichung - 2026 - Generator - Hydrogen Cooled Auxiliaries Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2026-06-17 01:00 |  | 0 | 2026-04-03 01:00 | 2026-04-08 01:00 | 2026-06-17 01:00 | 2026-06-19 01:00 |  | 2026-06-17 01:00 | 2026-06-17 01:00 | Formerly E-GEN10903 |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | Mandarin Chinese | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 5 | 0 | 12 | 2 | 26-121 | 26-121 - TPC - Taichung - 2026 - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2026-06-01 01:00 |  | 0 | 2026-02-09 | 2026-02-13 | 2026-06-01 01:00 | 2026-06-12 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Combined Cycle Ops using OTS cloud simulator | Combined Cycle | 10 | 10 | 0 | 12 | 2 | 26-120 | 26-120 - TPC - Taichung - 2026 - Combined Cycle Ops using OTS cloud simulator - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1225 Turing Room | 2026-03-23 01:00 |  | 0 | 2026-01-20 | 2026-01-22 | 2026-07-06 01:00 | 2026-07-17 01:00 |  | 2026-07-06 01:00 | 2026-07-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tom Walsh | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10903 | Electrical - Intelligent Electronic Device (IED) IED's Protection & Control | Excitation | 7 | 7 | 0 | 12 | 2 | 26-119 | 26-119 - TPC - Taichung - 2026 - Electrical - Intelligent Electronic Device (IED) IED's Protection & Control - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1101 Thomson-Houston Room | 2026-05-07 01:00 |  | 0 |  |  | 2026-10-15 01:00 | 2026-10-23 01:00 |  | 2026-10-15 01:00 | 2026-10-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays |  | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10902 | Electrical - Electrical Control System (ECS) Training | Excitation | 3 | 3 | 0 | 12 | 2 | 26-118 | 26-118 - TPC - Taichung - 2026 - Electrical - Electrical Control System (ECS) Training - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1101 Thomson-Houston Room | 2026-05-04 01:00 |  | 0 |  |  | 2026-10-12 01:00 | 2026-10-14 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays |  | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 10 | 5 | 0 | 12 | 2 | 26-117 | 26-117 - TPC - Taichung - 2026 - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-04-20 01:00 |  | 0 | 2026-05-04 01:00 | 2026-05-06 01:00 | 2026-09-28 01:00 | 2026-10-09 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-111005 / PO 4102715600 | English | English | NU | Gavin Yoong | E-CON13412 | Control System - Mark VIe Distributed Control System Operation | Controls | 7 | 5 | 0 | 12 | 2 | 26-116 | 26-116 - TPC - Taichung - 2026 - Control System - Mark VIe Distributed Control System Operation - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-04-02 01:00 |  | 0 | 2025-12-23 | 2026-06-18 01:00 | 2026-09-17 01:00 | 2026-09-25 01:00 |  | 2026-09-17 01:00 | 2026-09-17 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
TPC | Taichung | 2026 | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-111005 / PO 4102715600 | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 13 | 10 | 0 | 12 | 2 | 26-115 | 26-115 - TPC - Taichung - 2026 - Control System - Mark VIe Maintenance (Extended) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-03-16 01:00 |  | 0 | 2025-12-15 | 2026-06-17 01:00 | 2026-08-31 01:00 | 2026-09-16 01:00 |  | 2026-08-31 01:00 | 2026-08-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-111005 / PO 4102715600 | English | English | IB | Gavin Yoong | E-CON13701 | Control System - Control Server and Thin Client Familiarization | Controls | 3 | 3 | 0 | 6 |  | 26-114 | 26-114 - TPC - Taichung - New GTCC - Control System - Control Server and Thin Client Familiarization | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-02-13 |  | 0 | 2026-01-21 | 2026-01-23 | 2026-02-13 | 2026-02-24 |  | 2026-02-13 | 2026-02-13 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Confirmed | 2026.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-111005 / PO 4102715600 | English | English | IB | Gavin Yoong | E-CON13414 | Control System - Mark Vle Foundation Fieldbus | Controls | 2 | 2 | 0 | 4 |  | 26-113 | 26-113 - TPC - Taichung - New GTCC - Control System - Mark Vle Foundation Fieldbus | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-02-11 |  | 0 | 2026-01-19 | 2026-01-20 | 2026-02-11 | 2026-02-12 |  | 2026-02-11 | 2026-02-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Confirmed | 2026.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | IB | Gavin Yoong | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 7 | 0 | 12 | 2 | 26-112 | 26-112 - TPC - Taichung - New GTCC - Control System - Mark VIe Distributed Control System Maintenance - G2 | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-02-04 |  | 0 | 2025-11-03 | 2026-02-03 | 2026-02-04 | 2026-02-10 |  | 2026-02-04 | 2026-02-04 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Khaled Al Behiri | Confirmed | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-111 | 26-111 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2027-02-08 |  | 0 | 2026-12-23 | 2026-12-31 | 2027-02-08 | 2027-02-12 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 26-110 | 26-110 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Steam Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2027-02-01 |  | 0 | 2026-10-05 01:00 | 2026-10-09 01:00 | 2027-02-01 | 2027-02-05 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-109 | 26-109 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2027-01-25 |  | 0 | 2026-11-23 | 2026-12-15 | 2027-01-25 | 2027-01-29 |  | 2027-01-25 | 2027-01-25 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-GAS22101 | Gas Turbine - Operation E-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-108 | 26-108 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Gas Turbine - Operation E-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2027-01-18 |  | 0 | 2026-11-16 | 2026-11-20 | 2027-01-18 | 2027-01-22 |  | 2027-01-18 | 2027-01-18 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-107 | 26-107 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2027-01-11 |  | 0 | 2026-11-30 | 2026-12-04 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13412 | Control System - Mark VIe Distributed Control System Operation | Controls | 5 | 5 | 0 | 12 |  | 26-106 | 26-106 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Control System - Mark VIe Distributed Control System Operation | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2026-10-26 01:00 | 2026-10-30 01:00 | 2027-01-04 | 2027-01-08 |  | 2027-01-04 | 2027-01-04 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-105 | 26-105 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2026-12-07 |  | 0 | 2026-10-05 01:00 | 2026-10-15 01:00 | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Nasreddine Laroussi | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 26-104 | 26-104 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2026-11-30 |  | 0 | 2026-09-15 01:00 | 2026-10-02 01:00 | 2026-11-30 | 2026-12-04 |  | 2026-11-30 | 2026-11-30 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 1 | 12 |  | 26-103 | 26-103 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2026-11-16 |  | 0 | 2026-08-27 01:00 | 2026-09-14 01:00 | 2026-11-16 | 2026-11-18 |  | 2026-11-16 | 2026-11-16 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 26-102 | 26-102 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Steam Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2026-11-02 |  | 0 | 2026-09-08 01:00 | 2026-09-18 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Raghunath Yeturi | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 | EGM-00365-1CSTO-TRAINALL |  | EGM-00365-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-101 | 26-101 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2026-10-19 01:00 |  | 0 | 2026-07-13 01:00 | 2026-07-24 01:00 | 2026-10-19 01:00 | 2026-10-30 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Tentative | 2026.0
Venture Global LNG | VGL Calcasieu Pass 2 | Ph 1 - Aero | EGM-00390-1CSTO-TRAINALL |  |  |  | English | English | NU | Patrick Molumby | E-AER10201 | Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-100 | 26-100 - Venture Global LNG - VGL Calcasieu Pass 2 - Ph 1 - Aero - Gas Turbine - LM2500+ Aero and LM2500+ Xpress Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Cameron Parish | Customer Site | Monday |  |  | 2026-10-12 01:00 |  | 0 | 2026-09-08 01:00 | 2026-09-11 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
Western Farmers | - | - | EGM-00434-1CSTO-TRAINALL |  | EGM-00434-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-97 | 26-97 - Western Farmers - - - - - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Anadarko | Customer Site | Monday |  |  | 2026-01-26 |  | 0 |  |  | 2026-08-03 01:00 | 2026-08-07 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
Western Farmers | - | - | EGM-00434-1CSTO-TRAINALL |  | EGM-00434-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10302 | Gas Turbine - LM6000 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-96 | 26-96 - Western Farmers - - - - - Gas Turbine - LM6000 Package Maintenance | Customer Site | UNITED STATES | TAS-N | Anadarko | Customer Site | Monday |  |  | 2026-01-20 |  | 0 | 2026-03-09 01:00 | 2026-03-13 01:00 | 2026-07-27 01:00 | 2026-07-31 01:00 |  | 2026-07-27 01:00 | 2026-07-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
Western Farmers | - | - | EGM-00434-1CSTO-TRAINALL |  | EGM-00434-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-95 | 26-95 - Western Farmers - - - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Anadarko | Customer Site | Monday |  |  | 2026-01-12 |  | 0 |  |  | 2026-07-13 01:00 | 2026-07-17 01:00 |  | 2026-07-13 01:00 | 2026-07-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
Western Farmers | - | - | EGM-00434-1CSTO-TRAINALL |  | EGM-00434-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-AER10301 | Gas Turbine - LM6000 Aero Package Operation/Familiarization | Aeroderivative | 5 | 5 | 0 | 12 |  | 26-94 | 26-94 - Western Farmers - - - - - Gas Turbine - LM6000 Aero Package Operation/Familiarization | Customer Site | UNITED STATES | TAS-N | Anadarko | Customer Site | Monday |  |  | 2026-01-05 |  | 0 | 2026-02-17 | 2026-02-20 | 2026-07-06 01:00 | 2026-07-10 01:00 |  | 2026-07-06 01:00 | 2026-07-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2026.0
NNPC | Abuja IPP | 240MW CC | EGM-00502-1CSTO-TRAINALL |  | EGM-00502-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 0 | 12 |  | 26-93 | 26-93 - NNPC - Abuja IPP - 240MW CC - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Customer Site | NIGERIA | TAS-S | Abuja | Customer Site | Monday |  |  | 2026-08-10 01:00 |  | 0 | 2026-06-29 01:00 | 2026-07-03 01:00 | 2026-10-19 01:00 | 2026-10-23 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Tentative | 2026.0
NNPC | Abuja IPP | 240MW CC | EGM-00502-1CSTO-TRAINALL |  | EGM-00502-1CSTO-TRAINALL |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 13 | 0 | 12 |  | 26-92 | 26-92 - NNPC - Abuja IPP - 240MW CC - Control System - Mark VIe Maintenance (Extended) | Customer Site | NIGERIA | TAS-S | Abuja | Customer Site | Monday |  |  | 2026-06-22 01:00 |  | 0 | 2026-04-06 01:00 | 2026-10-28 01:00 | 2026-11-02 | 2026-11-13 |  | 2026-11-02 | 2026-11-02 | Reached out to Isaiah to verify if he's willing to travel as of 23Jun26 |  | Created | 2025-11-07 | US Workweek and Holidays | Salvatore Genovese | Tentative | 2026.0
NNPC | Abuja IPP | 240MW CC | EGM-00502-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-ELX11101 | Excitation - CombiSystem Excitation & Static Starting Device Maintenance | Excitation | 5 | 5 | 0 | 8 |  | 26-91 | 26-91 - NNPC - Abuja IPP - 240MW CC - Excitation - CombiSystem Excitation & Static Starting Device Maintenance | Customer Site | NIGERIA | TAS-S | Abuja | Customer Site | Monday |  |  | 2026-08-01 01:00 |  | 0 |  |  | 2026-09-28 01:00 | 2026-10-02 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 | Mansoor to Schedule |  | Created | 2025-11-07 | US Workweek and Holidays | Grid Solution Excitation Instructor | Resourcing In Progress | 2026.0
NNPC | Abuja IPP | 240MW CC | EGM-00502-1CSTO-TRAINALL |  | EGM-00502-1CSTO-TRAINALL | I01-117910 / PO 4200326044 | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-90 | 26-90 - NNPC - Abuja IPP - 240MW CC - Gas Turbine - Maintenance | Customer Site | NIGERIA | TAS-S | Abuja | Customer Site | Monday |  |  | 2026-06-15 01:00 |  | 0 | 2026-03-16 01:00 | 2026-03-20 01:00 | 2026-09-21 01:00 | 2026-09-25 01:00 |  |  | 2026-09-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Carlos Arevalo | Tentative | 2026.0
NNPC | Abuja IPP | 240MW CC | EGM-00502-1CSTO-TRAINALL |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-89 | 26-89 - NNPC - Abuja IPP - 240MW CC - Gas Turbine - Operation | Customer Site | NIGERIA | TAS-S | Abuja | Customer Site | Monday |  |  | 2026-06-01 01:00 |  | 0 |  |  | 2026-10-05 01:00 | 2026-10-16 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 | Anna has asked borrowed instructor for availability as of 11Jun26 |  | Created | 2025-11-07 | US Workweek and Holidays | Marcelo Oliveira | Tentative | 2026.0
NNPC | Abuja IPP | 240MW CC | IFF-007306-CC-101-TRX |  | IFF-007306-CC-101-TRX |  | English | English | NU | Abuobaida El Mansoor | E-ELX10901 | Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Excitation | 5 | 5 | 0 | 12 |  | 26-88 | 26-88 - NNPC - Abuja IPP - 240MW CC - Excitation -Electrical - Operation & Maintenance (GE Integrated Systems) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-10-12 01:00 |  | 0 | 2026-06-29 01:00 | 2026-07-03 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Zakaria Al-Qawasmeh | Cancelled | 2026.0
NNPC | Abuja IPP | 240MW CC | IFF-007306-CC-101-TRX |  | IFF-007306-CC-101-TRX |  | English | English | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-87 | 26-87 - NNPC - Abuja IPP - 240MW CC - Control System - Mark VIe Maintenance (Extended) | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-28 01:00 |  | 0 | 2026-07-13 01:00 | 2026-08-07 01:00 | 2026-09-28 01:00 | 2026-10-09 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Santosh Kumar | Cancelled | 2026.0
NNPC | Abuja IPP | 240MW CC | IFF-007306-CC-101-TRX |  |  | I01-117910 / PO 4200326044 | English | English | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-86 | 26-86 - NNPC - Abuja IPP - 240MW CC - Gas Turbine - Maintenance | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-21 01:00 |  | 0 | 2026-05-12 01:00 | 2026-05-12 01:00 | 2026-09-21 01:00 | 2026-09-25 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Carlos Arevalo | Cancelled | 2026.0
NNPC | Abuja IPP | 240MW CC | IFF-007306-CC-101-TRX |  | IFF-007306-CC-101-TRX |  | English | English | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-85 | 26-85 - NNPC - Abuja IPP - 240MW CC - Gas Turbine - Operation | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-09-07 01:00 |  | 0 | 2026-02-26 | 2026-08-14 01:00 | 2026-09-07 01:00 | 2026-09-18 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2025-11-07 | Birr Workweek and Holidays | Aleksandar Kitanovic | Cancelled | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 9 | 10 | 1 | 12 | 2 | 26-84 | 26-84 - LG&E - Mill Creek - 5 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-05-10 01:00 |  | 0 | 2027-03-15 01:00 | 2027-03-19 01:00 | 2027-05-10 01:00 | 2027-05-20 01:00 |  | 2027-05-10 01:00 | 2027-05-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-CON33703 | Control System - Controls Operation & Maintenance On-the-Job Training (OJT) | Controls | 9 | 10 | 1 | 12 | 1 | 26-83 | 26-83 - LG&E - Mill Creek - 5 - Control System - Controls Operation & Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-04-26 01:00 |  | 0 | 2027-02-22 | 2027-03-05 | 2027-04-26 01:00 | 2027-05-06 01:00 |  | 2027-04-26 01:00 | 2027-04-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 9 | 10 | 1 | 12 | 2 | 26-82 | 26-82 - LG&E - Mill Creek - 5 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-04-12 01:00 |  | 0 | 2027-02-22 | 2027-02-26 | 2027-04-12 01:00 | 2027-04-22 01:00 |  | 2027-04-12 01:00 | 2027-04-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11503 | Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) | Excitation | 9 | 10 | 0 | 12 | 1 | 26-81 | 26-81 - LG&E - Mill Creek - 5 - Excitation - Excitation Operation & Maintenance - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-03-29 01:00 |  | 0 | 2027-02-08 | 2027-02-19 | 2027-03-29 01:00 | 2027-04-08 01:00 |  | 2027-03-29 01:00 | 2027-03-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 4 | 5 | 1 | 12 | 2 | 26-80 | 26-80 - LG&E - Mill Creek - 5 - Steam Turbine - Maintenance On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-03-22 01:00 |  | 0 |  |  | 2027-03-22 01:00 | 2027-03-25 01:00 |  | 2027-03-22 01:00 | 2027-03-22 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Amin Houidi;Domingo Aleman;Donald Hopkins | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-STM10805 | Steam Turbine - Maintenance On-the-Job Training (OJT) | Steam Turbine | 5 | 5 | 0 | 12 | 1 | 26-79 | 26-79 - LG&E - Mill Creek - 5 - Steam Turbine - Maintenance On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-03-15 01:00 |  | 0 | 2027-01-11 | 2027-01-15 | 2027-03-15 01:00 | 2027-03-18 01:00 |  | 2027-03-15 01:00 | 2027-03-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Amin Houidi;Domingo Aleman;Donald Hopkins | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 9 | 10 | 0 | 12 | 2 | 26-78 | 26-78 - LG&E - Mill Creek - 5 - Steam Turbine - Operation - On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-03-01 |  | 0 |  |  | 2027-03-01 | 2027-03-11 |  | 2027-03-01 | 2027-03-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Amin Houidi;Domingo Aleman;Donald Hopkins | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-STM10804 | Steam Turbine - Operation - On-the-Job Training (OJT) | Steam Turbine | 10 | 10 | 0 | 12 | 1 | 26-77 | 26-77 - LG&E - Mill Creek - 5 - Steam Turbine - Operation - On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-02-15 |  | 0 | 2026-12-28 | 2027-01-08 | 2027-02-16 | 2027-02-26 |  | 2027-02-16 | 2027-02-16 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Amin Houidi;Domingo Aleman;Donald Hopkins | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 4 | 5 | 1 | 12 | 2 | 26-76 | 26-76 - LG&E - Mill Creek - 5 - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-02-08 |  | 0 | 2026-10-22 01:00 | 2026-11-25 | 2027-02-08 | 2027-02-11 |  | 2027-02-08 | 2027-02-08 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12005 | Gas Turbine - Maintenance-On-the-Job Training (OJT) | Gas Turbine | 4 | 5 | 1 | 12 | 1 | 26-75 | 26-75 - LG&E - Mill Creek - 5 - Gas Turbine - Maintenance-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-02-01 |  | 0 | 2026-12-28 | 2027-01-04 | 2027-02-01 | 2027-02-04 |  | 2027-02-01 | 2027-02-01 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 26-74 | 26-74 - LG&E - Mill Creek - 5 - Gas Turbine - Operation-On-the-Job Training (OJT) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-01-18 |  | 0 | 2026-09-08 01:00 | 2026-09-11 01:00 | 2027-01-19 | 2027-01-29 |  | 2027-01-19 | 2027-01-19 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 9 | 10 | 1 | 12 | 1 | 26-73 | 26-73 - LG&E - Mill Creek - 5 - Gas Turbine - Operation-On-the-Job Training (OJT) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2027-01-04 |  | 0 | 2026-10-12 01:00 | 2026-10-23 01:00 | 2027-01-04 | 2027-01-14 |  | 2027-01-04 | 2027-01-04 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-118918 / PO 4102854085 | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 4 | 5 | 1 | 12 | 2 | 26-72 | 26-72 - LG&E - Mill Creek - 5 - Control System - Mark VIe Distributed Control System Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-10-26 01:00 |  | 0 | 2026-07-06 01:00 | 2026-07-08 01:00 | 2026-10-26 01:00 | 2026-10-29 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-118925 / PO 4102854083 | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 4 | 5 | 1 | 12 | 1 | 26-71 | 26-71 - LG&E - Mill Creek - 5 - Control System - Mark VIe Distributed Control System Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-10-19 01:00 |  | 0 | 2026-06-01 01:00 | 2026-06-05 01:00 | 2026-10-19 01:00 | 2026-10-22 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Isaiah Mason | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-118533 / PO 4102854080 | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 9 | 10 | 1 | 12 | 2 | 26-70 | 26-70 - LG&E - Mill Creek - 5 - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-10-05 01:00 |  | 0 | 2026-09-14 01:00 | 2026-09-18 01:00 | 2026-10-05 01:00 | 2026-10-15 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-118533 / PO 4102854080 | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 1 | 26-69 | 26-69 - LG&E - Mill Creek - 5 - Control System - Mark VIe Maintenance (Extended) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-09-21 01:00 |  | 0 | 2026-04-27 01:00 | 2026-05-08 01:00 | 2026-09-21 01:00 | 2026-10-01 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 4 | 5 | 1 | 12 | 2 | 26-68 | 26-68 - LG&E - Mill Creek - 5 - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-09-14 01:00 |  | 0 | 2026-06-22 01:00 | 2026-06-24 01:00 | 2026-09-14 01:00 | 2026-09-17 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 1 | 26-67 | 26-67 - LG&E - Mill Creek - 5 - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-09-07 01:00 |  | 0 | 2026-06-15 01:00 | 2026-06-18 01:00 | 2026-09-07 01:00 | 2026-09-10 01:00 |  | 2026-09-07 01:00 | 2026-09-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-117327 / PO 4102830774 | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 4 | 5 | 1 | 12 | 2 | 26-66 | 26-66 - LG&E - Mill Creek - 5 - Combined Cycle - Operation (GE Integrated Systems) - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-08-31 01:00 |  | 0 | 2026-04-20 01:00 | 2026-04-24 01:00 | 2026-08-31 01:00 | 2026-09-03 01:00 |  | 2026-08-31 01:00 | 2026-08-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-117327 / PO 4102830774 | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 4 | 4 | 0 | 12 | 1 | 26-65 | 26-65 - LG&E - Mill Creek - 5 - Combined Cycle - Operation (GE Integrated Systems) - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-08-24 01:00 |  | 0 | 2026-04-20 01:00 | 2026-04-28 01:00 | 2026-08-24 01:00 | 2026-08-27 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-117329 / PO 4102830777 | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 4 | 5 | 1 | 12 | 2 | 26-64 | 26-64 - LG&E - Mill Creek - 5 - Steam Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-08-17 01:00 |  | 0 | 2026-05-27 01:00 | 2026-05-29 01:00 | 2026-08-17 01:00 | 2026-08-20 01:00 |  | 2026-08-17 01:00 | 2026-08-17 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL | I01-117344 / PO 4102830776 | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 4 | 5 | 0 | 12 | 1 | 26-63 | 26-63 - LG&E - Mill Creek - 5 - Steam Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-08-10 01:00 |  | 0 | 2026-05-26 01:00 | 2026-05-29 01:00 | 2026-08-10 01:00 | 2026-08-13 01:00 |  | 2026-08-10 01:00 | 2026-08-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  |  | I01-117344 / PO 4102830776 | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 | 2 | 26-62 | 26-62 - LG&E - Mill Creek - 5 - Steam Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-07-27 01:00 |  | 0 | 2026-04-30 01:00 | 2026-05-06 01:00 | 2026-07-27 01:00 | 2026-08-06 01:00 |  | 2026-07-27 01:00 | 2026-07-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  |  | I01-117327 / PO 4102830774 | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 9 | 10 | 1 | 12 | 1 | 26-61 | 26-61 - LG&E - Mill Creek - 5 - Steam Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-07-13 01:00 |  | 0 | 2026-03-19 01:00 | 2026-04-17 01:00 | 2026-07-13 01:00 | 2026-07-23 01:00 |  | 2026-07-13 01:00 | 2026-07-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 4 | 5 | 1 | 12 | 2 | 26-60 | 26-60 - LG&E - Mill Creek - 5 - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2026-04-06 01:00 | 2026-04-08 01:00 | 2026-07-06 01:00 | 2026-07-09 01:00 |  | 2026-07-06 01:00 | 2026-07-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 4 | 5 | 0 | 12 | 1 | 26-59 | 26-59 - LG&E - Mill Creek - 5 - Gas Turbine - Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-06-29 01:00 |  | 0 | 2026-04-20 01:00 | 2026-04-24 01:00 | 2026-06-29 01:00 | 2026-07-02 01:00 |  | 2026-06-29 01:00 | 2026-06-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 26-58 | 26-58 - LG&E - Mill Creek - 5 - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-06-15 01:00 |  | 0 | 2026-03-30 01:00 | 2026-04-06 01:00 | 2026-06-15 01:00 | 2026-06-25 01:00 |  | 2026-06-15 01:00 | 2026-06-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2026.0
LG&E | Mill Creek | 5 | EGM-00419-1CSTO-TRAINALL |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 9 | 10 | 1 | 12 | 1 | 26-57 | 26-57 - LG&E - Mill Creek - 5 - Gas Turbine - Operation - G1 | Customer Site | UNITED STATES | TAS-N | Louisville | Customer Site | Monday |  |  | 2026-06-01 01:00 |  | 0 | 2026-03-16 01:00 | 2026-04-09 01:00 | 2026-06-01 01:00 | 2026-06-11 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2026.0
Duke | Woodsdale | - |  |  |  | I01-113726 / PO 4102768302 | English | English | IB | Patrick Molumby | Customer-Project Specific | Gas Turbine -Maintenance (GT11) | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-56 | 26-56 - Duke - Woodsdale - - - Gas Turbine -Maintenance (GT11) | Customer Site | UNITED STATES | TAS-N | Trenton | Customer Site | Monday |  |  | 2026-01-26 |  | 0 |  |  | 2026-02-02 | 2026-02-06 |  | 2026-02-02 | 2026-02-02 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Carlos Arevalo | Confirmed | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 2 | 12 |  | 26-54 | 26-54 - Sonelgaz - Djelfa - - - Steam Turbine - Maintenance | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | 2026-03-02 | 2026-03-06 | [5 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 1 | 12 |  | 26-53 | 26-53 - Sonelgaz - Djelfa - - - Steam Turbine - Operation | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | 2026-04-20 01:00 | 2026-05-01 01:00 | [5 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | E-CCP10201 | Combined Cycle - Power Plant Familiarization | Combined Cycle | 5 | 5 | 0 | 20 |  | 26-52 | 26-52 - Sonelgaz - Djelfa - - - Combined Cycle - Power Plant Familiarization | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | [7 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX | I01-118191 / PO 4200326726 | French | French | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 15 | 3 | 12 |  | 26-50 | 26-50 - Sonelgaz - Djelfa - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | 2026-01-12 | 2026-06-22 01:00 | [5 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | E-ELX10302 | Excitation - EX2100e Operation & Maintenance | Excitation | 5 | 8 | 0 | 12 |  | 26-49 | 26-49 - Sonelgaz - Djelfa - - - Excitation - EX2100e Operation & Maintenance | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | 2026-01-05 | 2026-01-28 | [5 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-48 | 26-48 - Sonelgaz - Djelfa - - - Gas Turbine - Maintenance | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | [7 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-47 | 26-47 - Sonelgaz - Djelfa - - - Gas Turbine - Operation | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | [7 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
Sonelgaz | Djelfa | - | EGM-99005-1CSTO-TRAINALL |  | IFF-007329-CC-101-TRX |  | French | French | NU | Abuobaida El Mansoor | Customer-Project Specific | Commissioning Familiarization | General | 10 | 10 | 0 | 12 |  | 26-46 | 26-46 - Sonelgaz - Djelfa - - - Commissioning Familiarization | Customer Site | ALGERIA | TAS-S | Djelfa | Customer Site | Sunday |  |  | 2027-03-07 |  | 0 | [7 empty] | Do not Schedule yet, new c/o request will be submitted by Mansoor 7Jul26 |  | Created | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  |  | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  |  | I01-116142 | German | German | NU | Anna Petrella | Customer-Project Specific | GT & ST Controls O&M w/ Distributed C/S On-the-Job Training | Controls | 10 | 10 | 0 | 12 |  | 26-45 | 26-45 - EnBW - Heilbronn - - - GT & ST Controls O&M w/ Distributed C/S On-the-Job Training | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-09-21 01:00 |  | 0 | 2026-11-23 | 2026-12-22 | 2027-04-19 01:00 | 2027-04-30 01:00 |  | 2027-03-08 | 2027-04-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Excitation O&M (GT only, ST only or Single Shaft CC Plant) OJT | Excitation | 10 | 10 | 0 | 12 |  | 26-44 | 26-44 - EnBW - Heilbronn - - - Excitation O&M (GT only, ST only or Single Shaft CC Plant) OJT | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-09-07 01:00 |  | 0 | 2027-02-01 | 2027-02-12 | 2027-04-05 01:00 | 2027-04-16 01:00 |  | 2027-04-05 01:00 | 2027-04-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Steam Turbine – Maintenance On-the-Job Training | Steam Turbine | 5 | 5 | 0 | 12 |  | 26-43 | 26-43 - EnBW - Heilbronn - - - Steam Turbine – Maintenance On-the-Job Training | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-08-31 01:00 |  | 0 | 2027-02-08 | 2027-02-12 | 2027-06-07 01:00 | 2027-06-11 01:00 |  | 2026-02-02 | 2027-06-07 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Gas Turbine – Maintenance On-the-Job Training | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-42 | 26-42 - EnBW - Heilbronn - - - Gas Turbine – Maintenance On-the-Job Training | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-08-24 01:00 |  | 0 | 2027-02-01 | 2027-02-05 | 2027-05-31 01:00 | 2027-06-04 01:00 |  | 2027-05-31 01:00 | 2027-05-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Steam Turbine – Operation On-the-Job Training | Steam Turbine | 9 | 10 | 1 | 12 |  | 26-41 | 26-41 - EnBW - Heilbronn - - - Steam Turbine – Operation On-the-Job Training | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-08-10 01:00 |  | 0 | 2027-01-25 | 2027-04-23 01:00 | 2027-05-18 01:00 | 2027-05-28 01:00 |  | 2027-05-18 01:00 | 2027-05-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Gas Turbine – Operation On-the-Job Training | Gas Turbine | 10 | 5 | 0 | 12 |  | 26-40 | 26-40 - EnBW - Heilbronn - - - Gas Turbine – Operation On-the-Job Training | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-07-27 01:00 |  | 0 | 2027-01-04 | 2027-01-08 | 2027-05-03 01:00 | 2027-05-14 01:00 |  | 2027-05-03 01:00 | 2027-05-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 2 | 12 |  | 26-39 | 26-39 - EnBW - Heilbronn - - - Balance of Plant - Operation (GE Integrated Systems) | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-07-06 01:00 |  | 0 | 2026-01-26 | 2026-01-30 | 2026-07-06 01:00 | 2026-07-10 01:00 |  | 2026-07-06 01:00 | 2026-07-06 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  |  | I01-116142 | German | German | NU | Anna Petrella | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-38 | 26-38 - EnBW - Heilbronn - - - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-06-29 01:00 |  | 0 | 2026-01-20 | 2026-01-23 | 2026-06-29 01:00 | 2026-07-03 01:00 |  | 2026-06-29 01:00 | 2026-06-29 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  |  | I01-116142 | German | German | NU | Anna Petrella | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 8 | 2 | 12 |  | 26-37 | 26-37 - EnBW - Heilbronn - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-06-15 01:00 |  | 0 | 2026-01-12 | 2026-01-16 | 2026-06-15 01:00 | 2026-06-26 01:00 |  | 2026-06-15 01:00 | 2026-06-15 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-36 | 26-36 - EnBW - Heilbronn - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-06-08 01:00 |  | 0 | 2026-01-12 | 2026-01-16 | 2026-06-08 01:00 | 2026-06-12 01:00 |  | 2026-06-08 01:00 | 2026-06-08 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Zakaria Al-Qawasmeh | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 26-35 | 26-35 - EnBW - Heilbronn - - - Steam Turbine - Maintenance | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-05-18 01:00 |  | 0 | 2026-03-09 01:00 | 2026-03-13 01:00 | 2026-05-18 01:00 | 2026-05-22 01:00 |  | 2026-05-18 01:00 | 2026-05-18 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Amin Houidi | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-34 | 26-34 - EnBW - Heilbronn - - - Gas Turbine - Maintenance | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-05-04 01:00 |  | 0 | 2025-11-17 | 2025-11-21 | 2026-05-04 01:00 | 2026-05-08 01:00 |  | 2026-05-04 01:00 | 2026-05-04 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 26-33 | 26-33 - EnBW - Heilbronn - - - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-04-27 01:00 |  | 0 | 2026-03-09 01:00 | 2026-03-13 01:00 | 2026-04-27 01:00 | 2026-05-01 01:00 |  | 2026-04-27 01:00 | 2026-04-27 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 |  | 26-32 | 26-32 - EnBW - Heilbronn - - - Steam Turbine - Operation | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-04-13 01:00 |  | 0 | 2026-03-02 | 2026-03-06 | 2026-04-13 01:00 | 2026-04-24 01:00 |  | 2026-04-13 01:00 | 2026-04-13 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 1 | 12 |  | 26-31 | 26-31 - EnBW - Heilbronn - - - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-03-30 01:00 |  | 0 | 2026-01-20 | 2026-01-22 | 2026-03-30 01:00 | 2026-04-01 01:00 |  | 2026-03-30 01:00 | 2026-03-30 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman;Hichem Mesli | Confirmed | 2026.0
EnBW | Heilbronn | - | EGM-00281-1CSTO-TRAINALL |  | EGM-00281-1CSTO-TRAINALL | G10-US-0001238 | German | German | NU | Anna Petrella | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-30 | 26-30 - EnBW - Heilbronn - - - Gas Turbine - Operation | Customer Site | GERMANY | TAS-N | Heilbronn | Customer Site | Monday |  |  | 2026-03-16 01:00 |  | 0 | 2025-11-03 | 2025-11-07 | 2026-03-16 01:00 | 2026-03-27 01:00 |  | 2026-03-16 01:00 | 2026-03-16 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli;Mohamed Abdelaziz | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117325 / PO 4102825960 | Portugese | Portugese | NU | Alejandra Saldana | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 |  | 26-23 | 26-23 - ENEVA - UTE Azulao - II - Balance of Plant - Operation (GE Integrated Systems) | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-05-21 01:00 |  | 0 | 2026-06-22 01:00 | 2026-06-26 01:00 | 2026-10-26 01:00 | 2026-10-30 01:00 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117325 / PO 4102825960 | Portugese | Portugese | NU | Alejandra Saldana | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 |  | 26-22 | 26-22 - ENEVA - UTE Azulao - II - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-05-18 01:00 |  | 0 | 2026-07-06 01:00 | 2026-07-08 01:00 | 2026-10-19 01:00 | 2026-10-21 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117325 / PO 4102825960 | Portugese | Portugese | NU | Alejandra Saldana | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 26-21 | 26-21 - ENEVA - UTE Azulao - II - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-05-11 01:00 |  | 0 | 2026-06-15 01:00 | 2026-06-18 01:00 | 2026-10-12 01:00 | 2026-10-16 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117023 / PO 4102825540 | Portugese | Portugese | NU | Alejandra Saldana | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 26-20 | 26-20 - ENEVA - UTE Azulao - II - Control System - Mark VIe Maintenance (Extended) | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-04-27 01:00 |  | 0 | 2026-02-10 | 2026-02-24 | 2026-08-10 01:00 | 2026-08-20 01:00 |  | 2026-08-10 01:00 | 2026-08-10 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117023 / PO 4102825540 | Portugese | Portugese | NU | Alejandra Saldana | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 |  | 26-19 | 26-19 - ENEVA - UTE Azulao - II - Control System - Mark VIe Distributed Control System Maintenance | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-04-20 01:00 |  | 0 | 2026-03-02 | 2026-03-06 | 2026-08-24 01:00 | 2026-08-28 01:00 |  | 2026-08-24 01:00 | 2026-08-24 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  | EGM-00319-1CSTO-TRAINALL |  | Portugese | Portugese | NU | Alejandra Saldana | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 26-18 | 26-18 - ENEVA - UTE Azulao - II - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-04-13 01:00 |  | 0 | 2026-05-11 01:00 | 2026-05-15 01:00 | 2026-08-31 01:00 | 2026-09-04 01:00 |  | 2026-08-31 01:00 | 2026-08-31 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117325 / PO 4102825960 | Portugese | Portugese | NU | Alejandra Saldana | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 2 | 12 |  | 26-17 | 26-17 - ENEVA - UTE Azulao - II - Steam Turbine - Maintenance | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-04-06 01:00 |  | 0 | 2026-03-23 01:00 | 2026-03-27 01:00 | 2026-10-05 01:00 | 2026-10-09 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  | EGM-00339-1CSTO-TRAINALL |  | Portugese | Portugese | NU | Alejandra Saldana | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 3 | 12 |  | 26-16 | 26-16 - ENEVA - UTE Azulao - II - Steam Turbine - Operation | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-03-23 01:00 |  | 0 | 2026-03-26 01:00 | 2026-04-10 01:00 | 2026-09-21 01:00 | 2026-10-01 01:00 |  | 2026-09-21 01:00 | 2026-09-21 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Amin Houidi | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117020 / PO 4102825083 | Portugese | Portugese | NU | Alejandra Saldana | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 26-15 | 26-15 - ENEVA - UTE Azulao - II - Gas Turbine - Maintenance | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-03-16 01:00 |  | 0 | 2026-02-23 | 2026-02-27 | 2026-08-03 01:00 | 2026-08-07 01:00 |  | 2026-08-03 01:00 | 2026-08-03 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
ENEVA | UTE Azulao | II | EGM-00339-1CSTO-TRAINALL |  |  | I01-117020 / PO 4102825083 | Portugese | Portugese | NU | Alejandra Saldana | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 26-14 | 26-14 - ENEVA - UTE Azulao - II - Gas Turbine - Operation | Customer Site | BRAZIL | TAS-N | Silves | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2026-02-09 | 2026-02-20 | 2026-07-20 01:00 | 2026-07-30 01:00 |  | 2026-07-20 01:00 | 2026-07-20 01:00 |  |  | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2026.0
LG&E | Mill Creek | - |  |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 26-6 | 26-6 - LG&E - Mill Creek - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2029-11-19 |  | 0 |  |  | 2029-11-19 | 2029-12-14 |  | 2029-11-19 | 2029-11-19 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2026.0
LG&E | Mill Creek | - |  |  | EGM-00419-1CSTO-TRAINALL | 4102900505 | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 2 | 6 |  | 26-5 | 26-5 - LG&E - Mill Creek - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2027-03-09 |  | 0 |  |  | 2026-08-27 01:00 | 2026-09-04 01:00 |  | 2026-08-27 01:00 | 2026-08-27 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Tentative | 2026.0
LG&E | Mill Creek | - |  |  | EGM-00419-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 59 | 0 | 0 | 0 |  | 26-4 | 26-4 - LG&E - Mill Creek - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2026-08-17 01:00 |  | 0 |  |  | 2026-06-01 01:00 | 2026-08-24 01:00 |  | 2026-06-01 01:00 | 2026-06-01 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2026.0
NYPA | Eugene W. Zeltmann Power Project | - | IFF-006245-GT-101-TRX |  | IFF-006245-GT-101-TRX |  | English | English | IB | Patrick Molumby | Customer-Project Specific | Combined Cycle -Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 |  | 25-660 | 25-660 - NYPA - Eugene W. Zeltmann Power Project - - - Combined Cycle -Operation (GE Integrated Systems) | Customer Site | UNITED STATES | TAS-N | Queens | Customer Site | Monday |  |  | 2026-02-23 |  | 0 | 2025-11-17 | 2025-11-21 | 2026-02-23 | 2026-02-27 |  | 2026-02-23 | 2026-02-23 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Tom Walsh | Confirmed | 2025.0
CPV | Woodbridge | - | IFF-006528-GT-101-OSX |  | IFF-006528-GT-101-OSX | I01-115462 / PO 4102794171 | English | English | IB | Patrick Molumby | E-CON13402 | Control System - Mark VIe Maintenance | Controls | 5 | 5 | 0 | 12 |  | 25-655 | 25-655 - CPV - Woodbridge - - - Control System - Mark VIe Maintenance | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-03-09 01:00 |  | 0 | 2026-02-02 | 2026-02-06 | 2026-03-09 01:00 | 2026-03-13 01:00 |  | 2026-03-09 01:00 | 2026-03-09 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar | Confirmed | 2025.0
BIRDSBORO POWER | Hill Top | - | IFF-007531-GT-101-TRX |  | IFF-007531-GT-101-TRX |  | English | English | IB | Patrick Molumby | SIM-RemoteTrng | Remote-Hosted Simulator Introductory Training | Simulator | 1 | 0 | 0 | 6 |  | 25-635 | 25-635 - BIRDSBORO POWER - Hill Top - - - Remote-Hosted Simulator Introductory Training | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2026-02-09 |  | 0 |  |  | 2026-03-16 01:00 | 2026-03-16 01:00 |  | 2026-03-16 01:00 | 2026-03-16 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Confirmed | 2025.0
BIRDSBORO POWER | Hill Top | - | IFF-007531-GT-101-TRX |  | IFF-007531-GT-101-TRX |  | English | English | IB | Patrick Molumby | SIM-RemotePrep | Remote-Hosted Simulator Preparation | Simulator | 3 | 0 | 0 | 0 |  | 25-634 | 25-634 - BIRDSBORO POWER - Hill Top - - - Remote-Hosted Simulator Preparation | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2026-02-02 |  | 0 |  |  | 2026-03-02 | 2026-03-04 |  | 2026-03-02 | 2026-03-02 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Confirmed | 2025.0
Ingredion | Ingredion-San Juan | - | IFF-005660-CC-101-TRX | 202815 | IFF-005660-CC-101-TRX |  | Spanish | Spanish | IB | Alejandra Saldana | E-AER10102 | Gas Turbine - LM2500 Package Maintenance | Aeroderivative | 5 | 5 | 0 | 12 |  | 25-632 | 25-632 - Ingredion - Ingredion-San Juan - - - Gas Turbine - LM2500 Package Maintenance | Customer Site | MEXICO | TAS-N | San Juan del Rio | Customer Site | Monday |  |  | 2026-02-09 |  | 0 | 2025-12-29 | 2025-12-31 | 2026-02-09 | 2026-02-13 |  | 2026-02-09 | 2026-02-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Mark Girling | Confirmed | 2025.0
Power Gen Corp | Territory Generation | - | EGM-00239-1CSTO-TRAINALL |  | EGM-00239-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-CON13602 | Control System - Woodward Operation, Maintenance & Troubleshooting | Controls | 5 | 5 | 0 | 12 |  | 25-621 | 25-621 - Power Gen Corp - Territory Generation - - - Control System - Woodward Operation, Maintenance & Troubleshooting | Customer Site | AUSTRALIA | TAS-N | Darwin | Customer Site | Monday |  |  | 2026-02-09 |  | 0 |  |  | 2026-03-16 01:00 | 2026-03-20 01:00 |  | 2026-03-16 01:00 | 2026-03-16 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | John Selman | Confirmed | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13701 | Control System - Control Server and Thin Client Familiarization | Controls | 2 | 0 | 0 | 6 |  | 25-616 | 25-616 - Invenergy - Invenergy St. Clair - - - Control System - Control Server and Thin Client Familiarization | Customer Site | CANADA | TAS-N | Corunna | Customer Site | Monday |  |  | 2026-01-12 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13413 | Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Controls | 5 | 0 | 0 | 12 |  | 25-615 | 25-615 - Invenergy - Invenergy St. Clair - - - Control System - Mark VIe Migration from Mark V (HMI on 1st day) | Customer Site | CANADA | TAS-N | Corunna | Customer Site | Monday |  |  | 2026-01-05 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | Customer-Project Specific | LS2100e LCI for Turbine Static Start | Excitation | 1 | 0 | 0 | 12 | 2 | 25-614 | 25-614 - Invenergy - Invenergy St. Clair - - - LS2100e LCI for Turbine Static Start - G2 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [7 empty] | Custom E-ELX30501 |  | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-ELX10304 | Excitation - EX2100e Platform Upgrade Maintenance | Excitation | 1 | 0 | 0 | 12 | 2 | 25-613 | 25-613 - Invenergy - Invenergy St. Clair - - - Excitation - EX2100e Platform Upgrade Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | Customer-Project Specific | LS2100e LCI for Turbine Static Start | Excitation | 1 | 0 | 0 | 12 | 1 | 25-612 | 25-612 - Invenergy - Invenergy St. Clair - - - LS2100e LCI for Turbine Static Start - G1 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [7 empty] | Custom E-ELX30501 |  | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-ELX10304 | Excitation - EX2100e Platform Upgrade Maintenance | Excitation | 1 | 0 | 0 | 12 | 1 | 25-611 | 25-611 - Invenergy - Invenergy St. Clair - - - Excitation - EX2100e Platform Upgrade Maintenance - G1 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON11901 | Control System - DLN 2.6+ Standard Combustor | Controls | 1 | 0 | 0 | 12 | 2 | 25-610 | 25-610 - Invenergy - Invenergy St. Clair - - - Control System - DLN 2.6+ Standard Combustor - G2 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON23406 | Control System - OpFlex Enhanced Transient Stability with AutoTune DX & Cold Day Performance Operation | Controls | 1 | 0 | 0 | 12 | 2 | 25-609 | 25-609 - Invenergy - Invenergy St. Clair - - - Control System - OpFlex Enhanced Transient Stability with AutoTune DX & Cold Day Performance Operation - G2 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13406 | Control System - Mark VIe HMI | Controls | 1 | 0 | 0 | 12 | 2 | 25-608 | 25-608 - Invenergy - Invenergy St. Clair - - - Control System - Mark VIe HMI - G2 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON11901 | Control System - DLN 2.6+ Standard Combustor | Controls | 1 | 0 | 0 | 12 | 1 | 25-607 | 25-607 - Invenergy - Invenergy St. Clair - - - Control System - DLN 2.6+ Standard Combustor - G1 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON23406 | Control System - OpFlex Enhanced Transient Stability with AutoTune DX & Cold Day Performance Operation | Controls | 1 | 0 | 0 | 12 | 1 | 25-606 | 25-606 - Invenergy - Invenergy St. Clair - - - Control System - OpFlex Enhanced Transient Stability with AutoTune DX & Cold Day Performance Operation - G1 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Invenergy | Invenergy St. Clair | - |  |  |  |  | English | English | IB | Patrick Molumby | E-CON13406 | Control System - Mark VIe HMI | Controls | 1 | 1 | 0 | 12 | 1 | 25-605 | 25-605 - Invenergy - Invenergy St. Clair - - - Control System - Mark VIe HMI - G1 | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-01 |  | 0 |  |  | 2026-01-05 | 2026-01-05 |  | 2026-01-05 | 2026-01-05 |  |  | Created | 2025-11-07 | US Workweek and Holidays |  | Cancelled | 2025.0
Alliant | Sheboygan Falls | - | IFF-904438-GT-101-TRX |  |  | I01-113823 / PO 4102655468 | English | English | IB | Patrick Molumby | E-GAS22201 | Gas Turbine - Operation F-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-593 | 25-593 - Alliant - Sheboygan Falls - - - Gas Turbine - Operation F-Class (Advanced) | Customer Site | UNITED STATES | TAS-N | Sheboygan Falls | Customer Site | Monday |  |  | 2026-01-26 |  | 0 |  |  | 2026-01-26 | 2026-01-30 |  | 2026-01-26 | 2026-01-26 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2025.0
OMAN INDIA FERTILISER SAOC | Plant Sur | - | IFF-004832-CC-101-TRX |  | IFF-004832-CC-101-TRX |  | English | English | IB | Abuobaida El Mansoor | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 25-591 | 25-591 - OMAN INDIA FERTILISER SAOC - Plant Sur - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Learning Center | SWITZERLAND | TAS-N | Birr | Birr Learning Center | Monday |  |  | 2026-07-27 01:00 |  | 0 | 2026-05-18 01:00 | 2026-05-22 01:00 | 2026-11-16 | 2026-11-20 |  | 2026-11-16 | 2026-11-16 |  | Yes | Created | 2025-11-07 | Birr Workweek and Holidays | Zakaria Al-Qawasmeh | Confirmed | 2025.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX30501 | Excitation - LS2100e LCI for Turbine Static Start | Excitation | 2 | 2 | 0 | 12 | 1 | 25-587 | 25-587 - TPC - Taichung - New GTCC - Excitation - LS2100e LCI for Turbine Static Start - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2026-05-28 01:00 |  | 0 | 2026-05-04 01:00 | 2026-05-05 01:00 | 2027-06-07 01:00 | 2027-06-08 01:00 |  | 2026-07-23 01:00 | 2027-06-07 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2025.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GEN10403 | Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Generator | 5 | 5 | 0 | 12 | 1 | 25-586 | 25-586 - TPC - Taichung - New GTCC - Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3103 Rodeo Room | 2026-05-21 01:00 |  | 0 | 2026-12-28 | 2026-12-31 | 2027-05-28 01:00 | 2027-06-04 01:00 |  | 2026-08-13 01:00 | 2027-05-28 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2025.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Generator - Hydrogen Cooled Auxiliaries Maintenance | Generator | 3 | 3 | 0 | 12 | 1 | 25-585 | 25-585 - TPC - Taichung - New GTCC - Generator - Hydrogen Cooled Auxiliaries Maintenance - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3103 Rodeo Room | 2026-05-18 01:00 |  | 0 | 2026-12-21 | 2026-12-23 | 2027-06-09 01:00 | 2027-06-11 01:00 |  | 2026-08-10 01:00 | 2027-06-09 01:00 | Formerly E-GEN10903 | Yes | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Tentative | 2025.0
EnBW | Altbach | - | EGM-00270-1CSTO-TRAINALL |  |  | I01-118139 / PO 4102845578 | German | German | NU | Anna Petrella | Customer-Project Specific | GT & ST Controls O&M w/ Distributed C/S On-the-Job Training) | Controls | 10 | 10 | 0 | 12 |  | 25-581 | 25-581 - EnBW - Altbach - - - GT & ST Controls O&M w/ Distributed C/S On-the-Job Training) | Customer Site | GERMANY | TAS-N | Altbach | Customer Site | Monday |  |  | 2026-03-16 01:00 |  | 0 | 2026-09-14 01:00 | 2026-09-18 01:00 | 2026-10-26 01:00 | 2026-11-06 |  | 2026-10-26 01:00 | 2026-10-26 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Confirmed | 2025.0
EnBW | Altbach | - | EGM-00270-1CSTO-TRAINALL |  | EGM-00270-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Excitation O&M (GT only, ST only or Single Shaft CC Plant) OJT | Excitation | 10 | 10 | 0 | 12 |  | 25-580 | 25-580 - EnBW - Altbach - - - Excitation O&M (GT only, ST only or Single Shaft CC Plant) OJT | Customer Site | GERMANY | TAS-N | Altbach | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2026-02-23 | 2026-02-27 | 2026-10-12 01:00 | 2026-10-23 01:00 |  | 2026-10-12 01:00 | 2026-10-12 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2025.0
EnBW | Altbach | - | EGM-00270-1CSTO-TRAINALL |  | EGM-00270-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Steam Turbine – Maintenance On-the-Job Training | Steam Turbine | 5 | 5 | 0 | 12 |  | 25-579 | 25-579 - EnBW - Altbach - - - Steam Turbine – Maintenance On-the-Job Training | Customer Site | GERMANY | TAS-N | Altbach | Customer Site | Monday |  |  | 2026-02-23 |  | 0 | 2025-12-01 | 2025-12-05 | 2027-01-18 | 2027-01-22 |  | 2027-01-18 | 2027-01-18 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2025.0
EnBW | Altbach | - | EGM-00270-1CSTO-TRAINALL |  | EGM-00270-1CSTO-TRAINALL | I01-110149 | German | German | NU | Anna Petrella | Customer-Project Specific | Gas Turbine – Maintenance On-the-Job Training | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-578 | 25-578 - EnBW - Altbach - - - Gas Turbine – Maintenance On-the-Job Training | Customer Site | GERMANY | TAS-N | Altbach | Customer Site | Monday |  |  | 2026-02-16 |  | 0 | 2025-11-17 | 2025-11-21 | 2027-01-11 | 2027-01-15 |  | 2027-01-11 | 2027-01-11 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2025.0
EnBW | Altbach | - | EGM-00270-1CSTO-TRAINALL |  | EGM-00270-1CSTO-TRAINALL |  | German | German | NU | Anna Petrella | Customer-Project Specific | Steam Turbine – Operation On-the-Job Training | Steam Turbine | 10 | 10 | 2 | 12 |  | 25-577 | 25-577 - EnBW - Altbach - - - Steam Turbine – Operation On-the-Job Training | Customer Site | GERMANY | TAS-N | Altbach | Customer Site | Monday |  |  | 2026-02-02 |  | 0 | 2026-01-05 | 2026-10-23 01:00 | 2026-12-07 | 2026-12-18 |  | 2026-12-07 | 2026-12-07 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Domingo Aleman | Confirmed | 2025.0
EnBW | Altbach | - | EGM-00270-1CSTO-TRAINALL |  |  | I01-117347 / PO 4102829654 | German | German | NU | Anna Petrella | E-GAS12004 | Gas Turbine - Operation-On-the-Job Training (OJT) | Gas Turbine | 10 | 10 | 0 | 12 |  | 25-576 | 25-576 - EnBW - Altbach - - - Gas Turbine - Operation-On-the-Job Training (OJT) | Customer Site | GERMANY | TAS-N | Altbach | Customer Site | Monday |  |  | 2026-01-19 |  | 0 | 2025-11-10 | 2026-06-26 01:00 | 2026-11-09 | 2026-11-20 |  | 2026-11-09 | 2026-11-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2025.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX30501 | Excitation - LS2100e LCI for Turbine Static Start | Excitation | 2 | 2 | 0 | 12 | 2 | 25-553 | 25-553 - TPC - Hsinta - - - Excitation - LS2100e LCI for Turbine Static Start - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1227 Brown Room | 2026-04-30 01:00 |  | 0 | 2026-06-30 01:00 | 2026-07-01 01:00 | 2026-10-15 01:00 | 2026-10-16 01:00 |  | 2026-10-15 01:00 | 2026-10-15 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2025.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GEN10403 | Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems | Generator | 5 | 5 | 0 | 12 | 2 | 25-552 | 25-552 - TPC - Hsinta - - - Generator - Water & Hydrogen Cooled Operation & Maintenance of Auxiliary Systems - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1227 Brown Room | 2026-04-23 01:00 |  | 0 | 2026-08-24 01:00 | 2026-08-28 01:00 | 2026-10-08 01:00 | 2026-10-14 01:00 |  | 2026-10-08 01:00 | 2026-10-08 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2025.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | Customer-Project Specific | Generator - Hydrogen Cooled Auxiliaries Maintenance | Generator | 3 | 3 | 0 | 12 | 2 | 25-551 | 25-551 - TPC - Hsinta - - - Generator - Hydrogen Cooled Auxiliaries Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1227 Brown Room | 2026-04-20 01:00 |  | 0 | 2026-08-31 01:00 | 2026-09-02 01:00 | 2026-10-05 01:00 | 2026-10-07 01:00 |  | 2026-10-05 01:00 | 2026-10-05 01:00 | Formerly E-GEN10903 | Yes | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Confirmed | 2025.0
Homer City | Homer City | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 25-532 | 25-532 - Homer City - Homer City - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2029-12-17 |  | 0 |  |  | 2029-12-17 | 2030-01-11 |  | 2029-12-17 | 2029-12-17 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2025.0
Homer City | Homer City | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 2 | 6 |  | 25-531 | 25-531 - Homer City - Homer City - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2028-06-01 01:00 |  | 0 |  |  | 2028-06-01 01:00 | 2028-06-09 01:00 |  | 2028-06-01 01:00 | 2028-06-01 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Yegor Spencer | Tentative | 2025.0
Homer City | Homer City | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-DevCC | OTS Simulator Development & Testing - CC Sim | Simulator | 44 | 0 | 0 | 0 |  | 25-530 | 25-530 - Homer City - Homer City - - - OTS Simulator Development & Testing - CC Sim | Remote | UNITED STATES | TAS-N | - | Distance Learning | Monday |  |  | 2027-11-15 |  | 0 |  |  | 2027-11-15 | 2028-01-13 |  | 2027-11-15 | 2027-11-15 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Tentative | 2025.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 5 | 0 | 12 | 1 | 25-519 | 25-519 - TPC - Taichung - New GTCC - Excitation - Generator Excitation, Protection and Static Starter Introduction - G1 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1226 Tesla Room | 2026-06-01 01:00 |  | 0 | 2026-01-20 | 2026-01-23 | 2027-06-14 01:00 | 2027-06-25 01:00 |  | 2026-07-27 01:00 | 2027-06-14 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Tentative | 2025.0
TPC | Hsinta | - | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 10 | 5 | 0 | 12 | 2 | 25-507 | 25-507 - TPC - Hsinta - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1225 Turing Room | 2026-05-04 01:00 |  | 0 | 2026-08-10 01:00 | 2026-08-14 01:00 | 2026-10-19 01:00 | 2026-10-30 01:00 |  | 2026-10-19 01:00 | 2026-10-19 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2025.0
HARBIN ELECTRIC INTERNATIONAL COMPANY LIMITED | Bhikki CCPP | MYA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | Combined Cycle Simulation - Week2 | Combined Cycle | 6 | 0 | 0 | 12 |  | 25-491 | 25-491 - HARBIN ELECTRIC INTERNATIONAL COMPANY LIMITED - Bhikki CCPP - MYA - Combined Cycle Simulation - Week2 | Remote | PAKISTAN | TAS-N | - | Distance Learning | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2025.0
HARBIN ELECTRIC INTERNATIONAL COMPANY LIMITED | Bhikki CCPP | MYA |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | Combined Cycle Simulation - Week1 | Combined Cycle | 5 | 0 | 0 | 12 |  | 25-490 | 25-490 - HARBIN ELECTRIC INTERNATIONAL COMPANY LIMITED - Bhikki CCPP - MYA - Combined Cycle Simulation - Week1 | Customer Site | PAKISTAN | TAS-S | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2025.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL |  | English | English | IB | Gavin Yoong | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 | 2 | 25-381 | 25-381 - TPC - Taichung - New GTCC - Control System - Mark VIe Distributed Control System Maintenance - G2 | Remote | UNITED STATES | TAS-M | - | Distance Learning | Monday |  |  | 2026-01-05 |  | 0 |  |  | 2026-01-05 | 2026-01-09 |  | 2026-01-05 | 2026-01-05 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Bharat Vispara | Confirmed | 2025.0
Horseshoe Lake | Horseshoe Lake | - | WBS EGM-00362-1CSTO-TRAINALL |  | WBS EGM-00362-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 25-184 | 25-184 - Horseshoe Lake - Horseshoe Lake - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday |  |  | 2026-03-09 01:00 |  | 0 | 2026-02-02 | 2026-02-06 | 2026-05-04 01:00 | 2026-05-08 01:00 |  | 2026-05-04 01:00 | 2026-05-04 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2025.0
Horseshoe Lake | Horseshoe Lake | - | WBS EGM-00362-1CSTO-TRAINALL |  |  | I01-116774 / PO 4102785569 | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 13 | 0 | 12 |  | 25-183 | 25-183 - Horseshoe Lake - Horseshoe Lake - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2026-01-21 | 2026-02-20 | 2026-03-30 01:00 | 2026-04-10 01:00 |  | 2026-03-30 01:00 | 2026-03-30 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2025.0
Horseshoe Lake | Horseshoe Lake | - | WBS EGM-00362-1CSTO-TRAINALL |  |  | I01-115018 / PO 4102785566 | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-182 | 25-182 - Horseshoe Lake - Horseshoe Lake - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday |  |  | 2026-02-23 |  | 0 | 2025-12-17 | 2025-12-23 | 2026-03-23 01:00 | 2026-03-27 01:00 |  | 2026-03-23 01:00 | 2026-03-23 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2025.0
Horseshoe Lake | Horseshoe Lake | - | WBS EGM-00362-1CSTO-TRAINALL |  |  | I01-115018 / PO 4102785566 | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 25-181 | 25-181 - Horseshoe Lake - Horseshoe Lake - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | Harrah | Customer Site | Monday |  |  | 2026-02-09 |  | 0 | 2025-11-17 | 2025-12-16 | 2026-03-09 01:00 | 2026-03-20 01:00 |  | 2026-03-09 01:00 | 2026-03-09 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Confirmed | 2025.0
Graphic Packaging | Graphic Packaging | - | EGM-00426-1CSTO-TRAINALL |  | EGM-00426-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 |  | 25-171 | 25-171 - Graphic Packaging - Graphic Packaging - - - Excitation - Generator Excitation, Protection and Static Starter Introduction | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2025-12-29 | 2026-01-02 | 2026-03-23 01:00 | 2026-03-26 01:00 |  | 2026-03-23 01:00 | 2026-03-23 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Joe Mcandrews | Confirmed | 2025.0
Graphic Packaging | Graphic Packaging | - | EGM-00426-1CSTO-TRAINALL |  | EGM-00426-1CSTO-TRAINALL | I01-115235 / PO 4102793873 | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 9 | 10 | 1 | 12 |  | 25-170 | 25-170 - Graphic Packaging - Graphic Packaging - - - Control System - Mark VIe Maintenance (Extended) | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-02-16 |  | 0 | 2025-12-08 | 2026-01-28 | 2026-02-16 | 2026-02-26 |  | 2026-02-16 | 2026-02-16 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Bharat Vispara | Confirmed | 2025.0
Graphic Packaging | Graphic Packaging | - | EGM-00426-1CSTO-TRAINALL |  | EGM-00426-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 4 | 5 | 1 | 12 |  | 25-169 | 25-169 - Graphic Packaging - Graphic Packaging - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-02-09 |  | 0 | 2025-12-15 | 2025-12-19 | 2026-02-09 | 2026-02-12 |  | 2026-02-09 | 2026-02-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2025.0
Graphic Packaging | Graphic Packaging | - | EGM-00426-1CSTO-TRAINALL |  | EGM-00426-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 |  | 25-168 | 25-168 - Graphic Packaging - Graphic Packaging - - - Gas Turbine - Operation | Customer Site | UNITED STATES | TAS-N | - | Customer Site | Monday |  |  | 2026-01-26 |  | 0 | 2025-11-17 | 2025-11-28 | 2026-01-26 | 2026-02-05 |  | 2026-01-26 | 2026-01-26 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2025.0
Korea Western Power | Gong Ju CCPP | - | EGM-00425-1CSTO-TRAINALL |  | EGM-00425-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 10 | 5 | 0 | 12 | 2 | 25-165 | 25-165 - Korea Western Power - Gong Ju CCPP - - - Gas Turbine - Maintenance - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1235 Curtis Room | 2026-03-02 |  | 0 | 2026-01-12 | 2026-01-16 | 2026-03-02 | 2026-03-13 01:00 |  | 2026-03-02 | 2026-03-02 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2025.0
Korea Western Power | Gong Ju CCPP | - | EGM-00425-1CSTO-TRAINALL |  | EGM-00425-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 15 | 10 | 0 | 12 | 2 | 25-164 | 25-164 - Korea Western Power - Gong Ju CCPP - - - Gas Turbine - Operation - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 1233 Adams Room | 2026-02-09 |  | 0 | 2026-01-05 | 2026-01-09 | 2026-02-09 | 2026-02-27 |  | 2026-02-09 | 2026-02-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2025.0
Korea Western Power | Gong Ju CCPP | - | EGM-00425-1CSTO-TRAINALL |  | EGM-00425-1CSTO-TRAINALL |  | English | English | NU | Gavin Yoong | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 2 | 25-163 | 25-163 - Korea Western Power - Gong Ju CCPP - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-02-23 |  | 0 | 2025-12-15 | 2025-12-17 | 2026-02-23 | 2026-02-27 |  | 2026-02-23 | 2026-02-23 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2025.0
Korea Western Power | Gong Ju CCPP | - | EGM-00425-1CSTO-TRAINALL |  |  | I01-111498 / PO 4102723306 | English | English | NU | Gavin Yoong | Customer-Project Specific | Control System - Mark VIe On-the-Job Training (OJT) | Controls | 5 | 5 | 0 | 12 | 2 | 25-162 | 25-162 - Korea Western Power - Gong Ju CCPP - - - Control System - Mark VIe On-the-Job Training (OJT) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-01-12 |  | 0 |  |  | 2026-03-09 01:00 | 2026-03-13 01:00 |  | 2026-03-09 01:00 | 2026-03-09 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2025.0
Korea Western Power | Gong Ju CCPP | - | EGM-00425-1CSTO-TRAINALL |  |  | I01-111498 / PO 4102723306 | English | English | NU | Gavin Yoong | E-CON23404 | Control System - Mark VIe Troubleshooting (Advanced) | Controls | 5 | 5 | 0 | 12 | 2 | 25-161 | 25-161 - Korea Western Power - Gong Ju CCPP - - - Control System - Mark VIe Troubleshooting (Advanced) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-03-02 |  | 0 |  |  | 2026-03-02 | 2026-03-06 |  | 2026-03-02 | 2026-03-02 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2025.0
Korea Western Power | Gong Ju CCPP | - | EGM-00425-1CSTO-TRAINALL |  |  | I01-111498 / PO 4102723306 | English | English | NU | Gavin Yoong | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 2 | 25-160 | 25-160 - Korea Western Power - Gong Ju CCPP - - - Control System - Mark VIe Maintenance (Extended) - G2 | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3102 Bush Room | 2026-02-09 |  | 0 |  |  | 2026-02-09 | 2026-02-20 |  | 2026-02-09 | 2026-02-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Gerardo Gonzalez | Confirmed | 2025.0
Alliant | Sheboygan Falls | - | IFF-904438-GT-101-TRX |  | IFF-904438-GT-101-TRX | I01-114575 / PO 4102777501 | English | English | IB | Patrick Molumby | E-CON11901 | Control System - DLN 2.6+ Standard Combustor | Controls | 2 | 3 | 1 | 12 |  | 25-148 | 25-148 - Alliant - Sheboygan Falls - - - Control System - DLN 2.6+ Standard Combustor | Customer Site | UNITED STATES | TAS-N | Sheboygan Falls | Customer Site | Monday |  |  | 2026-01-12 |  | 0 | 2025-11-13 | 2026-01-06 | 2026-01-12 | 2026-01-13 |  | 2026-01-12 | 2026-01-12 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2025.0
Alliant | Sheboygan Falls | - | IFF-904438-GT-101-TRX |  | IFF-904438-GT-101-TRX |  | English | English | IB | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-147 | 25-147 - Alliant - Sheboygan Falls - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Sheboygan Falls | Customer Site | Monday |  |  | 2026-01-26 |  | 0 | 2025-11-03 | 2025-11-07 | 2026-01-20 | 2026-01-23 |  | 2026-01-20 | 2026-01-20 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2025.0
Alliant | Neenah | - | IFF-904438-GT-101-TRX |  | IFF-904438-GT-101-TRX | I01-114575 / PO 4102777501 | English | English | IB | Patrick Molumby | E-CON11901 | Control System - DLN 2.6+ Standard Combustor | Controls | 2 | 3 | 1 | 12 |  | 25-145 | 25-145 - Alliant - Neenah - - - Control System - DLN 2.6+ Standard Combustor | Customer Site | UNITED STATES | TAS-N | Neenah | Customer Site | Monday |  |  | 2026-01-05 |  | 0 | 2025-11-10 | 2026-01-05 | 2026-01-08 | 2026-01-09 |  | 2026-01-08 | 2026-01-08 |  | Yes | Created | 2025-11-06 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2025.0
Alliant | Neenah | - | IFF-904438-GT-101-TRX |  | IFF-904438-GT-101-TRX |  | English | English | IB | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-144 | 25-144 - Alliant - Neenah - - - Gas Turbine - Maintenance | Customer Site | UNITED STATES | TAS-N | Neenah | Customer Site | Monday |  |  | 2026-01-19 |  | 0 |  |  | 2026-01-26 | 2026-01-30 |  | 2026-01-26 | 2026-01-26 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Steve Brasseaux | Confirmed | 2025.0
ENKA KIRKLARELI ELEKTRIK URETIM A.S. | Verbena | - | EGM-00423-1CSTO-TRAINALL |  | EGM-00423-1CSTO-TRAINALL | G10-US-0001238 | English | English | NU | Anna Petrella | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 |  | 25-136 | 25-136 - ENKA KIRKLARELI ELEKTRIK URETIM A.S. - Verbena - - - Steam Turbine - Maintenance | Customer Site | TURKEY | TAS-N | ERIKLERYURDU | Customer Site | Monday |  |  | 2026-01-05 |  | 0 |  |  | 2026-01-05 | 2026-01-09 |  | 2026-01-05 | 2026-01-05 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Tom Walsh | Confirmed | 2025.0
ENKA KIRKLARELI ELEKTRIK URETIM A.S. | Verbena | - | EGM-00423-1CSTO-TRAINALL |  | EGM-00423-1CSTO-TRAINALL | I01-107501 | English | English | NU | Anna Petrella | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-134 | 25-134 - ENKA KIRKLARELI ELEKTRIK URETIM A.S. - Verbena - - - Gas Turbine - Maintenance | Customer Site | TURKEY | TAS-N | ERIKLERYURDU | Customer Site | Monday |  |  | 2026-01-12 |  | 0 |  |  | 2026-01-12 | 2026-01-16 |  | 2026-01-12 | 2026-01-12 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Agustin Collado | Confirmed | 2025.0
SEC | PP14 | - |  |  |  |  | English | English | IB | Abuobaida El Mansoor | E-GEN10901 | Generator - Hydrogen Cooling System Operation & Maintenance | Generator | 3 | 3 | 1 | 12 |  | 25-82 | 25-82 - SEC - PP14 - - - Generator - Hydrogen Cooling System Operation & Maintenance | Customer Site | SAUDI ARABIA | TAS-M | Riyadh | Customer Site | Monday |  |  | 2026-01-11 |  | 0 |  |  | 2027-02-07 | 2027-02-09 |  | 2027-02-07 | 2027-02-07 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Hichem Mesli | Tentative | 2025.0
SEC | PP14 | - | 7903062757 |  |  | I01-119176 / PO 7903062757 | English | English | IB | Abuobaida El Mansoor | E-GAS22201 | Gas Turbine - Operation F-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 |  | 25-81 | 25-81 - SEC - PP14 - - - Gas Turbine - Operation F-Class (Advanced) | Customer Site | SAUDI ARABIA | TAS-M | Riyadh | Customer Site | Monday |  |  | 2026-01-04 |  | 0 | 2026-06-15 01:00 | 2026-06-18 01:00 | 2026-08-30 01:00 | 2026-09-03 01:00 |  | 2026-08-30 01:00 | 2026-08-30 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Tim Taylor | Resourcing In Progress | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | G10-US-0001238 | English | English | NU | Patrick Molumby | E-CON13410 | Control System - Mark VIe Distributed Control System Maintenance | Controls | 5 | 5 | 0 | 12 | 2 | 25-70 | 25-70 - SECI - Shady Hills Energy Center - - - Control System - Mark VIe Distributed Control System Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-03-30 01:00 |  | 0 | 2026-02-04 | 2026-03-03 | 2026-03-30 01:00 | 2026-04-03 01:00 |  | 2026-03-30 01:00 | 2026-03-30 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Bharat Vispara;Gopinath Kumar;Isaiah Mason | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | I01-115458 / PO 4102793870 | English | English | NU | Patrick Molumby | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 | 2 | 25-68 | 25-68 - SECI - Shady Hills Energy Center - - - Control System - Mark VIe Maintenance (Extended) - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-03-16 01:00 |  | 0 | 2025-12-22 | 2025-12-30 | 2026-03-16 01:00 | 2026-03-27 01:00 |  | 2026-03-16 01:00 | 2026-03-16 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Gopinath Kumar;Isaiah Mason | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS22501 | Gas Turbine - Operation H-Class (Advanced) | Gas Turbine | 5 | 5 | 0 | 12 | 2 | 25-66 | 25-66 - SECI - Shady Hills Energy Center - - - Gas Turbine - Operation H-Class (Advanced) - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-03-09 01:00 |  | 0 | 2026-01-20 | 2026-01-23 | 2026-03-09 01:00 | 2026-03-13 01:00 |  | 2026-03-09 01:00 | 2026-03-09 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-ELX11501 | Excitation - Generator Excitation, Protection and Static Starter Introduction | Excitation | 5 | 5 | 0 | 12 | 2 | 25-64 | 25-64 - SECI - Shady Hills Energy Center - - - Excitation - Generator Excitation, Protection and Static Starter Introduction - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-03-02 |  | 0 | 2026-01-05 | 2026-01-09 | 2026-03-02 | 2026-03-06 |  | 2026-03-02 | 2026-03-02 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Willy Bueno | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | I01-110760 | English | English | NU | Patrick Molumby | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 0 | 12 | 2 | 25-62 | 25-62 - SECI - Shady Hills Energy Center - - - Combined Cycle - Operation (GE Integrated Systems) - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-02-23 |  | 0 | 2026-02-02 | 2026-02-06 | 2026-02-23 | 2026-02-27 |  | 2026-02-23 | 2026-02-23 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | I01-110760 | English | English | NU | Patrick Molumby | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | HRSG | 3 | 3 | 0 | 12 | 2 | 25-60 | 25-60 - SECI - Shady Hills Energy Center - - - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-02-16 |  | 0 | 2025-11-13 | 2025-11-17 | 2026-02-17 | 2026-02-19 |  | 2026-02-17 | 2026-02-17 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | I01-110760 | English | English | NU | Patrick Molumby | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 5 | 0 | 12 | 2 | 25-58 | 25-58 - SECI - Shady Hills Energy Center - - - Steam Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-02-09 |  | 0 | 2025-12-15 | 2025-12-19 | 2026-02-09 | 2026-02-13 |  | 2026-02-09 | 2026-02-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Dave Miller | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | I01-115461 / PO 4102793867 | English | English | NU | Patrick Molumby | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 10 | 0 | 12 | 2 | 25-56 | 25-56 - SECI - Shady Hills Energy Center - - - Steam Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-01-26 |  | 0 | 2026-01-12 | 2026-01-16 | 2026-01-26 | 2026-02-06 |  | 2026-01-26 | 2026-01-26 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Donald Hopkins | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL | I01-110760 | English | English | NU | Patrick Molumby | E-GAS12002 | Gas Turbine - Maintenance | Gas Turbine | 5 | 5 | 0 | 12 | 2 | 25-54 | 25-54 - SECI - Shady Hills Energy Center - - - Gas Turbine - Maintenance - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-01-19 |  | 0 | 2025-11-10 | 2025-11-12 | 2026-04-06 01:00 | 2026-04-10 01:00 |  | 2026-04-06 01:00 | 2026-04-06 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2025.0
SECI | Shady Hills Energy Center | - | EGM-00359-1CSTO-TRAINALL |  | EGM-00359-1CSTO-TRAINALL |  | English | English | NU | Patrick Molumby | E-GAS12001 | Gas Turbine - Operation | Gas Turbine | 10 | 10 | 0 | 12 | 2 | 25-52 | 25-52 - SECI - Shady Hills Energy Center - - - Gas Turbine - Operation - G2 | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-01-05 |  | 0 |  |  | 2026-01-12 | 2026-01-23 |  | 2026-01-12 | 2026-01-12 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Coy Jackson | Confirmed | 2025.0
Seminole | Shady Hills | - |  |  |  |  | English | English | NU | Patrick Molumby | SIM-CODRefCC | OTS Post-COD Refresh - CC Sim | Simulator | 20 | 0 | 0 | 0 |  | 25-7 | 25-7 - Seminole - Shady Hills - - - OTS Post-COD Refresh - CC Sim | Remote | UNITED STATES | TAS-N | Pasco County | Distance Learning | Monday |  |  | 2026-11-15 |  | 0 |  |  | 2026-11-15 | 2026-12-14 |  | 2026-11-15 | 2026-11-15 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Charles Wall | Confirmed | 2025.0
Seminole | Shady Hills | - |  |  |  | I01-118777 / PO 4102831358 | English | English | NU | Patrick Molumby | SIM-TrngSAT | Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Simulator | 7 | 0 | 1 | 6 |  | 25-6 | 25-6 - Seminole - Shady Hills - - - Simulator Introductory Training & Site Acceptance Test (SAT) - Simulation Server | Customer Site | UNITED STATES | TAS-N | Pasco County | Customer Site | Monday |  |  | 2026-04-17 01:00 |  | 0 |  |  | 2026-05-15 01:00 | 2026-05-23 01:00 |  | 2026-05-15 01:00 | 2026-05-15 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Confirmed | 2025.0
TPC | Taichung | New GTCC | EGM-00166-1CSTO-TRAINALL |  | EGM-00166-1CSTO-TRAINALL | I01-111005 | English | English | IB | Gavin Yoong | E-CON11901 | Control System - DLN 2.6+ Standard Combustor | Controls | 2 | 2 | 0 | 12 |  | 24-544 | 24-544 - TPC - Taichung - New GTCC - Control System - DLN 2.6+ Standard Combustor | Remote | TAIWAN REPUBLIC OF CHINA | TAS-M | - | Distance Learning | Monday |  |  | 2026-02-25 |  | 0 | 2026-01-20 | 2026-02-09 | 2026-02-25 | 2026-02-26 |  | 2026-02-25 | 2026-02-25 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2024.0
STEG | BIR MCHERGA | - |  |  |  |  | English | English | IB | Abuobaida El Mansoor | SIM-RemoteTrng | Remote-Hosted Simulator Introductory Training | Simulator | 1 | 0 | 0 | 6 |  | 24-469 | 24-469 - STEG - BIR MCHERGA - - - Remote-Hosted Simulator Introductory Training | Remote | TUNISIA | TAS-N | - | Distance Learning | Monday |  |  | 2026-01-01 |  | 0 |  |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  | 2026-09-28 01:00 | 2026-09-28 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Aaron Hayes | Tentative | 2024.0
STEG | BIR MCHERGA | - |  |  |  |  | English | English | IB | Abuobaida El Mansoor | SIM-RemotePrep | Remote-Hosted Simulator Preparation | Simulator | 6 | 0 | 0 | 0 |  | 24-468 | 24-468 - STEG - BIR MCHERGA - - - Remote-Hosted Simulator Preparation | Remote | TUNISIA | TAS-N | - | Distance Learning | Monday |  |  | 2026-01-01 |  | 0 |  |  | 2026-09-14 01:00 | 2026-09-21 01:00 |  | 2026-09-14 01:00 | 2026-09-14 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Aaron Hayes | Tentative | 2024.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | Control System - ALSPA HMI Operation | Controls | 3 | 0 | 0 | 12 |  | 24-467 | 24-467 - Yanbu - III - - - Control System - ALSPA HMI Operation | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [7 empty] | formerly E-CON10401 |  | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2024.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 0 | 0 | 12 |  | 24-466 | 24-466 - Yanbu - III - - - Steam Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2024.0
STM | Pakistan Navy | MILGEM Corvette Project - Ship Set 4 Crew | G10-US-0001319-001-00247 |  | G10-US-0001319-001-00247 |  | English | English | NU | Patrick Molumby | E-AER10108 | Gas Turbine - LM2500 Borescope Inspection | Aeroderivative | 2 | 2 | 0 | 8 |  | 23-542 | 23-542 - STM - Pakistan Navy - MILGEM Corvette Project - Ship Set 4 Crew - Gas Turbine - LM2500 Borescope Inspection | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-10-01 01:00 |  | 0 | 2027-04-23 01:00 | 2027-04-23 01:00 | 2027-07-29 01:00 | 2027-07-30 01:00 |  | 2027-07-29 01:00 | 2027-07-29 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Richard Fisher | Tentative | 2023.0
STM | Pakistan Navy | MILGEM Corvette Project - Ship Set 4 Crew | G10-US-0001319-001-00247 |  | G10-US-0001319-001-00247 |  | English | English | NU | Patrick Molumby | E-AER10105 | Gas Turbine - LM2500 Level 2 Cold Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 23-541 | 23-541 - STM - Pakistan Navy - MILGEM Corvette Project - Ship Set 4 Crew - Gas Turbine - LM2500 Level 2 Cold Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-09-24 01:00 |  | 0 | 2027-04-19 01:00 | 2027-04-22 01:00 | 2027-07-22 01:00 | 2027-07-28 01:00 |  | 2027-07-22 01:00 | 2027-07-22 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Richard Fisher | Tentative | 2023.0
STM | Pakistan Navy | MILGEM Corvette Project - Ship Set 4 Crew | G10-US-0001319-001-00247 |  | G10-US-0001319-001-00247 |  | English | English | NU | Patrick Molumby | E-AER10104 | Gas Turbine - LM2500 Level 1 Maintenance | Aeroderivative | 5 | 5 | 0 | 8 |  | 23-540 | 23-540 - STM - Pakistan Navy - MILGEM Corvette Project - Ship Set 4 Crew - Gas Turbine - LM2500 Level 1 Maintenance | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-09-17 01:00 |  | 0 | 2027-04-15 01:00 | 2027-04-16 01:00 | 2027-07-15 01:00 | 2027-07-21 01:00 |  | 2027-07-15 01:00 | 2027-07-15 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Richard Fisher | Tentative | 2023.0
STM | Pakistan Navy | MILGEM Corvette Project - Ship Set 4 Crew | G10-US-0001319-001-00247 |  | G10-US-0001319-001-00247 |  | English | English | NU | Patrick Molumby | E-AER10103 | Gas Turbine - LM2500 Engine Familiarization | Aeroderivative | 3 | 3 | 0 | 12 |  | 23-539 | 23-539 - STM - Pakistan Navy - MILGEM Corvette Project - Ship Set 4 Crew - Gas Turbine - LM2500 Engine Familiarization | Learning Center | UNITED STATES | TAS-N | Houston | Houston Learning Center | Monday |  | 3202 Astrodome Room | 2026-09-14 01:00 |  | 0 | 2027-04-12 01:00 | 2027-04-14 01:00 | 2027-07-12 01:00 | 2027-07-14 01:00 |  | 2027-07-12 01:00 | 2027-07-12 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Richard Fisher | Tentative | 2023.0
TPC | Hsinta | OTS Training | EGM-00165-1CSTO-TRAINALL |  | EGM-00165-1CSTO-TRAINALL |  | Mandarin Chinese | English | NU | Gavin Yoong | Customer-Project Specific | Maintaining the Operator Training Simulator (OTS) | Simulator | 6 | 5 | 2 | 6 |  | 23-456 | 23-456 - TPC - Hsinta - OTS Training - Maintaining the Operator Training Simulator (OTS) | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday |  |  | 2026-01-26 |  | 0 | 2026-01-26 | 2026-01-30 | 2026-03-23 01:00 | 2026-03-30 01:00 |  | 2026-03-23 01:00 | 2026-03-23 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Santosh Kumar | Confirmed | 2023.0
TPC | Hsinta | OTS Training | EGM-00165-1CSTO-TRAINALL |  |  | I01-115476 / PO 4102794272 | English | English | NU | Gavin Yoong | Customer-Project Specific | Operator Training Simulator (OTS) & Train the Trainer | Simulator | 10 | 10 | 1 | 6 |  | 23-455 | 23-455 - TPC - Hsinta - OTS Training - Operator Training Simulator (OTS) & Train the Trainer | Customer Site | TAIWAN REPUBLIC OF CHINA | TAS-M | Kaohsiung | Customer Site | Monday |  |  | 2026-01-12 |  | 0 | 2026-01-05 | 2026-01-16 | 2026-03-09 01:00 | 2026-03-20 01:00 |  | 2026-03-09 01:00 | 2026-03-09 01:00 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Doug Wadsworth | Confirmed | 2023.0
CALIK ENERJI SANAYI VE TICARET A S | 300 MW Senegal IPP | DLN Option | EGM-00283-1CSTO-TRAINALL |  | EGM-00283-1CSTO-TRAINALL | I01-114538 | French | French | NU | Abuobaida El Mansoor | E-BOP10202 | Balance of Plant - Operation (GE Integrated Systems) | Balance of Plant | 5 | 5 | 0 | 12 |  | 22-596 | 22-596 - CALIK ENERJI SANAYI VE TICARET A S - 300 MW Senegal IPP - DLN Option - Balance of Plant - Operation (GE Integrated Systems) | Customer Site | SENEGAL | TAS-M | Rufisque | Customer Site | Monday |  |  | 2026-02-02 |  | 0 | 2025-11-24 | 2025-12-02 | 2026-02-02 | 2026-02-06 |  | 2026-02-02 | 2026-02-02 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2022.0
CALIK ENERJI SANAYI VE TICARET A S | 300 MW Senegal IPP | DLN Option | EGM-00283-1CSTO-TRAINALL |  | EGM-00283-1CSTO-TRAINALL | I01-114538 | French | French | NU | Abuobaida El Mansoor | E-BOI10302 | Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Balance of Plant | 3 | 3 | 2 | 12 |  | 22-595 | 22-595 - CALIK ENERJI SANAYI VE TICARET A S - 300 MW Senegal IPP - DLN Option - Heat Recovery Steam Generator (HRSG) - Operation & Maintenance (GE Engineered) | Customer Site | SENEGAL | TAS-M | Rufisque | Customer Site | Monday |  |  | 2026-02-09 |  | 0 | 2025-12-22 | 2025-12-26 | 2026-02-09 | 2026-02-11 |  | 2026-02-09 | 2026-02-09 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2022.0
CALIK ENERJI SANAYI VE TICARET A S | 300 MW Senegal IPP | DLN Option | EGM-00283-1CSTO-TRAINALL |  | EGM-00283-1CSTO-TRAINALL | I01-114538 | French | French | NU | Abuobaida El Mansoor | E-CCP10203 | Combined Cycle - Operation (GE Integrated Systems) | Combined Cycle | 5 | 5 | 1 | 12 |  | 22-594 | 22-594 - CALIK ENERJI SANAYI VE TICARET A S - 300 MW Senegal IPP - DLN Option - Combined Cycle - Operation (GE Integrated Systems) | Customer Site | SENEGAL | TAS-M | Rufisque | Customer Site | Monday |  |  | 2026-01-26 |  | 0 | 2025-11-17 | 2025-11-21 | 2026-01-26 | 2026-01-30 |  | 2026-01-26 | 2026-01-26 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2022.0
CALIK ENERJI SANAYI VE TICARET A S | 300 MW Senegal IPP | DLN Option | EGM-00283-1CSTO-TRAINALL |  | EGM-00283-1CSTO-TRAINALL | I01-115084 / PO 41027853 | French | French | NU | Abuobaida El Mansoor | E-CON13401 | Control System - Mark VIe Maintenance (Extended) | Controls | 10 | 10 | 0 | 12 |  | 22-593 | 22-593 - CALIK ENERJI SANAYI VE TICARET A S - 300 MW Senegal IPP - DLN Option - Control System - Mark VIe Maintenance (Extended) | Customer Site | SENEGAL | TAS-M | Rufisque | Customer Site | Monday |  |  | 2026-01-12 |  | 0 | 2025-12-08 | 2026-01-09 | 2026-01-12 | 2026-01-23 |  | 2026-01-12 | 2026-01-12 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Rafael Venancio | Confirmed | 2022.0
CALIK ENERJI SANAYI VE TICARET A S | 300 MW Senegal IPP | DLN Option | EGM-00283-1CSTO-TRAINALL |  | EGM-00283-1CSTO-TRAINALL | I01-114538 / PO 4200314785 | French | French | NU | Abuobaida El Mansoor | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 4 | 1 | 12 |  | 22-590 | 22-590 - CALIK ENERJI SANAYI VE TICARET A S - 300 MW Senegal IPP - DLN Option - Steam Turbine - Maintenance | Customer Site | SENEGAL | TAS-M | Rufisque | Customer Site | Monday |  |  | 2026-01-05 |  | 0 |  |  | 2026-01-05 | 2026-01-09 |  | 2026-01-05 | 2026-01-05 |  | Yes | Created | 2025-11-07 | US Workweek and Holidays | Jeff Ogletree | Confirmed | 2022.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | CONTROGEN HX V3 MAINTENANCE ENHANCED | Controls | 5 | 0 | 0 | 12 |  | 20-721 | 20-721 - Yanbu - III - - - CONTROGEN HX V3 MAINTENANCE ENHANCED | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-GEN10301 | Generator - Mechanical Systems & Components | Generator | 5 | 0 | 0 | 10 |  | 20-720 | 20-720 - Yanbu - III - - - Generator - Mechanical Systems & Components | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | CONTROCAD with MFC3000 | Controls | 7 | 0 | 0 | 12 |  | 20-719 | 20-719 - Yanbu - III - - - CONTROCAD with MFC3000 | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [7 empty] | Formerly E-CON20402 |  | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | Control System- MFC3000 Hardware | Controls | 3 | 0 | 0 | 12 |  | 20-718 | 20-718 - Yanbu - III - - - Control System- MFC3000 Hardware | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [7 empty] | Formerly E-CON20404 |  | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | Control System - ALSPA HMI Configuration | Controls | 2 | 0 | 0 | 12 |  | 20-717 | 20-717 - Yanbu - III - - - Control System - ALSPA HMI Configuration | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [7 empty] | formerly E-CON20401 |  | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | Customer-Project Specific | Control System - ALSPA HMI Operation | Controls | 3 | 0 | 0 | 12 |  | 20-716 | 20-716 - Yanbu - III - - - Control System - ALSPA HMI Operation | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [7 empty] | formerly E-CON10401 |  | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10801 | Steam Turbine - Maintenance | Steam Turbine | 5 | 0 | 0 | 12 |  | 20-715 | 20-715 - Yanbu - III - - - Steam Turbine - Maintenance | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0
Yanbu | III | - |  |  |  |  | English | English | NU | Abuobaida El Mansoor | E-STM10802 | Steam Turbine - Operation | Steam Turbine | 10 | 0 | 0 | 12 |  | 20-714 | 20-714 - Yanbu - III - - - Steam Turbine - Operation | Customer Site | SAUDI ARABIA | TAS-M | - | Customer Site | Sunday |  |  | 2026-01-01 |  | 0 | [9 empty] | Imported | 2025-11-07 | Sun - Thurs Middle East 5 Day Workweek |  | Cancelled | 2020.0