## Capex
Row ID | Year | Order | Project | Cost Estimate [USD] | Comment | Priority | Category | Cost Impact | Training Quality Impact | Description | Estimated Starting Time | Estimated Receiving Date | Status | PO Issued | Delivery min | Delivery max | Expected Received by | Date Received | Actual Cost [USD] | Projected Cost | AR Number | Project Number | PO Number | Spend | Modified By | Modification Date
CAPEX2026_153 |  | 1 | CAPEX 2025 Overall | [20 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_154 | 2025 | 2 | Capex 2025 | 1490784 | [14 empty] | 701980.5 |  |  |  |  | 701980.5 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_155 | 2025 | 3 | Expansion Sleeve Coupling Mockup | 35000 | Ensures proper equipment handling, reduces safety risks during hands-on training | High | Capability Modernization Safety | Low | High | [9 empty] | Reallocated MKVIe |  |  |  |  | Reallocated MKVIe | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_156 | 2025 | 3 | Building 1 Bay 4 New Roof | 180000 | Protects against storm damage, ensuring continuity of operations at HLC | High | Modernization Safety | High | Low | [9 empty] | 171505 |  | ARGP24006358 |  | 4900520666 | 171505 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_157 | 2025 | 3 | Building 2 New Roof | 100000 | Ensures storm resistance and protects Building 2 from damage during severe weather | High | Modernization Safety | High | Low | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_158 | 2025 | 3 | Live Outage ST D11 / BOB & Mini BOB | 60000 | Supports critical outage training, ensuring participants are prepared with the right tools | Medium | Capability | Medium | High | [9 empty] | 40046.71 |  | ARGP25002275 |  | 4900490022 | 40046.71 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_159 | 2025 | 3 | Live Outage GT24 / ST BOB & Mini BOB | 60000 | Ensures proper training for GT and Generator outages | Medium | Capability | Medium | High | [9 empty] | 82681.41 |  | ARGP25002277 |  | 4900523677 | 82681.41 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_160 | 2025 | 3 | R Zero Milling Toolkit | 75000 | Supports R Zero Milling Class, ensuring proper tooling is available for internal training | Medium | Capability | Medium | High | [9 empty] | 73310 |  | ARGP25001088 |  | 4900514763 | 73310 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_161 | 2025 | 3 | Live Outage Kit (BOB) | 30000 | Supports parallel running of 7EA Live Outages | Medium | Capability | Medium | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_162 | 2025 | 3 | Spare Tablets Live Outage | 37000 | Ensures parallel running of 7EA outages with proper equipment | Medium | Capability | Medium | Medium | [9 empty] | 79540.17 |  | ARGP25002278 |  | 4900498548 | 79540.17 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_163 | 2025 | 3 | Lifting Equipment (Birr) | 25000 | Ensures compliance with the latest standards, enhancing operational safety | Medium | Capability Modernization Safety | Low | High | [9 empty] | Waiting on quote |  |  |  |  | Waiting on quote | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_164 | 2025 | 3 | Positect Brake Pac |  | Enhances safety during HA turbine training - Purchased on OPEX | Low | Safety | Low | Medium | [9 empty] | Purchased OPEX |  |  |  |  | Purchased OPEX | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_165 | 2025 | 3 | 9E Rotor Turning Gear |  | Enables use of the 9E rotor for training, reducing scheduling conflicts for other rotors | Medium | Capability | Low | Medium | [9 empty] | Cancelled |  |  |  |  | Cancelled | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_166 | 2025 | 3 | Set of Rolling Stands |  | Supports Blade Blending and R Zero Milling training | Medium | Capability | Low | Medium | [9 empty] | Cancelled |  |  |  |  | Cancelled | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_167 | 2025 | 3 | Generator Platform Installation | 10000 | Enhances efficiency during generator outages | Low | Capability | Low | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_168 | 2025 | 3 | Generator Pulling Post |  | Improves generator outage capabilities | Low | Capability | Low | Medium | [9 empty] | Purchased OPEX |  |  |  |  | Purchased OPEX | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_169 | 2025 | 3 | Control Server with OT Armor + Cybersecurity | 500000 | Enables advanced-level cybersecurity training, enhancing both internal and external training capabilities | High | Capability Modernization | High | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_170 | 2025 | 3 | Birr Distance Learning Room Set-up | 50000 | Move DL Room from Atlanta to Birr | [13 empty] | 56186.56 |  | ARGP24006359 |  | PO#: 4900451193 | 56186.56 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_171 | 2025 | 3 | Bucket Mill Fixture | 38754 | Enables proper bucket milling training without relying on external tools | Medium | Capability Modernization | Medium | Medium | [9 empty] | 42706.65 |  | ARGP25001535 |  | 4102708143 | 42706.65 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_172 | 2025 | 3 | FFB hardware for additional carts | 100000 | Expands FFB training capacity and allows for additional student participation | High | Capability | Medium | High | [9 empty] | in process |  |  |  |  | in process | philip.ganssmann@ge.com | 2025-12-15 11:03
CAPEX2026_173 | 2025 | 3 | UCSC Controller | 14530 | Supports hands-on labs and remote simulations, enabling remote training capabilities | High | Capability | Low | Medium | [9 empty] | 30550 |  | ARGP24006360 |  | 4102654327 | 30550 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_174 | 2025 | 3 | UCEC Controller | 5500 | Demonstrates programming used at field sites, supporting internal and customer training | High | Capability | Low | Medium | [11 empty] | ARGP24006360 |  | 4102654327 | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_175 | 2025 | 3 | DLN Simulations | 50000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_176 | 2025 | 3 | Digital Bus Cabinet | 120000 | Provides the necessary equipment to offer modern digital bus training | Medium | Capability Modernization | Medium | High | [9 empty] | 125454 |  | ARGP25002361 |  | 4900495822 | 125454 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_177 | 2025 | 2 | Capex 2025 - Back-up | 2264010 | [14 empty] | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_178 | 2025 | 3 | Kahuna iPads for LiveOutage Kits | 75000 | Improves field personnel's access to competency sign-offs through Kahuna, enhancing operational efficiency | Medium | Capability | Medium | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_179 | 2025 | 3 | Golf Cart for Security Guards | 25000 | Enables efficient security patrols across the 19-acre site, enhancing safety and security | Medium | Safety | Low | None | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_180 | 2025 | 3 | Facility Key System Upgrade | 50000 | Improves overall security by preventing unauthorized duplication of keys | Medium | Safety | Low | None | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_181 | 2025 | 3 | Replace HMIs | 300000 | Update aging HMIs with latest version | Medium | Modernization | High | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_182 | 2025 | 3 | LMS100 IPT Tooling | 400000 | Run reliable ELT LMS100 course and not rely on external tooling center (J Port) | Medium | Capability | High | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_183 | 2025 | 3 | ALA/PLL 9HA CDC Mock-up Training Fix | 140000 | Moch-up for use in Thailand Learning Center | Medium | Capability | High | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_184 | 2025 | 3 | UCSE Controllers | 320000 | Replaces obsolete controllers, allowing for continued effective MKVIe training | High | Capability Modernization | High | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_185 | 2025 | 3 | Lamina Drill and Power Pack | 43010 | Eliminates rental costs and enables self-sufficiency in turbine repair training | Medium | Capability Modernization | Medium | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_186 | 2025 | 3 | TracScan Laser Replacement | 25000 | Replaces outdated laser scanning tools to enhance accuracy | Medium | Modernization | Low | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_187 | 2025 | 3 | MKVIe desktop panels | 60000 | We are seeking approval for the purchase of new equipment to modernize the Mark VIe desktop panels at the BLC. Currently, we have nine panels in use, and upgrading this equipment will allow us to align with the latest technology installed. | Medium | Modernization | Medium | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_188 | 2025 | 3 | Electrical equipment upgrades | 16000 | This equipment is used in the field and would be used during our trainings of COMET, GT Expert, ST Expert and related labs. By having this instrument, we can ensure that we have the same instruments that are used on site and that our students are familiar with their use and properties and reduce our dependence on the tooling center. Historically, we have ordered this instrument from the tooling centers , but its availability is often limited due to prioritizing inspections or being part of a comprehensive instrument box. Therefore, most of the time we cannot complete some labs, or we do them with obsolete instruments | Medium | Modernization | Low | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_189 | 2025 | 3 | Hurricane TiIe Down | 60000 | Add hurricane straps on B1 AC units | High | Modernization | Medium | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_190 | 2025 | 3 | HLC Flood mitigation | 750000 | Grounds improvement to mitigate flood risk | Medium | Modernization | High | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_191 | 2025 | 2 | Capex 2025 - Capacity Growth | 500000 | [14 empty] | 300669 |  |  |  |  | 300669 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_192 | 2025 | 3 | MKVie Capacity increase | 400000 | Increase capacity of ELT MKVIe by 4 per session | High | Capability | High | High | [9 empty] | 125680 |  | ARGP25002358 |  | 4900514761 | 125680 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_193 | 2025 | 3 | MKVIeS Cabinet | 100000 | Modernizes training capabilities by introducing new safety controller training | Medium | Modernization | Medium | Medium | [9 empty] | 174989 |  | ARGP25000060 |  | 4900514762 | 174989 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_194 | 2025 | 2 | Capex 2025 - Capacity Growth - HA | 2340000 | [14 empty] | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_195 | 2025 | 3 | Possible HA turbine | 2340000 | Get HA Turbine from Greenville; includes moving to Houston | High | Modernization | High | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_196 | 2025 | 2 | Capex 2025 - Modernization | 125000 | [14 empty] | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_197 | 2025 | 3 | AR Headsets | 125000 | AR Equipment to support AR Content. | Medium | Modernization | Medium | High | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_198 | 2025 | 2 | 2-Capacity Growth - Backup | 250000 | [14 empty] | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_199 | 2025 | 3 | MKVIe Training Panels (Birr) | 250000 | The acquisition of these five panels to significantly enhance our Mark VIe training capabilities at the BLC. | Medium | Modernization | High | Medium | [14 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_200 |  | 1 | [21 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_201 | 2026 | 1 | CAPEX 2026 Overall | 5885038.9 | Requests with 'High Priority': 5.09M | [13 empty] | 4030647.27 | 513700 |  |  |  | 4544347.27 | philip.ganssmann@gevernova.com | 2026-06-18 04:23
CAPEX2026_202 | 2026 | 2 | Michele Alcantar | 53000 | [14 empty] | 49926.1 | 0 |  |  |  | 49926.1 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_203 | 2026 | 3 | UCSE | 53000 | Replace obsolete UCSB on SkyTap Rack for Virtual Simulations for customer training | High | [6 empty] | PO received - all done | 2025-11-17 | 14w | 16w | 2026-03-09 | 2026-05-29 | 49926.1 |  | ARGP25008468 | G04-US-0003444 |  | 49926.1 | philip.ganssmann@gevernova.com | 2026-06-04 07:19
CAPEX2026_204 | 2026 | 2 | Mohammed Nizami | 541000 | [14 empty] | 584699.78 | 0 |  |  |  | 584699.78 | philip.ganssmann@gevernova.com | 2026-06-09 12:33
CAPEX2026_205 | 2026 | 3 | FFB hardware for additional carts | 300000 | Expands FFB training capacity (6 students) and setup room for FFB training at HLC | High |  |  |  | Expands FFB training capacity (6 students) and setup room for FFB training at HLC |  |  | PO opened | 2026-01-29 | 20w | 22w | 2026-07-02 |  | 178113.39 |  | ARGP25007851 | G04-US-0003474 |  | 178113.39 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_206 | 2026 | 4 | 4 Carts |  | 4 Carts | [7 empty] | PO opened | 2026-01-29 |  | 15w | 2026-05-14 |  | 178113.39 |  |  |  |  | 178113.39 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_207 | 2026 | 5 | Instrumentation - Levelflex | [9 empty] | PO received - all done | 2026-01-29 |  | 4w | 2026-02-26 | 2026-02-17 | 10734 |  |  |  |  | 10734 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_208 | 2026 | 5 | Instrumentation - Emerson | [9 empty] | PO opened | 2026-01-29 |  | 15w | 2026-05-14 |  | 24792 |  |  |  |  | 24792 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_209 | 2026 | 5 | Instrumentation - P&F | [9 empty] | PO received - all done | 2026-01-29 |  | 15w | 2026-05-14 | 2026-05-05 | 7044 |  |  |  |  | 7044 | philip.ganssmann@gevernova.com | 2026-06-04 07:19
CAPEX2026_210 | 2026 | 3 | ST Controls TDI | 91000 | 13 HMIs - moved with project CAPEX2026_211 | High | [6 empty] | Cancelled | [5 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_211 | 2026 | 3 | Replace HMIs | 150000 | Update aging HMIs with latest version | High | Modernization | [5 empty] | AR Created | 2026-06-15 |  | 15w | 2026-09-28 |  | 406586.39 | 0 | ARGP26003639 | G04-US-0003855-1 |  | 406586.39 | philip.ganssmann@gevernova.com | 2026-06-09 12:33
CAPEX2026_212 | 2026 | 2 | Greg Walker | 121000 | [14 empty] | 20107 | 30000 |  |  |  | 50107 | philip.ganssmann@gevernova.com | 2026-05-29 06:56
CAPEX2026_213 | 2026 | 3 | Aero MKVIe Modernization | 100000 | Replace Aging/Outdated Aero Controls Equipment | High | Modernization | [5 empty] | with Sourcing | 2026-08-01 |  | 2w | 2026-08-15 |  |  | 30000 |  |  |  | 30000 | philip.ganssmann@gevernova.com | 2026-05-29 06:56
CAPEX2026_214 | 2026 | 3 | LM2500+ Air Seal Puller | 21000 | Tooling needed to cover gap in our internal training program | High | [6 empty] | PO opened | 2025-12-04 | 24w | 24w | 2026-05-21 |  | 20107 |  | ARGP25008847 | G04-US-0003486 |  | 20107 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_215 | 2026 | 2 | Salim Messekine | 1308264 | [14 empty] | 484096 | 36000 |  |  |  | 520096 | philip.ganssmann@gevernova.com | 2026-05-28 10:41
CAPEX2026_216 | 2026 | 3 | HA Mock-up for location outside US | 1308264 |  | High | [12 empty] | 484096 | 36000 |  |  |  | 520096 | philip.ganssmann@gevernova.com | 2026-05-28 10:41
CAPEX2026_217 | 2026 | 4 | CSC Mockup UH | 43436 | [8 empty] | PO Approved | 2026-05-11 | 10w | 12w | 2026-08-03 |  | 43436 |  | ARGP26003012 | G04-US-0003789-1 |  | 43436 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_218 | 2026 | 4 | CSC Mockup UH plattform | 13000 | [8 empty] | On Hold | 2026-08-03 |  | 5w | 2026-09-07 |  |  | 13000 |  |  |  | 13000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_219 | 2026 | 4 | PLL Outage Kit | 87123 | [8 empty] | PO Approved | 2026-05-15 | 18w | 18w | 2026-09-18 |  | 87123 |  | ARGP26003013 | G04-US-0003790-1 |  | 87123 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_220 | 2026 | 4 | CDC Mockup LH | 43436 | [8 empty] | AR Created | 2026-05-11 | 10w | 12w | 2026-08-03 |  | 43436 |  | ARGP26003012 | G04-US-0003789-1 |  | 43436 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_221 | 2026 | 4 | CDC Mockup LH plattform | 23000 | [8 empty] | On Hold | 2026-08-03 |  | 5w | 2026-09-07 |  |  | 23000 |  |  |  | 23000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_222 | 2026 | 4 | ALA Outage Kit | 211826 | [8 empty] | PO Approved | 2026-05-15 | 18w | 18w | 2026-09-18 |  | 211826 |  | ARGP26003013 | G04-US-0003790-1 |  | 211826 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_223 | 2026 | 4 | Unibodies | [9 empty] | On Hold | 2026-06-01 |  | 15w | 2026-09-14 | [6 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_224 | 2026 | 4 | Unibodies stands | 5000 | [8 empty] | On Hold | 2026-06-01 |  | 15w | 2026-09-14 |  | 5000 |  |  |  |  | 5000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_225 | 2026 | 4 | Unibodies stands (from Thomas) | 3275 | [8 empty] | On Hold | 2026-06-01 |  | 15w | 2026-09-14 |  | 3275 |  |  |  |  | 3275 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_226 | 2026 | 4 | Headend with stands | [9 empty] | On Hold | 2026-06-01 |  | 15w | 2026-09-14 | [6 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_227 | 2026 | 4 | Corss fire Tubes | [9 empty] | On Hold | 2026-06-01 |  | 15w | 2026-09-14 | [6 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_228 | 2026 | 4 | ITS Mockup | 578800 | leadtime 36 weeks - supplier will relook at lead time | [8 empty] | 2026-03-27 | 36w | 36w | 2026-12-04 |  | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-28 10:41
CAPEX2026_229 | 2026 | 4 | ITS plattform | 40000 | [8 empty] | with Sourcing | 2026-12-04 |  | 5w | 2027-01-08 |  | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-28 10:41
CAPEX2026_230 | 2026 | 4 | Counterweight and storage stand | 169368 | [8 empty] | On Hold | 2026-04-12 | 20w | 22w | 2026-09-13 |  | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_231 | 2026 | 4 | ITS laser alignment tool | 60000 | [8 empty] | with Sourcing | 2026-04-12 |  | 15w | 2026-07-26 |  | 60000 |  |  |  |  | 60000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_232 | 2026 | 4 | ITS rollout/alignment toolkit | 30000 | [8 empty] | with Sourcing | 2026-04-12 |  | 15w | 2026-07-26 |  | 30000 |  |  |  |  | 30000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_233 | 2026 | 2 | Sherif Khalifa | 1917274.9 | [14 empty] | 1156902.69 | 160000 |  |  |  | 1316902.69 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_234 | 2026 | 3 | HA Tooling | 700000 |  | High | [6 empty] | Everything requested for Project | [5 empty] | 702763 |  |  |  |  | 702763 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_235 | 2026 | 4 | HA Tooling - update ALA and PLL | [9 empty] | PO received - all done | 2025-11-18 |  | 40w | 2026-08-25 | 2026-05-21 | 88768 |  | ARGP25008670 | G04-US-0003472 |  | 88768 | philip.ganssmann@gevernova.com | 2026-06-04 07:19
CAPEX2026_304 |  | 5 | PLL Outage Kit – 7HA.03 - ARGP25008670 | [9 empty] | PO Approved | [5 empty] | 72841 |  |  |  | 4900558600 | 72841 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_305 |  | 5 | 7HA PLL Tooling - ARGP25008670 | [9 empty] | PO Approved | [5 empty] | 15927 |  |  |  | 4900558371 | 15927 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_236 | 2026 | 4 | 7HA.03 PLL/ALA Combustion Kit | [9 empty] | PO received - all done | 2025-11-18 |  | 22w | 2026-04-21 | 2026-05-20 | 220920 |  | ARGP25007855 | G04-US-0003415 | 4900554451 | 220920 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_237 | 2026 | 4 | HA ITS Counter Weight | [9 empty] | PO opened | 2026-01-12 |  | 35w | 2026-09-14 |  | 190000 |  | ARGP25009640 | G04-US-0003543 |  | 190000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_238 | 2026 | 4 | Tracc Scan- ITS Pusher, HE Stand, UB Stand, Centerline Jacks | [9 empty] | PO opened | 2026-02-09 |  | 14w | 2026-05-18 |  | 203075 |  | ARGP26001034 | G04-US-0003601 |  | 203075 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_239 | 2026 | 3 | HA Improvements | 600000 |  | High | [7 empty] | n/a |  |  | n/a |  | 396906.95 |  |  |  |  | 396906.95 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_240 | 2026 | 4 | 3x Unibodies | [9 empty] | PO opened | 2026-01-12 |  | 12w | 2026-04-06 |  | 50460 |  | ARGP25009642 | G04-US-0003535 |  | 50460 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_241 | 2026 | 4 | HA platform | [9 empty] | PO received - all done | 2025-12-15 |  | 15w | 2026-03-30 | 2026-01-01 | 287124 |  | ARGP25007962 | G04-US-0003414 | 4900561718 | 287124 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_242 | 2026 | 4 | Fall Arest | 59322.95 | [8 empty] | PO Approved | 2026-03-20 |  | 4w | 2026-04-17 |  | 59322.95 |  | ARGP26002128 |  | 4900595386 | 59322.95 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_243 | 2026 | 3 | Lean Tools - 7E | 200000 |  | High | [12 empty] | 57232.74 |  |  |  |  | 57232.74 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_244 | 2026 | 4 | Bump Check Tools | 13347 | [8 empty] | AR Created | 2026-01-12 |  | 7w | 2026-03-02 |  | 13347 |  | ARGP25009641 | G04-US-0003533-1 |  | 13347 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_245 | 2026 | 4 | Rotating Device | 43885.74 | [8 empty] | PO opened | 2026-02-17 |  | 19w | 2026-06-30 |  | 43885.74 |  | ARGP25009643 |  |  | 43885.74 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_246 | 2026 | 3 | TracScan Laser Replacement | 25000 | Replaces outdated laser scanning tools to enhance accuracy | High | Modernization | [5 empty] | On Hold | [10 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_279 |  | 3 | Lean Tools (Sherif) | 392274.9 | Additional Lean Tools | [7 empty] | Requesting Quote from Vendor | [6 empty] | 160000 |  |  |  | 160000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_307 |  | 4 | 7HA.03 CMPR IDC Aft Jack Support Kit | 5000 | [8 empty] | Requesting Quote from Vendor | 2026-06-22 |  | 12w | 2026-09-14 |  |  | 5000 |  |  |  | 5000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_308 |  | 4 | 7HA.03 CMPR ICC/ IDC to OCC Leveling Tool | 10000 | [8 empty] | Requesting Quote from Vendor | 2026-06-22 |  | 12w | 2026-09-14 |  |  | 10000 |  |  |  | 10000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_309 |  | 4 | 7HA.03 ITS/OTS Guide Pin, Jacking Bolt & Hoist Ring Kit | 40000 | [8 empty] | Requesting Quote from Vendor | 2026-06-22 |  | 16w | 2026-10-12 |  |  | 40000 |  |  |  | 40000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_310 |  | 4 | 7HA.03 ITS Lateral Alignment Pusher | 5000 | [8 empty] | Requesting Quote from Vendor | 2026-06-22 |  | 6w | 2026-08-03 |  |  | 5000 |  |  |  | 5000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_311 |  | 4 | 7HA.03 ITS Hydraulic Drive Motor & Adapter Plate Kit | 50000 | [8 empty] | Requesting Quote from Vendor | 2026-06-22 |  | 24w | 2026-12-07 |  |  | 50000 |  |  |  | 50000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_312 |  | 4 | 7HA.01/02/03 & 9HA.01/02 ITS Hydraulic Pump and Cart | 50000 | [8 empty] | Requesting Quote from Vendor | 2026-06-22 |  | 24w | 2026-12-07 |  |  | 50000 |  |  |  | 50000 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_313 |  | 4 | ITH KIT | 178608.59 | [8 empty] | AR Created | 2026-06-22 |  | 12w | 2026-09-14 |  | 178608.59 |  | ARGP26005181 |  |  | 178608.59 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_314 |  | 4 | Composite cribbing | 15000 | not a CAPEX spend | [7 empty] | Cancelled | 2026-06-22 |  |  | #INVALID OPERATION | [6 empty] | 0 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_315 |  | 4 | Enerpac Kit | 33666.31 | [8 empty] | AR Created | 2026-06-22 |  | 5w | 2026-07-27 |  | 33666.31 |  | ARGP26005181 |  |  | 33666.31 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_316 |  | 4 | 7HA.03 CMPR IDC Aft Jack Support Kit | 5000 | [8 empty] | AR Created | 2026-06-22 |  | 12w | 2026-09-14 |  | 14606 |  | ARGP26005181 |  |  | 14606 | philip.ganssmann@gevernova.com | 2026-06-16 02:29
CAPEX2026_317 |  | 2 | 7HA Unbalancing Turning Device | [10 empty] | 2026-06-22 |  | 14w | 2026-09-28 |  | 78060 |  |  |  |  | 78060 | philip.ganssmann@gevernova.com | 2026-06-18 04:23
CAPEX2026_247 | 2026 | 2 | Steve Urban | 1370000 | [14 empty] | 1180958.7 | 100000 |  |  |  | 1280958.7 | philip.ganssmann@gevernova.com | 2026-06-17 13:43
CAPEX2026_248 | 2026 | 3 | Hurricane Tie Down | 100000 | Add hurricane straps on B1 AC units | High | [6 empty] | with Sourcing | [6 empty] | 100000 |  |  |  | 100000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_249 | 2026 | 3 | Building 2 New Roof | 575000 | Ensures storm resistance and protects Building 2 from damage during severe weather | High | [6 empty] | PO opened | 2026-06-01 |  | 16w | 2026-09-21 |  | 411134 |  | ARGP26004508 | G04-US-0003964-1 |  | 411134 | philip.ganssmann@gevernova.com | 2026-06-18 11:05
CAPEX2026_250 | 2026 | 3 | New AC units bldg. 1 phase A | 250000 |  | High |  |  |  |  | 2026-01-01 | 2026-02-28 | PO received - all done | 2026-01-12 |  | 8w | 2026-03-09 |  | 179455 |  | ARGP25007837 | G04-US-0003413 |  | 179455 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_251 | 2026 | 3 | New Switchgear bldg. 2 | 350000 |  | High | [6 empty] | PO Approved | 2026-01-12 |  | 37w | 2026-09-28 |  | 512331 |  | ARGP26000596 | G04-US-0003572 |  | 512331 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_252 | 2026 | 3 | New Scissors gates bldg. 1 | 15000 |  | High | Safety | [5 empty] | PO opened | 2026-04-19 |  | 10w | 2026-06-28 |  | 8745 |  | ARGP26003479 | G04-US-0003847-1 |  | 8745 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_253 | 2026 | 3 | Fans for Bay 3,4,1 | 80000 | - 1 fan for the HA CDC Mockup Ground Level - 1 Fan for the HA CDC Mockup upper Level - 1 Fan for the 7FH2 Generator upper Level - 1 Fan for the 7FA north side - 2 Fans for the HA upper level North and South - 2 Fans for the HA Lower Level North and South. | [7 empty] | AR Created | 2026-06-08 |  | 5w | 2026-07-13 |  | 69293.7 |  | ARGP26004976 | G04-US-0003975-1 |  | 69293.7 | philip.ganssmann@gevernova.com | 2026-06-17 13:43
CAPEX2026_254 | 2026 | 2 | Pablo Schibli | 69000 | [14 empty] | 0 | 41000 |  |  |  | 41000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_255 | 2026 | 3 | Lifting Equipment (Birr) | 25000 | Ensures compliance with the latest standards, enhancing operational safety | High | Safety | [5 empty] | No action done yet | [6 empty] | 25000 |  |  |  | 25000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_256 | 2026 | 3 | Electrical equipment upgrades (BLC) | 16000 | This equipment is used in the field and would be used during our trainings of COMET, GT Expert, ST Expert and related labs. By having this instrument, we can ensure that we have the same instruments that are used on site and that our students are familiar with their use and properties and reduce our dependence on the tooling center. Historically, we have ordered this instrument from the tooling centers , but its availability is often limited due to prioritizing inspections or being part of a comprehensive instrument box. Therefore, most of the time we cannot complete some labs, or we do them with obsolete instruments | High | Capability | [5 empty] | No action done yet | [6 empty] | 16000 |  |  |  | 16000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_257 | 2026 | 3 | Cribbing blocks (HLC) | 14000 | Ensures compliance with the latest standards, enhancing operational safety. | High | Safety | [5 empty] | Cancelled | [5 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_258 | 2026 | 3 | Cribbing blocks (BLC) | 14000 | Ensures compliance with the latest standards, enhancing operational safety. | High | Safety | [5 empty] | Cancelled | [5 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_259 | 2026 | 2 | Harry Hanson | 240500 | [14 empty] | 210897 | 0 |  |  |  | 210897 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_260 |  | 3 | Entry Level Generator Repairs Accelerated - Equipment | 40000 | Tables and Mockups | [7 empty] | PO received - all done | 2025-11-17 | 4w | 5w | 2025-12-22 |  | 39015 |  | ARGP25008209 | G04-US-0003430 | 4900558618 | 39015 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_261 | 2026 | 3 | Tools for Bucket Tech Class | 165000 |  | High | [6 empty] | PO opened | [5 empty] | 156382 |  | ARGP26003096 | G04-US-0003791 |  | 156382 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_262 |  | 4 | 6B LOCK WIRE DOWEL PINHOLE DRILLING TOOL | 8115 | [9 empty] | 2026-04-13 | 6w | 8w | 2026-06-08 |  | 8115 |  |  |  | 4900610143 | 8115 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_263 |  | 4 | 6B LOCKTAB DOWEL PIN HOLE DRILLING | 9574 | [9 empty] | 2026-04-13 | 6w | 8w | 2026-06-08 |  | 9574 |  |  |  | 4900610142 | 9574 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_264 |  | 4 | 7E ROTOR TURNING DEVICE | 8665 | [9 empty] | 2026-04-13 | 6w | 8w | 2026-06-08 |  | 8665 |  |  |  | 4900610141 | 8665 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_265 |  | 4 | 7E TWISTLOCK STAKING TOOL | 41539 | [9 empty] | 2026-04-13 | 8w | 12w | 2026-07-06 |  | 41539 |  |  |  |  | 41539 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_266 |  | 4 | 7F STAGE 5 THRU 16 STATOR BLADE MILLING MACHINE | 38635 | [9 empty] | 2026-04-13 | 8w | 12w | 2026-07-06 |  | 38635 |  |  |  |  | 38635 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_267 |  | 4 | 7FA STG# I—3 LOCKWIRE DRILL FIXTURE | 7923 | [9 empty] | 2026-04-13 | 6w | 10w | 2026-06-22 |  | 7923 |  |  |  | 4900610144 | 7923 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_268 |  | 4 | 7EA RI7 DOVE TAIL MILL | 41931 | [9 empty] | 2026-04-13 | 8w | 12w | 2026-07-06 |  | 41931 |  |  |  |  | 41931 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_269 | 2026 | 3 | Fast Stator Rewind Class - Round Pack Tool | 15500 | [8 empty] | PO received - all done | 2026-03-19 |  | 8w | 2026-05-14 | 2026-05-29 | 15500 |  | ARGP26001597 | G04-US-0003649-1 | 4900595027 | 15500 | philip.ganssmann@gevernova.com | 2026-06-04 07:19
CAPEX2026_270 | 2026 | 3 | CNC controller on the Bridgeport milling machine | 20000 |  | High | [6 empty] | Cancelled | [5 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_271 | 2026 | 2 | Carry Over 2025 | 265000 | [14 empty] | 265000 | 0 |  |  |  | 265000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_272 |  | 3 | Backlog X | 65000 | [8 empty] | PO received - all done | 2025-10-06 |  | 1w | 2025-10-13 |  | 65000 |  |  |  |  | 65000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_273 | 2026 | 3 | Scheduling Panels | 50000 | [8 empty] | PO received - all done | 2025-07-01 |  | 35w | 2026-03-03 |  | 50000 |  |  |  |  | 50000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_274 |  | 3 | Roof Building 1 | 150000 | [8 empty] | PO received - all done | 2025-10-06 |  | 1w | 2025-10-13 |  | 150000 |  |  |  |  | 150000 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_275 | 2026 | 2 | To be discussed to add | [15 empty] | 0 | 100000 |  |  |  | 100000 | philip.ganssmann@gevernova.com | 2026-06-04 07:24
CAPEX2026_276 |  | 3 | 2nd Person Training | 270000 | Update existing 2nd Person online Training | [8 empty] | 2026-06-01 |  | 24w | 2026-11-16 |  |  | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-29 08:57
CAPEX2026_277 |  | 3 | Diaphragm mock-ups | 47000 | [15 empty] | 47000 |  |  |  | 47000 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_278 |  | 3 | Michele USC | 53000 | Additional USCs for customer trainings | [14 empty] | 53000 |  |  |  | 53000 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_306 |  | 3 | Not in Budget | [20 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_280 | 2026 | 4 | Michele Alcantar | 54000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_281 | 2026 | 5 | T60 and G60 relay | 30000 | Ability to deliver OJT to customers | Medium | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_282 | 2026 | 5 | CIAB Kits | 24000 | Replace stolen and obsolete CIAB kits for customer training | Medium | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_283 | 2026 | 4 | Mohammed Nizami | 1030000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_284 | 2026 | 5 | MKVIe desktop panels | 60000 | We are seeking approval for the purchase of new equipment to modernize the Mark VIe desktop panels at the BLC. Currently, we have nine panels in use, and upgrading this equipment will allow us to align with the latest technology installed. | Medium | Modernization | [16 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_285 | 2026 | 5 | Replace HMIs | 150000 | Update aging HMIs with latest version | Medium | Modernization | [16 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_286 | 2026 | 5 | UCSE Controllers | 320000 | Replaces obsolete controllers, allowing for continued effective MKVIe training | Medium | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_287 | 2026 | 5 | Control Server with OT Armor + Cybersecurity | 500000 | Enables advanced-level cybersecurity training, enhancing both internal and external training capabilities | Medium | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_288 | 2026 | 4 | Greg Walker | 400000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_289 | 2026 | 5 | LMS100 IPT Tooling | 400000 | Run reliable ELT LMS100 course and not rely on external tooling center (J Port) | Low | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_290 | 2026 | 4 | Sherif Khalifa | 0 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_291 | 2026 | 5 | Expansion Sleeve Coupling Mockup | 0 | Ensures proper equipment handling, reduces safety risks during hands-on training | Cancel | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_292 | 2026 | 5 | Lamina Drill and Power Pack | 0 | Eliminates rental costs and enables self-sufficiency in turbine repair training | Cancel | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_293 | 2026 | 5 | Lab mock-up to run additional GT ELT class |  | Run additional classes in Birr, Switzerland | [18 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_294 | 2026 | 4 | Steve Urban | 1100000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_295 | 2026 | 5 | New Breakers Bld1 1 East Switchgear | 0 | Grounds improvement to mitigate flood risk | Cancel | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_296 | 2026 | 5 | New man doors bldg. 1 | 100000 |  | Medium | [17 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_297 | 2026 | 5 | New Crane for Bay 1 | 1000000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_298 | 2026 | 4 | Pablo Schibli | 40000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_299 | 2026 | 5 | Distance Learning Room Modernisation | 40000 | [19 empty] | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_300 | 2026 | 4 | Harry Hanson | 0 | [14 empty] | 0 |  |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:26
CAPEX2026_301 | 2027 | 1 | CAPEX 2027 Overall | 578800 | Requests with 'High Priority': 5.09M | [13 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_302 | 2027 | 2 | Salim Messekine | 578800 | [14 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12
CAPEX2026_303 | 2027 | 3 | ITS Mockup | 578800 | leadtime 36 weeks | [13 empty] | 0 | 0 |  |  |  | 0 | philip.ganssmann@gevernova.com | 2026-05-22 05:12

## Comments
Row 51 | look at getting them over OPEX | Philip Ganssmann | 08/06/25 7:36 AM
Row 61 | Tamil will be meeting with the engineering team in Mexico in mid-March to finalize simulations and confirm hardware requirements. Based on that timing, we’re targeting mid-April to complete quotes and submit the POs. None of the anticipated items are long lead, so we don’t see schedule risk once requirements are locked in. | Philip Ganssmann | 02/18/26 1:26 PM
Row 61 | Working on quotes, should have everything ready before end of January | Philip Ganssmann | 12/15/25 1:57 PM
Row 115 | wait until April | Philip Ganssmann | 02/20/26 9:18 AM
Row 123 | Quotes being prepared by vendor | Philip Ganssmann | 02/19/26 2:37 AM
Row 132 | Would rather cancel this and use the $$$ for the Gen Repairs Round Packing tooling | Philip Ganssmann | 02/19/26 2:37 AM
Row 144 | look at getting them over OPEX | Philip Ganssmann | 08/06/25 7:36 AM

## Summary
Priority High | 5092264
Priority Medium | 1184000