## Capex
Row ID | Year | Order | Project | Responsible Person | Suplier | Cost Estimate [USD] | Comment | Priority | Category | Cost Impact | Training Quality Impact | Description | Estimated Starting Time | Estimated Receiving Date | Status | PO Requested | PO Issued | Delivery min | Delivery max | Actual Cost [USD] | Projected Cost | AR Number | Project Number | PO Number | Expected Received by earliest | Expected Received by | Date Received | Spend | Modified By | Modification Date
CAPEX2026_153 |  | 1 | CAPEX 2025 Overall | [21 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_154 | 2025 | 2 | Capex 2025 |  |  | 1490784 | [13 empty] | 701980.5 |  |  |  |  | #INVALID OPERATION |  |  | 701980.5 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_155 | 2025 | 3 | Expansion Sleeve Coupling Mockup |  |  | 35000 | Ensures proper equipment handling, reduces safety risks during hands-on training | High | Capability Modernization Safety | Low | High | [8 empty] | Reallocated MKVIe |  |  |  |  | #INVALID OPERATION |  |  | Reallocated MKVIe | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_156 | 2025 | 3 | Building 1 Bay 4 New Roof |  |  | 180000 | Protects against storm damage, ensuring continuity of operations at HLC | High | Modernization Safety | High | Low | [8 empty] | 171505 |  | ARGP24006358 |  | 4900520666 | #INVALID OPERATION |  |  | 171505 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_157 | 2025 | 3 | Building 2 New Roof |  |  | 100000 | Ensures storm resistance and protects Building 2 from damage during severe weather | High | Modernization Safety | High | Low | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_158 | 2025 | 3 | Live Outage ST D11 / BOB & Mini BOB |  |  | 60000 | Supports critical outage training, ensuring participants are prepared with the right tools | Medium | Capability | Medium | High | [8 empty] | 40046.71 |  | ARGP25002275 |  | 4900490022 | #INVALID OPERATION |  |  | 40046.71 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_159 | 2025 | 3 | Live Outage GT24 / ST BOB & Mini BOB |  |  | 60000 | Ensures proper training for GT and Generator outages | Medium | Capability | Medium | High | [8 empty] | 82681.41 |  | ARGP25002277 |  | 4900523677 | #INVALID OPERATION |  |  | 82681.41 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_160 | 2025 | 3 | R Zero Milling Toolkit |  |  | 75000 | Supports R Zero Milling Class, ensuring proper tooling is available for internal training | Medium | Capability | Medium | High | [8 empty] | 73310 |  | ARGP25001088 |  | 4900514763 | #INVALID OPERATION |  |  | 73310 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_161 | 2025 | 3 | Live Outage Kit (BOB) |  |  | 30000 | Supports parallel running of 7EA Live Outages | Medium | Capability | Medium | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_162 | 2025 | 3 | Spare Tablets Live Outage |  |  | 37000 | Ensures parallel running of 7EA outages with proper equipment | Medium | Capability | Medium | Medium | [8 empty] | 79540.17 |  | ARGP25002278 |  | 4900498548 | #INVALID OPERATION |  |  | 79540.17 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_163 | 2025 | 3 | Lifting Equipment (Birr) |  |  | 25000 | Ensures compliance with the latest standards, enhancing operational safety | Medium | Capability Modernization Safety | Low | High | [8 empty] | Waiting on quote |  |  |  |  | #INVALID OPERATION |  |  | Waiting on quote | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_164 | 2025 | 3 | Positect Brake Pac |  |  |  | Enhances safety during HA turbine training - Purchased on OPEX | Low | Safety | Low | Medium | [8 empty] | Purchased OPEX |  |  |  |  | #INVALID OPERATION |  |  | Purchased OPEX | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_165 | 2025 | 3 | 9E Rotor Turning Gear |  |  |  | Enables use of the 9E rotor for training, reducing scheduling conflicts for other rotors | Medium | Capability | Low | Medium | [8 empty] | Cancelled |  |  |  |  | #INVALID OPERATION |  |  | Cancelled | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_166 | 2025 | 3 | Set of Rolling Stands |  |  |  | Supports Blade Blending and R Zero Milling training | Medium | Capability | Low | Medium | [8 empty] | Cancelled |  |  |  |  | #INVALID OPERATION |  |  | Cancelled | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_167 | 2025 | 3 | Generator Platform Installation |  |  | 10000 | Enhances efficiency during generator outages | Low | Capability | Low | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_168 | 2025 | 3 | Generator Pulling Post |  |  |  | Improves generator outage capabilities | Low | Capability | Low | Medium | [8 empty] | Purchased OPEX |  |  |  |  | #INVALID OPERATION |  |  | Purchased OPEX | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_169 | 2025 | 3 | Control Server with OT Armor + Cybersecurity |  |  | 500000 | Enables advanced-level cybersecurity training, enhancing both internal and external training capabilities | High | Capability Modernization | High | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_170 | 2025 | 3 | Birr Distance Learning Room Set-up |  |  | 50000 | Move DL Room from Atlanta to Birr | [12 empty] | 56186.56 |  | ARGP24006359 |  | PO#: 4900451193 | #INVALID OPERATION |  |  | 56186.56 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_171 | 2025 | 3 | Bucket Mill Fixture |  |  | 38754 | Enables proper bucket milling training without relying on external tools | Medium | Capability Modernization | Medium | Medium | [8 empty] | 42706.65 |  | ARGP25001535 |  | 4102708143 | #INVALID OPERATION |  |  | 42706.65 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_172 | 2025 | 3 | FFB hardware for additional carts |  |  | 100000 | Expands FFB training capacity and allows for additional student participation | High | Capability | Medium | High | [8 empty] | in process |  |  |  |  | #INVALID OPERATION |  |  | in process | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_173 | 2025 | 3 | UCSC Controller |  |  | 14530 | Supports hands-on labs and remote simulations, enabling remote training capabilities | High | Capability | Low | Medium | [8 empty] | 30550 |  | ARGP24006360 |  | 4102654327 | #INVALID OPERATION |  |  | 30550 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_174 | 2025 | 3 | UCEC Controller |  |  | 5500 | Demonstrates programming used at field sites, supporting internal and customer training | High | Capability | Low | Medium | [10 empty] | ARGP24006360 |  | 4102654327 | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_175 | 2025 | 3 | DLN Simulations |  |  | 50000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_176 | 2025 | 3 | Digital Bus Cabinet |  |  | 120000 | Provides the necessary equipment to offer modern digital bus training | Medium | Capability Modernization | Medium | High | [8 empty] | 125454 |  | ARGP25002361 |  | 4900495822 | #INVALID OPERATION |  |  | 125454 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_177 | 2025 | 2 | Capex 2025 - Back-up |  |  | 2264010 | [13 empty] | 0 |  |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_178 | 2025 | 3 | Kahuna iPads for LiveOutage Kits |  |  | 75000 | Improves field personnel's access to competency sign-offs through Kahuna, enhancing operational efficiency | Medium | Capability | Medium | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_179 | 2025 | 3 | Golf Cart for Security Guards |  |  | 25000 | Enables efficient security patrols across the 19-acre site, enhancing safety and security | Medium | Safety | Low | None | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_180 | 2025 | 3 | Facility Key System Upgrade |  |  | 50000 | Improves overall security by preventing unauthorized duplication of keys | Medium | Safety | Low | None | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_181 | 2025 | 3 | Replace HMIs |  |  | 300000 | Update aging HMIs with latest version | Medium | Modernization | High | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_182 | 2025 | 3 | LMS100 IPT Tooling |  |  | 400000 | Run reliable ELT LMS100 course and not rely on external tooling center (J Port) | Medium | Capability | High | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_183 | 2025 | 3 | ALA/PLL 9HA CDC Mock-up Training Fix |  |  | 140000 | Moch-up for use in Thailand Learning Center | Medium | Capability | High | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_184 | 2025 | 3 | UCSE Controllers |  |  | 320000 | Replaces obsolete controllers, allowing for continued effective MKVIe training | High | Capability Modernization | High | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_185 | 2025 | 3 | Lamina Drill and Power Pack |  |  | 43010 | Eliminates rental costs and enables self-sufficiency in turbine repair training | Medium | Capability Modernization | Medium | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_186 | 2025 | 3 | TracScan Laser Replacement |  |  | 25000 | Replaces outdated laser scanning tools to enhance accuracy | Medium | Modernization | Low | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_187 | 2025 | 3 | MKVIe desktop panels |  |  | 60000 | We are seeking approval for the purchase of new equipment to modernize the Mark VIe desktop panels at the BLC. Currently, we have nine panels in use, and upgrading this equipment will allow us to align with the latest technology installed. | Medium | Modernization | Medium | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_188 | 2025 | 3 | Electrical equipment upgrades |  |  | 16000 | This equipment is used in the field and would be used during our trainings of COMET, GT Expert, ST Expert and related labs. By having this instrument, we can ensure that we have the same instruments that are used on site and that our students are familiar with their use and properties and reduce our dependence on the tooling center. Historically, we have ordered this instrument from the tooling centers , but its availability is often limited due to prioritizing inspections or being part of a comprehensive instrument box. Therefore, most of the time we cannot complete some labs, or we do them with obsolete instruments | Medium | Modernization | Low | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_189 | 2025 | 3 | Hurricane TiIe Down |  |  | 60000 | Add hurricane straps on B1 AC units | High | Modernization | Medium | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_190 | 2025 | 3 | HLC Flood mitigation |  |  | 750000 | Grounds improvement to mitigate flood risk | Medium | Modernization | High | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_191 | 2025 | 2 | Capex 2025 - Capacity Growth |  |  | 500000 | [13 empty] | 300669 |  |  |  |  | #INVALID OPERATION |  |  | 300669 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_192 | 2025 | 3 | MKVie Capacity increase |  |  | 400000 | Increase capacity of ELT MKVIe by 4 per session | High | Capability | High | High | [8 empty] | 125680 |  | ARGP25002358 |  | 4900514761 | #INVALID OPERATION |  |  | 125680 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_193 | 2025 | 3 | MKVIeS Cabinet |  |  | 100000 | Modernizes training capabilities by introducing new safety controller training | Medium | Modernization | Medium | Medium | [8 empty] | 174989 |  | ARGP25000060 |  | 4900514762 | #INVALID OPERATION |  |  | 174989 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_194 | 2025 | 2 | Capex 2025 - Capacity Growth - HA |  |  | 2340000 | [13 empty] | 0 |  |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_195 | 2025 | 3 | Possible HA turbine |  |  | 2340000 | Get HA Turbine from Greenville; includes moving to Houston | High | Modernization | High | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_196 | 2025 | 2 | Capex 2025 - Modernization |  |  | 125000 | [13 empty] | 0 |  |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_197 | 2025 | 3 | AR Headsets |  |  | 125000 | AR Equipment to support AR Content. | Medium | Modernization | Medium | High | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_198 | 2025 | 2 | 2-Capacity Growth - Backup |  |  | 250000 | [13 empty] | 0 |  |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_199 | 2025 | 3 | MKVIe Training Panels (Birr) |  |  | 250000 | The acquisition of these five panels to significantly enhance our Mark VIe training capabilities at the BLC. | Medium | Modernization | High | Medium | [13 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_200 |  | 1 | [22 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_201 | 2026 | 1 | CAPEX 2026 Overall |  |  | 6066650.37 | Requests with 'High Priority': 5.09M | [12 empty] | 4015338.16 | 633900.938 |  |  |  | #INVALID OPERATION |  |  | 4649239.098 | philip.ganssmann@gevernova.com | 2026-07-01 02:27
CAPEX2026_202 | 2026 | 2 | Michele Alcantar |  |  | 53000 | [13 empty] | 49926.1 | 0 |  |  |  | #INVALID OPERATION |  |  | 49926.1 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_203 | 2026 | 3 | UCSE |  |  | 53000 | Replace obsolete UCSB on SkyTap Rack for Virtual Simulations for customer training | High | [6 empty] | PO received - all done |  | 2025-11-17 | 14w | 16w | 49926.1 |  | ARGP25008468 | G04-US-0003444 |  | 2026-02-23 | 2026-03-09 | 2026-05-29 | 49926.1 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_204 | 2026 | 2 | Mohammed Nizami |  |  | 541000 | [13 empty] | 584472.77 | 0 |  |  |  | #INVALID OPERATION |  |  | 584472.77 | gregoryd.walker@gevernova.com | 2026-06-25 07:44
CAPEX2026_205 | 2026 | 3 | FFB hardware for additional carts |  |  | 300000 | Expands FFB training capacity (6 students) and setup room for FFB training at HLC | High |  |  |  | Expands FFB training capacity (6 students) and setup room for FFB training at HLC |  |  | PO opened |  | 2026-01-29 | 20w | 22w | 177886.38 |  | ARGP25007851 | G04-US-0003474 |  | 2026-06-18 | 2026-07-02 |  | 177886.38 | gregoryd.walker@gevernova.com | 2026-06-25 07:44
CAPEX2026_206 | 2026 | 4 | 4 Carts |  |  |  | 4 Carts | [7 empty] | PO opened |  | 2026-01-29 |  | 15w | 177886.38 |  |  |  | 4900565025 | 2026-05-14 | 2026-05-14 |  | 177886.38 | gregoryd.walker@gevernova.com | 2026-06-25 07:44
CAPEX2026_207 | 2026 | 5 | Instrumentation - Levelflex | [11 empty] | PO received - all done |  | 2026-01-29 |  | 4w | 10734 |  |  |  | 4900576959 | 2026-02-26 | 2026-02-26 | 2026-02-17 | 10734 | gregoryd.walker@gevernova.com | 2026-06-25 07:18
CAPEX2026_318 | 2026 | 5 | FFB Carts Birr | [13 empty] | 2026-05-05 |  | 12w | 13302 |  |  |  | 4900610658 | 2026-07-28 | 2026-07-28 |  | 13302 | gregoryd.walker@gevernova.com | 2026-06-25 08:01
CAPEX2026_319 | 2026 | 5 | Pressure Transmitter - Emerson | Mohammed Nizami | [12 empty] | 2026-02-11 |  | 20w | 6551.94 |  |  |  | 4900581446 | 2026-07-01 | 2026-07-01 |  | 6551.94 | gregoryd.walker@gevernova.com | 2026-06-25 07:47
CAPEX2026_208 | 2026 | 5 | Instrumentation - Emerson | [11 empty] | PO opened |  | 2026-01-29 |  | 15w | 24792 |  |  |  | 4900576964 | 2026-05-14 | 2026-05-14 |  | 24792 | gregoryd.walker@gevernova.com | 2026-06-25 07:33
CAPEX2026_209 | 2026 | 5 | Instrumentation - P&F | [11 empty] | PO received - all done |  | 2026-01-29 |  | 15w | 7044 |  |  |  | PCard | 2026-05-14 | 2026-05-14 | 2026-05-05 | 7044 | gregoryd.walker@gevernova.com | 2026-06-25 07:18
CAPEX2026_210 | 2026 | 3 | ST Controls TDI |  |  | 91000 | 13 HMIs - moved with project CAPEX2026_211 | High | [6 empty] | Cancelled |  |  |  |  | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_211 | 2026 | 3 | Replace HMIs |  |  | 150000 | Update aging HMIs with latest version | High | Modernization | [5 empty] | AR Created |  | 2026-06-15 |  | 15w | 406586.39 | 0 | ARGP26003639 | G04-US-0003855-1 |  | 2026-09-28 | 2026-09-28 |  | 406586.39 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_212 | 2026 | 2 | Greg Walker |  |  | 121000 | [13 empty] | 20107 | 30000 |  |  |  | #INVALID OPERATION |  |  | 50107 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_213 | 2026 | 3 | Aero MKVIe Modernization |  |  | 100000 | Replace Aging/Outdated Aero Controls Equipment | High | Modernization | [5 empty] | with Sourcing |  | 2026-08-01 |  | 2w |  | 30000 |  |  |  | 2026-08-15 | 2026-08-15 |  | 30000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_214 | 2026 | 3 | LM2500+ Air Seal Puller |  |  | 21000 | Tooling needed to cover gap in our internal training program | High | [6 empty] | PO opened |  | 2025-12-04 | 24w | 24w | 20107 |  | ARGP25008847 | G04-US-0003486 | 4900564710 | 2026-05-21 | 2026-05-21 |  | 20107 | gregoryd.walker@gevernova.com | 2026-06-25 06:46
CAPEX2026_215 | 2026 | 2 | Salim Messekine |  |  | 1308264 | [13 empty] | 474096 | 36000 |  |  |  | #INVALID OPERATION |  |  | 510096 | gregoryd.walker@gevernova.com | 2026-06-25 08:04
CAPEX2026_216 | 2026 | 3 | HA Mock-up for location outside US |  |  | 1308264 |  | High | [11 empty] | 474096 | 36000 |  |  |  | #INVALID OPERATION |  |  | 510096 | gregoryd.walker@gevernova.com | 2026-06-25 08:04
CAPEX2026_217 | 2026 | 4 | CSC Mockup UH |  |  | 43436 | [8 empty] | PO Approved |  | 2026-05-11 | 10w | 12w | 38436 |  | ARGP26003012 | G04-US-0003789-1 | 4900611340 | 2026-07-20 | 2026-08-03 |  | 38436 | gregoryd.walker@gevernova.com | 2026-06-25 08:04
CAPEX2026_218 | 2026 | 4 | CSC Mockup UH plattform |  |  | 13000 | [8 empty] | On Hold |  | 2026-08-03 |  | 5w |  | 13000 |  |  |  | 2026-09-07 | 2026-09-07 |  | 13000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_219 | 2026 | 4 | PLL Outage Kit |  |  | 87123 | [8 empty] | PO Approved |  | 2026-05-15 | 18w | 18w | 87123 |  | ARGP26003013 | G04-US-0003790-1 | 4900614412 | 2026-09-18 | 2026-09-18 |  | 87123 | gregoryd.walker@gevernova.com | 2026-06-25 06:46
CAPEX2026_220 | 2026 | 4 | CDC Mockup LH |  |  | 43436 | [8 empty] | AR Created |  | 2026-05-11 | 10w | 12w | 38436 |  | ARGP26003012 | G04-US-0003789-1 | 4900611340 | 2026-07-20 | 2026-08-03 |  | 38436 | gregoryd.walker@gevernova.com | 2026-06-25 08:04
CAPEX2026_221 | 2026 | 4 | CDC Mockup LH plattform |  |  | 23000 | [8 empty] | On Hold |  | 2026-08-03 |  | 5w |  | 23000 |  |  |  | 2026-09-07 | 2026-09-07 |  | 23000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_222 | 2026 | 4 | ALA Outage Kit |  |  | 211826 | [8 empty] | PO Approved |  | 2026-05-15 | 18w | 18w | 211826 |  | ARGP26003013 | G04-US-0003790-1 | 4900614412 | 2026-09-18 | 2026-09-18 |  | 211826 | gregoryd.walker@gevernova.com | 2026-06-25 06:46
CAPEX2026_223 | 2026 | 4 | Unibodies | [11 empty] | On Hold |  | 2026-06-01 |  | 15w | [5 empty] | 2026-09-14 | 2026-09-14 |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_224 | 2026 | 4 | Unibodies stands |  |  | 5000 | [8 empty] | On Hold |  | 2026-06-01 |  | 15w | 5000 |  |  |  |  | 2026-09-14 | 2026-09-14 |  | 5000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_225 | 2026 | 4 | Unibodies stands (from Thomas) |  |  | 3275 | [8 empty] | On Hold |  | 2026-06-01 |  | 15w | 3275 |  |  |  |  | 2026-09-14 | 2026-09-14 |  | 3275 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_226 | 2026 | 4 | Headend with stands | [11 empty] | On Hold |  | 2026-06-01 |  | 15w | [5 empty] | 2026-09-14 | 2026-09-14 |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_227 | 2026 | 4 | Corss fire Tubes | [11 empty] | On Hold |  | 2026-06-01 |  | 15w | [5 empty] | 2026-09-14 | 2026-09-14 |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_228 | 2026 | 4 | ITS Mockup |  |  | 578800 | leadtime 36 weeks - supplier will relook at lead time | [7 empty] | PO Approved |  | 2026-03-27 | 36w | 36w | 0 |  | ARGP26002898 | G10-US-0001070-006-00006 | 4900597690 | 2026-12-04 | 2026-12-04 |  | 0 | gregoryd.walker@gevernova.com | 2026-06-25 08:21
CAPEX2026_229 | 2026 | 4 | ITS plattform |  |  | 40000 | [8 empty] | with Sourcing |  | 2026-12-04 |  | 5w | 0 |  |  |  |  | 2027-01-08 | 2027-01-08 |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_230 | 2026 | 4 | Counterweight and storage stand |  |  | 169368 | [8 empty] | On Hold |  | 2026-04-12 | 20w | 22w | 0 | 0 |  |  |  | 2026-08-30 | 2026-09-13 |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_231 | 2026 | 4 | ITS laser alignment tool |  |  | 60000 | [8 empty] | with Sourcing |  | 2026-04-12 |  | 15w | 60000 |  |  |  |  | 2026-07-26 | 2026-07-26 |  | 60000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_232 | 2026 | 4 | ITS rollout/alignment toolkit |  |  | 30000 | [8 empty] | with Sourcing |  | 2026-04-12 |  | 15w | 30000 |  |  |  |  | 2026-07-26 | 2026-07-26 |  | 30000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_233 | 2026 | 2 | Sherif Khalifa |  |  | 1937612.79 | [13 empty] | 1151820.59 | 155000 |  |  |  | #INVALID OPERATION |  |  | 1306820.59 | philip.ganssmann@gevernova.com | 2026-06-26 04:15
CAPEX2026_234 | 2026 | 3 | HA Tooling | Sherif Khalifa |  | 700000 |  | High | [6 empty] | Everything requested for Project |  |  |  |  | 699361 |  |  |  |  | #INVALID OPERATION |  |  | 699361 | gregoryd.walker@gevernova.com | 2026-06-25 08:30
CAPEX2026_235 | 2026 | 4 | HA Tooling - update ALA and PLL | Sherif Khalifa | [10 empty] | PO received - all done |  | 2025-11-18 |  | 40w | 88768 |  | ARGP25008670 | G04-US-0003472 |  | 2026-08-25 | 2026-08-25 | 2026-05-21 | 88768 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_304 |  | 5 | PLL Outage Kit – 7HA.03 - ARGP25008670 | [11 empty] | PO Approved |  |  |  |  | 72841 |  |  |  | 4900558600 | #INVALID OPERATION |  |  | 72841 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_305 |  | 5 | 7HA PLL Tooling - ARGP25008670 | [11 empty] | PO Approved |  |  |  |  | 15927 |  |  |  | 4900558371 | #INVALID OPERATION |  |  | 15927 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_236 | 2026 | 4 | 7HA.03 PLL/ALA Combustion Kit | Sherif Khalifa | [10 empty] | PO received - all done |  | 2025-11-18 |  | 22w | 220920 |  | ARGP25007855 | G04-US-0003415 | 4900554451 | 2026-04-21 | 2026-04-21 | 2026-05-20 | 220920 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_237 | 2026 | 4 | HA ITS Counter Weight | Sherif Khalifa | [10 empty] | PO opened |  | 2026-01-12 |  | 35w | 186598 |  | ARGP25009640 | G04-US-0003543 | 4900583450 | 2026-09-14 | 2026-09-14 |  | 186598 | gregoryd.walker@gevernova.com | 2026-06-25 08:30
CAPEX2026_238 | 2026 | 4 | Tracc Scan- ITS Pusher, HE Stand, UB Stand, Centerline Jacks | Sherif Khalifa | [10 empty] | PO opened |  | 2026-02-09 |  | 14w | 203075 |  | ARGP26001034 | G04-US-0003601 | 4900583224 | 2026-05-18 | 2026-05-18 | 2026-06-24 | 203075 | gregoryd.walker@gevernova.com | 2026-06-25 08:30
CAPEX2026_239 | 2026 | 3 | HA Improvements | Sherif Khalifa |  | 600000 |  | High | [8 empty] | n/a |  |  | 393756.95 |  |  |  |  | n/a | n/a |  | 393756.95 | gregoryd.walker@gevernova.com | 2026-06-25 08:44
CAPEX2026_240 | 2026 | 4 | 3x Unibodies | Sherif Khalifa |  |  | The vendor is shipping only 2 UB and requested the PO to be amended | [7 empty] | PO Approved |  | 2026-01-12 |  | 12w | 47310 |  | ARGP25009642 | G04-US-0003535 | 4900576426 | 2026-04-06 | 2026-04-06 |  | 47310 | philip.ganssmann@gevernova.com | 2026-06-30 03:41
CAPEX2026_241 | 2026 | 4 | HA platform | Sherif Khalifa | [10 empty] | PO received - all done |  | 2025-12-15 |  | 15w | 287124 |  | ARGP25007962 | G04-US-0003414 | 4900561718 | 2026-03-30 | 2026-03-30 | 2026-01-01 | 287124 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_242 | 2026 | 4 | Fall Arest | Sherif Khalifa |  | 59322.95 | [8 empty] | PO received - all done |  | 2026-03-20 |  | 4w | 59322.95 |  | ARGP26002128 |  | 4900595386 | 2026-04-17 | 2026-04-17 | 2026-05-22 | 59322.95 | philip.ganssmann@gevernova.com | 2026-06-30 03:41
CAPEX2026_243 | 2026 | 3 | Lean Tools - 7E | Sherif Khalifa |  | 200000 |  | High | [11 empty] | 58702.64 |  |  |  |  | #INVALID OPERATION |  |  | 58702.64 | gregoryd.walker@gevernova.com | 2026-06-25 08:51
CAPEX2026_244 | 2026 | 4 | Bump Check Tools | Sherif Khalifa |  | 13347 | [8 empty] | PO Approved |  | 2026-01-12 |  | 7w | 13547 |  | ARGP25009641 | G04-US-0003533-1 | 4900575893 | 2026-03-02 | 2026-03-02 | 2026-05-22 | 13547 | gregoryd.walker@gevernova.com | 2026-06-25 08:51
CAPEX2026_245 | 2026 | 4 | Rotating Device | Sherif Khalifa |  | 43885.74 | [8 empty] | PO Approved |  | 2026-02-17 |  | 19w | 45155.64 |  | ARGP25009643 |  | 4900595387 | 2026-06-30 | 2026-06-30 |  | 45155.64 | gregoryd.walker@gevernova.com | 2026-06-25 08:51
CAPEX2026_246 | 2026 | 3 | TracScan Laser Replacement | Sherif Khalifa |  | 25000 | Replaces outdated laser scanning tools to enhance accuracy | High | Modernization | [5 empty] | PO received - all done | [9 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-30 03:41
CAPEX2026_279 |  | 3 | Lean Tools (Sherif) | Sherif Khalifa |  | 397274.9 | Additional Lean Tools | [7 empty] | Requesting Quote from Vendor | [5 empty] | 155000 |  |  |  | #INVALID OPERATION |  |  | 155000 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_308 |  | 4 | 7HA.03 CMPR ICC/ IDC to OCC Leveling Tool | Jimmy Capps |  | 10000 | [8 empty] | Requesting Quote from Vendor |  | 2026-06-22 |  | 12w |  | 10000 |  |  |  | 2026-09-14 | 2026-09-14 |  | 10000 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_309 |  | 4 | 7HA.03 ITS/OTS Guide Pin, Jacking Bolt & Hoist Ring Kit | Jimmy Capps |  | 40000 | [8 empty] | Requesting Quote from Vendor |  | 2026-06-22 |  | 16w |  | 40000 |  |  |  | 2026-10-12 | 2026-10-12 |  | 40000 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_310 |  | 4 | 7HA.03 ITS Lateral Alignment Pusher | Jimmy Capps |  | 5000 | [8 empty] | Requesting Quote from Vendor |  | 2026-06-22 |  | 6w |  | 5000 |  |  |  | 2026-08-03 | 2026-08-03 |  | 5000 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_311 |  | 4 | 7HA.03 ITS Hydraulic Drive Motor & Adapter Plate Kit | Jimmy Capps |  | 50000 | [8 empty] | Requesting Quote from Vendor |  | 2026-06-22 |  | 24w |  | 50000 |  |  |  | 2026-12-07 | 2026-12-07 |  | 50000 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_312 |  | 4 | 7HA.01/02/03 & 9HA.01/02 ITS Hydraulic Pump and Cart | Jimmy Capps |  | 50000 | [8 empty] | Requesting Quote from Vendor |  | 2026-06-22 |  | 24w |  | 50000 |  |  |  | 2026-12-07 | 2026-12-07 |  | 50000 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_313 |  | 4 | ITH KIT | Jimmy Capps |  | 178608.59 | [8 empty] | with Sourcing |  | 2026-06-22 |  | 12w | 178608.59 |  | ARGP26005181 |  |  | 2026-09-14 | 2026-09-14 |  | 178608.59 | gregoryd.walker@gevernova.com | 2026-06-25 08:51
CAPEX2026_314 |  | 4 | Composite cribbing | Jimmy Capps |  | 15000 | not a CAPEX spend | [7 empty] | Cancelled |  | 2026-06-22 | [7 empty] | 2026-06-22 | #INVALID OPERATION |  | 0 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_315 |  | 4 | Enerpac Kit | Jimmy Capps |  | 33666.31 | [8 empty] | AR Created |  | 2026-07-01 |  | 5w | 33666.31 |  | ARGP26005181 | G04-US-0004014-1 |  | 2026-08-05 | 2026-08-05 |  | 33666.31 | philip.ganssmann@gevernova.com | 2026-07-01 02:24
CAPEX2026_316 |  | 4 | 7HA.03 CMPR IDC Aft Jack Support Kit | Jimmy Capps | South Coast Manufacturing, LLC | 15000 | [8 empty] | PO Approved | 2026-06-22 | 2026-06-24 | 4w | 5w | 14606 |  | ARGP26005181 | G04-US-0004014-3 | 4900626850 | 2026-07-22 | 2026-07-29 |  | 14606 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_326 |  | 3 | TDI Lab Tools |  |  | 15337.89 | [8 empty] | AR Created | [9 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-26 04:15
CAPEX2026_327 |  | 4 | Wyler/Fowler Adjustable Micrometer Spirit Level 68 Manufacturer P/N 168-150-111-020 |  | PENN TOOL Co. | 4795 | Fixator /Fixators setup | [17 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-26 04:15
CAPEX2026_328 |  | 4 | Straight Edge 60" (1540x70x15mm) Code No. EA204 |  | Obishi site | 4761.8 | Fixator /Fixators setup | [17 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-26 04:15
CAPEX2026_329 |  | 4 | 200T Hydrualic Jack |  | Enerpac Link | 5781.09 | GT Dropcheck (7F) | [17 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-26 04:15
CAPEX2026_317 |  | 2 | 7HA Unbalancing Turning Device | Jimmy Capps | [12 empty] | 2026-06-22 |  | 14w | 78060 |  |  |  |  | 2026-09-28 | 2026-09-28 |  | 78060 | philip.ganssmann@gevernova.com | 2026-06-25 02:43
CAPEX2026_247 | 2026 | 2 | Steve Urban |  |  | 1484273.58 | [13 empty] | 1180958.7 | 214273.58 |  |  |  | #INVALID OPERATION |  |  | 1395232.28 | philip.ganssmann@gevernova.com | 2026-06-26 04:08
CAPEX2026_248 | 2026 | 3 | Hurricane Tie Down |  |  | 100000 | Add hurricane straps on B1 AC units | High | [6 empty] | with Sourcing | [5 empty] | 100000 |  |  |  | #INVALID OPERATION |  |  | 100000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_249 | 2026 | 3 | Building 2 New Roof |  |  | 575000 | Ensures storm resistance and protects Building 2 from damage during severe weather | High | [6 empty] | PO opened |  | 2026-06-01 |  | 16w | 411134 |  | ARGP26004508 | G04-US-0003964-1 |  | 2026-09-21 | 2026-09-21 |  | 411134 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_250 | 2026 | 3 | New AC units bldg. 1 phase A |  |  | 250000 |  | High |  |  |  |  | 2026-01-01 | 2026-02-28 | PO received - all done |  | 2026-01-12 |  | 8w | 179455 |  | ARGP25007837 | G04-US-0003413 |  | 2026-03-09 | 2026-03-09 |  | 179455 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_251 | 2026 | 3 | New Switchgear bldg. 2 |  |  | 350000 |  | High | [6 empty] | PO Approved |  | 2026-01-12 |  | 37w | 512331 |  | ARGP26000596 | G04-US-0003572 |  | 2026-09-28 | 2026-09-28 |  | 512331 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_252 | 2026 | 3 | New Scissors gates bldg. 1 |  |  | 15000 |  | High | Safety | [5 empty] | PO opened |  | 2026-04-19 |  | 10w | 8745 |  | ARGP26003479 | G04-US-0003847-1 |  | 2026-06-28 | 2026-06-28 |  | 8745 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_320 |  | 3 | Carpet |  |  | 114273.58 | New Carpet after Hurrican damage | [7 empty] | AR Created |  | 2026-07-06 | 3w | 3w |  | 114273.58 | ARGP26005809 |  |  | 2026-07-27 | 2026-07-27 |  | 114273.58 | philip.ganssmann@gevernova.com | 2026-06-26 04:08
CAPEX2026_321 |  | 4 | Rooms #1200 & 1201 |  |  | 9947.25 | [10 empty] | 2026-07-06 | 3w | 3w |  | 9947.25 | ARGP26005809 |  |  | 2026-07-27 | 2026-07-27 |  | 9947.25 | philip.ganssmann@gevernova.com | 2026-06-26 04:55
CAPEX2026_322 |  | 4 | Rooms #1202, 1203, 1204 & 1205 |  |  | 8936 | [10 empty] | 2026-07-06 | 3w | 3w |  | 8936 | ARGP26005809 |  |  | 2026-07-27 | 2026-07-27 |  | 8936 | philip.ganssmann@gevernova.com | 2026-06-26 04:55
CAPEX2026_323 |  | 4 | Rooms #1206, 1207, 1208 & 1209 |  |  | 9673.2 | [10 empty] | 2026-07-06 | 3w | 3w |  | 9673.2 | ARGP26005809 |  |  | 2026-07-27 | 2026-07-27 |  | 9673.2 | philip.ganssmann@gevernova.com | 2026-06-26 04:55
CAPEX2026_324 |  | 4 | Rooms #1210, 1211 & 124 |  |  | 8002.29 | [10 empty] | 2026-07-06 | 3w | 3w |  | 8002.29 | ARGP26005809 |  |  | 2026-07-27 | 2026-07-27 |  | 8002.29 | philip.ganssmann@gevernova.com | 2026-06-26 04:55
CAPEX2026_325 |  | 4 | Rooms #1200 & 1201 |  |  | 77714.84 | [10 empty] | 2026-07-06 | 3w | 3w |  | 77714.84 | ARGP26005809 |  |  | 2026-07-27 | 2026-07-27 |  | 77714.84 | philip.ganssmann@gevernova.com | 2026-06-26 04:55
CAPEX2026_253 | 2026 | 3 | Fans for Bay 3,4,1 |  |  | 80000 | - 1 fan for the HA CDC Mockup Ground Level - 1 Fan for the HA CDC Mockup upper Level - 1 Fan for the 7FH2 Generator upper Level - 1 Fan for the 7FA north side - 2 Fans for the HA upper level North and South - 2 Fans for the HA Lower Level North and South. | [7 empty] | AR Created |  | 2026-06-08 |  | 5w | 69293.7 |  | ARGP26004976 | G04-US-0003975-1 |  | 2026-07-13 | 2026-07-13 |  | 69293.7 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_254 | 2026 | 2 | Pablo Schibli |  |  | 69000 | [13 empty] | 0 | 41000 |  |  |  | #INVALID OPERATION |  |  | 41000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_255 | 2026 | 3 | Lifting Equipment (Birr) |  |  | 25000 | Ensures compliance with the latest standards, enhancing operational safety | High | Safety | [5 empty] | No action done yet | [5 empty] | 25000 |  |  |  | #INVALID OPERATION |  |  | 25000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_256 | 2026 | 3 | Electrical equipment upgrades (BLC) |  |  | 16000 | This equipment is used in the field and would be used during our trainings of COMET, GT Expert, ST Expert and related labs. By having this instrument, we can ensure that we have the same instruments that are used on site and that our students are familiar with their use and properties and reduce our dependence on the tooling center. Historically, we have ordered this instrument from the tooling centers , but its availability is often limited due to prioritizing inspections or being part of a comprehensive instrument box. Therefore, most of the time we cannot complete some labs, or we do them with obsolete instruments | High | Capability | [5 empty] | No action done yet | [5 empty] | 16000 |  |  |  | #INVALID OPERATION |  |  | 16000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_257 | 2026 | 3 | Cribbing blocks (HLC) |  |  | 14000 | Ensures compliance with the latest standards, enhancing operational safety. | High | Safety | [5 empty] | Cancelled |  |  |  |  | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_258 | 2026 | 3 | Cribbing blocks (BLC) |  |  | 14000 | Ensures compliance with the latest standards, enhancing operational safety. | High | Safety | [5 empty] | Cancelled |  |  |  |  | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_259 | 2026 | 2 | Harry Hanson |  |  | 240500 | [13 empty] | 210897 | 0 |  |  |  | #INVALID OPERATION |  |  | 210897 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_260 |  | 3 | Entry Level Generator Repairs Accelerated - Equipment | Harry Hanson |  | 40000 | Tables and Mockups | [7 empty] | PO received - all done |  | 2025-11-17 | 4w | 5w | 39015 |  | ARGP25008209 | G04-US-0003430 | 4900558618 | 2025-12-15 | 2025-12-22 |  | 39015 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_261 | 2026 | 3 | Tools for Bucket Tech Class | Harry Hanson |  | 165000 |  | High | [6 empty] | PO Approved |  |  |  |  | 156382 |  | ARGP26003096 | G04-US-0003791 |  | #INVALID OPERATION |  |  | 156382 | gregoryd.walker@gevernova.com | 2026-06-26 07:20
CAPEX2026_262 |  | 4 | 6B LOCK WIRE DOWEL PINHOLE DRILLING TOOL | Harry Hanson |  | 8115 | [8 empty] | PO Approved |  | 2026-04-13 | 6w | 8w | 8115 |  | ARGP26003096-001 | G04-US-0003791-1 | 4900610143 | 2026-05-25 | 2026-06-08 |  | 8115 | gregoryd.walker@gevernova.com | 2026-06-26 07:01
CAPEX2026_263 |  | 4 | 6B LOCKTAB DOWEL PIN HOLE DRILLING | Harry Hanson |  | 9574 | [8 empty] | PO Approved |  | 2026-04-13 | 6w | 8w | 9574 |  | ARGP26003096-002 | G04-US-0003791-2 | 4900610142 | 2026-05-25 | 2026-06-08 | 2026-06-25 | 9574 | gregoryd.walker@gevernova.com | 2026-06-26 06:53
CAPEX2026_264 |  | 4 | 7E ROTOR TURNING DEVICE | Harry Hanson |  | 8665 | [8 empty] | PO Approved |  | 2026-04-13 | 6w | 8w | 8665 |  | ARGP26003096-003 | G04-US-0003791-3 | 4900610141 | 2026-05-25 | 2026-06-08 |  | 8665 | gregoryd.walker@gevernova.com | 2026-06-26 07:01
CAPEX2026_265 |  | 4 | 7E TWISTLOCK STAKING TOOL | Harry Hanson |  | 41539 | [8 empty] | PO Approved |  | 2026-04-13 | 8w | 12w | 41539 |  | ARGP26003096-004 | G04-US-0003791-6 | 4900611324 | 2026-06-08 | 2026-07-06 | 2026-06-24 | 41539 | gregoryd.walker@gevernova.com | 2026-06-26 06:53
CAPEX2026_266 |  | 4 | 7F STAGE 5 THRU 16 STATOR BLADE MILLING MACHINE | Harry Hanson |  | 38635 | [8 empty] | PO Approved |  | 2026-04-13 | 8w | 12w | 38635 |  | ARGP26003096-005 | G04-US-0003791-4 | 4900611322 | 2026-06-08 | 2026-07-06 |  | 38635 | gregoryd.walker@gevernova.com | 2026-06-26 06:53
CAPEX2026_267 |  | 4 | 7FA STG# I—3 LOCKWIRE DRILL FIXTURE | Harry Hanson |  | 7923 | [8 empty] | PO Approved |  | 2026-04-13 | 6w | 10w | 7923 |  | ARGP26003096-006 | G04-US-0003791-5 | 4900610144 | 2026-05-25 | 2026-06-22 | 2026-06-26 | 7923 | gregoryd.walker@gevernova.com | 2026-06-26 06:53
CAPEX2026_268 |  | 4 | 7EA RI7 DOVE TAIL MILL | Harry Hanson |  | 41931 | [8 empty] | PO Approved |  | 2026-04-13 | 8w | 12w | 41931 |  | ARGP26003096-007 | G04-US-0003791-7 | 4900611323 | 2026-06-08 | 2026-07-06 |  | 41931 | gregoryd.walker@gevernova.com | 2026-06-26 07:01
CAPEX2026_269 | 2026 | 3 | Fast Stator Rewind Class - Round Pack Tool | Harry Hanson |  | 15500 | [8 empty] | PO Approved |  | 2026-03-19 |  | 8w | 15500 |  | ARGP26001597 | G04-US-0003649-1 | 4900595027 | 2026-05-14 | 2026-05-14 | 2026-05-29 | 15500 | gregoryd.walker@gevernova.com | 2026-06-26 07:20
CAPEX2026_270 | 2026 | 3 | CNC controller on the Bridgeport milling machine |  |  | 20000 |  | High | [6 empty] | Cancelled |  |  |  |  | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_277 |  | 2 | Diaphragm mock-ups |  |  | 47000 | [8 empty] | PO received - all done |  | 2026-05-11 | 5w | 8w |  | 47000 | ARGP26004137 |  |  | 2026-06-15 | 2026-07-06 | 2026-06-30 | 47000 | philip.ganssmann@gevernova.com | 2026-07-01 02:27
CAPEX2026_271 | 2026 | 2 | Carry Over 2025 |  |  | 265000 | [13 empty] | 265000 | 0 |  |  |  | #INVALID OPERATION |  |  | 265000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_272 |  | 3 | Backlog X |  |  | 65000 | [8 empty] | PO received - all done |  | 2025-10-06 |  | 1w | 65000 |  |  |  |  | 2025-10-13 | 2025-10-13 |  | 65000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_273 | 2026 | 3 | Scheduling Panels |  |  | 50000 | [8 empty] | PO received - all done |  | 2025-07-01 |  | 35w | 50000 |  |  |  |  | 2026-03-03 | 2026-03-03 |  | 50000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_274 |  | 3 | Roof Building 1 |  |  | 150000 | [8 empty] | PO received - all done |  | 2025-10-06 |  | 1w | 150000 |  |  |  |  | 2025-10-13 | 2025-10-13 |  | 150000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_275 | 2026 | 2 | To be discussed to add | [16 empty] | 0 | 53000 |  |  |  | #INVALID OPERATION |  |  | 53000 | philip.ganssmann@gevernova.com | 2026-07-01 02:27
CAPEX2026_276 |  | 3 | 2nd Person Training |  |  | 270000 | Update existing 2nd Person online Training | [9 empty] | 2026-06-01 |  | 24w |  | 0 |  |  |  | 2026-11-16 | 2026-11-16 |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_278 |  | 3 | Michele USC |  |  | 53000 | Additional USCs for customer trainings | [13 empty] | 53000 |  |  |  | #INVALID OPERATION |  |  | 53000 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_306 |  | 3 | Not in Budget | [21 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_280 | 2026 | 4 | Michele Alcantar |  |  | 54000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_281 | 2026 | 5 | T60 and G60 relay |  |  | 30000 | Ability to deliver OJT to customers | Medium | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_282 | 2026 | 5 | CIAB Kits |  |  | 24000 | Replace stolen and obsolete CIAB kits for customer training | Medium | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_283 | 2026 | 4 | Mohammed Nizami |  |  | 1030000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_284 | 2026 | 5 | MKVIe desktop panels |  |  | 60000 | We are seeking approval for the purchase of new equipment to modernize the Mark VIe desktop panels at the BLC. Currently, we have nine panels in use, and upgrading this equipment will allow us to align with the latest technology installed. | Medium | Modernization | [15 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_285 | 2026 | 5 | Replace HMIs |  |  | 150000 | Update aging HMIs with latest version | Medium | Modernization | [15 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_286 | 2026 | 5 | UCSE Controllers |  |  | 320000 | Replaces obsolete controllers, allowing for continued effective MKVIe training | Medium | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_287 | 2026 | 5 | Control Server with OT Armor + Cybersecurity |  |  | 500000 | Enables advanced-level cybersecurity training, enhancing both internal and external training capabilities | Medium | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_288 | 2026 | 4 | Greg Walker |  |  | 400000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_289 | 2026 | 5 | LMS100 IPT Tooling |  |  | 400000 | Run reliable ELT LMS100 course and not rely on external tooling center (J Port) | Low | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_290 | 2026 | 4 | Sherif Khalifa |  |  | 0 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_291 | 2026 | 5 | Expansion Sleeve Coupling Mockup |  |  | 0 | Ensures proper equipment handling, reduces safety risks during hands-on training | Cancel | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_292 | 2026 | 5 | Lamina Drill and Power Pack |  |  | 0 | Eliminates rental costs and enables self-sufficiency in turbine repair training | Cancel | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_293 | 2026 | 5 | Lab mock-up to run additional GT ELT class |  |  |  | Run additional classes in Birr, Switzerland | [17 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_294 | 2026 | 4 | Steve Urban |  |  | 1100000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_295 | 2026 | 5 | New Breakers Bld1 1 East Switchgear |  |  | 0 | Grounds improvement to mitigate flood risk | Cancel | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_296 | 2026 | 5 | New man doors bldg. 1 |  |  | 100000 |  | Medium | [16 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_297 | 2026 | 5 | New Crane for Bay 1 |  |  | 1000000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_298 | 2026 | 4 | Pablo Schibli |  |  | 40000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_299 | 2026 | 5 | Distance Learning Room Modernisation |  |  | 40000 | [18 empty] | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_300 | 2026 | 4 | Harry Hanson |  |  | 0 | [13 empty] | 0 |  |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_301 | 2027 | 1 | CAPEX 2027 Overall |  |  | 578800 | Requests with 'High Priority': 5.09M | [12 empty] | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_302 | 2027 | 2 | Salim Messekine |  |  | 578800 | [13 empty] | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59
CAPEX2026_303 | 2027 | 3 | ITS Mockup |  |  | 578800 | leadtime 36 weeks | [12 empty] | 0 | 0 |  |  |  | #INVALID OPERATION |  |  | 0 | philip.ganssmann@gevernova.com | 2026-06-24 08:59

## Comments
Row 51 | look at getting them over OPEX | Philip Ganssmann | 08/06/25 7:36 AM
Row 63 | Tamil will be meeting with the engineering team in Mexico in mid-March to finalize simulations and confirm hardware requirements. Based on that timing, we’re targeting mid-April to complete quotes and submit the POs. None of the anticipated items are long lead, so we don’t see schedule risk once requirements are locked in. | Philip Ganssmann | 02/18/26 1:26 PM
Row 63 | Working on quotes, should have everything ready before end of January | Philip Ganssmann | 12/15/25 1:57 PM
Row 126 | wait until April | Philip Ganssmann | 02/20/26 9:18 AM
Row 134 | Quotes being prepared by vendor | Philip Ganssmann | 02/19/26 2:37 AM
Row 143 | Would rather cancel this and use the $$$ for the Gen Repairs Round Packing tooling | Philip Ganssmann | 02/19/26 2:37 AM
Row 155 | look at getting them over OPEX | Philip Ganssmann | 08/06/25 7:36 AM

## Summary
Priority High | 5092264
Priority Medium | 1184000