## OFS Training Action Plan Tracke
AP# | Improvement | AP ID# | AutoNum | UniqueID | Parent ID | ParentID | Parent_Level | Child# | Is Parent | Is Child | Lead | Assist | Owner | Bucket | Description | Overall Status | No report-out at this level | Current Status | Current Start | Current Finish | Previous Finish Date | Move/Cancel Pending Discussion | Original Start | Original Finish | Impacted Trng Roles | Impacted Non Training Roles | KPI Connection | SQDCG | Source | Original Requester | Comments | One-pager Link | Duration | Predecessors | is starting this month | is due this month | Is due next month | Is due last month | At Risk | PLL Lead? | Start Date (date only) | Finish Date (date only) | Created | Created By
AP-007 | Capturing Standard Work | AP-007 | AP-0416 | Capturing Standard WorkAP-0416 | #INVALID COLUMN VALUE | Top | 0 | 1 | 1 | 0 | Jennifer Wright | Livia SILVA, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Develop & implement structure for capturing & communicating OFS Training Standard Work | Complete |  | On Track | 2024-11-01 | 2025-04-29 |  |  | 2024-11-01 | 2025-02-28 | [7 empty] | n/a-parent row | 128d | [6 empty] | No | 2024-11-01 | 2025-04-29 | 2024-12-16 09:19 | jennifer.b.wright@ge.com
AP-007-1 | Develop Guidebook Structure |  | AP-0418 | Develop Guidebook StructureAP-0418 | AP-007 | AP-007 | 1 | 1 | 0 | 1 | Jennifer Wright | David Ramey, James Rosen, Johann Josef Daxer, Leonardo Monzo, Livia SILVA, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Build structure for OFS Training Guidebook | Complete |  |  | 2024-11-01 | 2024-12-31 |  |  | 2024-11-01 | 2024-12-31 | Customer Delivery Internal Ops P&C | [5 empty] | Completed in 2024, copied here for context |  | 43d | [6 empty] | No | 2024-11-01 | 2024-12-31 | 2024-12-16 09:26 | jennifer.b.wright@ge.com
AP-007-2 | Build out Guidebook Content |  | AP-0419 | Build out Guidebook ContentAP-0419 | AP-007 | AP-007 | 1 | 2 | 0 | 1 | Jennifer Wright | David Ramey, James Rosen, Johann Josef Daxer, Leonardo Monzo, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Complete slides for all functions | Complete |  | On Track | 2024-11-01 | 2025-03-31 |  |  | 2024-11-01 | 2025-01-31 | Customer Delivery Internal Ops P&C | RM |  |  |  |  | 1/28/25-Moved to Feb closure to allow extra time to fully complete slides 2/21/25-Moved to March closure due to delays with gathering slides content. | https://gevernova.ent.box.com/file/1813584194223 | 107d | [6 empty] | No | 2024-11-01 | 2025-03-31 | 2024-12-16 09:26 | jennifer.b.wright@ge.com
AP-007-3 | Publish & Communicate Guidebook |  | AP-0417 | Publish & Communicate GuidebookAP-0417 | AP-007 | AP-007 | 1 | 3 | 0 | 1 | Jennifer Wright | Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Finalize Guidebook & release to Training & OFS community Develop Quarterly rhythm for reviewing/updating Guidebook | Complete |  | On Track | 2025-04-01 | 2025-04-29 |  |  | 2025-02-01 | 2025-02-28 | Customer Delivery Internal Ops P&C | FE OSS RM | [5 empty] | https://gevernova.ent.box.com/file/1847877433525 | 21d | 3 | [5 empty] | No | 2025-04-01 | 2025-04-29 | 2024-12-16 09:26 | jennifer.b.wright@ge.com
AP-0223 | Standard Work for Instructor Assignment Info |  | AP-0223 | Standard Work for Instructor Assignment InfoAP-0223 | #INVALID COLUMN VALUE | Top | 0 | 2 | 0 | 0 | patrick.molumby@gevernova.com | A. Ruch, Jen Wright, Michele Alcantar | johann.daxer@gevernova.com | Operational Simplification | Instructors to connect with PM at training start, Manual shipping expediting, close out docu storage | Complete |  | On Track | 2025-03-12 | 2025-08-08 |  |  | 2025-01-01 | 2025-05-31 | Instructors, CT PM | GRUPO | [5 empty] | https://gevernova.ent.box.com/file/1875051109521 | 108d | [6 empty] | No | 2025-03-12 | 2025-08-08 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0224 | Simplify LOI process |  | AP-0224 | Simplify LOI processAP-0224 | #INVALID COLUMN VALUE | Top | 0 | 3 | 0 | 0 | Gavin Yoong | Anna Carmela Petrella, Jennifer Wright, nelsa1.bernal@gevernova.com, Philip Ganssmann | johann.daxer@gevernova.com | Operational Simplification | HLC/BLC LOI process for customer training. consider using similar process as FC LOI automation | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | Logistics (Nelsa), CT PM | - | [5 empty] | https://gevernova.ent.box.com/file/1807900276063 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0227 | Simplify FC instructor invoice handling |  | AP-0227 | Simplify FC instructor invoice handlingAP-0227 | #INVALID COLUMN VALUE | Top | 0 | 4 | 0 | 0 | abuobaida.elmansoor@gevernova.com | Philip Ganssmann | johann.daxer@gevernova.com | Operational Simplification | FC Invoice copies to be shared with PMs – maybe this can be automated. | Complete |  | On Track | 2025-01-01 | 2025-06-30 |  |  | 2025-01-01 | 2025-04-30 | FieldCore RM, CT PM | [5 empty] | 14Apr25-moved to May to allow more time for investigation & solution development 28May25-moved to June due to technical issues with data sources. Need more time to validate once it's ready | https://gevernova.ent.box.com/file/1903617738838 | 129d | [6 empty] | No | 2025-01-01 | 2025-06-30 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0228 | Simplify equipment / facilities fee charging |  | AP-0228 | Simplify equipment / facilities fee chargingAP-0228 | #INVALID COLUMN VALUE | Top | 0 | 5 | 0 | 0 | anna.petrella@gevernova.com | nelsa1.bernal@gevernova.com | johann.daxer@gevernova.com | Operational Simplification | KB15N transaction instead of POs for Skytap & Facilities (generally approved), how to do it efficiently | Complete |  | On Track | 2024-12-01 | 2025-03-31 |  |  | 2024-12-01 | 2025-03-31 | Logistics (Nelsa), CT PM | [6 empty] | https://gevernova.ent.box.com/file/1808677305099 | 87d | [6 empty] | No | 2024-12-01 | 2025-03-31 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0229 | Simplify Open Enrollment Billing process |  | AP-0229 | Simplify Open Enrollment Billing processAP-0229 | #INVALID COLUMN VALUE | Top | 0 | 6 | 0 | 0 | maria.medina@gevernova.com | András Pintér, nelsa1.bernal@gevernova.com | johann.daxer@gevernova.com | Operational Simplification | OE Billing simplification: e.g. uploading invoice to customer systems by biller? | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-04-30 | Logistics (Nelsa), Finance (Andras) | Finance support team in India |  |  |  |  | 14Apr25-moved to May to allow more time to coordinate with Global teams 29Apr25-moved back to May - able to close on time | https://gevernova.ent.box.com/file/1848540112052 | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230 | Simplify & align overall CT PM process |  | AP-0230 | Simplify & align overall CT PM processAP-0230 | #INVALID COLUMN VALUE | Top | 0 | 7 | 1 | 0 | johann.daxer@gevernova.com | Abuobaida El Mansoor, Alejandra María Saldaña, Anna Carmela Petrella, Gavin.Yoong@gevernova.com, Jennifer Wright, MARIA MEDINA | johann.daxer@gevernova.com | Operational Simplification | Bringing the overall Customer Training Process up to date based on several sub-improvement projects | In Progress |  | On Track | 2025-04-01 | 2027-07-30 |  |  | 2025-04-01 | 2025-12-31 | CT PM, see sub-items | see sub-items | OFS-Cost-Cost-Gross Margin | C | Other |  | 11Mar26-adjusted dates & added new sub-tasks based on project review/update in Greenville | n/a-parent row | 609d | [6 empty] | No | 2025-04-01 | 2027-07-30 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230-1 | Support Customer Training inputs/outputs/fields/views for Scheduling Tool Transition |  | AP-0410 | Support Customer Training inputs/outputs/fields/views for Scheduling Tool TransitionAP-0410 | AP-0230 | AP-0230 | 1 | 1 | 0 | 1 | maria.medina@gevernova.com | Jennifer Wright, nelsa1.bernal@gevernova.com | johann.daxer@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2025-04-01 | 2025-10-31 |  |  | 2025-04-01 | 2025-05-30 | Customer Ops | [5 empty] | 1May25-cleared Current start & finish dates while we re-adjust these items to align with the new scheduling tool timing & requirements 6May25-updated improvement scope, team & dates 21Aug25-Moved to Sept due to UDC Team delays 18Sept25-Moved to Oct due to UDC Team delays | https://gevernova.ent.box.com/file/2029597177205 | 154d | [6 empty] | No | 2025-04-01 | 2025-10-31 | 2024-12-12 09:15 | johann.daxer@ge.com
AP-0230-2 | Support GRM View Development & notification process for new Scheduling Tool |  | AP-0231 | Support GRM View Development & notification process for new Scheduling ToolAP-0231 | AP-0230 | AP-0230 | 1 | 2 | 0 | 1 | patrick.molumby@gevernova.com | Jennifer Wright, nelsa1.bernal@gevernova.com | johann.daxer@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2025-04-01 | 2025-10-31 |  |  | 2025-04-01 | 2025-05-30 | Customer Ops | [5 empty] | 21Aug25-Moved to Sept due to UDC Team delays 18Sept25-Moved to Oct due to UDC Team delays | https://gevernova.ent.box.com/file/2029597177205 | 154d | [6 empty] | No | 2025-04-01 | 2025-10-31 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230-3 | Develop Customer Training Forecast & PM Tracking SmartSheet reports/automations |  | AP-0232 | Develop Customer Training Forecast & PM Tracking SmartSheet reports/automationsAP-0232 | AP-0230 | AP-0230 | 1 | 3 | 0 | 1 | alejandra.saldana@gevernova.com | Jennifer Wright | johann.daxer@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2025-11-01 | 2026-01-30 |  |  | 2025-05-01 | 2025-07-31 | Customer |  |  |  | Other |  | 1May25-cleared Current start & finish dates while we re-adjust these items to align with the new scheduling tool timing & requirements 6May25-updated improvement scope, team & dates 4Sept25-Moved back a month due to scheduling tool delays 29Sept25 (JD): start date adjusted to scheduling tool progress | https://gevernova.ent.box.com/file/2116931795507 | 66d | [6 empty] | No | 2025-11-01 | 2026-01-30 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230-4 | Develop Customer Training Financial Summary Smartsheet reports/automations |  | AP-0233 | Develop Customer Training Financial Summary Smartsheet reports/automationsAP-0233 | AP-0230 | AP-0230 | 1 | 4 | 0 | 1 | abuobaida.elmansoor@gevernova.com | Jennifer Wright | johann.daxer@gevernova.com | Operational Simplification |  | Cancelled |  |  | 2025-12-01 | 2026-04-01 |  |  | 2025-06-01 | 2025-08-29 | Customer |  |  |  | Other |  | 1May25-cleared Current start & finish dates while we re-adjust these items to align with the new scheduling tool timing & requirements 6May25-updated improvement scope, team & dates 4Sept25-Moved back a month due to scheduling tool delays 29Sept25 (JD): start date adjusted to scheduling tool progress 11Mar26-Cancelled to focus on other subtasks at this time |  | 88d | [6 empty] | No | 2025-12-01 | 2026-04-01 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230-5 | Develop Customer Training Master Billing File Smartsheet reports/automations |  | AP-0225 | Develop Customer Training Master Billing File Smartsheet reports/automationsAP-0225 | AP-0230 | AP-0230 | 1 | 5 | 0 | 1 | Gavin Yoong | Jennifer Wright | johann.daxer@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2026-01-01 | 2026-05-29 |  |  | 2025-08-01 | 2025-10-31 | Customer | Billing team in India |  |  | Other |  | 1May25-cleared Current start & finish dates while we re-adjust these items to align with the new scheduling tool timing & requirements 6May25-updated improvement scope, team & dates 4Sept25-Moved back a month due to scheduling tool delays 29Sept25 (JD): start date adjusted to scheduling tool progress 11Mar26-Start date adjusted to align with new approach from March Staff meeting | https://gevernova.ent.box.com/file/2246013179984 | 107d |  |  |  |  | TRUE |  | No | 2026-01-01 | 2026-05-29 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230-6 | Transfer CT projects from UDC and Tracking sheet into Smartsheet |  | AP-0838 | Transfer CT projects from UDC and Tracking sheet into SmartsheetAP-0838 | AP-0230 | AP-0230 | 1 | 6 | 0 | 1 | Jennifer Wright | abuobaida.elmansoor@gevernova.com, alejandra.saldana@gevernova.com, anna.petrella@gevernova.com, Gavin Yoong, johann.daxer@gevernova.com, patrick.molumby@gevernova.com | johann.daxer@gevernova.com | Operational Simplification | PMs have tracking sheets locally,they'll send to Jen. Establish "blackout" dates for no more changes to Tracking sheets. | Complete |  | On Track | 2026-03-15 | 2026-05-29 |  |  |  |  | Customer |  |  |  | Other |  | 11Mar26-added from March Staff Meeting | https://gevernova.ent.box.com/file/2248641421275 | 56d |  |  |  |  | TRUE |  | No | 2026-03-15 | 2026-05-29 | 2026-03-11 10:42 | jennifer.b.wright@gevernova.com
AP-0230-7 | Add 2027 projects within standard June/July forecasting cycle |  | AP-0840 | Add 2027 projects within standard June/July forecasting cycleAP-0840 | AP-0230 | AP-0230 | 1 | 7 | 0 | 1 | johann.daxer@gevernova.com | abuobaida.elmansoor@gevernova.com, alejandra.saldana@gevernova.com, anna.petrella@gevernova.com, Gavin Yoong, patrick.molumby@gevernova.com | johann.daxer@gevernova.com | Operational Simplification |  | Not Started |  |  | 2026-06-01 | 2026-07-31 |  |  |  |  | Customer |  |  |  | Other |  | 11Mar26-added from March Staff Meeting |  | 45d |  | TRUE |  | TRUE |  |  | No | 2026-06-01 | 2026-07-31 | 2026-03-11 10:42 | jennifer.b.wright@gevernova.com
AP-0230-8 | Set up OE Smartsheet for Forecast Reporting |  | AP-0839 | Set up OE Smartsheet for Forecast ReportingAP-0839 | AP-0230 | AP-0230 | 1 | 8 | 0 | 1 | maria.medina@gevernova.com | Jennifer Wright | johann.daxer@gevernova.com | Operational Simplification | Build Sheet in Smartsheet where Maria loads her UDC input file and then it pulls remaining UDC data for OE Forecast | Not Started |  |  | 2026-06-01 | 2026-07-31 |  |  |  |  | Customer |  |  |  | Other |  | 11Mar26-added from March Staff Meeting 16Apr26-Renamed to clarify scope |  | 45d |  | TRUE |  | TRUE |  |  | No | 2026-06-01 | 2026-07-31 | 2026-03-11 10:42 | jennifer.b.wright@gevernova.com
AP-0230-9 | Build Tableau reports for open PMx and Alpha Uplift POs, based on WBSEs and Alpha Uplift project #’s in Smartsheet |  | AP-0226 | Build Tableau reports for open PMx and Alpha Uplift POs, based on WBSEs and Alpha Uplift project #’s in SmartsheetAP-0226 | AP-0230 | AP-0230 | 1 | 9 | 0 | 1 | anna.petrella@gevernova.com | Jennifer Wright | johann.daxer@gevernova.com | Operational Simplification |  | In Progress |  |  | 2026-01-01 | 2026-09-30 | 2026-06-01 |  | 2025-10-01 | 2025-12-31 | Customer |  |  |  | Other |  | 1May25-cleared Current start & finish dates while we re-adjust these items to align with the new scheduling tool timing & requirements 6May25-updated improvement scope, team & dates 4Sept25-Moved back a month due to scheduling tool delays 29Sept25 (JD): start date adjusted to scheduling tool progress 11Mar26-updated name & target date due to discussion at March staff meeting |  | 195d | [6 empty] | No | 2026-01-01 | 2026-09-30 | 2024-11-21 04:54 | philip.ganssmann@ge.com
AP-0230-10 | Feed known 2028+ projects into Smartsheet |  | AP-0841 | Feed known 2028+ projects into SmartsheetAP-0841 | AP-0230 | AP-0230 | 1 | 10 | 0 | 1 | johann.daxer@gevernova.com | Abuobaida El Mansoor, Alejandra María Saldaña, Anna Carmela Petrella, Gavin.Yoong@gevernova.com, Patrick Molumby | johann.daxer@gevernova.com | Operational Simplification |  | Not Started |  |  | 2026-08-01 | 2026-10-30 |  |  |  |  | Customer | [5 empty] | 11Mar26-added from March Staff Meeting |  | 66d | [6 empty] | No | 2026-08-01 | 2026-10-30 | 2026-03-11 10:59 | jennifer.b.wright@gevernova.com
AP-0230-11 | Setup AI agent screening all known sources for new projects coming in for feeding them into Smartsheet monthly |  | AP-0842 | Setup AI agent screening all known sources for new projects coming in for feeding them into Smartsheet monthlyAP-0842 | AP-0230 | AP-0230 | 1 | 11 | 0 | 1 | johann.daxer@gevernova.com |  | johann.daxer@gevernova.com | Operational Simplification |  | Not Started |  |  | 2027-01-01 | 2027-04-30 |  |  |  |  | Customer | [5 empty] | 11Mar26-added from March Staff Meeting |  | 86d | [6 empty] | No | 2027-01-01 | 2027-04-30 | 2026-03-11 10:59 | jennifer.b.wright@gevernova.com
AP-0230-12 | Validate AI agent job as part of standard forecasting process |  | AP-0843 | Validate AI agent job as part of standard forecasting processAP-0843 | AP-0230 | AP-0230 | 1 | 12 | 0 | 1 | johann.daxer@gevernova.com | Abuobaida El Mansoor, Alejandra María Saldaña, Anna Carmela Petrella, Gavin.Yoong@gevernova.com, Patrick Molumby | johann.daxer@gevernova.com | Operational Simplification |  | Not Started |  |  | 2027-06-01 | 2027-07-30 |  |  |  |  | Customer | [5 empty] | 11Mar26-added from March Staff Meeting |  | 44d |  | TRUE |  |  |  |  | No | 2027-06-01 | 2027-07-30 | 2026-03-11 10:59 | jennifer.b.wright@gevernova.com
AP-0234 | HLC Renovation |  | AP-0234 | HLC RenovationAP-0234 | #INVALID COLUMN VALUE | Top | 0 | 8 | 1 | 0 | jim.rosen@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete |  | On Track | 2024-11-05 | 2025-12-31 |  |  | 2024-11-05 | 2025-03-31 | Customer Delivery Internal Ops P&C | FE OSS OTHERS? |  |  |  |  | 10Mar25-Moved to December, Break this into multiple milestones throughout the year | n/a-parent row | 302d | [6 empty] | Yes | 2024-11-05 | 2025-12-31 | 2024-11-21 04:59 | philip.ganssmann@ge.com
AP-0234-1 | HLC Renovation - Visioning |  | AP-0482 | HLC Renovation - VisioningAP-0482 | AP-0234 | AP-0234 | 1 | 1 | 0 | 1 | jim.rosen@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Competitiveness & Growth | Ideas & plan for full HLC Renovation program | Complete |  |  | 2024-11-05 | 2025-01-31 |  |  | 2024-11-05 | 2025-01-31 | Customer Delivery Internal Ops P&C | FE OSS OTHERS? | [6 empty] | 64d | [6 empty] | Yes | 2024-11-05 | 2025-01-31 | 2025-03-11 17:24 | jennifer.b.wright@ge.com
AP-0234-2 | HLC Renovation - Design |  | AP-0480 | HLC Renovation - DesignAP-0480 | AP-0234 | AP-0234 | 1 | 2 | 0 | 1 | jim.rosen@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Competitiveness & Growth | Complete the detailed design, budget & schedule for all renovation activities | Complete | TRUE | On Track | 2025-02-03 | 2025-08-29 |  |  | 2025-02-03 | 2025-08-29 | Customer Delivery Internal Ops P&C | FE OSS OTHERS? | [6 empty] | 150d | 24 | [5 empty] | Yes | 2025-02-03 | 2025-08-29 | 2025-03-11 17:24 | jennifer.b.wright@ge.com
AP-0234-3 | HLC Renovation - Construction |  | AP-0481 | HLC Renovation - ConstructionAP-0481 | AP-0234 | AP-0234 | 1 | 3 | 0 | 1 | jim.rosen@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Competitiveness & Growth | Implement Renovation activities | Complete |  | On Track | 2025-09-01 | 2025-12-31 |  |  | 2025-09-01 | 2025-12-31 | Customer Delivery Internal Ops P&C | FE OSS OTHERS? | [5 empty] | https://gevernova.ent.box.com/file/2095816681511 | 88d | 25 | [5 empty] | Yes | 2025-09-01 | 2025-12-31 | 2025-03-11 17:24 | jennifer.b.wright@ge.com
AP-0235 | Develop Xyleme LCMS Course Readiness Procedure |  | AP-0235 | Develop Xyleme LCMS Course Readiness ProcedureAP-0235 | #INVALID COLUMN VALUE | Top | 0 | 9 | 0 | 0 | philip.ganssmann@gevernova.com | James Rosen, Lee Fielding | philip.ganssmann@gevernova.com | Operational Simplification | Develop the standard process for communicating to instructors when a course is ready for use in Xyleme & ensuring that the Xyleme materials are only being used moving forward | Complete |  | On Track | 2025-12-01 | 2026-04-30 | 2026-03-31 |  | 2025-04-01 | 2025-12-31 | Delivery Ops |  | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 03Dec25-Adjusted scope of this item to be development of the procedure since the actually LCMS course loading will be part of the D&D team standard work. 29Jan26-Moved to March to integrate with Gradebook app (AP-775) 25Mar26-Moved to April to finalize after Gradebook roll-out at Svc Week | https://gevernova.ent.box.com/file/2176287467793 | 109d | [6 empty] | No | 2025-12-01 | 2026-04-30 | 2024-11-21 04:59 | philip.ganssmann@ge.com
AP-0236 | Improve Controls ELT-A Program |  | AP-0236 | Improve Controls ELT-A ProgramAP-0236 | #INVALID COLUMN VALUE | Top | 0 | 10 | 0 | 0 | mohammed.nizami@gevernova.com | Vispara Bharat | jim.rosen@gevernova.com | Content Development | Controls ELT-A - design & plan for 2026 implementation | In Progress |  | Delayed | 2025-08-04 | 2026-12-31 |  |  | 2025-08-04 | 2025-12-31 |  |  |  |  | Other |  | 22Dec25-Delayed due to other priorities. Plan to have ready for 2027 Blueprint & scheduling |  | 369d | [6 empty] | Yes | 2025-08-04 | 2026-12-31 | 2024-11-21 04:59 | philip.ganssmann@ge.com
AP-0237 | Improve ST Entry Level Training Accelerated (ELT-A) Program |  | AP-0237 | Improve ST Entry Level Training Accelerated (ELT-A) ProgramAP-0237 | #INVALID COLUMN VALUE | Top | 0 | 11 | 1 | 0 | pablo.schibli@gevernova.com | Leonardo Monzo | jim.rosen@gevernova.com | Content Development |  | In Progress |  |  | 2024-09-01 | 2026-10-30 |  |  | 2024-09-01 | 2025-10-31 |  |  |  |  | Other |  |  | n/a-parent row | 566d | [6 empty] | Yes | 2024-09-01 | 2026-10-30 | 2024-11-21 04:59 | philip.ganssmann@ge.com
AP-0237-1 | Determine ST ELT-A Content |  | AP-0430 | Determine ST ELT-A ContentAP-0430 | AP-0237 | AP-0237 | 1 | 1 | 0 | 1 | pablo.schibli@gevernova.com | RMs, TDMs | jim.rosen@gevernova.com | Content Development | Design ST ELT-A1 & ELT-A2 schedule/content, validate with Region teams, & Load Outline in MM for Steam Turbine ELT-A program. | Complete |  | On Track | 2024-09-01 | 2025-02-28 |  |  | 2024-09-01 | 2025-02-28 | Delivery Internal Ops | FE RM |  |  |  |  | 2/10/25-Pablo confirmed that content & new schedule is ready to be validated with RMs and TDMs. Then it can be loaded into MM. May not be able to implement new schedule in 2025 since Direct Hire course is already scheduled, but should be ready to deliver new schedule in 2026 | https://gevernova.ent.box.com/file/1788273417473 | 131d | [6 empty] | Yes | 2024-09-01 | 2025-02-28 | 2024-12-19 12:02 | jennifer.b.wright@ge.com
AP-0237-2 | Develop ST ELT-A Hiring Approach |  | AP-0431 | Develop ST ELT-A Hiring ApproachAP-0431 | AP-0237 | AP-0237 | 1 | 2 | 0 | 1 | pablo.schibli@gevernova.com | RMs, TDMs | jim.rosen@gevernova.com | Content Development | Develop Hiring Matrix, Annual plan/timing for ST ELT-A delivery, Technical interview questions, and roll-out approach to regional hiring teams | Complete |  |  | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-03-31 | Delivery Internal Ops | FE RM |  |  |  |  | 25Mar25-extended to April to allow more time to review hiring matrix with Leo's team 29Apr25-moved to May per Pablo's request. 12May25-Pablo has meetings scheduled for this month to receive feedback, confirmations, and make final adjustments so the AP can close 29May25-Moved to June - TBD reason for delay 26June25-Moved to August due to re-aligned priorities | https://gevernova.ent.box.com/file/1973297053547 | 173d | [6 empty] | Yes | 2025-01-01 | 2025-08-29 | 2024-12-19 12:02 | jennifer.b.wright@ge.com
AP-0237-3 | Pilot ST ELT-A Course |  | AP-0429 | Pilot ST ELT-A CourseAP-0429 | AP-0237 | AP-0237 | 1 | 3 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Assemble course content, roll out & pilot for Steam Turbine ELT-A program. | Not Started |  |  | 2025-05-01 | 2026-10-30 |  |  | 2025-04-01 | 2025-10-31 | Delivery Internal Ops | FE RM |  |  | Other |  | 25Mar25-Moved into 2026 because we can't modify the 2025 ST ELT schedule at this pont |  | 392d | [6 empty] | Yes | 2025-05-01 | 2026-10-30 | 2024-12-19 12:02 | jennifer.b.wright@ge.com
AP-0241 | Implement Instructor Utilization Flexibility Model |  | AP-0241 | Implement Instructor Utilization Flexibility ModelAP-0241 | #INVALID COLUMN VALUE | Top | 0 | 12 | 1 | 0 | jim.rosen@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Sub items for Development plans, Cross Training Plans (sub items per PLL), Scheduling Process | Complete |  |  | 2025-01-01 | 2026-01-30 |  |  | 2025-01-01 | 2025-12-31 |  |  |  |  | Other |  | 09Feb26-Marked complete - no additional report out needed | n/a-parent row | 283d | [6 empty] | Yes | 2025-01-01 | 2026-01-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-1 | Demand & Capacity Analysis |  | AP-0250 | Demand & Capacity AnalysisAP-0250 | AP-0241 | AP-0241 | 1 | 1 | 1 | 1 | jim.rosen@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | For each course/technology, how many instructors do we need over the next 3 years vs. what do we have? (our capacity target should be higher than demand to have buffer for unexpected demand, etc.) | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-1-1 | GT Demand & Capacity Analysis |  | AP-0309 | GT Demand & Capacity AnalysisAP-0309 | AP-0241-1 | AP-0250 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 10:53 | jennifer.b.wright@ge.com
AP-0241-1-2 | ST Demand & Capacity Analysis |  | AP-0308 | ST Demand & Capacity AnalysisAP-0308 | AP-0241-1 | AP-0250 | 2 | 2 | 0 | 1 | pablo.schibli@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 10:53 | jennifer.b.wright@ge.com
AP-0241-1-3 | Generator and Excitation Demand & Capacity Analysis |  | AP-0315 | Generator and Excitation Demand & Capacity AnalysisAP-0315 | AP-0241-1 | AP-0250 | 2 | 3 | 0 | 1 | michele.alcantar@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 11:01 | jennifer.b.wright@ge.com
AP-0241-1-4 | Controls Demand & Capacity Analysis |  | AP-0311 | Controls Demand & Capacity AnalysisAP-0311 | AP-0241-1 | AP-0250 | 2 | 4 | 0 | 1 | mohammed.nizami@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 11:01 | jennifer.b.wright@ge.com
AP-0241-1-5 | Aero Demand & Capacity Analysis |  | AP-0310 | Aero Demand & Capacity AnalysisAP-0310 | AP-0241-1 | AP-0250 | 2 | 5 | 0 | 1 | gregoryd.walker@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 11:01 | jennifer.b.wright@ge.com
AP-0241-1-6 | Craft Demand & Capacity Analysis |  | AP-0314 | Craft Demand & Capacity AnalysisAP-0314 | AP-0241-1 | AP-0250 | 2 | 6 | 0 | 1 | harry.hanson@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 11:01 | jennifer.b.wright@ge.com
AP-0241-1-7 | Repairs Demand & Capacity Analysis |  | AP-0313 | Repairs Demand & Capacity AnalysisAP-0313 | AP-0241-1 | AP-0250 | 2 | 7 | 0 | 1 | harry.hanson@gevernova.com | andrew.ruch@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Determine how many instructors we need for each course/skill set over the next 3 years & what is our current gap to meet that | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | [7 empty] | To be reported in combination with AP-0241-2 | 43d | [6 empty] | Yes | 2025-01-01 | 2025-02-28 | 2024-11-22 11:01 | jennifer.b.wright@ge.com
AP-0241-2 | Development Plans |  | AP-0238 | Development PlansAP-0238 | AP-0241 | AP-0241 | 1 | 2 | 1 | 1 | jim.rosen@gevernova.com | andrew.ruch@gevernova.com, Jennifer Wright | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs to fill capacity gaps Build list/tracker showing each instructor’s development targets (i.e. which courses, assignments they should complete by when) | Complete |  | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | https://gevernova.box.com/s/hepq86a28yvor80gvy4l3tzwcea219a1 | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-1 | GT Instructor Development Plan |  | AP-0248 | GT Instructor Development PlanAP-0248 | AP-0241-2 | AP-0238 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-2 | ST Instructor Development Plan |  | AP-0251 | ST Instructor Development PlanAP-0251 | AP-0241-2 | AP-0238 | 2 | 2 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-3 | Generator and Excitation Instructor Development Plan |  | AP-0254 | Generator and Excitation Instructor Development PlanAP-0254 | AP-0241-2 | AP-0238 | 2 | 3 | 0 | 1 | michele.alcantar@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-4 | Controls Instructor Development Plan |  | AP-0239 | Controls Instructor Development PlanAP-0239 | AP-0241-2 | AP-0238 | 2 | 4 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-5 | Aero Instructor Development Plan |  | AP-0242 | Aero Instructor Development PlanAP-0242 | AP-0241-2 | AP-0238 | 2 | 5 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-6 | Craft Instructor Development Plan |  | AP-0249 | Craft Instructor Development PlanAP-0249 | AP-0241-2 | AP-0238 | 2 | 6 | 0 | 1 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0241-2-7 | Repairs Instructor Development Plan |  | AP-0312 | Repairs Instructor Development PlanAP-0312 | AP-0241-2 | AP-0238 | 2 | 7 | 0 | 1 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Identify what cross training & OJT assignments each instructor needs complete over the next few year to fill capacity gaps | Complete | TRUE | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-05-30 | [7 empty] | Reported out at parent task level | 43d | [6 empty] | Yes | 2025-03-03 | 2025-04-30 | 2024-11-22 11:01 | jennifer.b.wright@ge.com
AP-0241-3 | Build Instructor Development Plans into 2026 schedule |  | AP-0240 | Build Instructor Development Plans into 2026 scheduleAP-0240 | AP-0241 | AP-0241 | 1 | 3 | 0 | 1 | andrew.ruch@gevernova.com | PLLs, TDMs | jim.rosen@gevernova.com | Operational Simplification | Incorporate Cross Training & OJT assignments into 2025 & 2026 schedule. -OJT will require support from TDMs to find appropriate assignments -Use Dev Plans tracker to do this. Could include regular meetings to review conflicting priorities/needs & make decisions -Need to incorporate/align with SMax assignments/data. -Need to establish process/communication plan for handling assignment date changes | Complete |  |  | 2025-06-02 | 2026-01-30 |  |  | 2025-06-02 | 2025-12-31 | Delivery |  |  |  | Other |  | 27Oct25-Moved to Feb 2026. Will be implemented when primary resource plan & BI forecast is completed 09Feb26-Marked complete - standard process for PLLs & Schedulers, no specific report out needed | n/a- no report out needed | 175d |  | TRUE |  |  |  |  | No | 2025-06-02 | 2026-01-30 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0245 | Standard work for Instructor Development Week |  | AP-0245 | Standard work for Instructor Development WeekAP-0245 | #INVALID COLUMN VALUE | Top | 0 | 13 | 0 | 0 | michele.alcantar@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2024-10-01 | 2025-03-17 |  |  | 2024-10-01 | 2025-03-17 | [7 empty] | https://gevernova.ent.box.com/file/1768329980999 | 120d | [6 empty] | Yes | 2024-10-01 | 2025-03-17 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0246 | Pilot Delivery of Bearing Inspection Procedures |  | AP-0246 | Pilot Delivery of Bearing Inspection ProceduresAP-0246 | #INVALID COLUMN VALUE | Top | 0 | 14 | 0 | 0 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Continuation of AP-225, pilot delivery of new content & evaluate feedback/effectiveness | Complete |  | On Track | 2025-02-01 | 2025-03-31 |  |  | 2025-02-01 | 2025-03-31 | Delivery Internal | FE | [5 empty] | Combined with AP-225 | 42d | [6 empty] | Yes | 2025-02-01 | 2025-03-31 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0247 | Advanced 6B Gas Turbine Alignment Class |  | AP-0247 | Advanced 6B Gas Turbine Alignment ClassAP-0247 | #INVALID COLUMN VALUE | Top | 0 | 15 | 0 | 0 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop a more robust training program for performing 61B train alignments for Field Engineers and Craft personnel. | Complete |  | On Track | 2025-03-31 | 2025-08-29 |  |  | 2025-03-31 | 2025-06-30 | Delivery Internal Ops | Craft FE |  |  |  |  | 17Mar25-Strategy & material is complete. Next step is to build into Online training 25June25-Moved to July to due delays in contingent worker setup 29Jul25-Core training is done. Extending to August to allow time to enhance the quiz functionality to improve learning | https://gevernova.ent.box.com/file/1973596554907 | 110d | [6 empty] | Yes | 2025-03-31 | 2025-08-29 | 2024-11-21 08:29 | jennifer.b.wright@ge.com
AP-0252 | Catching HA Turbine |  | AP-0252 | Catching HA TurbineAP-0252 | #INVALID COLUMN VALUE | Top | 0 | 16 | 0 | 0 | Sherif.Khalifa@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Content Quality & Improvements | Receive, operationalize, etc. On platform - ready to start using | In Progress |  | Delayed | 2024-11-01 | 2026-06-30 |  |  | 2024-11-01 | 2025-06-30 |  |  |  |  | Other |  | 25June25-HA is at HLC but extending this finish date to include installation & readiness 25Sept25-moved to Jan 12Jan26-moved to June to close after we complete a full pilot outage on it |  | 433d |  |  | TRUE |  |  |  | Yes | 2024-11-01 | 2026-06-30 | 2024-11-21 05:01 | philip.ganssmann@ge.com
AP-0253 | Finalize Excitation ELT Hiring & Training Approach |  | AP-0253 | Finalize Excitation ELT Hiring & Training ApproachAP-0253 | #INVALID COLUMN VALUE | Top | 0 | 17 | 0 | 0 | michele.alcantar@gevernova.com | TDMs, RMs, Julio Ramirez | jim.rosen@gevernova.com | Content Development | Assemble Technical Interview questions & roll out hiring/training approach to Region & Hiring teams | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-03-31 | Delivery Internal | FE RM |  |  |  |  | 3Apr25-Per Michele on track to close on time | https://gevernova.ent.box.com/file/1768335143017 | 86d | [6 empty] | Yes | 2025-01-01 | 2025-04-30 | 2024-11-21 05:01 | philip.ganssmann@ge.com
AP-0257 | Create Pacing Process |  | AP-0257 | Create Pacing ProcessAP-0257 | #INVALID COLUMN VALUE | Top | 0 | 18 | 0 | 0 | Jennifer Wright | András Pintér, philip.ganssmann@gevernova.com | philip.ganssmann@gevernova.com | Financial Simplification | Create one place to see upcoming spends hitting the training budget Ensure that any spend larger than $5K that is not liquidated is included - communicate with OFS team, ensure sustainment | Complete |  | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | Ops | n/a | [5 empty] | https://gevernova.ent.box.com/file/1876000147073 | 108d | [6 empty] | No | 2025-01-01 | 2025-05-30 | 2024-11-21 08:37 | jennifer.b.wright@ge.com
AP-0259 | Build process for analysis of NPS trends (i.e. what triggers a PSR/Action Plan item) |  | AP-0259 | Build process for analysis of NPS trends (i.e. what triggers a PSR/Action Plan item)AP-0259 | #INVALID COLUMN VALUE | Top | 0 | 19 | 0 | 0 | Jennifer Wright |  | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2025-07-01 | 2025-09-29 |  |  | 2025-07-01 | 2025-09-29 | Delivery Ops | n/a |  |  |  |  | start with internal, use AI? | https://gevernova.ent.box.com/file/1993586233757 | 65d | [6 empty] | No | 2025-07-01 | 2025-09-29 | 2024-11-21 08:37 | jennifer.b.wright@ge.com
AP-026 | Enter known/existing Borrowed Instructor Competencies into Kahuna | AP-026 | AP-0411 | Enter known/existing Borrowed Instructor Competencies into KahunaAP-0411 | #INVALID COLUMN VALUE | Top | 0 | 20 | 0 | 0 | jim.rosen@gevernova.com | PLLs | jim.rosen@gevernova.com | Instructor Qualification | Qualify all known/existing Borrowed Instructors as "Instructors" in Kahuna. | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-02-28 | Customer Delivery Internal Ops | Craft FE RM |  |  |  |  | 2/1025- Moved to March to accommodate new plan/understanding for loading borrowed instructor roles & competencies. May extend further to wait for OSS/Other instructors to be added into Kahuna | https://gevernova.box.com/s/gwwruciwhtojst9hfn0wb13of0vl54ob | 64d | [6 empty] | Yes | 2025-01-01 | 2025-03-31 | 2024-12-12 10:59 | jennifer.b.wright@ge.com
AP-028 | ER Cases Reduction - Incorporate New PowerNow Information Search Tool into standard ELT training | AP-028 | 53 | ER Cases Reduction - Incorporate New PowerNow Information Search Tool into standard ELT training53 | #INVALID COLUMN VALUE | Top | 0 | 21 | 0 | 0 | mohammed.nizami@gevernova.com | Ahmed Ijaz, Joshua Brand | jim.rosen@gevernova.com | Content Quality & Improvements |  | In Progress |  | Delayed | 2024-10-01 | 2026-12-31 |  |  | 2024-10-01 | 2025-12-31 |  |  |  |  | Other |  | 22Dec25-Tool got delayed until 2026. Expected to have more info in mid 2026 with TFAs using it in late 2026. |  | 588d | [6 empty] | Yes | 2024-10-01 | 2026-12-31 | 2024-11-08 13:06 | jennifer.b.wright@ge.com
AP-0282 | Scheduling Tool Phase 2 & 3 Development |  | AP-0282 | Scheduling Tool Phase 2 & 3 DevelopmentAP-0282 | #INVALID COLUMN VALUE | Top | 0 | 22 | 1 | 0 | andrew.ruch@gevernova.com | UDC Team | philip.ganssmann@gevernova.com | Operational simplification | These are additions to the scheduling tool and will be started once the base tool is completed and tested | Complete |  | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-03-31 | Customer Delivery Ops | n/a |  |  |  |  | 20Mar25-Updated completion to combine with Phase 3 (doesn't make sense to report separately) | https://gevernova.box.com/s/r5hua7jz7nh0kn3z55r9puiv4kwrswps | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2024-11-21 13:25 | philip.ganssmann@ge.com
AP-0282-1 | Mass upload feature for Instructor and courses |  | AP-0256 | Mass upload feature for Instructor and coursesAP-0256 | AP-0282 | AP-0282 | 1 | 1 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Mass Upload feature | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-03-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2024-11-21 08:37 | jennifer.b.wright@ge.com
AP-0282-2 | Integration with Kahuna via Datalake & Skill set UI in Instructor screen |  | AP-0317 | Integration with Kahuna via Datalake & Skill set UI in Instructor screenAP-0317 | AP-0282 | AP-0282 | 1 | 2 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Kahuna Integration for Instructor Skillset | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-03-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2024-11-25 10:53 | andrew.ruch@ge.com
AP-0282-3 | Mass upload for Internal, SS & Open Enrollment Projects |  | AP-0316 | Mass upload for Internal, SS & Open Enrollment ProjectsAP-0316 | AP-0282 | AP-0282 | 1 | 3 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Mass upload for Internal & Open Enrollment Projects | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-03-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2024-11-25 10:53 | andrew.ruch@ge.com
AP-0282-4 | Internal Change management User Interface, Internal change Management forms User interface and development, Workflow development and validation |  | AP-0320 | Internal Change management User Interface, Internal change Management forms User interface and development, Workflow development and validationAP-0320 | AP-0282 | AP-0282 | 1 | 4 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Change Management for Internal Projects | Complete | TRUE | On Track | 2024-12-16 | 2025-07-31 |  |  | 2024-12-16 | 2025-03-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 164d | [6 empty] | No | 2024-12-16 | 2025-07-31 | 2024-11-25 11:05 | andrew.ruch@ge.com
AP-0282-5 | Change Management for Open Enrollment Projects |  | AP-0318 | Change Management for Open Enrollment ProjectsAP-0318 | AP-0282 | AP-0282 | 1 | 5 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Change Management for OE Projects | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-03-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2024-11-25 11:05 | andrew.ruch@ge.com
AP-0282-6 | Change Management for Customer Demand Projects |  | AP-0505 | Change Management for Customer Demand ProjectsAP-0505 | AP-0282 | AP-0282 | 1 | 6 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Change Management for Customer Demand Projects | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-10-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2025-03-31 16:01 | andrew.ruch@ge.com
AP-0282-7 | Interactive Project Summary dashboard |  | AP-0507 | Interactive Project Summary dashboardAP-0507 | AP-0282 | AP-0282 | 1 | 7 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Customer Training GRM View | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-10-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2025-03-31 16:01 | andrew.ruch@ge.com
AP-0282-8 | Resource Availability Gantt Chart User interface and development / Resource availability dashboard integration with Resource assignment |  | AP-0508 | Resource Availability Gantt Chart User interface and development / Resource availability dashboard integration with Resource assignmentAP-0508 | AP-0282 | AP-0282 | 1 | 8 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Resource Availability Gantt Chart - Instructor, Rooms, Equipment | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-10-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2025-03-31 16:01 | andrew.ruch@ge.com
AP-0282-9 | Misc Scheduling (Misc Assigned, Misc Applied, Vacation, Etc) |  | AP-0504 | Misc Scheduling (Misc Assigned, Misc Applied, Vacation, Etc)AP-0504 | AP-0282 | AP-0282 | 1 | 9 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Misc Scheduling | Complete | TRUE | On Track | 2024-12-16 | 2025-10-31 |  |  | 2024-12-16 | 2025-10-31 | Ops | n/a | [5 empty] | Will be reported as roll-up to AP-0282 | 230d | [6 empty] | No | 2024-12-16 | 2025-10-31 | 2025-03-31 16:01 | andrew.ruch@ge.com
AP-0286 | Cost pacing process for Employees in Training & OJT |  | AP-0286 | Cost pacing process for Employees in Training & OJTAP-0286 | #INVALID COLUMN VALUE | Top | 0 | 23 | 0 | 0 | erica.peredo@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance | Pacing rhythm, budget improvement. Tools to use (dashboards, tableau). Define participants | Complete |  | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-04-30 | Internal Ops | Craft FE OSS |  |  |  |  | 14Apr25-Process is likely ready by end of April, not sure about data needed to support the process. Philip to confirm 28Apr25-Moved to May to allow more time to consolidate actuals & pacing data | https://gevernova.ent.box.com/file/1871312351440 | 108d | [6 empty] | No | 2025-01-01 | 2025-05-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0287 | Improve New hires feedback after 6 months |  | AP-0287 | Improve New hires feedback after 6 monthsAP-0287 | #INVALID COLUMN VALUE | Top | 0 | 24 | 0 | 0 | paula.pedrozanino@gevernova.com | Siaw Wei Tan | leonardo.monzo1@gevernova.com | TDM Performance | Define steps to get feedback from students after their program's graduation to improve it | Complete |  | On Track | 2025-03-01 | 2025-05-30 |  |  | 2025-03-01 | 2025-05-30 | Delivery Internal P&C | Craft FE OSS | [5 empty] | https://gevernova.ent.box.com/file/1868098220808 | 66d | [6 empty] | No | 2025-03-01 | 2025-05-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0288 | Improve alignment between PLL & TDM teams |  | AP-0288 | Improve alignment between PLL & TDM teamsAP-0288 | #INVALID COLUMN VALUE | Top | 0 | 25 | 0 | 0 | leonardo.monzo1@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance |  | Complete |  | On Track | 2025-02-01 | 2026-03-31 |  |  | 2025-02-01 | 2025-06-05 | Delivery Internal | Craft FE OSS |  |  | Other |  | 10Jun25-Pushed to July to allow more time to meet with PLLs to discuss 31Jul25-Moved to November to report back after system has been tested for a few months 2Dec25-Moved to Dec to allow oppty for additional alignment meetings 15Dec25-Move to Feb to have more alignment meetings (didn't happen in Dec) 26Feb26-Moved to March to allow time in Greenville to complete this. | https://gevernova.ent.box.com/file/2176425669365 | 303d | [6 empty] | No | 2025-02-01 | 2026-03-31 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0289 | Launch State of Art Seminar for Electrical/Excitation |  | AP-0289 | Launch State of Art Seminar for Electrical/ExcitationAP-0289 | #INVALID COLUMN VALUE | Top | 0 | 26 | 1 | 0 | paula.pedrozanino@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements | Plan, deliver & review feedback for Electrical/Excitation Seminar (similar to 2024 Controls Seminar) | Complete |  | On Track | 2025-02-01 | 2025-09-30 |  |  | 2025-02-01 | 2025-07-31 | Delivery Internal P&C | FE | [5 empty] | n/a-parent row | 173d | [6 empty] | No | 2025-02-01 | 2025-09-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0289-1 | Planning of State of Art Seminar for Electrical/Excitation |  | AP-0441 | Planning of State of Art Seminar for Electrical/ExcitationAP-0441 | AP-0289 | AP-0289 | 1 | 1 | 0 | 1 | paula.pedrozanino@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-02-01 | 2025-05-30 |  |  | 2025-02-01 | 2025-05-30 | Delivery Internal | FE | [5 empty] | https://gevernova.ent.box.com/file/1868123764687 | 86d | [6 empty] | No | 2025-02-01 | 2025-05-30 | 2025-01-09 10:31 | jennifer.b.wright@ge.com
AP-0289-2 | Launch State of Art Seminar for Electrical/Excitation |  | AP-0442 | Launch State of Art Seminar for Electrical/ExcitationAP-0442 | AP-0289 | AP-0289 | 1 | 2 | 0 | 1 | paula.pedrozanino@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-06-02 | 2025-07-11 |  |  | 2025-06-02 | 2025-06-30 | Delivery Internal | FE | [5 empty] | https://gevernova.ent.box.com/file/1929063160130 | 30d | 74 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-07-11 | 2025-01-09 10:31 | jennifer.b.wright@ge.com
AP-0289-3 | Review/Incorporate Feedback on State of Art Seminar for Electrical/Excitation |  | AP-0440 | Review/Incorporate Feedback on State of Art Seminar for Electrical/ExcitationAP-0440 | AP-0289 | AP-0289 | 1 | 3 | 0 | 1 | paula.pedrozanino@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-07-14 | 2025-09-30 |  |  | 2025-07-01 | 2025-07-31 | Delivery Internal | FE |  |  |  |  | 14July25-Move to September to allow time to review & implement changes from feedback | https://gevernova.ent.box.com/file/1995657599443 | 57d | 75 | [5 empty] | No | 2025-07-14 | 2025-09-30 | 2025-01-09 10:31 | jennifer.b.wright@ge.com
AP-0290 | Launch State of Art Seminar for Generator Specialist |  | AP-0290 | Launch State of Art Seminar for Generator SpecialistAP-0290 | #INVALID COLUMN VALUE | Top | 0 | 27 | 1 | 0 | brenda.romanvalle@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements | Plan, deliver & review feedback for Generator Specialist Seminar (similar to 2024 Controls Seminar) | Complete |  | On Track | 2025-03-01 | 2025-09-30 |  |  | 2025-03-01 | 2025-09-30 | Delivery Internal P&C | FE | [5 empty] | n/a-parent row | 153d | [6 empty] | No | 2025-03-01 | 2025-09-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0290-1 | Planning of State of Art for Generator Specialist |  | AP-0443 | Planning of State of Art for Generator SpecialistAP-0443 | AP-0290 | AP-0290 | 1 | 1 | 0 | 1 | brenda.romanvalle@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-03-01 | 2025-06-30 |  |  | 2025-03-01 | 2025-06-30 | Delivery Internal P&C | FE | [5 empty] | https://gevernova.ent.box.com/file/1904898603810 | 87d | [6 empty] | No | 2025-03-01 | 2025-06-30 | 2025-01-09 10:31 | jennifer.b.wright@ge.com
AP-0290-2 | Launch State of Art Seminar for Generator Specialist |  | AP-0444 | Launch State of Art Seminar for Generator SpecialistAP-0444 | AP-0290 | AP-0290 | 1 | 2 | 0 | 1 | brenda.romanvalle@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-07-01 | 2025-08-29 |  |  | 2025-07-01 | 2025-08-29 | Delivery Internal P&C | FE | [5 empty] | https://gevernova.ent.box.com/file/1974543507756 | 44d | 78 | [5 empty] | No | 2025-07-01 | 2025-08-29 | 2025-01-09 10:33 | jennifer.b.wright@ge.com
AP-0290-3 | Review/Incorporate Feedback on State of Art Seminar for Generator Specialist |  | AP-0445 | Review/Incorporate Feedback on State of Art Seminar for Generator SpecialistAP-0445 | AP-0290 | AP-0290 | 1 | 3 | 0 | 1 | brenda.romanvalle@gevernova.com | Michele Alcantar | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-09-01 | 2025-09-30 |  |  | 2025-09-01 | 2025-09-30 | Delivery Internal P&C | FE | [5 empty] | https://gevernova.ent.box.com/file/1993658216701 | 22d | 79 | [5 empty] | No | 2025-09-01 | 2025-09-30 | 2025-01-09 10:38 | jennifer.b.wright@ge.com
AP-0291 | Update TMIV Kahuna role to include Lead Mechanics responsibilities |  | AP-0291 | Update TMIV Kahuna role to include Lead Mechanics responsibilitiesAP-0291 | #INVALID COLUMN VALUE | Top | 0 | 28 | 1 | 0 | erica.peredo@gevernova.com |  | leonardo.monzo1@gevernova.com | Competencies | Understanding which skills are connected to specific courses - Covered by Dave's team | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-02-28 | Internal P&C | Craft |  |  |  |  | Split this item into 2 rows to address identifying what needs to be updated (if anything), then implement the changes | n/a-parent row | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0291-1 | Review TMIV Kahuna role to determine changes needed to include Lead Mechanics responsibilities |  | AP-0463 | Review TMIV Kahuna role to determine changes needed to include Lead Mechanics responsibilitiesAP-0463 | AP-0291 | AP-0291 | 1 | 1 | 0 | 1 | erica.peredo@gevernova.com |  | leonardo.monzo1@gevernova.com | Competencies | Identify what changes will need to be made to include Lead Mechanic responsibilities in TMIV role | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-02-28 | Internal P&C | Craft |  |  |  |  | 2/24/25-Per Erica, moved to March due to delays in gathering info from all regions 10Mar25-Per Leo, may be more difficult than expected, likely to be delayed 25Mar25-Moved to April to accommodate additional effort and revise plan with stakeholders | https://gevernova.ent.box.com/file/1848708772751 | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2025-02-10 11:17 | jennifer.b.wright@ge.com
AP-0291-2 | Implement TMIV Kahuna Role Changes identified above |  | AP-0462 | Implement TMIV Kahuna Role Changes identified aboveAP-0462 | AP-0291 | AP-0291 | 1 | 2 | 0 | 1 | erica.peredo@gevernova.com |  | leonardo.monzo1@gevernova.com | Competencies | Implement changes identified above | Cancelled |  |  | 2025-05-01 |  |  |  | 2025-05-01 |  | Internal P&C | Craft |  |  |  |  | No longer needed - no further actions needed as a result of 0291-1 |  |  | 82 | [5 empty] | No | 2025-05-01 | #INVALID DATA TYPE | 2025-02-10 11:17 | jennifer.b.wright@ge.com
AP-0292 | Recruiting Assessment for Craft New hires |  | AP-0292 | Recruiting Assessment for Craft New hiresAP-0292 | #INVALID COLUMN VALUE | Top | 0 | 29 | 0 | 0 | luca.martino@gevernova.com | Luca Martino | leonardo.monzo1@gevernova.com | Competencies | Not applicable for MA, only for direct hire, TM 1, etc. | Complete |  | Delayed | 2025-04-01 | 2025-06-30 |  |  | 2025-04-01 | 2025-06-30 | Internal P&C | Craft |  |  |  |  | delayed by 2 weeks | https://gevernova.box.com/s/tl3z8okca6rpikuvbxtldis306bap2cj | 65d | [6 empty] | No | 2025-04-01 | 2025-06-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0293 | Craft Kahuna Competencies for Electricians, I&C & Welders |  | AP-0293 | Craft Kahuna Competencies for Electricians, I&C & WeldersAP-0293 | #INVALID COLUMN VALUE | Top | 0 | 30 | 1 | 0 | luca.martino@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | In Progress |  | Delayed | 2025-01-01 | 2026-11-25 |  |  | 2025-01-01 | 2025-05-30 | Internal Programs & Competency | Craft RM |  |  | Other |  | Split into 3 lines, Welders Aug, Others Sept 12Jan26-Will be delayed to update after I&C training development | n/a-parent row | 496d | [6 empty] | No | 2025-01-01 | 2026-11-25 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0293-1 | Develop Welder, Electrician & I&C Competency Maps |  | AP-0678 | Develop Welder, Electrician & I&C Competency MapsAP-0678 | AP-0293 | AP-0293 | 1 | 1 | 1 | 1 | luca.martino@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | In Progress |  |  | 2025-01-01 | 2026-09-30 |  |  |  |  | Internal Programs & Competency | Craft RM | [5 empty] | https://gevernova.ent.box.com/file/1995533610387 | 456d | [6 empty] | No | 2025-01-01 | 2026-09-30 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-1-1 | Kahuna Competencies for Welders |  | AP-0588 | Kahuna Competencies for WeldersAP-0588 | AP-0293-1 | AP-0678 | 2 | 1 | 0 | 1 | luca.martino@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | In Progress | TRUE | Delayed | 2025-01-01 | 2026-09-30 | 2026-04-30 |  | 2025-01-01 | 2025-08-29 | Internal Programs & Competency | Craft RM |  |  |  |  | 29Jan26-re-opened due to update needed for LES welder map 08Apr26-Moved to Sept to align timing with new related APs (AP-0823 Welding & Pipefitting Training & Career Progression Framework & AP-0824 Craft E&I/I&C Training and Career Progression Framework) | report out at parent level | 456d | [6 empty] | No | 2025-01-01 | 2026-09-30 | 2025-08-11 10:00 | jennifer.b.wright@ge.com
AP-0293-1-2 | Kahuna Competencies for Electricians |  | AP-0586 | Kahuna Competencies for ElectriciansAP-0586 | AP-0293-1 | AP-0678 | 2 | 2 | 0 | 1 | luca.martino@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | In Progress | TRUE | Delayed | 2025-01-01 | 2026-09-30 | 2026-03-30 |  | 2025-01-01 | 2025-08-29 | Internal Programs & Competency | Craft RM |  |  |  |  | 11Aug25-Moved to Sept due to SME availability issues 29Jan26-re-opened due to concerns regarding impact on employee compensation 09Mar26-Had to cancel target work week due to SME availabiliity, new date TBD 18Mar26-Moved to Sept to align timing with new related APs (AP-0823 Welding & Pipefitting Training & Career Progression Framework & AP-0824 Craft E&I/I&C Training and Career Progression Framework) | report out at parent level | 456d | [6 empty] | No | 2025-01-01 | 2026-09-30 | 2025-08-11 10:00 | jennifer.b.wright@ge.com
AP-0293-1-3 | Kahuna Competencies for I&C |  | AP-0587 | Kahuna Competencies for I&CAP-0587 | AP-0293-1 | AP-0678 | 2 | 3 | 0 | 1 | luca.martino@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | In Progress | TRUE | Delayed | 2025-01-01 | 2026-09-30 | 2026-04-30 |  | 2025-01-01 | 2025-08-29 | Internal Programs & Competency | Craft RM |  |  |  |  | 11Aug25-Moved to Sept due to SME availability issues 29Jan26-re-opened due to updates from I&C classroom courses impacting maps 08Apr26-Moved to Sept to align timing with new related APs (AP-0823 Welding & Pipefitting Training & Career Progression Framework & AP-0824 Craft E&I/I&C Training and Career Progression Framework) | report out at parent level | 456d | [6 empty] | No | 2025-01-01 | 2026-09-30 | 2025-08-11 10:00 | jennifer.b.wright@ge.com
AP-0293-2 | Finalize Welder Map in Systems |  | AP-0680 | Finalize Welder Map in SystemsAP-0680 | AP-0293 | AP-0293 | 1 | 2 | 1 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 6-8 in Competency Map Checklist | Not Started |  | Delayed | 2026-10-01 | 2026-11-25 |  |  |  |  | Internal Programs & Competency | Craft RM |  |  | Other |  |  |  | 40d | [6 empty] | No | 2026-10-01 | 2026-11-25 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-2-1 | Import & Configure System for Welder Map |  | AP-0658 | Import & Configure System for Welder MapAP-0658 | AP-0293-2 | AP-0680 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-10-01 | 2026-10-28 | [8 empty] | Other |  | 23Jan26-Pushed to Feb 29Jan26-dates moved due to re-opened competency map projects |  | 20d | 87 | [5 empty] | No | 2026-10-01 | 2026-10-28 | 2025-10-31 07:42 | jennifer.b.wright@ge.com
AP-0293-2-2 | Baseline & Load Welder User Assignments |  | AP-0673 | Baseline & Load Welder User AssignmentsAP-0673 | AP-0293-2 | AP-0680 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-10-29 | 2026-11-25 | [8 empty] | Other |  | 29Jan26-dates moved due to re-opened competency map projects |  | 20d | 91 | [5 empty] | No | 2026-10-29 | 2026-11-25 | 2025-11-06 13:39 | jennifer.b.wright@ge.com
AP-0293-3 | Finalize Electrician Map in Systems |  | AP-0676 | Finalize Electrician Map in SystemsAP-0676 | AP-0293 | AP-0293 | 1 | 3 | 1 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 6-8 in Competency Map Checklist | Not Started |  | Delayed | 2026-10-01 | 2026-11-25 |  |  |  |  | Internal Programs & Competency | Craft RM |  |  | Other |  |  |  | 40d | [6 empty] | No | 2026-10-01 | 2026-11-25 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-3-1 | Import & Configure System for Electrician Map |  | AP-0682 | Import & Configure System for Electrician MapAP-0682 | AP-0293-3 | AP-0676 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-10-01 | 2026-10-28 | [8 empty] | Other |  | 23Jan26-Pushed to Feb 29Jan26-dates moved due to re-opened competency map projects |  | 20d | 88 | [5 empty] | No | 2026-10-01 | 2026-10-28 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-3-2 | Baseline & Load Electrician User Assignments |  | AP-0683 | Baseline & Load Electrician User AssignmentsAP-0683 | AP-0293-3 | AP-0676 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-10-29 | 2026-11-25 | [8 empty] | Other |  | 29Jan26-dates moved due to re-opened competency map projects |  | 20d | 94 | [5 empty] | No | 2026-10-29 | 2026-11-25 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-4 | Finalize I&C Map in Systems |  | AP-0677 | Finalize I&C Map in SystemsAP-0677 | AP-0293 | AP-0293 | 1 | 4 | 1 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 6-8 in Competency Map Checklist | Not Started |  | Delayed | 2026-10-01 | 2026-11-25 |  |  |  |  | Internal Programs & Competency | Craft RM |  |  | Other |  |  |  | 40d | [6 empty] | No | 2026-10-01 | 2026-11-25 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-4-1 | Import & Configure System for I&C Map |  | AP-0681 | Import & Configure System for I&C MapAP-0681 | AP-0293-4 | AP-0677 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-10-01 | 2026-10-28 | [8 empty] | Other |  | 23Jan26-Pushed to Feb 29Jan26-dates moved due to re-opened competency map projects |  | 20d | 89 | [5 empty] | No | 2026-10-01 | 2026-10-28 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0293-4-2 | Baseline & Load I&C User Assignments |  | AP-0679 | Baseline & Load I&C User AssignmentsAP-0679 | AP-0293-4 | AP-0677 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-10-29 | 2026-11-25 | [8 empty] | Other |  | 29Jan26-dates moved due to re-opened competency map projects |  | 20d | 97 | [5 empty] | No | 2026-10-29 | 2026-11-25 | 2025-11-06 13:48 | jennifer.b.wright@ge.com
AP-0294 | Alstom Kahuna Competency for Craft |  | AP-0294 | Alstom Kahuna Competency for CraftAP-0294 | #INVALID COLUMN VALUE | Top | 0 | 31 | 1 | 0 | luca.martino@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete |  | On Track | 2025-11-01 | 2026-02-27 |  |  | 2025-01-01 | 2025-06-30 | Internal Programs & Competency | Craft RM |  |  | Other |  | 2Sept25-Moved to Nov to allow more coordination with stakeholders 30Oct25-Added subtasks to include Kelly's Kahuna build | https://gevernova.ent.box.com/file/2146357314504 | 86d | [6 empty] | No | 2025-11-01 | 2026-02-27 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0294-1 | Review & Develop Craft Kahuna Competency Maps with SME |  | AP-0657 | Review & Develop Craft Kahuna Competency Maps with SMEAP-0657 | AP-0294 | AP-0294 | 1 | 1 | 0 | 1 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | Steps 1-5 in Competency Map Checklist | Complete | TRUE | On Track | 2025-11-01 | 2025-11-28 |  |  | 2025-11-01 | 2025-11-28 | Internal Programs & Competency | Craft RM | [5 empty] | Report at Parent Level | 21d | [6 empty] | No | 2025-11-01 | 2025-11-28 | 2025-10-30 10:43 | jennifer.b.wright@ge.com
AP-0294-2 | Import & Configure System for Alstom Craft Maps |  | AP-0656 | Import & Configure System for Alstom Craft MapsAP-0656 | AP-0294 | AP-0294 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Complete | TRUE | On Track | 2025-12-01 | 2025-12-31 |  |  | 2025-12-01 | 2025-12-31 | Internal Programs & Competency | Craft RM | [5 empty] | Report at Parent Level | 23d | [6 empty] | No | 2025-12-01 | 2025-12-31 | 2025-10-30 10:43 | jennifer.b.wright@ge.com
AP-0294-3 | Baseline & Load Alstom Craft User Assignments |  | AP-0674 | Baseline & Load Alstom Craft User AssignmentsAP-0674 | AP-0294 | AP-0294 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Complete | TRUE | On Track | 2026-01-01 | 2026-02-27 | [8 empty] | Other |  | If completed workbook received prior to start date 12Jan26-Move to Feb to gather all SSOs | Report at Parent Level | 42d | [6 empty] | No | 2026-01-01 | 2026-02-27 | 2025-11-06 13:39 | jennifer.b.wright@ge.com
AP-0295 | Enable TDM visibility to Existing OSS Competency & Training data |  | AP-0295 | Enable TDM visibility to Existing OSS Competency & Training dataAP-0295 | #INVALID COLUMN VALUE | Top | 0 | 32 | 1 | 0 | marcela.bohorquez1@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance | Complete handover and define next steps (break in several activities) | Complete |  | On Track | 2024-09-01 | 2025-11-28 |  |  | 2024-09-01 | 2025-03-31 | [6 empty] | 24Apr25-Updated this item & sub tasks to reflect new approach for identifying relevant OSS personnel data & building reports accordingly. | n/a-parent row | 326d | [6 empty] | No | 2024-09-01 | 2025-11-28 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0295-1 | Identify the OSS data TDMs need to be able to see and where that data currently resides |  | AP-0301 | Identify the OSS data TDMs need to be able to see and where that data currently residesAP-0301 | AP-0295 | AP-0295 | 1 | 1 | 0 | 1 | marcela.bohorquez1@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance | Assemble list of required data and where that data resided (i.e. why systems, existing reports, etc.) | Complete |  | On Track | 2025-04-01 | 2025-05-30 |  |  | 2025-04-01 | 2025-05-30 | Internal | OSS |  |  |  |  | 24Apr25-Updated to reflect new approach | https://gevernova.ent.box.com/file/1876233422272 | 44d | [6 empty] | No | 2025-04-01 | 2025-05-30 | 2024-11-22 08:59 | jennifer.b.wright@ge.com
AP-0295-2 | Build Resource to enable TDM access to OSS Competency & Training Data |  | AP-0537 | Build Resource to enable TDM access to OSS Competency & Training DataAP-0537 | AP-0295 | AP-0295 | 1 | 2 | 0 | 1 | marcela.bohorquez1@gevernova.com | daniel.barrera1@gevernova.com | leonardo.monzo1@gevernova.com | TDM Performance | Consider single dashboard or reference to enable TDMs to locate & use existing OSS competency & training data | Complete |  | On Track | 2025-06-02 | 2025-11-28 |  |  | 2025-06-02 | 2025-07-31 | Internal Ops | OSS |  |  |  |  | 14Jul25-Move to August to allow time to locate missing data sources 2Sept25-Alternate solution identified. Moved to September to allow time to review alternate solution with TDM team. 3Sept25-Updated Improvement title & Lead to reflect new solution (not a single dashboard, but a reference to help TDMs locate & use the available data) 24Sept25-Moved to close in Nov to allow time to grant all TDMs required access | https://gevernova.ent.box.com/file/2063319913380 | 130d | 104 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-11-28 | 2025-04-24 07:31 | jennifer.b.wright@ge.com
AP-197 | Enable TDM access to OSS LMS/HR data | AP-197 | AP-0323 | Enable TDM access to OSS LMS/HR dataAP-0323 | AP-0295 | AP-0295 | 1 | 3 | 0 | 1 | daniel.barrera1@gevernova.com | Marcela Bohorquez | leonardo.monzo1@gevernova.com | TDM Performance | Develop report for TDM visibility to OSS LMS/HR data | Cancelled |  |  | 2024-09-01 | 2025-04-30 |  |  | 2024-09-01 | 2025-03-31 | [6 empty] | Moved from 2024 to 2025 due to need for more HR support/coordination 21Mar25-Moved to April close to allow more time for coordination/realignment with Marcela 24Apr25-Replaced by AP-0295 & sub-tasks |  | 174d | [6 empty] | No | 2024-09-01 | 2025-04-30 | 2024-11-25 13:24 | jennifer.b.wright@ge.com
AP-0296 | SMax Training Fulfillment Adoption |  | AP-0296 | SMax Training Fulfillment AdoptionAP-0296 | #INVALID COLUMN VALUE | Top | 0 | 33 | 0 | 0 | siawwei.tan@gevernova.com |  | leonardo.monzo1@gevernova.com | Operational Simplification | Servicemax complete adoption / Review reports and dashboards | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | Delivery Internal Ops P&C | Craft FE | [5 empty] | https://gevernova.ent.box.com/file/1814007258497 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0297 | Develop Leader Standard Work Cadence for TDM |  | AP-0297 | Develop Leader Standard Work Cadence for TDMAP-0297 | #INVALID COLUMN VALUE | Top | 0 | 34 | 1 | 0 | nimra.kazmi1@gevernova.com | Jennifer Wright | leonardo.monzo1@gevernova.com | TDM Performance | Create the Standards | Complete |  | On Track | 2025-04-01 | 2025-11-28 |  |  | 2025-04-01 | 2025-07-31 | Internal Ops | Craft FE OSS |  |  |  |  | 14Jul25-Split into 2 subtasks. Design = complete in July, Implement & test = complete in Sept | n/a-parent row | 174d | [6 empty] | No | 2025-04-01 | 2025-11-28 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0297-1 | Design TDM LSW Cadence |  | AP-0582 | Design TDM LSW CadenceAP-0582 | AP-0297 | AP-0297 | 1 | 1 | 0 | 1 | nimra.kazmi1@gevernova.com | Jennifer Wright | leonardo.monzo1@gevernova.com | TDM Performance | Create the Standards | Complete |  | On Track | 2025-04-01 | 2025-07-31 |  |  | 2025-04-01 | 2025-07-31 | Internal Ops | Craft FE OSS | [5 empty] | https://gevernova.ent.box.com/file/1941517228439 | 88d | [6 empty] | No | 2025-04-01 | 2025-07-31 | 2025-07-14 09:30 | jennifer.b.wright@ge.com
AP-0297-2 | Implement & Test TDM LSW Cadence |  | AP-0583 | Implement & Test TDM LSW CadenceAP-0583 | AP-0297 | AP-0297 | 1 | 2 | 0 | 1 | nimra.kazmi1@gevernova.com | Jennifer Wright | leonardo.monzo1@gevernova.com | TDM Performance | Test the cadence & improve as needed | Complete |  | On Track | 2025-08-01 | 2025-11-28 |  |  | 2025-08-01 | 2025-09-30 | Internal Ops | Craft FE OSS |  |  |  |  | 17Sept25-Moved to Nov to allow more time to test & collect feedback | https://gevernova.ent.box.com/file/2063957699169 | 86d | [6 empty] | No | 2025-08-01 | 2025-11-28 | 2025-07-14 09:31 | jennifer.b.wright@ge.com
AP-0298 | FEP OJT Process |  | AP-0298 | FEP OJT ProcessAP-0298 | #INVALID COLUMN VALUE | Top | 0 | 35 | 0 | 0 | howayda.sabrymaher@gevernova.com |  | leonardo.monzo1@gevernova.com | Content Quality & Improvements | Define identification / opportunities / follow up / completion | Complete |  | On Track | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-05-30 | Delivery Internal Ops | FE |  |  |  |  | 18Mar25-Moved to July completion due to availability constraints in March & April 28Jul25-Moved to August to allow more time to finalize process with stakeholders | https://gevernova.ent.box.com/file/1973056379546 | 173d | [6 empty] | No | 2025-01-01 | 2025-08-29 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0299 | Field & Region to Global Training Connection / Feedback |  | AP-0299 | Field & Region to Global Training Connection / FeedbackAP-0299 | #INVALID COLUMN VALUE | Top | 0 | 36 | 0 | 0 | carlo.fabregas@gevernova.com |  | leonardo.monzo1@gevernova.com | Operational Simplification | Identify all expert pools/SMEs that need to be connected / supporting and establish process / rhythms (PLL, Chiefs, RMs, ROS, etc) | In Progress |  | Delayed | 2025-05-01 | 2026-06-30 | 2026-03-31 |  | 2025-05-01 | 2025-09-30 | Delivery Internal P&C | Craft FE OSS |  |  | Other |  | 8Sept25-Moved to Oct 13Oct25-Moved to Dec to allow more time to develop SME & PLL connections 03Dec25-Moived to March to allow more time to build the framework. 09Mar26- Moved to June. I have had some discussion already with Harry on this, and some backgrounder off of another call I will be chairing, so will definitely get traction soon. |  | 304d |  |  | TRUE |  |  |  | No | 2025-05-01 | 2026-06-30 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0300 | FEP Cycle improvement |  | AP-0300 | FEP Cycle improvementAP-0300 | #INVALID COLUMN VALUE | Top | 0 | 37 | 0 | 0 | alyssa.mays@gevernova.com | Jennifer Wright | leonardo.monzo1@gevernova.com | TDM Performance | Define pacing, process to follow, people involved in the revisions, implement Best in class practices | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | Delivery Internal Ops | FE | [5 empty] | https://gevernova.ent.box.com/file/1814089785397 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2024-11-22 08:58 | jennifer.b.wright@ge.com
AP-0302 | Integrate Regional FC Craft Training into OFS Trng Processes |  | AP-0302 | Integrate Regional FC Craft Training into OFS Trng ProcessesAP-0302 | #INVALID COLUMN VALUE | Top | 0 | 38 | 1 | 0 | leonardo.monzo1@gevernova.com |  | philip.ganssmann@gevernova.com | Operational Simplification | Complete for each regional program as sub-projects | Complete |  | On Track | 2025-03-01 | 2025-09-30 |  |  | 2025-03-01 | 2025-07-31 | Internal | RM |  |  |  |  | 28Jul25-Moved to August to allow more time to assemble & load courses into MM 2Sept25-moved to end of September - still missing some course info to load into MM. | https://gevernova.ent.box.com/file/1996849756635 | 153d | [6 empty] | No | 2025-03-01 | 2025-09-30 | 2024-11-22 09:18 | jennifer.b.wright@ge.com
AP-0302-1 | Integrate Europe Craft Training programs |  | AP-0303 | Integrate Europe Craft Training programsAP-0303 | AP-0302 | AP-0302 | 1 | 1 | 0 | 1 | beyza.yaver@gevernova.com | andrew.ruch@gevernova.com, brenda.romanvalle@gevernova.com, harry.hanson@gevernova.com | leonardo.monzo1@gevernova.com | Operational Simplification | Integrate existing courses into OFS Training scheduling processes (Blueprint, Catalog, Enrollment, LMS, etc.) | Complete | TRUE | On Track | 2025-03-01 | 2025-09-30 |  |  | 2025-03-01 | 2025-07-31 | Delivery Internal Ops P&C | Craft |  |  |  |  | 28Jul25-Moved to August to allow more time to assemble & load courses into MM 2Sept25-moved to end of September - still missing some course info to load into MM. | Present combined as AP-0302 | 153d | [6 empty] | No | 2025-03-01 | 2025-09-30 | 2024-11-22 09:24 | jennifer.b.wright@ge.com
AP-0302-2 | Integrate MEA Craft Training programs |  | AP-0304 | Integrate MEA Craft Training programsAP-0304 | AP-0302 | AP-0302 | 1 | 2 | 0 | 1 | shaimaa.galal@gevernova.com | andrew.ruch@gevernova.com, brenda.romanvalle@gevernova.com, harry.hanson@gevernova.com | leonardo.monzo1@gevernova.com | Operational Simplification | Integrate existing courses into OFS Training scheduling processes (Blueprint, Catalog, Enrollment, LMS, etc.) | Complete | TRUE | On Track | 2025-03-01 | 2025-09-30 |  |  | 2025-03-01 | 2025-07-31 | Delivery Internal Ops P&C | Craft |  |  |  |  | 28Jul25-Moved to August to allow more time to assemble & load courses into MM 2Sept25-moved to end of September - still missing some course info to load into MM. | Present combined as AP-0302 | 153d | [6 empty] | No | 2025-03-01 | 2025-09-30 | 2024-11-22 09:24 | jennifer.b.wright@ge.com
AP-0302-3 | Integrate LAM Craft Training programs |  | AP-0305 | Integrate LAM Craft Training programsAP-0305 | AP-0302 | AP-0302 | 1 | 3 | 0 | 1 | erica.peredo@gevernova.com | andrew.ruch@gevernova.com, brenda.romanvalle@gevernova.com, harry.hanson@gevernova.com | leonardo.monzo1@gevernova.com | Operational Simplification | Integrate existing courses into OFS Training scheduling processes (Blueprint, Catalog, Enrollment, LMS, etc.) | Complete | TRUE | On Track | 2025-03-01 | 2025-09-30 |  |  | 2025-03-01 | 2025-07-31 | Delivery Internal Ops P&C | Craft |  |  |  |  | 28Jul25-Moved to August to allow more time to assemble & load courses into MM 2Sept25-moved to end of September - still missing some course info to load into MM. | Present combined as AP-0302 | 153d | [6 empty] | No | 2025-03-01 | 2025-09-30 | 2024-11-22 09:24 | jennifer.b.wright@ge.com
AP-0302-4 | Integrate Asia Craft Training programs |  | AP-0306 | Integrate Asia Craft Training programsAP-0306 | AP-0302 | AP-0302 | 1 | 4 | 0 | 1 | carlo.fabregas@gevernova.com | andrew.ruch@gevernova.com, brenda.romanvalle@gevernova.com, harry.hanson@gevernova.com | leonardo.monzo1@gevernova.com | Operational Simplification | Integrate existing courses into OFS Training scheduling processes (Blueprint, Catalog, Enrollment, LMS, etc.) | Complete | TRUE | On Track | 2025-03-01 | 2025-09-30 |  |  | 2025-03-01 | 2025-07-31 | Delivery Internal Ops P&C | Craft |  |  |  |  | 28Jul25-Moved to August to allow more time to assemble & load courses into MM 2Sept25-moved to end of September - still missing some course info to load into MM. | Present combined as AP-0302 | 153d | [6 empty] | No | 2025-03-01 | 2025-09-30 | 2024-11-22 09:24 | jennifer.b.wright@ge.com
AP-0307 | Integrate FE Onboarding/ Leadership training into OFS Trng Process |  | AP-0307 | Integrate FE Onboarding/ Leadership training into OFS Trng ProcessAP-0307 | #INVALID COLUMN VALUE | Top | 0 | 39 | 0 | 0 | alyssa.mays@gevernova.com | andrew.ruch@gevernova.com, Jennifer Wright | leonardo.monzo1@gevernova.com | Operational Simplification | Catalog, Enrollment/Scheduling Process, LMS | Complete |  | On Track | 2025-05-01 | 2025-07-31 |  |  | 2025-05-01 | 2025-07-31 | Internal Ops P&C | FE | [5 empty] | https://gevernova.ent.box.com/file/1941531462847 | 66d | [6 empty] | No | 2025-05-01 | 2025-07-31 | 2024-11-22 09:24 | jennifer.b.wright@ge.com
AP-0319 | Scheduling Tool Phase 5 Development |  | AP-0319 | Scheduling Tool Phase 5 DevelopmentAP-0319 | #INVALID COLUMN VALUE | Top | 0 | 40 | 1 | 0 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification |  | In Progress |  |  | 2025-10-01 | 2026-11-30 |  |  | 2025-04-01 | 2025-06-30 | Delivery Ops P&C | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  |  | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2024-11-25 11:05 | andrew.ruch@ge.com
AP-0319-1 | Integration with Smax for Instructor immigration Automation |  | AP-0324 | Integration with Smax for Instructor immigration AutomationAP-0324 | AP-0319 | AP-0319 | 1 | 1 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification |  | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-04-01 | 2025-06-30 | Delivery Ops | n/a | OFS-Cost-Cost-Gross Margin | C | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2024-11-26 08:10 | andrew.ruch@ge.com
AP-0319-2 | Connect UDC Schedule Data to Data Lake |  | AP-0510 | Connect UDC Schedule Data to Data LakeAP-0510 | AP-0319 | AP-0319 | 1 | 2 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Reporting | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-3 | Standard Work Checklist in Activity Screen for each class |  | AP-0515 | Standard Work Checklist in Activity Screen for each classAP-0515 | AP-0319 | AP-0319 | 1 | 3 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Misc Scheduling | Not Started | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-4 | Automated Notification Triggers (schedule changes, course confirmations, resource gaps, etc) |  | AP-0517 | Automated Notification Triggers (schedule changes, course confirmations, resource gaps, etc)AP-0517 | AP-0319 | AP-0319 | 1 | 4 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Reporting | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-5 | Link to Internal Training Allocation/Enrollment data |  | AP-0511 | Link to Internal Training Allocation/Enrollment dataAP-0511 | AP-0319 | AP-0319 | 1 | 5 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Reporting | Not Started | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-6 | Immigration Request report / Automation |  | AP-0590 | Immigration Request report / AutomationAP-0590 | AP-0319 | AP-0319 | 1 | 6 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Immigration Request | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 11Aug25-not critical for roll-out, moved from Phase 3 | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-08-12 08:28 | jennifer.b.wright@ge.com
AP-0319-7 | Integration with Kahuna for resource skills visibility |  | AP-0321 | Integration with Kahuna for resource skills visibilityAP-0321 | AP-0319 | AP-0319 | 1 | 7 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, Kelly Kirby, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-04-01 | 2025-06-30 | Ops P&C | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2024-11-25 11:05 | andrew.ruch@ge.com
AP-0319-8 | Various queue in and automations from the change management process |  | AP-0518 | Various queue in and automations from the change management processAP-0518 | AP-0319 | AP-0319 | 1 | 8 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Change Management automations | Not Started | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-9 | Crane Operator Secondary Scheduling |  | AP-0589 | Crane Operator Secondary SchedulingAP-0589 | AP-0319 | AP-0319 | 1 | 9 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Misc Resource Utilization and Scheduling | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 11Aug25-not critical for roll-out, moved from phase 3 | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-08-12 08:28 | jennifer.b.wright@ge.com
AP-0319-10 | Automated cost generation of Course |  | AP-0516 | Automated cost generation of CourseAP-0516 | AP-0319 | AP-0319 | 1 | 10 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Automated course budgeting | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Cost-Cost-Gross Margin | C | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-11 | Course completion survey form distribution and feedback collection |  | AP-0514 | Course completion survey form distribution and feedback collectionAP-0514 | AP-0319 | AP-0319 | 1 | 11 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Course Completion Survey (TBD if possible) | Cancelled | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-12 | Instructor Crosstraining Tracker/Reporting for Kahuna updates |  | AP-0512 | Instructor Crosstraining Tracker/Reporting for Kahuna updatesAP-0512 | AP-0319 | AP-0319 | 1 | 12 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Misc Scheduling | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Cost-Cost-Gross Margin OFS-Quality-Customer Escapes-Escapes | C | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0319-13 | Scheduling Sandbox for scheduling mock changes |  | AP-0513 | Scheduling Sandbox for scheduling mock changesAP-0513 | AP-0319 | AP-0319 | 1 | 13 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Misc Scheduling | In Progress | TRUE |  | 2025-10-01 | 2026-11-30 |  |  | 2025-10-01 | 2026-01-30 | Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  |  | Will be reported as roll-up to AP-0319 | 304d | [6 empty] | No | 2025-10-01 | 2026-11-30 | 2025-04-01 11:09 | andrew.ruch@ge.com
AP-0322 | Internal Training for NCCCO Certifications |  | AP-0322 | Internal Training for NCCCO CertificationsAP-0322 | #INVALID COLUMN VALUE | Top | 0 | 41 | 0 | 0 | luca.martino@gevernova.com | andrew.samples@gevernova.com, brenda.romanvalle@gevernova.com | michele.alcantar@gevernova.com | Programs | Create an internal training program that prepares candidates for the NCCCO Lifting Director/ Rigger II/ Rigger I testing. The content needs to confirm with US standards and lifting operational procedure. Once completed the employees will only need to test for certifications. | Cancelled |  | Not Started | 2025-03-01 | 2025-12-31 |  |  | 2025-03-01 | 2025-12-31 | Internal Programs & Competency | Craft RM |  |  |  |  | 05Dec25-cancelled: we are using NCCCO external companies certified instructors to teach our people. Creating an internal pool of instructors is no more needed |  | 219d | [6 empty] | No | 2025-03-01 | 2025-12-31 | 2024-11-25 13:24 | jennifer.b.wright@ge.com
AP-0325 | HLC Massachusetts Crane Recertification |  | AP-0325 | HLC Massachusetts Crane RecertificationAP-0325 | #INVALID COLUMN VALUE | Top | 0 | 42 | 0 | 0 | luca.martino@gevernova.com | andrew.samples@gevernova.com, brenda.romanvalle@gevernova.com | michele.alcantar@gevernova.com | Programs | Offer Crane certifications at the HLC in conjunction with the Mass Crane Operators criteria for recertificaiton. | Cancelled |  | Not Started | 2025-03-01 | 2025-12-31 |  |  | 2025-03-01 | 2025-12-31 | [6 empty] | SMEs- Mike Randolph/ NAM RMs/ Mohamed Montaser (requested by NAM - is this even possible?) 05Dec25-cancelled: only valid for Massachusetts. Few employees involved then. It was a request from EHS team when they didn't know yet the impact. |  | 219d | [6 empty] | No | 2025-03-01 | 2025-12-31 | 2024-11-26 16:01 | jennifer.b.wright@ge.com
AP-0326 | Global Craft Employee Field Guide |  | AP-0326 | Global Craft Employee Field GuideAP-0326 | #INVALID COLUMN VALUE | Top | 0 | 43 | 0 | 0 | luca.martino@gevernova.com | andrew.samples@gevernova.com, Michael Randolph | michele.alcantar@gevernova.com | Content Development | Create an updated field guide for employees based off the 2014 FC Pocket Guide with updated content. This content can also be integrated into Live Outage access. | Complete |  | On Track | 2025-01-01 | 2025-07-31 |  |  | 2025-01-01 | 2025-07-31 | [6 empty] | SMEs- NAM RMs/ Mohamed Montaser Tam has a craft tech SME who would be good to help" | https://gevernova.ent.box.com/file/1940125069960 | 152d | [6 empty] | No | 2025-01-01 | 2025-07-31 | 2024-11-26 16:04 | jennifer.b.wright@ge.com
AP-0327 | Live Outage Application usage Competency & Proficiency Training |  | AP-0327 | Live Outage Application usage Competency & Proficiency TrainingAP-0327 | #INVALID COLUMN VALUE | Top | 0 | 44 | 1 | 0 | benalisalim.messekine@gevernova.com | Benjamin Gilder, Ezra Laurent, Georgios Gkatzoulis, Matthew Hope | michele.alcantar@gevernova.com | Content Development | Complete LO Application training | In Progress |  |  | 2024-11-01 | 2026-06-30 |  |  | 2024-11-01 | 2025-12-31 | Internal | Craft FE OSS RM |  |  | Other |  |  | n/a-parent row | 433d |  |  | TRUE |  |  |  | No | 2024-11-01 | 2026-06-30 | 2024-11-26 16:11 | jennifer.b.wright@ge.com
AP-0327-1 | Complete LO Application Usage Training-3 modules |  | AP-0428 | Complete LO Application Usage Training-3 modulesAP-0428 | AP-0327 | AP-0327 | 1 | 1 | 0 | 1 | benalisalim.messekine@gevernova.com | Benjamin Gilder, Ezra Laurent, Georgios Gkatzoulis, Matthew Hope | michele.alcantar@gevernova.com | Content Development | Complete the LO Application Usage online training (3 Modules) | Complete |  | On Track | 2024-11-01 | 2025-01-31 |  |  | 2024-11-01 | 2025-01-31 | Internal | Craft FE OSS RM |  |  |  |  | Replaces AP-224 from 2024 AP, delayed to 2025 due to PO delays from PMx challenges | https://gevernova.ent.box.com/file/1747897550275 | 66d | [6 empty] | No | 2024-11-01 | 2025-01-31 | 2024-12-19 11:45 | jennifer.b.wright@ge.com
AP-0327-2 | Complete LO Application Usage Training-10 modules |  | AP-0331 | Complete LO Application Usage Training-10 modulesAP-0331 | AP-0327 | AP-0327 | 1 | 2 | 0 | 1 | benalisalim.messekine@gevernova.com | Benjamin Gilder, Ezra Laurent, Georgios Gkatzoulis, Matthew Hope | michele.alcantar@gevernova.com | Content Development | Complete the LO Application Usage online training (Module 1, 2, 4, 6, 7, 8, 11, 12, 13, 14) | Complete |  | On Track | 2025-02-01 | 2025-07-30 |  |  | 2025-02-01 | 2025-07-30 | Internal | Craft FE OSS RM | [5 empty] | https://gevernova.ent.box.com/file/1939397529473 | 129d | [6 empty] | No | 2025-02-01 | 2025-07-30 | 2024-11-26 16:15 | jennifer.b.wright@ge.com
AP-0327-3 | Load LO Application Usage Training into LMS |  | AP-0584 | Load LO Application Usage Training into LMSAP-0584 | AP-0327 | AP-0327 | 1 | 3 | 0 | 1 | benalisalim.messekine@gevernova.com | Diana Torres Sanchez | michele.alcantar@gevernova.com | Content Development |  | Complete |  | On Track | 2025-08-01 | 2025-08-29 |  |  | 2025-08-01 | 2025-08-29 | Internal Ops | Craft FE OSS RM | [5 empty] | https://gevernova.ent.box.com/file/1973674055521 | 21d | [6 empty] | No | 2025-08-01 | 2025-08-29 | 2025-07-31 08:27 | jennifer.b.wright@ge.com
AP-0327-4 | Live Outage Tablet Competency & Proficiency Training |  | AP-0438 | Live Outage Tablet Competency & Proficiency TrainingAP-0438 | AP-0327 | AP-0327 | 1 | 4 | 0 | 1 | benalisalim.messekine@gevernova.com | Benjamin Gilder, Ezra Laurent, Georgios Gkatzoulis, Matthew Hope | michele.alcantar@gevernova.com | Content Development | This request is to build a training module that explain to the trainees how to use the LO tablets and how to determine if it’s connected and if it’s charged, this module is a small module, a small tablet illustration showing all the elements that a craft person should verify prior and during the use of the tablet. Budget is already confirmed from Value Stream and SMEs are available. | Cancelled |  | Delayed | 2026-03-01 | 2026-05-29 |  |  | 2025-06-01 | 2025-07-31 | Internal | Craft FE OSS RM |  |  | Other |  | 14July25-Need to develop a video for the tablet use in HLC 8Sept25-Push to October, video to be developed this month, training development to follow. 13Oct25-Underway, but may be delayed due to purchasing processes. 21Oct 25 The video produced need few weeks of editing by Value Stream team, moving to Dec25 to close 15Dec25-Existing videos are not usable so videos will be re-done at HLC. Need to revisit timeline with new approach. TBD new timeline 12Jan26-Move to March to allow time to work with Vendor 09Mar26-whole project shifted due to SME availability (original SME left). Now targeted March through May 2026 11May26-To be replaced by new Lean Tools Training Refresher AP |  | 66d |  |  |  |  | TRUE |  | No | 2026-03-01 | 2026-05-29 | 2025-01-06 08:21 | jennifer.b.wright@ge.com
AP-0327-5 | LO Application Management |  | AP-0328 | LO Application ManagementAP-0328 | AP-0327 | AP-0327 | 1 | 5 | 0 | 1 | benalisalim.messekine@gevernova.com | Benjamin Gilder, Ezra Laurent, Georgios Gkatzoulis, Matthew Hope | michele.alcantar@gevernova.com | Content Development | Complete the LO Application Management training modules | Complete |  | On Track | 2025-06-01 | 2025-12-31 |  |  | 2025-06-01 | 2025-12-31 | Internal | Craft FE OSS RM | [5 empty] | https://gevernova.ent.box.com/file/2096828380576 | 154d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-12-31 | 2024-11-26 16:15 | jennifer.b.wright@ge.com
AP-0327-6 | LO Application Management (Additional modules) |  | AP-0649 | LO Application Management (Additional modules)AP-0649 | AP-0327 | AP-0327 | 1 | 6 | 0 | 1 | benalisalim.messekine@gevernova.com | Benjamin Gilder, Ezra Laurent, Georgios Gkatzoulis, Matthew Hope | michele.alcantar@gevernova.com | Content Development | Complete the additional LO Application Management training modules | Not Started |  |  | 2026-04-01 | 2026-06-30 |  |  | 2026-04-01 | 2026-06-30 | Internal | Craft FE OSS RM |  |  | Other |  |  |  | 65d |  |  | TRUE |  |  |  | No | 2026-04-01 | 2026-06-30 | 2025-10-22 13:03 | jennifer.b.wright@ge.com
AP-0329 | Live Outage sustainment |  | AP-0329 | Live Outage sustainmentAP-0329 | #INVALID COLUMN VALUE | Top | 0 | 45 | 1 | 0 | benalisalim.messekine@gevernova.com |  | michele.alcantar@gevernova.com | Programs |  | In Progress |  |  | 2025-06-01 | 2026-12-31 |  |  | 2025-04-01 | 2025-08-29 |  |  |  |  | Other |  |  | n/a-parent row | 415d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2026-12-31 | 2024-11-26 16:15 | jennifer.b.wright@ge.com
AP-0329-1 | Live Outage Move to TDMs |  | AP-0330 | Live Outage Move to TDMsAP-0330 | AP-0329 | AP-0329 | 1 | 1 | 0 | 1 | benalisalim.messekine@gevernova.com | TDMs | michele.alcantar@gevernova.com | Programs | Define the portion of activities that can be moved to the training managers, with file aids and processes | Not Started |  | Delayed | 2025-08-04 | 2026-12-31 | 2026-03-31 |  | 2025-04-01 | 2025-07-31 |  |  |  |  | Other |  | 14July25-Some roles were added to the go live unit, I'll schedule trainings for these new roles before moving it to TDMs 03Dec25-moved to March to accommodate various changes this year 09Mar26-Salim to discuss with Leo regarding correct target timing for this. Put on hold or reschedule? 18Mar26-Moved to Dec |  | 369d | [6 empty] | No | 2025-08-04 | 2026-12-31 | 2024-11-26 16:15 | jennifer.b.wright@ge.com
AP-0329-2 | Live Outage Move to PLLs |  | AP-0332 | Live Outage Move to PLLsAP-0332 | AP-0329 | AP-0329 | 1 | 2 | 0 | 1 | benalisalim.messekine@gevernova.com | PLLs | michele.alcantar@gevernova.com | Programs | Define the portion of activities that can be moved to the PLLs, with file aids and processes | Not Started |  | Delayed | 2025-08-04 | 2026-12-31 | 2026-03-31 |  | 2025-04-01 | 2025-07-31 |  |  |  |  | Other |  | 14July25-Some roles were added to the go live unit, I'll schedule trainings for these new roles before moving it to TDMs 03Dec25-moved to March to accommodate various changes this year 09Mar26-Salim to discuss with Jim regarding correct target timing for this. Put on hold or reschedule? 18Mar26-Moved to Dec |  | 369d | [6 empty] | No | 2025-08-04 | 2026-12-31 | 2024-11-26 16:17 | jennifer.b.wright@ge.com
AP-0329-3 | Standardize Box folders & Load Live Outage materials in Xyleme (7FA) |  | AP-0334 | Standardize Box folders & Load Live Outage materials in Xyleme (7FA)AP-0334 | AP-0329 | AP-0329 | 1 | 3 | 0 | 1 | benalisalim.messekine@gevernova.com | sherif.khalifa@gevernova.com | michele.alcantar@gevernova.com | Programs | Standardize the Box folders we are using for Live Outage with other trainings. Changed to moving into Xyleme instead of Box | Complete |  | On Track | 2025-06-01 | 2025-11-28 |  |  | 2025-06-01 | 2025-08-29 | [6 empty] | Will need to work with PLLs to ensure folder structure matches that of our other trainings/ Need additional time to uncloud newly added techs 22Sept25-Moved to Oct to allow time to move into Xyleme 13Oct25-Will be delayed, need to confirm new target timeline with team | https://gevernova.ent.box.com/file/2063463179680 | 131d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-11-28 | 2024-11-26 16:17 | jennifer.b.wright@ge.com
AP-0329-4 | Standardize Box folders & Load Live Outage materials in Xyleme (remaining frames) |  | AP-0695 | Standardize Box folders & Load Live Outage materials in Xyleme (remaining frames)AP-0695 | AP-0329 | AP-0329 | 1 | 4 | 0 | 1 | benalisalim.messekine@gevernova.com |  | michele.alcantar@gevernova.com | Programs |  | In Progress |  |  | 2025-11-01 | 2026-06-30 |  |  | 2025-11-01 | 2026-06-30 |  |  |  |  | Other |  |  |  | 173d |  |  | TRUE |  |  |  | No | 2025-11-01 | 2026-06-30 | 2025-11-10 09:20 | jennifer.b.wright@ge.com
AP-0333 | Live Outage Lower Half Nozzle Removal |  | AP-0333 | Live Outage Lower Half Nozzle RemovalAP-0333 | #INVALID COLUMN VALUE | Top | 0 | 46 | 0 | 0 | benalisalim.messekine@gevernova.com | sherif.khalifa@gevernova.com | michele.alcantar@gevernova.com | Programs | Investigate the Lower half nozzle removal training gap and do problem solving | Cancelled |  |  | 2025-01-01 | 2025-12-31 |  |  | 2025-01-01 | 2025-12-31 |  |  |  |  | Other |  | Tooling is too complicated, and isn't being leveraged on jobs. Is this a tool problem? Training problem? 03Dec25-On hold to determine if this is still needed 11May26-To be replaced by new Lean Tools Training Refresher AP |  | 261d | [6 empty] | No | 2025-01-01 | 2025-12-31 | 2024-11-26 16:17 | jennifer.b.wright@ge.com
AP-0335 | Aero Standardization |  | AP-0335 | Aero StandardizationAP-0335 | #INVALID COLUMN VALUE | Top | 0 | 47 | 1 | 0 | tamara.biediger@gevernova.com |  | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2025-01-01 | 2025-12-31 |  |  | 2025-01-01 | 2025-12-31 | [7 empty] | n/a-parent row | 261d | [6 empty] | No | 2025-01-01 | 2025-12-31 | 2024-11-27 13:08 | jennifer.b.wright@ge.com
AP-0335-1 | Develop plan to standardize Aero employees types globally |  | AP-0336 | Develop plan to standardize Aero employees types globallyAP-0336 | AP-0335 | AP-0335 | 1 | 1 | 0 | 1 | tamara.biediger@gevernova.com | HR | michele.alcantar@gevernova.com | Programs | Will they be FEs, TFAs, Technicians, or…? | Complete |  | On Track | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-02-28 | [6 empty] | 2/24/25-Moved from Feb to April due to need for further discussions with Legal 17Apr25-Moved to May to allow more time to discuss with key stakeholders 29Apr25-Moved to July to complete steps 335-2 for discussion with key stakeholders. 30Jul25-Moved to Aug to allow time review completed Competency maps with HR. | https://gevernova.ent.box.com/file/1968518528849 | 173d | [6 empty] | No | 2025-01-01 | 2025-08-29 | 2024-11-27 13:13 | jennifer.b.wright@ge.com
AP-0335-2 | Complete Aero Competency Maps revisions |  | AP-0337 | Complete Aero Competency Maps revisionsAP-0337 | AP-0335 | AP-0335 | 1 | 2 | 1 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs | Prior to being reviewed and later implemented in Kahuna | Complete |  | On Track | 2025-01-01 | 2025-06-30 |  |  | 2025-01-01 | 2025-04-30 | [6 empty] | 17Apr25-split into sub tasks & adjusted dates accordingly | https://gevernova.box.com/s/wdh47na6xmzq0n3cvljc2tc4xox8jkqe | 129d | [6 empty] | No | 2025-01-01 | 2025-06-30 | 2024-11-27 13:13 | jennifer.b.wright@ge.com
AP-0335-2-1 | Develop Aero Mechanical Services Competency Map |  | AP-0532 | Develop Aero Mechanical Services Competency MapAP-0532 | AP-0335-2 | AP-0337 | 2 | 1 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE |  | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-04-30 | [7 empty] | Report out at parent task level when all remainder complete | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-2-2 | Develop Aero Mechanical Installs Competency Map |  | AP-0526 | Develop Aero Mechanical Installs Competency MapAP-0526 | AP-0335-2 | AP-0337 | 2 | 2 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-01-01 | 2025-06-30 |  |  | 2025-01-01 | 2025-06-30 | [7 empty] | Report out at parent task level when all remainder complete | 129d | [6 empty] | No | 2025-01-01 | 2025-06-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-2-3 | Develop Aero Controls Services Competency Map |  | AP-0529 | Develop Aero Controls Services Competency MapAP-0529 | AP-0335-2 | AP-0337 | 2 | 3 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [7 empty] | Report out at parent task level when all remainder complete | 108d | [6 empty] | No | 2025-01-01 | 2025-05-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-2-4 | Develop Aero Controls Installs Competency Map |  | AP-0531 | Develop Aero Controls Installs Competency MapAP-0531 | AP-0335-2 | AP-0337 | 2 | 4 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [7 empty] | Report out at parent task level when all remainder complete | 108d | [6 empty] | No | 2025-01-01 | 2025-05-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-3 | Review Aero individual employee competencies on an SSO by SSO basis |  | AP-0338 | Review Aero individual employee competencies on an SSO by SSO basisAP-0338 | AP-0335 | AP-0335 | 1 | 3 | 1 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2025-05-01 | 2025-08-28 |  |  | 2025-04-01 | 2025-07-31 | [6 empty] | 17Apr25-split into sub tasks & adjusted dates accordingly | https://gevernova.ent.box.com/file/1968572737896 | 86d | [6 empty] | No | 2025-05-01 | 2025-08-28 | 2024-11-27 13:13 | jennifer.b.wright@ge.com
AP-0335-3-1 | Review Aero Mechanical Services employee Competencies |  | AP-0527 | Review Aero Mechanical Services employee CompetenciesAP-0527 | AP-0335-3 | AP-0338 | 2 | 1 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-05-01 | 2025-06-30 |  |  | 2025-05-01 | 2025-06-30 | [7 empty] | Report out at parent task level when all remainder complete | 43d | 153 | [5 empty] | No | 2025-05-01 | 2025-06-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-3-2 | Review Aero Mechanical Installs employee Competencies |  | AP-0530 | Review Aero Mechanical Installs employee CompetenciesAP-0530 | AP-0335-3 | AP-0338 | 2 | 2 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-07-01 | 2025-08-28 |  |  | 2025-07-01 | 2025-08-28 | [7 empty] | Report out at parent task level when all remainder complete | 43d | 154 | [5 empty] | No | 2025-07-01 | 2025-08-28 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-3-3 | Review Aero Controls Services employee Competencies |  | AP-0525 | Review Aero Controls Services employee CompetenciesAP-0525 | AP-0335-3 | AP-0338 | 2 | 3 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-06-02 | 2025-07-30 |  |  | 2025-06-02 | 2025-07-30 | [7 empty] | Report out at parent task level when all remainder complete | 43d | 155 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-07-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-3-4 | Review Aero Mechanical Controls employee Competencies |  | AP-0528 | Review Aero Mechanical Controls employee CompetenciesAP-0528 | AP-0335-3 | AP-0338 | 2 | 4 | 0 | 1 | tamara.biediger@gevernova.com | Aero RMs, Field SMEs, Region TDMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-06-02 | 2025-07-30 |  |  | 2025-06-02 | 2025-07-30 | [7 empty] | Report out at parent task level when all remainder complete | 43d | 156 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-07-30 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-4 | Aero Academy inclusion |  | AP-0344 | Aero Academy inclusionAP-0344 | AP-0335 | AP-0335 | 1 | 4 | 0 | 1 | tamara.biediger@gevernova.com | Region GMs, RDs | michele.alcantar@gevernova.com | Programs | Investigate potential for Aero Academy and outline requirements | Complete |  | On Track | 2025-09-01 | 2025-12-31 |  |  | 2025-09-01 | 2025-11-28 | [6 empty] | 24Nov25-moved to end of Dec | https://gevernova.ent.box.com/file/2096001976440 | 88d | [6 empty] | No | 2025-09-01 | 2025-12-31 | 2024-11-27 13:25 | jennifer.b.wright@ge.com
AP-0335-5 | Update Kahuna with new Aero competency maps created in step above |  | AP-0339 | Update Kahuna with new Aero competency maps created in step aboveAP-0339 | AP-0335 | AP-0335 | 1 | 5 | 1 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2025-07-01 | 2025-08-29 |  |  | 2025-08-01 | 2025-12-31 | [6 empty] | 17Apr25-split into sub tasks & adjusted dates accordingly |  | 44d | [6 empty] | No | 2025-07-01 | 2025-08-29 | 2024-11-27 13:13 | jennifer.b.wright@ge.com
AP-0335-5-1 | Update Aero Mechanical Services Map in Kahuna |  | AP-0534 | Update Aero Mechanical Services Map in KahunaAP-0534 | AP-0335-5 | AP-0339 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-07-01 | 2025-07-31 |  |  | 2025-07-01 | 2025-07-31 | [7 empty] | Report out at parent task level when all remainder complete | 23d | 158 | [5 empty] | No | 2025-07-01 | 2025-07-31 | 2025-04-17 12:55 | jennifer.b.wright@ge.com
AP-0335-5-2 | Update Aero Mechanical Installs Map in Kahuna |  | AP-0535 | Update Aero Mechanical Installs Map in KahunaAP-0535 | AP-0335-5 | AP-0339 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-07-01 | 2025-07-31 |  |  | 2025-08-29 | 2025-09-30 | [6 empty] | Move to August all these will be complete | Report out at parent task level when all remainder complete | 23d | 158 | [5 empty] | No | 2025-07-01 | 2025-07-31 | 2025-04-17 13:00 | jennifer.b.wright@ge.com
AP-0335-5-3 | Update Aero Controls Services Map in Kahuna |  | AP-0533 | Update Aero Controls Services Map in KahunaAP-0533 | AP-0335-5 | AP-0339 | 2 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-07-31 | 2025-08-29 |  |  | 2025-07-31 | 2025-08-29 | [7 empty] | Report out at parent task level when all remainder complete | 22d | 160 | [5 empty] | No | 2025-07-31 | 2025-08-29 | 2025-04-17 13:00 | jennifer.b.wright@ge.com
AP-0335-5-4 | Update Aero Controls Installs Map in Kahuna |  | AP-0536 | Update Aero Controls Installs Map in KahunaAP-0536 | AP-0335-5 | AP-0339 | 2 | 4 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-07-31 | 2025-08-29 |  |  | 2025-07-31 | 2025-08-29 | [7 empty] | Report out at parent task level when all remainder complete | 22d | 161 | [5 empty] | No | 2025-07-31 | 2025-08-29 | 2025-04-17 13:00 | jennifer.b.wright@ge.com
AP-034 | Retire Low Utilized Classes | AP-034 | AP-0412 | Retire Low Utilized ClassesAP-0412 | #INVALID COLUMN VALUE | Top | 0 | 48 | 0 | 0 | pablo.schibli@gevernova.com | andrew.ruch@gevernova.com, johann.daxer@gevernova.com, PLL | jim.rosen@gevernova.com | Operational Simplification | Catalogue refresh / simplification: Eliminate low utilized classes from catalogue | Complete |  | On Track | 2024-01-01 | 2025-02-28 |  |  | 2024-01-01 | 2025-01-31 | Customer Delivery Internal Ops | [5 empty] | 29Jan25-Moved date to February. List is compiled and is now pending review with Johann & submitting MM requests. | https://gevernova.ent.box.com/file/1458194079972 | 305d | [6 empty] | Yes | 2024-01-01 | 2025-02-28 | 2024-12-12 12:11 | jennifer.b.wright@ge.com
AP-0340 | FE Field Project and Scope Management Course |  | AP-0340 | FE Field Project and Scope Management CourseAP-0340 | #INVALID COLUMN VALUE | Top | 0 | 49 | 1 | 0 | tamara.biediger@gevernova.com | FE RMs, 3rd party | michele.alcantar@gevernova.com | Programs | Create modular curriculum for FE Field Leadership Course | In Progress |  | On Track | 2025-01-01 | 2026-11-30 | 2026-08-31 |  | 2025-01-01 | 2025-06-30 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 25June25-Split into sub tasks and updated dates accordingly 23Apr26- Adjusted name & delivery dates to clarify course & approach. | n/a-parent row | 499d | [6 empty] | No | 2025-01-01 | 2026-11-30 | 2024-11-27 13:14 | jennifer.b.wright@ge.com
AP-0340-1 | Finalize Field Project and Scope Management Course Curriculum |  | AP-0580 | Finalize Field Project and Scope Management Course CurriculumAP-0580 | AP-0340 | AP-0340 | 1 | 1 | 0 | 1 | tamara.biediger@gevernova.com | FE RMs, 3rd party | michele.alcantar@gevernova.com | Programs | Organize & review curriculum with SMEs Develop materials accordingly | Complete | TRUE | On Track | 2025-01-01 | 2026-02-27 |  |  | 2025-01-01 | 2025-08-29 | Delivery Internal Ops Programs & Competency | FE |  |  |  |  | 11Aug25-At risk due to SME availability 28Aug25-Design & review is complete. Moved to September to include time for vendor to develop materials 18Sept25-Moved to Nov based on vendor estimated timelines 10Nov25-Moved to Jan due to vendor timing 23Jan26-Moved to Feb due to vendor delays |  | 303d | [6 empty] | No | 2025-01-01 | 2026-02-27 | 2025-06-25 11:15 | jennifer.b.wright@ge.com
AP-0340-2 | Identify Field Project and Scope Management Course Instructors |  | AP-0581 | Identify Field Project and Scope Management Course InstructorsAP-0581 | AP-0340 | AP-0340 | 1 | 2 | 0 | 1 | tamara.biediger@gevernova.com | FE RMs, 3rd party | michele.alcantar@gevernova.com | Programs | Identify instructor(s) from field to deliver the course | Complete | TRUE | On Track | 2025-12-01 | 2025-12-31 |  |  | 2025-09-01 | 2025-09-30 | Delivery Internal Ops Programs & Competency | FE | [5 empty] | https://gevernova.ent.box.com/file/2096019565283 | 23d | [6 empty] | No | 2025-12-01 | 2025-12-31 | 2025-06-25 11:15 | jennifer.b.wright@ge.com
AP-0340-3 | Deliver Field Project and Scope Management Course Pilot Session |  | AP-0578 | Deliver Field Project and Scope Management Course Pilot SessionAP-0578 | AP-0340 | AP-0340 | 1 | 3 | 0 | 1 | tamara.biediger@gevernova.com | FE RMs, 3rd party | michele.alcantar@gevernova.com | Programs | Schedule, prep & deliver pilot session | Not Started | TRUE |  | 2026-01-01 | 2026-06-30 |  |  | 2025-10-01 | 2026-01-30 | Delivery Internal Ops Programs & Competency | FE |  |  |  |  | 12Jan26-Moved to June due to scheduling |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-06-25 11:15 | jennifer.b.wright@ge.com
AP-0340-4 | Load Field Project and Scope Management course into our relevant systems |  | AP-0822 | Load Field Project and Scope Management course into our relevant systemsAP-0822 | AP-0340 | AP-0340 | 1 | 4 | 0 | 1 | tamara.biediger@gevernova.com | Benali Salim Messekine, konstantina.georga@gevernova.com, lee.s.fielding@gevernova.com, marisol.guidry1@gevernova.com | michele.alcantar@gevernova.com | Programs | NOTE - needs to include determining if it will be 1 generic course or different technology-specific courses. If 1 generic, how do we handle making sure we have the right instructor & students in each course? 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | In Progress | TRUE | On Track | 2026-07-01 | 2026-08-31 | 2026-04-30 |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  |  |  | 26Feb26-Added as new sub-task 02Apr26-Moved back to April to confirm outline questions 23Apr26-Moved to after Pilot session to use pilot to confirm how the course will be structured |  | 44d | [6 empty] | No | 2026-07-01 | 2026-08-31 | 2026-02-23 13:07 | jennifer.b.wright@ge.com
AP-0340-5 | Finalize & Sustain Field Project and Scope Management Course Curriculum based on pilot feedback |  | AP-0579 | Finalize & Sustain Field Project and Scope Management Course Curriculum based on pilot feedbackAP-0579 | AP-0340 | AP-0340 | 1 | 5 | 0 | 1 | tamara.biediger@gevernova.com | FE RMs, 3rd party | michele.alcantar@gevernova.com | Programs | Gather feedback from participants & instructors, modify accordingly, build into standard BluePrint process | Not Started | TRUE |  | 2026-07-01 | 2026-11-30 | 2026-08-31 |  | 2026-02-02 | 2026-05-29 | Delivery Internal Ops Programs & Competency | FE |  |  |  |  | 12Jan26-moved back due to pilot delivery delay 23Feb26-moved earlier from Oct to Aug. 23Apr26-added time to build case studies for other discpilines |  | 109d | [6 empty] | No | 2026-07-01 | 2026-11-30 | 2025-06-25 11:15 | jennifer.b.wright@ge.com
AP-0341 | FEHS Standardization |  | AP-0341 | FEHS StandardizationAP-0341 | #INVALID COLUMN VALUE | Top | 0 | 50 | 1 | 0 | tamara.biediger@gevernova.com |  | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2025-01-01 | 2025-10-31 |  |  | 2025-01-01 | 2025-05-30 | [7 empty] | https://gevernova.ent.box.com/file/2029875083116 | 218d | [6 empty] | No | 2025-01-01 | 2025-10-31 | 2024-11-27 13:20 | jennifer.b.wright@ge.com
AP-0341-1 | Create standard onboarding class for FEHS |  | AP-0342 | Create standard onboarding class for FEHSAP-0342 | AP-0341 | AP-0341 | 1 | 1 | 0 | 1 | tamara.biediger@gevernova.com | TDMs, RMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-01-01 | 2025-10-31 |  |  | 2025-01-01 | 2025-04-30 | [6 empty] | 17Apr25-extended to June to allow more time to work with stakeholders to revise & scale existing NAM course. 19May2025 Extended dates to August 2025 to accommodate Kaizen input and feedback from a second run of the course 11Aug25-Pending results/changes from latest session 28Aug25-Moved to September to allow more time to review/build curriculum 18Sept25-Moved to Oct to allow time for final review & loading into catalog/LMS | Report at parent level | 218d | [6 empty] | No | 2025-01-01 | 2025-10-31 | 2024-11-27 13:25 | jennifer.b.wright@ge.com
AP-0341-2 | Create ELT training and curriculum for FEHS |  | AP-0343 | Create ELT training and curriculum for FEHSAP-0343 | AP-0341 | AP-0341 | 1 | 2 | 0 | 1 | tamara.biediger@gevernova.com | TDMs, RMs | michele.alcantar@gevernova.com | Programs |  | Complete | TRUE | On Track | 2025-01-01 | 2025-10-31 |  |  | 2025-01-01 | 2025-05-30 | [6 empty] | 12May25-Due to results of last week's kaizen, will be delayed. New dates TBD 19May2025 Extended dates to August 2025 to accommodate Kaizen input and feedback from a second run of the course 11Aug25-Pending results/changes from latest session 28Aug25-Moved to September to allow more time to review/build curriculum 18Sept25-Moved to Oct to allow time for final review & loading into catalog/LMS | Report at parent level | 218d | [6 empty] | No | 2025-01-01 | 2025-10-31 | 2024-11-27 13:25 | jennifer.b.wright@ge.com
AP-0345 | Map Advanced Level Courses to Competencies covered in course |  | AP-0345 | Map Advanced Level Courses to Competencies covered in courseAP-0345 | #INVALID COLUMN VALUE | Top | 0 | 51 | 1 | 0 | Jennifer Wright | David Ramey, James Rosen, Kelly Kirby, Leonardo Monzo | michele.alcantar@gevernova.com | Competencies | What skills/competencies are supported by the ALT courses - which Roles would this class support? | Complete |  | On Track | 2025-12-01 | 2026-02-27 |  |  | 2025-12-01 | 2026-02-27 | Delivery Internal Programs & Competency |  |  |  | Other | leonardo.monzo1@gevernova.com | 18Mar25-working with team to better understand the root cause of the problem. Once the solution is identified the timeline to implement will be determined. Next meeting is 15Apr25; 1Sept25 need to identify who should take the lead on identifying which competencies are covered by with ADV level courses (Internal training/PLLs?) 08Dec25-Updated sub-tasks to align with latest approach | https://gevernova.ent.box.com/file/2144314569181 | 65d | [6 empty] | No | 2025-12-01 | 2026-02-27 | 2024-11-27 13:25 | jennifer.b.wright@ge.com
AP-0345-1 | Implement standard sub-tasks for all Content Development projects |  | AP-0543 | Implement standard sub-tasks for all Content Development projectsAP-0543 | AP-0345 | AP-0345 | 1 | 1 | 0 | 1 | Jennifer Wright | David Ramey, James Rosen, Kelly Kirby, Leonardo Monzo | michele.alcantar@gevernova.com | Competencies | Includes competency review, setup in Kahuna, course materials, target instructors, system setup & pilot session delivery. All steps must be completed to consider a development project complete. | Complete | TRUE | On Track | 2025-12-01 | 2026-01-30 |  |  | 2025-12-01 | 2026-01-30 | Delivery Internal Programs & Competency |  |  |  | Other |  |  | n/a-report at parent level | 45d | [6 empty] | No | 2025-12-01 | 2026-01-30 | 2025-04-24 10:32 | jennifer.b.wright@ge.com
AP-0345-2 | Add question to Intake Review to determine competency connection for new training requests |  | AP-0719 | Add question to Intake Review to determine competency connection for new training requestsAP-0719 | AP-0345 | AP-0345 | 1 | 2 | 0 | 1 | Jennifer Wright | David Ramey, James Rosen, Kelly Kirby, Leonardo Monzo | michele.alcantar@gevernova.com | Competencies | Add question to PM step to identify if corresponding competencies already exist in Kahuna If no, or not completely, must include Kelly/Program Manager(?) in development process to support competency items in Content Development sub-tasks | Complete | TRUE | On Track | 2026-01-01 | 2026-02-27 |  |  | 2026-01-01 | 2026-02-27 | Delivery Internal Programs & Competency |  |  |  | Other |  |  | n/a-report at parent level | 42d | [6 empty] | No | 2026-01-01 | 2026-02-27 | 2025-12-08 14:59 | jennifer.b.wright@ge.com
AP-0345-3 | Incorporate a “Training Content Review” step into the Competency Map development standard work |  | AP-0542 | Incorporate a “Training Content Review” step into the Competency Map development standard workAP-0542 | AP-0345 | AP-0345 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | David Ramey, Jennifer Wright | michele.alcantar@gevernova.com | Competencies | Ensure that training is aligned with any new/updated competency maps | Complete | TRUE | On Track | 2026-01-01 | 2026-02-27 |  |  | 2026-01-01 | 2026-02-27 | Delivery Internal Programs & Competency |  |  |  | Other |  |  | n/a-report at parent level | 42d | [6 empty] | No | 2026-01-01 | 2026-02-27 | 2025-04-24 10:32 | jennifer.b.wright@ge.com
AP-0346 | Kahuna Mobile App Update |  | AP-0346 | Kahuna Mobile App UpdateAP-0346 | #INVALID COLUMN VALUE | Top | 0 | 52 | 1 | 0 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | Complete |  |  | 2025-01-01 | 2025-07-31 |  |  | 2025-01-01 | 2025-10-27 | [7 empty] | n/a-parent row | 152d | [6 empty] | No | 2025-01-01 | 2025-07-31 | 2024-11-27 13:25 | jennifer.b.wright@ge.com
AP-0346-1 | Complete Kahuna Mobile App UIA testing/feedback |  | AP-0351 | Complete Kahuna Mobile App UIA testing/feedbackAP-0351 | AP-0346 | AP-0346 | 1 | 1 | 0 | 1 | kelly.kirby@gevernova.com | Volunteers | michele.alcantar@gevernova.com | Competencies |  | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-01-31 | [6 empty] | 13Jan25-Initial testing is complete but found a number of issues that require changes by the vendor. Testing will be required once vendor adds 'My Assessment' page to mobile app. 26Feb25-Kelly to try to get sense of timing for our requested changes to new mobile app. If they can't commit to a reasonable timeline we'll cancel this AP group. 24Mar25-Extended to April to accommodate extra time to review newly released changes to the app | https://gevernova.ent.box.com/file/1849003934177 | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-27 13:28 | jennifer.b.wright@ge.com
AP-0346-2 | Develop Kahuna Mobile App implementation plan |  | AP-0348 | Develop Kahuna Mobile App implementation planAP-0348 | AP-0346 | AP-0346 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | implementation plan for communication/training/adoption of Mobile App | Complete |  | On Track | 2025-05-01 | 2025-05-30 |  |  | 2025-04-01 | 2025-05-29 | [7 empty] | https://gevernova.box.com/s/mzp1dwnjhgsk0l2zktp8pwmxg59rqq89 | 22d | 183 | [5 empty] | No | 2025-05-01 | 2025-05-30 | 2024-11-27 13:28 | jennifer.b.wright@ge.com
AP-0346-3 | Develop Kahuna Mobile App training |  | AP-0349 | Develop Kahuna Mobile App trainingAP-0349 | AP-0346 | AP-0346 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Diana Torres Sanchez | michele.alcantar@gevernova.com | Competencies |  | Complete |  | On Track | 2025-06-02 | 2025-07-31 |  |  | 2025-05-30 | 2025-07-29 | [7 empty] | https://gevernova.box.com/s/hmom50d3is4jszawiw02u6e3o01k946z | 44d | 184 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-07-31 | 2024-11-27 13:28 | jennifer.b.wright@ge.com
AP-0346-4 | Roll out Kahuna Mobile app updates |  | AP-0350 | Roll out Kahuna Mobile app updatesAP-0350 | AP-0346 | AP-0346 | 1 | 4 | 0 | 1 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | Complete |  | On Track | 2025-06-02 | 2025-07-31 |  |  | 2025-07-30 | 2025-10-27 | [6 empty] | Mobile rolled out ahead of schedule. Project completed with AP-0346-3 | https://gevernova.box.com/s/hmom50d3is4jszawiw02u6e3o01k946z | 44d |  | TRUE |  |  |  |  | No | 2025-06-02 | 2025-07-31 | 2024-11-27 13:28 | jennifer.b.wright@ge.com
AP-0347 | Kahuna Access |  | AP-0347 | Kahuna AccessAP-0347 | #INVALID COLUMN VALUE | Top | 0 | 53 | 0 | 0 | kelly.kirby@gevernova.com | Marcela Bohorquez | michele.alcantar@gevernova.com | Competencies | Explore using existing equipment (HLC laptops) at the Craft 5 week onboarding for accessing kahuna via phone / laptop/ tablet. | Not Started |  | At Risk | 2026-02-01 | 2026-07-31 | 2026-03-31 |  | 2025-05-01 | 2025-07-31 |  |  |  |  | Other |  | very unlikely, due to lack of funding. Add site access to existing tablets? 14Jul25-Confirmed not feasible. Cancelled 16Oct25-re-opened with modified scope, description and 2026 dates 25Mar26-Moved to July to allow time to investigate further how access is happening across regions and whether system access is truly a barrier. |  | 131d |  |  |  | TRUE |  |  | No | 2026-02-01 | 2026-07-31 | 2024-11-27 13:28 | jennifer.b.wright@ge.com
AP-0352 | Develop Kahuna Talking Points: Standardize Kahuna Communications |  | AP-0352 | Develop Kahuna Talking Points: Standardize Kahuna CommunicationsAP-0352 | #INVALID COLUMN VALUE | Top | 0 | 54 | 0 | 0 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | Develop standard Kahuna deck/talking points to be used by training team as needed, when conversing on Kahuna topics | Complete |  | On Track | 2025-08-01 | 2025-10-31 |  |  | 2025-06-01 | 2025-08-29 | [6 empty] | will be rolled into guide book 02Sept25-moved to October due to other priorities | https://gevernova.ent.box.com/file/2030016558309 | 66d | [6 empty] | No | 2025-08-01 | 2025-10-31 | 2024-11-27 13:29 | jennifer.b.wright@ge.com
AP-0353 | Kahuna refresher training |  | AP-0353 | Kahuna refresher trainingAP-0353 | #INVALID COLUMN VALUE | Top | 0 | 55 | 0 | 0 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | Develop a Kahuna refresher training for Certified Assessors | Complete |  | On Track | 2025-02-01 | 2025-04-30 |  |  | 2025-02-01 | 2025-03-31 | [7 empty] | https://gevernova.ent.box.com/file/1848778599821 | 64d | [6 empty] | No | 2025-02-01 | 2025-04-30 | 2024-11-27 13:29 | jennifer.b.wright@ge.com
AP-0354 | Critical Competencies |  | AP-0354 | Critical CompetenciesAP-0354 | #INVALID COLUMN VALUE | Top | 0 | 56 | 1 | 0 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | On Hold |  |  | 2026-01-01 | 2026-06-30 |  |  | 2025-08-01 | 2025-11-28 |  |  |  |  | Other |  | 24Sept25-Due to volume of system work (Electrical, Controls, Mech, I&C, Welder, etc) taking priority for 4Q, moving to 1Q 2026 25Feb26-Moved to On-Hold due to prioritization of system/mapping work. Will revisit in May/June | n/a-parent row | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2024-11-27 13:35 | jennifer.b.wright@ge.com
AP-0354-1 | Define Methodology for identifying Critical Competencies |  | AP-0617 | Define Methodology for identifying Critical CompetenciesAP-0617 | AP-0354 | AP-0354 | 1 | 1 | 0 | 1 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | On Hold |  | At Risk | 2026-01-01 | 2026-02-27 |  |  | 2026-01-01 | 2026-01-30 |  |  |  |  | Other |  | 26Jan26-Moved to Feb due to other priorities in Jan 09Feb26-To be moved back due to other priorites |  | 42d | [6 empty] | No | 2026-01-01 | 2026-02-27 | 2025-09-08 09:14 | jennifer.b.wright@ge.com
AP-0354-2 | Identify safety critical competencies in kahuna |  | AP-0357 | Identify safety critical competencies in kahunaAP-0357 | AP-0354 | AP-0354 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | PLLs / SMEs | michele.alcantar@gevernova.com | Competencies |  | On Hold |  |  | 2026-03-01 | 2026-04-30 |  |  | 2025-08-01 | 2025-09-30 |  |  |  |  | Other |  | 2Feb26-Moved back a month due to delay for 0354-1 |  | 45d | [6 empty] | No | 2026-03-01 | 2026-04-30 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-0354-3 | Define if safety critical competencies expire or not |  | AP-0356 | Define if safety critical competencies expire or notAP-0356 | AP-0354 | AP-0354 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | PLLs / SMEs | michele.alcantar@gevernova.com | Competencies |  | On Hold |  |  | 2026-04-01 | 2026-05-29 |  |  | 2025-09-01 | 2025-10-29 |  |  |  |  | Other |  | 2Feb26-Moved back a month due to delay for 0354-1 |  | 43d |  |  |  |  | TRUE |  | No | 2026-04-01 | 2026-05-29 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-0354-4 | Identify business critical competencies in kahuna |  | AP-0358 | Identify business critical competencies in kahunaAP-0358 | AP-0354 | AP-0354 | 1 | 4 | 0 | 1 | kelly.kirby@gevernova.com | PLLs / SMEs | michele.alcantar@gevernova.com | Competencies |  | On Hold |  |  | 2026-05-01 | 2026-06-30 |  |  | 2025-10-01 | 2025-11-28 |  |  |  |  | Other |  | 2Feb26-Moved back a month due to delay for 0354-1 |  | 43d |  |  | TRUE |  |  |  | No | 2026-05-01 | 2026-06-30 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-0355 | Generic CC Simulators with documentation |  | AP-0355 | Generic CC Simulators with documentationAP-0355 | #INVALID COLUMN VALUE | Top | 0 | 57 | 0 | 0 | aaron.hayes@gevernova.com | Charles Wall | michele.alcantar@gevernova.com | Content Development | Choose OTS simulators of different configuration and document start up instructions for operations training. Add Malfunctions for Operations and troubleshooting. | Complete |  | On Track | 2025-01-01 | 2025-12-31 |  |  | 2025-01-01 | 2025-12-31 | Customer Internal | [5 empty] | 9HA02/D650 Single Shaft Complete 7HA02/D654 Multi Shaft Complete | https://gevernova.ent.box.com/file/2095872621289 | 261d | [6 empty] | No | 2025-01-01 | 2025-12-31 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-0359 | Add standard labs to new frame simulations |  | AP-0359 | Add standard labs to new frame simulationsAP-0359 | #INVALID COLUMN VALUE | Top | 0 | 58 | 0 | 0 | aaron.hayes@gevernova.com | Charles Wall, Mohammed Nizami, Santosh Kumar | michele.alcantar@gevernova.com | Content Development | Add standard (virtual) lab exercises with matching procedures to newer frame size simulations. (eg 7HA03, 9HA02). Poll PLL and Instructors for priority list and lab changes needed. | On Hold |  | Delayed | 2025-01-01 | 2026-04-30 |  |  | 2025-01-01 | 2025-09-30 | Customer Internal |  |  |  | Other |  | 9HA02 in progress with estimated completion end of 2025 7HA03 in progress but paused with work shifted to AP-211 08Apr26- Put on hold due to higher priority projects |  | 347d | [6 empty] | No | 2025-01-01 | 2026-04-30 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-036 | Simplify cost reconciliation per each internal training class | AP-036 | AP-0267 | Simplify cost reconciliation per each internal training classAP-0267 | #INVALID COLUMN VALUE | Top | 0 | 59 | 1 | 0 | jim.rosen@gevernova.com |  | jim.rosen@gevernova.com | Financial Simplification | Continuation of sub-projects from 2024 | Complete |  |  | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [8 empty] | 108d | [6 empty] | Yes | 2025-01-01 | 2025-05-30 | 2024-11-21 09:01 | jennifer.b.wright@ge.com
AP-036 | Document new standard work for Cost Reconciliation | AP-036 | AP-0266 | Document new standard work for Cost ReconciliationAP-0266 | AP-036 | AP-036 | 1 | 1 | 0 | 1 | jim.rosen@gevernova.com | Jennifer Wright | jim.rosen@gevernova.com | Financial Simplification |  | Complete |  | On Track | 2025-01-01 | 2025-03-28 |  |  | 2025-01-01 | 2025-03-28 | Delivery | [5 empty] | 11/18/24-Move to Q1 2025 to allow time to better undertsand new PMx processes. | https://gevernova.box.com/s/hwj4lgc2q32flyth8kocprcnd1guxfln | 63d | [6 empty] | Yes | 2025-01-01 | 2025-03-28 | 2024-11-21 09:01 | jennifer.b.wright@ge.com
AP-037 | Identify root causes and reduce lag in cost allocation | AP-037 | AP-0265 | Identify root causes and reduce lag in cost allocationAP-0265 | AP-036 | AP-036 | 1 | 2 | 0 | 1 | jim.rosen@gevernova.com | Philip Ganssmann | jim.rosen@gevernova.com | Financial Simplification |  | Cancelled |  |  | 2025-04-01 | 2025-05-30 |  |  | 2025-04-01 | 2025-05-30 | [6 empty] | Improve lagging in cost allocation 11/18/24-Move to mid-2025 to re-evaluate with PMx data (is this still an issue?) 12May25-Put on hold - may not be needed anymore - maybe roll into new PO process? 14Oct25-No longer needed. PMx process has eliminated this issue. |  | 44d | [6 empty] | Yes | 2025-04-01 | 2025-05-30 | 2024-11-21 09:01 | jennifer.b.wright@ge.com
AP-0361 | Develop HMI testing system based. |  | AP-0361 | Develop HMI testing system based.AP-0361 | #INVALID COLUMN VALUE | Top | 0 | 60 | 0 | 0 | aaron.hayes@gevernova.com | Charles Wall | michele.alcantar@gevernova.com | Content Quality & Improvements | Examine the possibility of creating a testing system built into the MarkVIe simulations. Using HMI screens as a testing platform and reading inputs from students and controllers to give feedback or grades. | Cancelled |  |  | 2025-07-01 | 2025-09-30 |  |  | 2025-07-01 | 2025-09-30 | [6 empty] | If needed/desired, check with M. Nizami first. No initial interest in this concept currently. Cancelling for 2025. |  | 66d | [6 empty] | No | 2025-07-01 | 2025-09-30 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-0362 | CloudShare hosting |  | AP-0362 | CloudShare hostingAP-0362 | #INVALID COLUMN VALUE | Top | 0 | 61 | 0 | 0 | aaron.hayes@gevernova.com | Charles Wall | michele.alcantar@gevernova.com | Content Quality & Improvements | On board CloudShare as a GEV supplier and conduct testing, then pilot training. CloudShare would be a secondary option to Skytap and offer hypervisor hosting used for control server training. | Complete |  | On Track | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-06-30 | Customer Delivery Internal | [5 empty] | 06Jun25-LIkely to push out, potential pilot session July 7th, 2025 26Jun25-push completion to end of August to complete testing with a live class and decide how to proceed | https://gevernova.ent.box.com/file/1887775326636 | 173d | [6 empty] | No | 2025-01-01 | 2025-08-29 | 2024-11-27 13:37 | jennifer.b.wright@ge.com
AP-0363 | Integrate SkyTap/CloudShare into Xyleme |  | AP-0363 | Integrate SkyTap/CloudShare into XylemeAP-0363 | #INVALID COLUMN VALUE | Top | 0 | 62 | 0 | 0 | aaron.hayes@gevernova.com | Lee Fielding, Philip Ganssmann | michele.alcantar@gevernova.com | Operational Simplification |  | Cancelled | [14 empty] | 9May25-Team agreed to cancel this. Initial investigation shows small benefit & fairly substantial effort to integrate it. Not a priority at this time, can revisit in the future if needed. Be cautious of existing customer VenU connects |  | 66d | [6 empty] | No | #INVALID DATA TYPE | #INVALID DATA TYPE | 2024-11-27 13:43 | jennifer.b.wright@ge.com
AP-0364 | Program Effectiveness |  | AP-0364 | Program EffectivenessAP-0364 | #INVALID COLUMN VALUE | Top | 0 | 63 | 0 | 0 | julieta.ponceh@gevernova.com | daniel.barrera1@gevernova.com, Jennifer Wright | michele.alcantar@gevernova.com | Programs | Implement comprehensive metrics to evaluate and improve Program effectiveness (e.g. qualification timelines, outage quality). | Not Started |  | Delayed | 2026-04-01 | 2026-12-31 | 2026-05-29 |  | 2025-07-01 | 2025-09-30 |  |  |  |  | Other |  | 19Jun25-Shifted due to bandwidth challenge 9Feb26-Shifted later due to other priorities 19Mar26-Changed Lead from Ankita to Julieta & moved to Dec due to other priorities |  | 197d | [6 empty] | No | 2026-04-01 | 2026-12-31 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0365 | Create Installation Site Manager course |  | AP-0365 | Create Installation Site Manager courseAP-0365 | #INVALID COLUMN VALUE | Top | 0 | 64 | 1 | 0 | ankita.gupta@gevernova.com | SMEs | michele.alcantar@gevernova.com | Programs | Redesign TIM training course and add needed modules | In Progress |  | Delayed | 2025-06-01 | 2026-07-31 | 2026-03-31 |  | 2025-05-01 | 2025-09-30 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 05June25-pushed back finish date to Sept due to priorities. Also revised AP# to be standalone item, not child of AP-214 | n/a-parent row | 306d |  | TRUE |  | TRUE |  |  | No | 2025-06-01 | 2026-07-31 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0365-1 | Define Installation Site Manager course |  | AP-0567 | Define Installation Site Manager courseAP-0567 | AP-0365 | AP-0365 | 1 | 1 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Define what tops/content is needed, what needs to be modified in the existing SM program | Complete |  | On Track | 2025-06-01 | 2025-06-30 |  |  | 2025-06-01 | 2025-06-30 | Delivery Internal Ops Programs & Competency | FE | [5 empty] | https://gevernova.ent.box.com/file/1904721999772 | 22d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-06-30 | 2025-06-06 07:24 | jennifer.b.wright@ge.com
AP-0365-2 | Develop Installation Site Manager course |  | AP-0568 | Develop Installation Site Manager courseAP-0568 | AP-0365 | AP-0365 | 1 | 2 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Develop List of relevant Competencies & identify which can be delivered via training vs. OJT/other Develop course content / storyboard (not formatting) | In Progress | TRUE | Delayed | 2025-07-01 | 2026-06-30 | 2026-06-30 |  | 2025-07-01 | 2025-09-30 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 8Sept25-Move to November 10Nov25-moved to December 9Feb26-Delayed due to SME availability 09Mar26-At Risk - may not actually be an OFS Role. TBD if project should proceed or be cancelled - pending business decision 19Mar26-moved to May due to business de-prioritization |  | 261d |  |  | TRUE |  |  |  | No | 2025-07-01 | 2026-06-30 | 2025-06-06 07:24 | jennifer.b.wright@ge.com
AP-0365-3 | Finalize Installation Site Manager course |  | AP-0569 | Finalize Installation Site Manager courseAP-0569 | AP-0365 | AP-0365 | 1 | 3 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Work with PLLs to finalise the content | Not Started |  | Delayed | 2026-01-01 | 2026-06-30 | 2026-04-30 |  | 2025-10-01 | 2025-12-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25- Delayed to January to accommodate new training development rigor 23Jan26-Moved to Feb 9Feb26-Delayed due to SME availability for previous task 19Mar26-moved to June due to business de-prioritization |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-06-06 07:24 | jennifer.b.wright@ge.com
AP-0365-4 | Ensure Installation Site Manager competencies are reflected in Kahuna |  | AP-0726 | Ensure Installation Site Manager competencies are reflected in KahunaAP-0726 | AP-0365 | AP-0365 | 1 | 4 | 0 | 1 | ankita.gupta@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Programs | Work with Kelly on updating Kahuna | Not Started |  | Delayed | 2026-01-01 | 2026-06-30 | 2026-03-31 |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to accommodate new training development rigor. Linked to overall TDI Competency Project 09Mar26-At Risk - may not actually be an OFS Role. TBD business decision 19Mar26-moved to June due to business de-prioritization |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-12-11 09:50 | jennifer.b.wright@ge.com
AP-0365-5 | Load Installation Site Manager course into our relevant systems |  | AP-0728 | Load Installation Site Manager course into our relevant systemsAP-0728 | AP-0365 | AP-0365 | 1 | 5 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | MM & Xyleme | Not Started |  | Delayed | 2026-01-01 | 2026-06-30 | 2026-04-30 |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to acccommodate new training development rigor. Work with Lee & Team to determine timeline for loading materials into Xyleme 9Feb26-Delayed due to SME availability for previous task 19Mar26-moved to June due to business de-prioritization |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-12-11 09:50 | jennifer.b.wright@ge.com
AP-0365-6 | First Installation Site Manager Pilot session in summer |  | AP-0727 | First Installation Site Manager Pilot session in summerAP-0727 | AP-0365 | AP-0365 | 1 | 6 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Work with PLLs to identify/qualify Instructors & update Kahuna accordingly | Not Started |  |  | 2026-06-01 | 2026-07-31 |  |  | 2026-01-01 |  | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to acccommodate new training development rigor. Timeline to be linked to blueprint'26 |  | 45d |  | TRUE |  | TRUE |  |  | No | 2026-06-01 | 2026-07-31 | 2025-12-11 09:50 | jennifer.b.wright@ge.com
AP-0366 | O&M WBT Redesign |  | AP-0366 | O&M WBT RedesignAP-0366 | #INVALID COLUMN VALUE | Top | 0 | 65 | 0 | 0 | julieta.ponceh@gevernova.com | SMEs | michele.alcantar@gevernova.com | Programs | Review and update O&M Maintenance WBTs (9) to support new regional support team function, as needed | Not Started |  | Delayed | 2025-10-01 | 2026-12-31 | 2026-03-31 |  | 2025-10-01 | 2025-12-31 |  |  |  |  | Other |  | 10Oct25-Shifted Finish date due to maternity leave. 12Mar26-Currently updating material and nominations for: “O&M Maintenance Playbook - Maintenance Program Training” and; (Scheduled in May, 2026) “O&M Maintenance Playbook – Predictive Maintenance Training” (Scheduled in Nov, 2026). Moved to December, 2026. |  | 327d | [6 empty] | No | 2025-10-01 | 2026-12-31 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0367 | O&M Finance Program for Plant Managers |  | AP-0367 | O&M Finance Program for Plant ManagersAP-0367 | #INVALID COLUMN VALUE | Top | 0 | 66 | 0 | 0 | julieta.ponceh@gevernova.com | SMEs | michele.alcantar@gevernova.com | Content Development | Design the finance training to support PM development of contract and finance acumen. | Complete |  | On Track | 2025-08-01 | 2026-04-30 | 2026-03-31 |  | 2025-04-01 | 2025-06-27 |  |  |  |  | Other |  | 1May25 - Shifted start & finish dates based on onboarding of new O&M Program Manager 10Oct25-Shifted Finish date due to maternity leave. 26Mar26-Moved to April since Julieta is out today | https://gevernova.ent.box.com/file/2175079225471 | 195d | [6 empty] | No | 2025-08-01 | 2026-04-30 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0368 | Enhance existing TIM role |  | AP-0368 | Enhance existing TIM roleAP-0368 | #INVALID COLUMN VALUE | Top | 0 | 67 | 1 | 0 | ankita.gupta@gevernova.com | SMEs | michele.alcantar@gevernova.com | Programs | Create/add leadership components, to build into Installation Site Lead role -Consolidate all site lead roles (e.g., Site Lead, TIM, CCPP Site Manager) into one role -Document the technical, leadership and administrative requirements required of successful Installation Site Leads. | In Progress |  |  | 2025-06-01 | 2026-08-31 |  |  | 2025-03-01 | 2025-06-30 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 05June25-pushed back finish date to Sept due to priorities. Also revised AP# to be standalone item, not child of AP-214 | n/a-parent row | 327d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2026-08-31 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0368-1 | Define Enhancements for TIM role |  | AP-0563 | Define Enhancements for TIM roleAP-0563 | AP-0368 | AP-0368 | 1 | 1 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Define what tops/content is needed, what needs to be modified in the existing TIM program | Complete |  | On Track | 2025-06-01 | 2025-06-30 |  |  | 2025-06-01 | 2025-06-30 | Delivery Internal Ops Programs & Competency | FE | [5 empty] | https://gevernova.ent.box.com/file/1904726559757 | 22d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-06-30 | 2025-06-06 07:23 | jennifer.b.wright@ge.com
AP-0368-2 | Develop Enhancements for TIM role |  | AP-0566 | Develop Enhancements for TIM roleAP-0566 | AP-0368 | AP-0368 | 1 | 2 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Develop List of relevant Competencies & identify which can be delivered via training vs. OJT/other Develop course content / storyboard (not formatting) | Complete | TRUE | On Track | 2025-07-01 | 2026-01-30 | 2025-12-31 |  | 2025-07-01 | 2025-09-30 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 8Sept25-Move to November 11Dec25-Moved to Dec. No report out required. |  | 154d | [6 empty] | No | 2025-07-01 | 2026-01-30 | 2025-06-06 07:23 | jennifer.b.wright@ge.com
AP-0368-3 | Finalize Enhancements for TIM role |  | AP-0565 | Finalize Enhancements for TIM roleAP-0565 | AP-0368 | AP-0368 | 1 | 3 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Work with PLLs to finalise the content | Complete |  | On Track | 2026-01-01 | 2026-02-27 |  |  | 2025-10-01 | 2025-12-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Moved to Feb to accommodate new training development rigor | https://gevernova.ent.box.com/file/2147403206220 | 42d | [6 empty] | No | 2026-01-01 | 2026-02-27 | 2025-06-06 07:23 | jennifer.b.wright@ge.com
AP-0368-4 | Ensure TIM competencies are reflected in Kahuna |  | AP-0725 | Ensure TIM competencies are reflected in KahunaAP-0725 | AP-0368 | AP-0368 | 1 | 4 | 0 | 1 | ankita.gupta@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Programs | Work with Kelly on updating Kahuna | Cancelled |  |  | 2026-01-01 | 2026-06-30 | 2026-03-31 |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to accommodate new training development rigor. Linked to overall TDI Competency Project 09Mar26-To be delayed. Ankita to work with Kelly to determine new date 19Mar26-Moved to June due to other ongoing Competency work. 28Apr26-Cancelled since this will be addressed by GT Mechanical Competencies as part of AP-214 |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-12-11 09:32 | jennifer.b.wright@ge.com
AP-0368-5 | Load/Update TIM course into our relevant systems |  | AP-0723 | Load/Update TIM course into our relevant systemsAP-0723 | AP-0368 | AP-0368 | 1 | 5 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Outline in MM, Schedule in UDC, Materials in Xyleme, Instructors qualified in Kahuna | Complete | TRUE | On Track | 2026-01-01 | 2026-04-30 | 2026-03-31 |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to acccommodate new training development rigor. Work with Lee & Team to determine timeline for loading materials into Xyleme 25Mar26-Moved to April to allow time to wrap up remaining system loads (Xyleme & Kahuna) |  | 86d | [6 empty] | No | 2026-01-01 | 2026-04-30 | 2025-12-11 09:32 | jennifer.b.wright@ge.com
AP-0368-6 | First TIM Pilot session in summer |  | AP-0724 | First TIM Pilot session in summerAP-0724 | AP-0368 | AP-0368 | 1 | 6 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Deliver training & Update materials as needed due to feedback | Not Started |  |  | 2026-01-01 | 2026-08-31 |  |  | 2026-01-01 |  | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to accommodate new training development rigor. Timeline to be linked to blueprint'26. Technical Installation Manager Level 2 26-1 scheduled for 27 Jul'26 - 19 Aug 26 |  | 173d | [6 empty] | No | 2026-01-01 | 2026-08-31 | 2025-12-11 09:32 | jennifer.b.wright@ge.com
AP-0369 | Competency Translations |  | AP-0369 | Competency TranslationsAP-0369 | #INVALID COLUMN VALUE | Top | 0 | 68 | 1 | 0 | carlo.fabregas@gevernova.com | Kelly Kirby, Siaw Wei Tan | michele.alcantar@gevernova.com | Competencies | Translate Kahuna Competencies: Needed Asian languages | Complete |  | On Track | 2024-12-01 | 2025-09-30 |  |  | 2024-12-01 | 2025-02-28 | [6 empty] | 30Jan-Move to end of march due to other priorities, will asses target finish based on how first language progresses Initial translation targeting GT TM I-IV + SUP I/II - starting with the most used 3-4 languages 10Mar25-split into 2 items, templates ready by end of March, upload into Kahuna TBD | https://gevernova.ent.box.com/file/1996816868485 | 218d | [6 empty] | No | 2024-12-01 | 2025-09-30 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0369-1 | Finalize GT Mechanical Competency Translation Templates |  | AP-0472 | Finalize GT Mechanical Competency Translation TemplatesAP-0472 | AP-0369 | AP-0369 | 1 | 1 | 0 | 1 | carlo.fabregas@gevernova.com | Kelly Kirby, Siaw Wei Tan | michele.alcantar@gevernova.com | Competencies | Finalize templates for core languages | Complete |  |  | 2024-12-01 | 2025-04-30 |  |  | 2024-12-01 | 2025-03-31 | Internal Programs & Competency | Craft EHS FE RM |  |  |  |  | 26Mar25-Moved to April closure to accommodate more time for data validation. 24Apr25-Reduced scope to GT Mechanical & added new rows for other roles | https://gevernova.box.com/s/ay66bzw0wm5cf0j25c8qsjajhc57bweh | 109d | [6 empty] | No | 2024-12-01 | 2025-04-30 | 2025-03-10 09:44 | jennifer.b.wright@ge.com
AP-0369-2 | Load GT Mechanical Competency Translation Templates into Kahuna |  | AP-0473 | Load GT Mechanical Competency Translation Templates into KahunaAP-0473 | AP-0369 | AP-0369 | 1 | 2 | 0 | 1 | carlo.fabregas@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE |  | 2025-05-01 | 2025-05-30 |  |  | 2025-05-01 | 2025-05-30 | Internal Programs & Competency | Craft EHS FE RM |  |  |  |  | 10Mar25-need to get timeline from Kahuna team 12May25-from Kelly - encountering issues with duplicates/data cleanup. More time consuming than expected | Report out at parent task level when all remainder complete | 22d | 221 | [5 empty] | No | 2025-05-01 | 2025-05-30 | 2025-03-10 09:44 | jennifer.b.wright@ge.com
AP-0369-3 | Translate Instrumentation and controls competency map & Load into Kahuna |  | AP-0541 | Translate Instrumentation and controls competency map & Load into KahunaAP-0541 | AP-0369 | AP-0369 | 1 | 3 | 0 | 1 | carlo.fabregas@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE |  | 2025-05-01 | 2025-08-29 |  |  | 2025-05-01 | 2025-06-30 | Internal Programs & Competency | Craft EHS FE RM |  |  |  |  | 9June25 - May get delayed due to changes to translation template process. To be confirmed by June 20. 20June25 - Moving to August due to delays in securing the translation templates | Report out at parent task level when all remainder complete | 87d | [6 empty] | No | 2025-05-01 | 2025-08-29 | 2025-04-24 08:35 | jennifer.b.wright@ge.com
AP-0369-4 | Translate EHS Professionals competency map & Load into Kahuna |  | AP-0539 | Translate EHS Professionals competency map & Load into KahunaAP-0539 | AP-0369 | AP-0369 | 1 | 4 | 0 | 1 | carlo.fabregas@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE | On Track | 2025-05-01 | 2025-09-30 |  |  | 2025-05-01 | 2025-07-31 | Internal Programs & Competency | Craft EHS FE RM |  |  |  |  | 14Jul25-Move to August 8Sept25-Timing switched with AP-0369-5, moved EHS to Sept and finished Electrical in Aug | Report out at parent task level when all remainder complete | 109d | [6 empty] | No | 2025-05-01 | 2025-09-30 | 2025-04-24 08:35 | jennifer.b.wright@ge.com
AP-0369-5 | Translate Electrical competency map & Load into Kahuna |  | AP-0538 | Translate Electrical competency map & Load into KahunaAP-0538 | AP-0369 | AP-0369 | 1 | 5 | 0 | 1 | carlo.fabregas@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE |  | 2025-05-01 | 2025-08-29 |  |  | 2025-05-01 | 2025-09-30 | Internal Programs & Competency | Craft EHS FE RM | [5 empty] | Report out at parent task level when all remainder complete | 87d | [6 empty] | No | 2025-05-01 | 2025-08-29 | 2025-04-24 08:35 | jennifer.b.wright@ge.com
AP-0369-6 | Translate TDI competency map & Load into Kahuna |  | AP-0540 | Translate TDI competency map & Load into KahunaAP-0540 | AP-0369 | AP-0369 | 1 | 6 | 0 | 1 | carlo.fabregas@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Cancelled | TRUE |  | 2025-05-01 | 2025-09-30 |  |  | 2025-05-01 | 2025-11-28 | Internal Programs & Competency | Craft EHS FE RM |  |  |  |  | 8Sept25-Cancelled - only FEs for TDI, don't need to translate their maps | Report out at parent task level when all remainder complete | 109d | [6 empty] | No | 2025-05-01 | 2025-09-30 | 2025-04-24 08:35 | jennifer.b.wright@ge.com
AP-0370 | Enhance existing ELT programs to incorporate TDI topics |  | AP-0370 | Enhance existing ELT programs to incorporate TDI topicsAP-0370 | #INVALID COLUMN VALUE | Top | 0 | 69 | 1 | 0 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Add-on module to the ELT program for NU specific hires | In Progress |  | Delayed | 2025-06-01 | 2026-09-30 | 2026-03-31 |  | 2025-02-01 | 2025-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 21Mar25-purshed back finish date 05June25-pushed back finish date to Sept due to priorities. Also revised AP# to be standalone item, not child of AP-214 | n/a-parent row | 349d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2026-09-30 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0370-1 | Define TDI Enhancements for ELT |  | AP-0564 | Define TDI Enhancements for ELTAP-0564 | AP-0370 | AP-0370 | 1 | 1 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Develop add on module to the existing GT ELT program | Complete |  | On Track | 2025-06-01 | 2025-06-30 |  |  | 2025-06-01 | 2025-06-30 | Delivery Internal Ops Programs & Competency | FE | [5 empty] | https://gevernova.ent.box.com/file/1904727842370 | 22d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-06-30 | 2025-06-06 07:23 | jennifer.b.wright@ge.com
AP-0370-2 | Develop TDI Enhancements for ELT |  | AP-0562 | Develop TDI Enhancements for ELTAP-0562 | AP-0370 | AP-0370 | 1 | 2 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Develop List of relevant Competencies & identify which can be delivered via training vs. OJT/other Develop course content / storyboard (not formatting) | In Progress | TRUE | Delayed | 2025-07-01 | 2026-06-30 | 2026-04-30 |  | 2025-07-01 | 2025-09-30 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 8Sept25-Move to November 10Nov25-Moved to December 05Dec25-Moved to January 23Jan26-Moved to Feb 9Feb26-Delayed due to SME availability 09Mar26-Delayed again due to SME availability. Escalated to Cal & Mac Todd. 06Apr26-Moved to June, but need to ensure SME availability. NOTE - delivery of summer ELT with TDI enhancements is currently at risk. Pending SME availability confirmation from Mac Todd |  | 261d | 228 |  | TRUE |  |  |  | No | 2025-07-01 | 2026-06-30 | 2025-06-06 07:23 | jennifer.b.wright@ge.com
AP-0370-3 | Finalize TDI Enhancements for ELT |  | AP-0561 | Finalize TDI Enhancements for ELTAP-0561 | AP-0370 | AP-0370 | 1 | 3 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Work with PLLs to finalise the content | Not Started |  | Delayed | 2026-07-01 | 2026-07-29 | 2026-05-29 |  | 2025-10-01 | 2025-12-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Moved to February to accommodate new trng development rigor 9Feb26-Delayed due to SME availability for previous task 9Mar26-Delayed due to SME availability for previous task 06Apr26-Delayed due to SME availability for previous task |  | 21d | 229 |  |  | TRUE |  |  | No | 2026-07-01 | 2026-07-29 | 2025-06-06 07:23 | jennifer.b.wright@ge.com
AP-0370-4 | Ensure TDI competencies are reflected in Kahuna |  | AP-0720 | Ensure TDI competencies are reflected in KahunaAP-0720 | AP-0370 | AP-0370 | 1 | 4 | 0 | 1 | ankita.gupta@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Programs | Work with Kelly on updating Kahuna | Cancelled |  |  | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to accommodate new training development rigor. Linked to overall TDI Competency Project 09Mar26-cancelled. Duplicate of AP-214 |  | 64d | [6 empty] | No | 2026-01-01 | 2026-03-31 | 2025-12-11 09:16 | jennifer.b.wright@ge.com
AP-0370-5 | Load ELT with TDI course into our relevant systems |  | AP-0721 | Load ELT with TDI course into our relevant systemsAP-0721 | AP-0370 | AP-0370 | 1 | 5 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | MM & Xyleme | Not Started | TRUE | Delayed | 2026-07-01 | 2026-07-30 | 2026-06-30 |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to acccommodate new training development rigor. Work with Lee & Team to determine timeline for loading materials into Xyleme 9Feb26-Delayed due to SME availability for previous task 9Mar26-Delayed due to SME availability for previous task 06Apr26-Delayed due to SME availability for previous task |  | 22d | 229 |  |  | TRUE |  |  | No | 2026-07-01 | 2026-07-30 | 2025-12-11 09:16 | jennifer.b.wright@ge.com
AP-0370-6 | First ELT with TDI Pilot session in summer |  | AP-0722 | First ELT with TDI Pilot session in summerAP-0722 | AP-0370 | AP-0370 | 1 | 6 | 0 | 1 | ankita.gupta@gevernova.com | PLLs, SME Instructors | michele.alcantar@gevernova.com | Programs | Work with PLLs to identify/qualify Instructors & update Kahuna accordingly | Not Started |  |  | 2026-01-01 | 2026-09-30 |  |  | 2026-01-01 |  | Delivery Internal Ops Programs & Competency | FE |  |  | Other |  | 11Dec25-Added to acccommodate new training development rigor. Timeline to be linked to blueprint'26 |  | 195d | [6 empty] | No | 2026-01-01 | 2026-09-30 | 2025-12-11 09:16 | jennifer.b.wright@ge.com
AP-0373 | Online Presence |  | AP-0373 | Online PresenceAP-0373 | #INVALID COLUMN VALUE | Top | 0 | 70 | 0 | 0 | ankita.gupta@gevernova.com | Program Manager | michele.alcantar@gevernova.com | Programs | Design online resource for OFS Programs (Craft, TFA, Aero, etc.) to help guide our field employees in how best to (or not to) represent themselves and the company on social media | Not Started |  | Delayed | 2026-04-01 | 2026-06-29 | 2026-03-31 |  | 2025-07-01 | 2025-09-30 |  |  |  |  | Other |  | 19Jun25-Shifted due to bandwidth challenge 9Feb26-Shifted later due to other priorities |  | 64d |  |  | TRUE |  |  |  | No | 2026-04-01 | 2026-06-29 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0374 | O&M Instructor Proficiency |  | AP-0374 | O&M Instructor ProficiencyAP-0374 | #INVALID COLUMN VALUE | Top | 0 | 71 | 0 | 0 | julieta.ponceh@gevernova.com | Luca Martino, Tamara Biediger | michele.alcantar@gevernova.com | Programs | Leverage existing Train-the-Trainer Program for O&M Key Staff Training presenters - pull known O&M presenters into Borrowed Instructor Program | Complete |  | On Track | 2025-07-01 | 2026-04-30 | 2026-03-31 |  | 2025-01-01 | 2025-03-31 |  |  |  |  | Other |  | 26Feb25 - shifted to May close to accommodate onboarding new O&M Program Manager 1May25 - Shifted start & finish dates based on onboarding of new O&M Program Manager 10Oct25-Shifted Finish date due to maternity leave. 26Mar26-Moved to April since Julieta is out today | https://gevernova.ent.box.com/file/2175074766270 | 218d | [6 empty] | No | 2025-07-01 | 2026-04-30 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0376 | O&M Training Enhancements |  | AP-0376 | O&M Training EnhancementsAP-0376 | #INVALID COLUMN VALUE | Top | 0 | 72 | 0 | 0 | julieta.ponceh@gevernova.com | SMEs | michele.alcantar@gevernova.com | Programs | Refresh Key Staff Training to ensure programs encompass experiential learning techniques - leverage training centers (not sites) | Complete |  | On Track | 2025-07-01 | 2025-10-31 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 26Feb25 - shifted to May close to accommodate onboarding new O&M Program Manager 1May25 - Shifted start & finish dates based on onboarding of new O&M Program Manager |  | 89d | [6 empty] | No | 2025-07-01 | 2025-10-31 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-0377 | Gas Turbine Alignment Training with FARO |  | AP-0377 | Gas Turbine Alignment Training with FAROAP-0377 | #INVALID COLUMN VALUE | Top | 0 | 73 | 0 | 0 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Request is for Gas Turbine casing alignment training using Faro laser technology, this is the same technology used for Steam Turbine laser alighment. This activity for Gas Turbines is increasing. The strategy discussed would be to have one or of the SME's go to the HLC (with guidance/facilitation by one of the OFS Trainng team instructors). Dan Hogan is cecking into the timing of the SME's availability in 2025. There is projected interest this from other Region's ouside NAM due to current situations where NAM qualified individuals are required to travel due to no qualified resources in the Region. | Complete |  | On Track | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-04-30 | Delivery Internal | Craft |  |  |  |  | 21Apr25-Moved to August to develop during summer when SME is available 11Aug25-Training is ready & scheduled, need to load into MM. | https://gevernova.ent.box.com/file/1973606200765 | 173d | [6 empty] | Yes | 2025-01-01 | 2025-08-29 | 2024-12-03 09:08 | jennifer.b.wright@ge.com
AP-0378 | GT11N Familiarization Class |  | AP-0378 | GT11N Familiarization ClassAP-0378 | #INVALID COLUMN VALUE | Top | 0 | 74 | 0 | 0 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Looking to develop GT 11 Familiarization class...same as GT 24/26 and 13 classes that currently exist. | Complete |  | On Track | 2025-02-01 | 2025-08-29 |  |  | 2025-02-01 | 2025-04-18 | Delivery Internal | Craft |  |  |  |  | 21Apr25-Moved to August to develop during summer when ROS SMEs are available | https://gevernova.ent.box.com/file/1973591375346 | 151d | [6 empty] | Yes | 2025-02-01 | 2025-08-29 | 2024-12-03 09:27 | jennifer.b.wright@ge.com
AP-0379 | Review TM I-IV Competencies |  | AP-0379 | Review TM I-IV CompetenciesAP-0379 | #INVALID COLUMN VALUE | Top | 0 | 75 | 1 | 0 | Tamara Biediger | erica.peredo@gevernova.com, Kelly Kirby, Luca Martino, Marcela Bohorquez | michele.alcantar@gevernova.com | Competencies | Inital scope is to review competencies in TM I-IV and re-level so that there is more differentiation between levels 2-to-3 and 3-to-4. Modifying or re-leveling will impact existing Craft employees competency records/compliance rates and will require additional steps to try to minimize user impacts. | Not Started |  |  | 2026-01-01 | 2026-08-31 |  |  | 2025-02-01 | 2025-05-30 |  |  |  |  | Intake Review | David Hopper | From Intake # 13362241948 4/2/25 Update: Call with MB, LM, KK, DR to review request prioritization. Agreed that this would move to 4Q in order to accommodate other priorities. Brenda Roman Valle is Primary focal point for SMEs. She attended intake call for David Hopper. I recommend that the SME list be updated to include one SME per region for global input. Need to review with Marcela/Leo on availability of SMEs. |  | 173d | [6 empty] | No | 2026-01-01 | 2026-08-31 | 2024-12-03 09:30 | jennifer.b.wright@ge.com
AP-0379-1 | Develop TM I-IV Competency Maps |  | AP-0665 | Develop TM I-IV Competency MapsAP-0665 | AP-0379 | AP-0379 | 1 | 1 | 0 | 1 | Tamara Biediger | erica.peredo@gevernova.com, Marcela Bohorquez | michele.alcantar@gevernova.com | Competencies | Steps 1-5 in Competency Map Checklist | Not Started | TRUE |  | 2026-01-01 | 2026-06-30 | [12 empty] | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-11-06 13:09 | jennifer.b.wright@ge.com
AP-0379-2 | Import & Configure System for TM I-IV Maps |  | AP-0663 | Import & Configure System for TM I-IV MapsAP-0663 | AP-0379 | AP-0379 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE |  | 2026-07-01 | 2026-07-31 | [10 empty] | Dates dependent on AP-0379-1; Will fill in once Luca adds dates |  | 23d | 240 |  |  | TRUE |  |  | No | 2026-07-01 | 2026-07-31 | 2025-11-06 13:09 | jennifer.b.wright@ge.com
AP-0379-3 | Baseline & Load TM I-IV User Assignments |  | AP-0664 | Baseline & Load TM I-IV User AssignmentsAP-0664 | AP-0379 | AP-0379 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE |  | 2026-08-03 | 2026-08-31 | [10 empty] | Dates dependent on AP-0379-1; Will fill in once Luca adds dates |  | 21d | 241 | [5 empty] | No | 2026-08-03 | 2026-08-31 | 2025-11-06 13:09 | jennifer.b.wright@ge.com
AP-0380 | Review Supervisor I & II Competencies |  | AP-0380 | Review Supervisor I & II CompetenciesAP-0380 | #INVALID COLUMN VALUE | Top | 0 | 76 | 1 | 0 | Tamara Biediger | erica.peredo@gevernova.com, Kelly Kirby, marcela.bohorquez1@gevernova.com | michele.alcantar@gevernova.com | Competencies | To complete after AP-0379. Review competencies for Supervisor I & II to ensure proper alignment & differentiation. | Not Started |  |  | 2026-09-01 | 2027-01-29 |  |  | 2025-05-01 | 2025-07-31 |  |  |  |  | Intake Review |  | From Intake # 13362241948 22Jan26-Moved to March to allow more global coordination 09Mar26-Move to start after AP-0379 is complete. Add sub tasks. 16Apr26-Changed Lead to Tam instead of Marcela |  | 109d | [6 empty] | No | 2026-09-01 | 2027-01-29 | 2024-12-03 09:31 | jennifer.b.wright@ge.com
AP-0380-1 | Develop Supervisor I & II Competency Maps |  | AP-0830 | Develop Supervisor I & II Competency MapsAP-0830 | AP-0380 | AP-0380 | 1 | 1 | 0 | 1 | Tamara Biediger | erica.peredo@gevernova.com, Kelly Kirby, marcela.bohorquez1@gevernova.com | michele.alcantar@gevernova.com | Competencies | Steps 1-5 in Competency Map Checklist | Not Started | TRUE |  | 2026-09-01 | 2026-11-30 | [12 empty] | 65d | [6 empty] | No | 2026-09-01 | 2026-11-30 | 2026-03-09 10:05 | jennifer.b.wright@gevernova.com
AP-0380-2 | Import & Configure System for Supervisor I & II Maps |  | AP-0832 | Import & Configure System for Supervisor I & II MapsAP-0832 | AP-0380 | AP-0380 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | luca.martino@gevernova.com | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE |  | 2026-12-01 | 2026-12-31 | [12 empty] | 23d | 244 | [5 empty] | No | 2026-12-01 | 2026-12-31 | 2026-03-09 10:05 | jennifer.b.wright@gevernova.com
AP-0380-3 | Baseline & Load Supervisor I & II User Assignments |  | AP-0831 | Baseline & Load Supervisor I & II User AssignmentsAP-0831 | AP-0380 | AP-0380 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | luca.martino@gevernova.com | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE |  | 2027-01-01 | 2027-01-29 | [12 empty] | 21d | 245 | [5 empty] | No | 2027-01-01 | 2027-01-29 | 2026-03-09 10:05 | jennifer.b.wright@gevernova.com
AP-0387 | Standardize Controls Classroom Equipment |  | AP-0387 | Standardize Controls Classroom EquipmentAP-0387 | #INVALID COLUMN VALUE | Top | 0 | 77 | 0 | 0 | mohammed.nizami@gevernova.com | Yegor Spencer | jim.rosen@gevernova.com | Content Quality & Improvements | Ensure that all Controls classrooms at the HLC have standard equipment setups | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-03-31 | Customer Delivery | [5 empty] | Moving to April to complete documentation and Rm 3208-09 setup | https://gevernova.ent.box.com/file/1848506410919 | 86d | [6 empty] | Yes | 2025-01-01 | 2025-04-30 | 2024-12-09 15:15 | jennifer.b.wright@ge.com
AP-0388 | Update OE MkVIe Labs |  | AP-0388 | Update OE MkVIe LabsAP-0388 | #INVALID COLUMN VALUE | Top | 0 | 78 | 1 | 0 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | Update labs in MkVIe Familiarization, Troubleshooting & Internal courses to align with standard HLC equipment | In Progress |  | Delayed | 2026-01-01 | 2026-08-31 | 2026-06-30 | TRUE | 2025-03-01 | 2025-12-31 | Customer Delivery Ops |  |  |  | NPS Review | johann.daxer@gevernova.com | 22Dec25-Labs have been updated. Plan to pilot by mid 2026 18Feb26-Added sub tasks 10Jun26-Moved final to Aug to finalize updates & implement for July/Aug sessions. |  | 173d | [6 empty] | Yes | 2026-01-01 | 2026-08-31 | 2024-12-09 15:17 | jennifer.b.wright@ge.com
AP-0388-1 | Update OE Mark VIe Familiarization & Intermediate Labs |  | AP-0797 | Update OE Mark VIe Familiarization & Intermediate LabsAP-0797 | AP-0388 | AP-0388 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | For O-CON13405, O-CON13406, O-CON13407, O-CON13408 – Revise & update Labs to remove overlap & clearly align with relevant simulators/labs. Confirm what should be printed for students (labs, drawings, etc), | Complete | TRUE | On Track | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 | Customer Delivery Ops |  |  |  | NPS Review |  |  |  | 64d | [6 empty] | Yes | 2026-01-01 | 2026-03-31 | 2026-02-18 13:01 | jennifer.b.wright@ge.com
AP-0388-2 | Run Pilot Sessions of updated OE Fam & Intermediate Labs |  | AP-0800 | Run Pilot Sessions of updated OE Fam & Intermediate LabsAP-0800 | AP-0388 | AP-0388 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE |  | 2026-05-01 | 2026-06-30 |  |  | 2026-05-01 | 2026-06-30 | Customer Delivery Ops |  |  |  | NPS Review |  |  |  | 43d |  |  | TRUE |  |  |  | Yes | 2026-05-01 | 2026-06-30 | 2026-02-18 13:09 | jennifer.b.wright@ge.com
AP-0388-3 | Incorporate feedback from OE Fam & Intermediate pilot sessions & update course outline as needed |  | AP-0801 | Incorporate feedback from OE Fam & Intermediate pilot sessions & update course outline as neededAP-0801 | AP-0388 | AP-0388 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | In Progress | TRUE |  | 2026-06-01 | 2026-08-31 | 2026-06-30 |  | 2026-06-01 | 2026-06-30 | Customer Delivery Ops |  |  |  | NPS Review |  |  |  | 66d |  | TRUE |  |  |  |  | Yes | 2026-06-01 | 2026-08-31 | 2026-02-18 13:09 | jennifer.b.wright@ge.com
AP-0388-4 | Update OE Mark VIe Advanced Labs |  | AP-0802 | Update OE Mark VIe Advanced LabsAP-0802 | AP-0388 | AP-0388 | 1 | 4 | 0 | 1 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | For O-CON23401 & O-CON33401 – Revise & update Labs to remove overlap & clearly align with relevant simulators/labs. Confirm what should be printed for students (labs, drawings, etc), | Complete | TRUE | On Track | 2026-02-01 | 2026-04-30 |  |  | 2026-02-01 | 2026-04-30 | Customer Delivery Ops |  |  |  | NPS Review |  |  |  | 65d | [6 empty] | Yes | 2026-02-01 | 2026-04-30 | 2026-02-18 13:13 | jennifer.b.wright@ge.com
AP-0388-5 | Run Pilot Sessions of updated OE Advanced Labs |  | AP-0803 | Run Pilot Sessions of updated OE Advanced LabsAP-0803 | AP-0388 | AP-0388 | 1 | 5 | 0 | 1 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE | On Track | 2026-05-01 | 2026-05-29 |  |  | 2026-05-01 | 2026-05-29 | Customer Delivery Ops |  |  |  | NPS Review |  |  |  | 21d |  |  |  |  | TRUE |  | Yes | 2026-05-01 | 2026-05-29 | 2026-02-18 13:13 | jennifer.b.wright@ge.com
AP-0388-6 | Incorporate feedback from OE Advanced pilot sessions & update course outline as needed |  | AP-0804 | Incorporate feedback from OE Advanced pilot sessions & update course outline as neededAP-0804 | AP-0388 | AP-0388 | 1 | 6 | 0 | 1 | mohammed.nizami@gevernova.com | gerardo.gonzalezdodero@gevernova.com, gopinath.kumar1@gevernova.com, rafael.venancio@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | In Progress | TRUE | On Track | 2026-05-01 | 2026-08-31 | 2026-05-31 |  | 2026-05-01 | 2026-05-29 | Customer Delivery Ops |  |  |  | NPS Review |  |  |  | 87d | [6 empty] | Yes | 2026-05-01 | 2026-08-31 | 2026-02-18 13:13 | jennifer.b.wright@ge.com
AP-0404 | Improve Workforce Competency Rate |  | AP-0404 | Improve Workforce Competency RateAP-0404 | #INVALID COLUMN VALUE | Top | 0 | 79 | 1 | 0 | david.ramey@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | Complete |  |  | 2025-01-01 | 2025-12-31 |  |  | 2025-01-01 | 2025-12-31 | [7 empty] | https://gevernova.ent.box.com/file/2096001283199 | 261d | [6 empty] | No | 2025-01-01 | 2025-12-31 | 2024-12-10 14:45 | jennifer.b.wright@ge.com
AP-0404-1 | Communicate/drive visibility/usage of Kahuna Dashboards |  | AP-0405 | Communicate/drive visibility/usage of Kahuna DashboardsAP-0405 | AP-0404 | AP-0404 | 1 | 1 | 0 | 1 | david.ramey@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies | Ensure Leadership, RMs, etc. are using the dashboards to see how their teams are doing | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-01-31 | [6 empty] | Moved from Jan to Feb completion. I am slated to present on the next RD meeting 2/5. | https://gevernova.box.com/s/rarimjppdhn7oph1xuzg3jvepffj3435 | 43d | [6 empty] | No | 2025-01-01 | 2025-02-28 | 2024-12-10 14:45 | jennifer.b.wright@ge.com
AP-0404-2 | Identify Target Areas for Competency Rate improvement |  | AP-0406 | Identify Target Areas for Competency Rate improvementAP-0406 | AP-0404 | AP-0404 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | TDMs | michele.alcantar@gevernova.com | Competencies | Analyze data to see where we should focus our efforts (low-hanging fruit, biggest impact, etc.) | Complete |  |  | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 21Mar25-purshed back finish date | https://gevernova.ent.box.com/file/1812570358806 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2024-12-10 14:45 | jennifer.b.wright@ge.com
AP-0404-3 | Develop plan for Competency Rate target improvements |  | AP-0407 | Develop plan for Competency Rate target improvementsAP-0407 | AP-0404 | AP-0404 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | TDMs | michele.alcantar@gevernova.com | Competencies | Determine what we can do to impact the focus areas above | Complete |  | On Track | 2025-04-01 | 2025-07-31 |  |  | 2025-04-01 | 2025-05-30 | [6 empty] | 28May25-pushed back to June to allow more time for review 25June25-moved to July | https://gevernova.ent.box.com/file/1940994884579 | 88d | [6 empty] | No | 2025-04-01 | 2025-07-31 | 2024-12-10 14:52 | jennifer.b.wright@ge.com
AP-0404-4 | Implement Competency Rate Improvement Plans |  | AP-0408 | Implement Competency Rate Improvement PlansAP-0408 | AP-0404 | AP-0404 | 1 | 4 | 0 | 1 | kelly.kirby@gevernova.com | TDMs | leonardo.monzo1@gevernova.com | Competencies | Detail TBD based on AP-0404-3, lead by each TDM as applicable | Complete |  | On Track | 2025-06-01 | 2025-12-31 |  |  | 2025-06-01 | 2025-12-31 | [7 empty] | https://gevernova.ent.box.com/file/2096021015166 | 154d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-12-31 | 2024-12-10 14:52 | jennifer.b.wright@ge.com
AP-0413 | Standard Onboarding/Offboarding checklist/process for OFS Trng Employees |  | AP-0413 | Standard Onboarding/Offboarding checklist/process for OFS Trng EmployeesAP-0413 | #INVALID COLUMN VALUE | Top | 0 | 80 | 1 | 0 | Jennifer Wright |  | philip.ganssmann@gevernova.com | Operational Simplification | Document/standardize all the various Tools, DLs, Systems, Comms, Meetings, etc. employees need to be added/removed from when hired and/or leaving OFS Training | Complete |  | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 24Mar25 Expanded to 2 sub actions | n/a-parent row | 108d | [6 empty] | No | 2025-01-01 | 2025-05-30 | 2024-12-12 13:52 | jennifer.b.wright@ge.com
AP-0413-1 | Assemble Standard Onboarding Actions & References |  | AP-0489 | Assemble Standard Onboarding Actions & ReferencesAP-0489 | AP-0413 | AP-0413 | 1 | 1 | 0 | 1 | Jennifer Wright |  | philip.ganssmann@gevernova.com | Operational Simplification | Assemble list of key activities, request process, info needed, etc. | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | [7 empty] | https://gevernova.ent.box.com/file/1812575632464 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2025-03-24 15:35 | jennifer.b.wright@ge.com
AP-0413-2 | Develop Workflow to Streamline Onboarding Activity Requests |  | AP-0490 | Develop Workflow to Streamline Onboarding Activity RequestsAP-0490 | AP-0413 | AP-0413 | 1 | 2 | 0 | 1 | Jennifer Wright |  | philip.ganssmann@gevernova.com | Operational Simplification | Develop workflow & feedback process to streamline requests | Complete |  | On Track | 2025-04-01 | 2025-05-30 |  |  | 2025-04-01 | 2025-05-30 | [7 empty] | https://gevernova.ent.box.com/file/1876066573852 | 44d | 261 | [5 empty] | No | 2025-04-01 | 2025-05-30 | 2025-03-24 15:35 | jennifer.b.wright@ge.com
AP-0414 | Rebuild Utilization Reports |  | AP-0414 | Rebuild Utilization ReportsAP-0414 | #INVALID COLUMN VALUE | Top | 0 | 81 | 1 | 0 | daniel.barrera1@gevernova.com | James Rosen, Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Rebuild existing Utilization reports to accommodate PMx / OTL changes -Simplify how instructor designations are changed -Remove OTL data -Simplify/Verify Assigned vs. Applied time calcs (especially for FC instructors) -Add charts for # of instructors outside target Utilization range -Adjust "monthly" calcs to be 4 week increments, not calendar months (to align with OFS approach) | Complete |  |  | 2025-01-01 | 2025-06-30 |  |  | 2025-01-01 | 2025-03-31 | Delivery Ops | [5 empty] | 21Mar25-Split into 2 parts | n/a-parent row | 129d | [6 empty] | No | 2025-01-01 | 2025-06-30 | 2024-12-12 13:55 | jennifer.b.wright@ge.com
AP-0414-1 | Validate Data sources and Applied/Assigned Time Calculations for new Utilization reports |  | AP-0487 | Validate Data sources and Applied/Assigned Time Calculations for new Utilization reportsAP-0487 | AP-0414 | AP-0414 | 1 | 1 | 0 | 1 | daniel.barrera1@gevernova.com | James Rosen, Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Determine which Data sources contain the correct PMx timecard data and add data source to include People Leader (PLL). Verify correct Activity Type/WBS combinations for assigning OOO/Applied/Assigned time categories to timecards | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | Customer Delivery Internal Ops | [6 empty] | https://gevernova.box.com/s/3cso1u9e6g78yuk9unyvc2uch8hrvk78 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2025-03-21 11:06 | jennifer.b.wright@ge.com
AP-0414-2 | Build new Utilization Reports |  | AP-0488 | Build new Utilization ReportsAP-0488 | AP-0414 | AP-0414 | 1 | 2 | 0 | 1 | daniel.barrera1@gevernova.com | James Rosen, Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Build/Rebuild new reports using data validated above | Complete |  | On Track | 2025-04-01 | 2025-06-30 |  |  | 2025-04-01 | 2025-05-30 | Customer Delivery Internal Ops | [5 empty] | 28May25-moved to June to allow additional time to resolve technical issues and fully test the reports | https://gevernova.box.com/s/ix7qrywrf2p37knf7xmq3nlxabdzdszd | 65d | 264 | [5 empty] | No | 2025-04-01 | 2025-06-30 | 2025-03-21 11:07 | jennifer.b.wright@ge.com
AP-0415 | Formalize Customer Training Laptop Request Process |  | AP-0415 | Formalize Customer Training Laptop Request ProcessAP-0415 | #INVALID COLUMN VALUE | Top | 0 | 82 | 1 | 0 | Jennifer Wright | Andrew Ruch, michael.evans@gevernova.com, Michele Alcantar, Mohammed Nizami, nelsa1.bernal@gevernova.com, Stephen Urban | philip.ganssmann@gevernova.com | Operational Simplification | Develop process for requesting use of HLC laptops for customer training (at HLC & off-site) | Complete |  | On Track | 2024-01-01 | 2025-04-30 |  |  | 2024-06-01 | 2025-02-28 | Customer Delivery Ops | [5 empty] | 2/10/25-split into 2 child lines to cover process standardization & workflow development | n/a-parent row | 348d | [6 empty] | No | 2024-01-01 | 2025-04-30 | 2024-12-16 08:30 | jennifer.b.wright@ge.com
AP-0415-1 | Standardize Process for Laptop Inventory Management & Requests |  | AP-0460 | Standardize Process for Laptop Inventory Management & RequestsAP-0460 | AP-0415 | AP-0415 | 1 | 1 | 0 | 1 | Jennifer Wright | Andrew Ruch, michael.evans@gevernova.com, Michele Alcantar, Mohammed Nizami, nelsa1.bernal@gevernova.com, Stephen Urban | philip.ganssmann@gevernova.com | Operational Simplification | Develop process for managing/tracking HLC Laptop Inventory and clear process for determining if laptops are needed and how to request them for Customer Training (at HLC & off-site) | Complete |  | On Track | 2024-01-01 | 2025-02-28 |  |  | 2024-01-01 | 2025-02-28 | Customer Delivery Ops | [5 empty] | Will close this in Feb with email process | https://gevernova.ent.box.com/file/1786229740288 | 305d | [6 empty] | No | 2024-01-01 | 2025-02-28 | 2025-02-10 10:00 | jennifer.b.wright@ge.com
AP-0415-2 | Create Workflow for Customer Training Laptop Request Process |  | AP-0459 | Create Workflow for Customer Training Laptop Request ProcessAP-0459 | AP-0415 | AP-0415 | 1 | 2 | 0 | 1 | Jennifer Wright | Andrew Ruch, michael.evans@gevernova.com, Michele Alcantar, Mohammed Nizami, Stephen Urban | philip.ganssmann@gevernova.com | Operational Simplification | Develop Workflow to track Laptop Requests (currently sent via email) | Complete |  | On Track | 2025-03-03 | 2025-04-30 |  |  | 2025-03-03 | 2025-04-30 | Customer Delivery Ops | [6 empty] | https://gevernova.ent.box.com/file/1847982983572 | 43d | 267 | [5 empty] | No | 2025-03-03 | 2025-04-30 | 2025-02-10 10:00 | jennifer.b.wright@ge.com
AP-0421 | Consolidate Training Sites |  | AP-0421 | Consolidate Training SitesAP-0421 | #INVALID COLUMN VALUE | Top | 0 | 83 | 0 | 0 | daniel.barrera1@gevernova.com | Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Decommission legacy GP Support Central Sites, Communicate new Sharepoint & decommissioned SC sites, Develop Change Management process | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-01-31 | Customer Delivery Internal Ops P&C | FE OSS RM |  |  |  |  | Extend to Feb to ensure that all remaining links are fully validated and moved to Sharepoint | https://gevernova.box.com/s/nhr4t3khwypm6q6ggbfw96edbawedgbj | 43d | [6 empty] | No | 2025-01-01 | 2025-02-28 | 2024-12-16 14:12 | jennifer.b.wright@ge.com
AP-0422 | HA Craft Training Delivered in Region |  | AP-0422 | HA Craft Training Delivered in RegionAP-0422 | #INVALID COLUMN VALUE | Top | 0 | 84 | 1 | 0 | luca.martino@gevernova.com | Harry Hanson | michele.alcantar@gevernova.com | Programs | Build capability to deliver HA training in other regions, not just at HLC | In Progress |  | On Track | 2025-01-01 | 2027-06-30 |  |  | 2025-01-01 | 2025-03-31 |  |  |  |  | Other |  | 24Apr25 - Moved this entire group to On-Hold since there is no budget to support Warsaw improvements for this year. Will re-visit for 2026 budget | https://gevernova.box.com/s/b44q6477kni12zm3l9xloayw5t12ypit | 651d | [6 empty] | No | 2025-01-01 | 2027-06-30 | 2024-12-17 09:17 | jennifer.b.wright@ge.com
AP-0422-1 | Needs Analysis for HA Craft Training in Region |  | AP-0423 | Needs Analysis for HA Craft Training in RegionAP-0423 | AP-0422 | AP-0422 | 1 | 1 | 0 | 1 | luca.martino@gevernova.com | Harry Hanson | michele.alcantar@gevernova.com | Programs | Work with region personnel to complete analysis of what resources/equipment/etc. would be needed locally, what is available, what the right target location would be, etc. Prepare cost analysis & proposal for next steps | Complete |  | On Track | 2025-01-01 | 2025-12-31 |  |  | 2025-01-01 | 2025-03-31 | Delivery Internal P&C | Craft RM |  |  |  |  | 26Mar25-Moved to April to allow further investigation of costs needed for Warsaw HA improvements 24Apr25 - Moved this entire group to On-Hold since there is no budget to support Warsaw improvements for this year. Will re-visit for 2026 budget 13Oct25-Moved to Nov to allow more time to review quote & decide on approach. 2Dec25-Moved to Dec, still pending leadership decision | https://gevernova.ent.box.com/file/1813512302006 | 261d | [6 empty] | No | 2025-01-01 | 2025-12-31 | 2024-12-17 09:26 | jennifer.b.wright@ge.com
AP-0422-2 | Acquire Equipment for HA Fixture at KLC |  | AP-0424 | Acquire Equipment for HA Fixture at KLCAP-0424 | AP-0422 | AP-0422 | 1 | 2 | 0 | 1 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Programs | Purchase and deliver all required equipment to KLC | Not Started |  |  | 2026-01-01 | 2026-09-30 |  |  | 2025-04-01 | 2026-09-30 | Delivery Internal P&C | Craft RM |  |  | Other |  | Target finish date TBD based on output from AP-0422-1 24Apr25 - Moved this entire group to On-Hold since there is no budget to support Warsaw improvements for this year. Will re-visit for 2026 budget |  | 195d | 271 | [5 empty] | No | 2026-01-01 | 2026-09-30 | 2024-12-17 09:26 | jennifer.b.wright@ge.com
AP-0422-3 | Complete Pilot Delivery of HA Training at KLC |  | AP-0746 | Complete Pilot Delivery of HA Training at KLCAP-0746 | AP-0422 | AP-0422 | 1 | 3 | 0 | 1 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Programs | Prepare HA Fixture & deliver pilot session. Review feedback and adjust accordingly | Not Started |  |  | 2026-10-01 | 2027-06-30 |  |  | 2026-10-01 | 2027-06-30 | Delivery Internal P&C | Craft RM |  |  | Other |  | 8Jan26-Added per output from AP-0422-1 |  | 195d | [6 empty] | No | 2026-10-01 | 2027-06-30 | 2026-01-08 09:12 | jennifer.b.wright@ge.com
AP-0434 | Roll-Out Respectful Workplace Training |  | AP-0434 | Roll-Out Respectful Workplace TrainingAP-0434 | #INVALID COLUMN VALUE | Top | 0 | 85 | 0 | 0 | kelly.kirby@gevernova.com | Leonardo Monzo | leonardo.monzo1@gevernova.com | Content Development | Complete Train-the-Trainer for Respectful Workplace training & Complete Pilot Delivery | Complete |  | On Track | 2025-01-01 | 2025-02-28 |  |  | 2025-01-01 | 2025-02-28 | Internal Programs & Competency | Craft FE |  |  |  |  | Next steps from 2024 AP-217; Met with Fernando to review/update scenarios. Provided final slide to Fernando to add to HR Box folder for presenters. | https://gevernova.ent.box.com/file/1729729554704 | 43d | [6 empty] | No | 2025-01-01 | 2025-02-28 | 2024-12-19 13:10 | jennifer.b.wright@ge.com
AP-0439 | Lifting Kahuna roles and training course |  | AP-0439 | Lifting Kahuna roles and training courseAP-0439 | #INVALID COLUMN VALUE | Top | 0 | 86 | 1 | 0 | luca.martino@gevernova.com | Brenda Roman Valle, Kelly Kirby | michele.alcantar@gevernova.com | Competencies | According to the OFS Lifting Workshop docs, create Kahuna roles and associated competencies, and provide a training path to qualify EEs in the use of the new procedure | Complete |  | On Track | 2025-02-01 | 2026-06-30 |  |  | 2025-02-01 | 2025-10-31 | Internal Programs & Competency | Craft EHS FE RM |  |  | Other |  | 13Oct25-To split into sub tasks for training paths & competencies 26May26-Moved to June so Luca can be available at monthly review |  | 368d |  |  | TRUE |  |  |  | No | 2025-02-01 | 2026-06-30 | 2025-01-09 09:54 | luca.martino@ge.com
AP-0439-1 | Develop Lifting Roles Training Paths |  | AP-0647 | Develop Lifting Roles Training PathsAP-0647 | AP-0439 | AP-0439 | 1 | 1 | 0 | 1 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | Complete |  | On Track | 2025-02-01 | 2025-10-31 |  |  | 2025-02-01 | 2025-10-31 | Internal Programs & Competency | Craft EHS FE RM | [5 empty] | https://gevernova.ent.box.com/file/2030652155145 | 196d | [6 empty] | No | 2025-02-01 | 2025-10-31 | 2025-10-22 10:28 | jennifer.b.wright@ge.com
AP-0439-2 | Develop Lifting Roles & Competency Maps |  | AP-0645 | Develop Lifting Roles & Competency MapsAP-0645 | AP-0439 | AP-0439 | 1 | 2 | 0 | 1 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | Steps 1-5 in Competency Map Checklist | Complete | TRUE | On Track | 2025-11-01 | 2026-02-27 |  |  | 2025-11-01 | 2025-12-31 | Internal Programs & Competency | Craft EHS FE RM |  |  | Other |  | 15Dec25-Move to Feb |  | 86d | [6 empty] | No | 2025-11-01 | 2026-02-27 | 2025-10-22 10:28 | jennifer.b.wright@ge.com
AP-0439-3 | Update Lifting Competency Maps |  | AP-0646 | Update Lifting Competency MapsAP-0646 | AP-0439 | AP-0439 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Complete | TRUE | At Risk | 2026-03-02 | 2026-04-30 | 2026-03-31 |  | 2026-01-01 | 2026-04-30 | Internal Programs & Competency | Craft EHS FE RM |  |  | Other |  | 15Dec25-Moved to March due to 0439-2 delay 08Apr26-Delayed to April after confirmation of scope |  | 44d | 277 | [5 empty] | No | 2026-03-02 | 2026-04-30 | 2025-10-22 10:28 | jennifer.b.wright@ge.com
AP-0439-4 | Baseline & Load Lifting Roles User Assignments |  | AP-0675 | Baseline & Load Lifting Roles User AssignmentsAP-0675 | AP-0439 | AP-0439 | 1 | 4 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Cancelled | TRUE |  | 2026-05-01 | 2026-06-30 | 2026-04-30 |  |  |  | Internal Programs & Competency | Craft EHS FE RM |  |  | Other |  | 15Dec25-Moved to March due to 0439-2 delay 08Apr26-Moved to May based on delay for previous item 11May26-Cancelled because No role changes needed. |  | 43d | 278 |  | TRUE |  |  |  | No | 2026-05-01 | 2026-06-30 | 2025-11-06 13:39 | jennifer.b.wright@ge.com
AP-0446 | Digital Valve Positioners (DVP) Training |  | AP-0446 | Digital Valve Positioners (DVP) TrainingAP-0446 | #INVALID COLUMN VALUE | Top | 0 | 87 | 0 | 0 | mohammed.nizami@gevernova.com | Muhammad Ahmed Ijaz | jim.rosen@gevernova.com | Content Development | We will develop this new lab to cover initial setup and download to Woodward DVPs using vendor software for hardware available at HLC as part of ELT lab rotations. | Complete |  | On Track | 2025-04-01 | 2025-10-31 |  |  | 2025-04-01 | 2025-09-30 | Delivery Internal | FE |  |  |  | douglas.dunn@gevernova.com | Added from 14Jan25 Intake Review meeting. Request #13309018685 24Sept25 -pushed to Oct close to finalize pilot feedback | https://gevernova.ent.box.com/folder/348388919102 | 154d | [6 empty] | Yes | 2025-04-01 | 2025-10-31 | 2025-01-09 09:57 | luca.martino@ge.com
AP-0447 | Customer Training Webinars |  | AP-0447 | Customer Training WebinarsAP-0447 | #INVALID COLUMN VALUE | Top | 0 | 88 | 0 | 0 | johann.daxer@gevernova.com |  | johann.daxer@gevernova.com | Competitiveness & Growth | Promote transactional Customer Training through quarterly webinars | Cancelled |  |  | 2025-01-01 | 2025-02-26 |  |  | 2025-01-01 | 2025-02-26 | [6 empty] | 26Feb25-Per discussions with the specialists, Customer Webinars are not the right approach. Whenever the team determines what the approach should be we can add a new AP Item as needed. |  | 41d | [6 empty] | No | 2025-01-01 | 2025-02-26 | 2025-01-21 09:32 | jennifer.b.wright@ge.com
AP-0452 | Bucket tech training revision - Spacer 0 |  | AP-0452 | Bucket tech training revision - Spacer 0AP-0452 | #INVALID COLUMN VALUE | Top | 0 | 89 | 0 | 0 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Include TIL 2445 in our HA S1B bucket training by discussing and reviewing this TIL. The HA Turbine Spool, we currently have at the HLC, did not include the zero spacer when obtained from Greenville so we cannot do any hands on training on it. If the arriving 7HA.03 Rotor Turbine section has the Zero spacer attached to the rotor then a Hands on inspection and show and tell can be also included in the lab portion of the HA S1B training if the turbine wheels are accessible. | Complete |  | On Track | 2025-01-28 | 2025-02-28 |  |  | 2025-01-28 | 2025-02-28 | Delivery Internal | Craft |  |  |  | Teresa Weiser | Added from 28Jan25 Intake Review meeting. Request #13376758636 | https://gevernova.ent.box.com/file/1787491748808 | 24d | [6 empty] | Yes | 2025-01-28 | 2025-02-28 | 2025-01-28 09:49 | jennifer.b.wright@ge.com
AP-0454 | Scheduling Tool Phase 4 Implementation |  | AP-0454 | Scheduling Tool Phase 4 ImplementationAP-0454 | #INVALID COLUMN VALUE | Top | 0 | 90 | 1 | 0 | andrew.ruch@gevernova.com |  | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete |  |  | 2025-08-01 | 2026-11-30 | [11 empty] | https://gevernova.box.com/s/zxlylusjsdgmolqcld423dce7nqyyko6 | 347d | [6 empty] | No | 2025-08-01 | 2026-11-30 | 2025-02-07 12:26 | jennifer.b.wright@ge.com
AP-0454-1 | Load Course Catalog |  | AP-0458 | Load Course CatalogAP-0458 | AP-0454 | AP-0454 | 1 | 1 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Detailed Dates and scope TBD once the full tool UAT is complete | Complete | TRUE | On Track | 2025-08-01 | 2026-11-30 |  |  | 2025-08-01 | 2025-08-29 | Ops | [5 empty] | 11Aug25-Moved to Sept to allow time to finalize & load all data | Will be reported as roll-up to AP-0454 | 347d | [6 empty] | No | 2025-08-01 | 2026-11-30 | 2025-02-07 12:32 | jennifer.b.wright@ge.com
AP-0454-2 | Load Resource Catalogs |  | AP-0457 | Load Resource CatalogsAP-0457 | AP-0454 | AP-0454 | 1 | 2 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Detailed Dates and scope TBD once the full tool UAT is complete | Complete | TRUE | On Track | 2025-08-01 | 2026-11-30 |  |  | 2025-08-01 | 2025-08-29 | Ops | [5 empty] | 11Aug25-Moved to Sept to allow time to finalize & load all data | Will be reported as roll-up to AP-0454 | 347d | [6 empty] | No | 2025-08-01 | 2026-11-30 | 2025-02-07 12:32 | jennifer.b.wright@ge.com
AP-0454-3 | Load Schedule Templates |  | AP-0455 | Load Schedule TemplatesAP-0455 | AP-0454 | AP-0454 | 1 | 3 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Detailed Dates and scope TBD once the full tool UAT is complete | Complete | TRUE | On Track | 2025-08-01 | 2026-11-30 |  |  | 2025-08-01 | 2025-08-29 | Ops | [5 empty] | 11Aug25-Moved to Sept to allow time to finalize & load all data | Will be reported as roll-up to AP-0454 | 347d | [6 empty] | No | 2025-08-01 | 2026-11-30 | 2025-02-07 12:32 | jennifer.b.wright@ge.com
AP-0454-4 | Go Live |  | AP-0456 | Go LiveAP-0456 | AP-0454 | AP-0454 | 1 | 4 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Start loading real schedule data into system (SS, OE first, then Internal) Detailed Dates and scope TBD once the full tool UAT is complete | Complete | TRUE | On Track | 2025-08-01 | 2026-11-30 |  |  | 2025-08-01 | 2025-08-29 | Ops | [5 empty] | 27Aug25-Moved to Nov to cover full go-live of all training types 24Nov25-Moved to Dec to cover training roll-out and remaining critical releases | Will be reported as roll-up to AP-0454 | 347d | [6 empty] | No | 2025-08-01 | 2026-11-30 | 2025-02-07 12:32 | jennifer.b.wright@ge.com
AP-0461 | Add Vernova Sustainability content to Training Programs |  | AP-0461 | Add Vernova Sustainability content to Training ProgramsAP-0461 | #INVALID COLUMN VALUE | Top | 0 | 91 | 0 | 0 | kelly.kirby@gevernova.com | Leonardo Monzo | leonardo.monzo1@gevernova.com | Content Development | Craft and FE Onboarding, TM4 to Supervisor Training and FE leadership training | On Hold |  | Delayed | 2025-01-01 | 2026-03-31 |  |  | 2025-01-01 | 2025-06-30 | Internal P&C | Craft FE |  |  | Other |  | 25June25-moved to July; 14July25 - GEV corporate training initiative moved to 3Q 4Nov25-Corporate Sustainability training is finished and in the process of being uploaded to GEV University. Once there, the extended sustainability team will be piloting it in 4Q with an anticipated GEV-wide launch 1Q ’26 |  | 325d | [6 empty] | No | 2025-01-01 | 2026-03-31 | 2025-02-10 11:03 | jennifer.b.wright@ge.com
AP-0464 | Alstom Craft GT Familiarization Briefing |  | AP-0464 | Alstom Craft GT Familiarization BriefingAP-0464 | #INVALID COLUMN VALUE | Top | 0 | 92 | 1 | 0 | carlo.fabregas@gevernova.com | Harry Hanson, Lee Fielding, Pablo Schibli | leonardo.monzo1@gevernova.com | Content Development | Standard Familiarization materials to made available for pre-outage briefings - this content wouldn't be used for qualification purposes, just awareness. Content should be shared via Xyleme - not distributed freely, so we can control the content. Covers GT 24/26 & GT13 scope. Carlo to work with region SMEs to determine which content should be made available to region teams (all vs sub-set), then work with Harry & Lee to assemble relevant content and load into Xyleme. | Cancelled |  |  | 2025-02-01 | 2026-09-30 |  |  | 2025-02-11 | 2025-05-30 | Delivery Internal Ops | Craft |  |  |  | carlo.fabregas@gevernova.com | Added from 11Feb25 Intake Review meeting. Request #13378800752 13May25-Moved to July for further calibration & material review with SME. 14Jul25 - Push to August 31Jul26-Moved to On Hold due to other priorities 3Sept25-Carlo approved new approach . On hold until new approach & timeline is discussed & validated with stakeholders. 14Oct25-Split into sub tasks 15Dec25-Cancelling this project & subtasks per discussion in previous intake review for similar request. Instead, when materials are in Xyleme, will make them available to regions teams for customized briefings as needed |  | 434d | [6 empty] | No | 2025-02-01 | 2026-09-30 | 2025-02-11 10:07 | jennifer.b.wright@ge.com
AP-0464-1 | Develop Briefing Materials for GT24/26 |  | AP-0641 | Develop Briefing Materials for GT24/26AP-0641 | AP-0464 | AP-0464 | 1 | 1 | 0 | 1 | carlo.fabregas@gevernova.com | Harry Hanson, Lee Fielding, Pablo Schibli | leonardo.monzo1@gevernova.com | Content Development |  | Cancelled |  |  | 2025-02-01 | 2025-12-31 |  |  | 2025-02-01 | 2025-12-31 | Delivery Internal Ops | Craft | [6 empty] | 239d | [6 empty] | No | 2025-02-01 | 2025-12-31 | 2025-10-14 14:54 | jennifer.b.wright@ge.com
AP-0464-2 | Pilot Briefing Materials for GT24/26 |  | AP-0642 | Pilot Briefing Materials for GT24/26AP-0642 | AP-0464 | AP-0464 | 1 | 2 | 0 | 1 | carlo.fabregas@gevernova.com | Harry Hanson, Lee Fielding, Pablo Schibli | leonardo.monzo1@gevernova.com | Content Development |  | Cancelled |  |  | 2026-01-01 | 2026-01-30 |  |  | 2026-01-01 | 2026-01-30 | Delivery Internal Ops | Craft | [6 empty] | 22d | [6 empty] | No | 2026-01-01 | 2026-01-30 | 2025-10-14 14:54 | jennifer.b.wright@ge.com
AP-0464-3 | Develop Briefing Materials for GT13 |  | AP-0643 | Develop Briefing Materials for GT13AP-0643 | AP-0464 | AP-0464 | 1 | 3 | 0 | 1 | carlo.fabregas@gevernova.com | Harry Hanson, Lee Fielding, Pablo Schibli | leonardo.monzo1@gevernova.com | Content Development |  | Cancelled |  |  | 2026-01-01 | 2026-07-31 |  |  | 2026-01-01 | 2026-07-31 | Delivery Internal Ops | Craft | [6 empty] | 152d |  |  |  | TRUE |  |  | No | 2026-01-01 | 2026-07-31 | 2025-10-14 14:54 | jennifer.b.wright@ge.com
AP-0464-4 | Pilot Briefing Materials for GT13 |  | AP-0644 | Pilot Briefing Materials for GT13AP-0644 | AP-0464 | AP-0464 | 1 | 4 | 0 | 1 | carlo.fabregas@gevernova.com | Harry Hanson, Lee Fielding, Pablo Schibli | leonardo.monzo1@gevernova.com | Content Development |  | Cancelled |  |  | 2026-08-01 | 2026-08-31 |  |  | 2026-08-01 | 2026-08-31 | Delivery Internal Ops | Craft | [6 empty] | 22d | [6 empty] | No | 2026-08-01 | 2026-08-31 | 2025-10-14 14:54 | jennifer.b.wright@ge.com
AP-0464-5 | Incorporate Pilot feedback and finalize Briefing Materials for GT 24/26 & GT13 |  | AP-0640 | Incorporate Pilot feedback and finalize Briefing Materials for GT 24/26 & GT13AP-0640 | AP-0464 | AP-0464 | 1 | 5 | 0 | 1 | carlo.fabregas@gevernova.com | Harry Hanson, Lee Fielding, Pablo Schibli | leonardo.monzo1@gevernova.com | Content Development |  | Cancelled |  |  | 2026-02-01 | 2026-09-30 |  |  | 2026-02-01 | 2026-09-30 | Delivery Internal Ops | Craft | [6 empty] | 174d | [6 empty] | No | 2026-02-01 | 2026-09-30 | 2025-10-14 14:54 | jennifer.b.wright@ge.com
AP-0465 | Aero FME Online Training Module |  | AP-0465 | Aero FME Online Training ModuleAP-0465 | #INVALID COLUMN VALUE | Top | 0 | 93 | 0 | 0 | gregoryd.walker@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Content Development | Develop self-paced Aero FME module in Xyleme to replace read & acknowledge process | Complete |  | On Track | 2025-03-01 | 2025-10-31 |  |  | 2025-03-01 | 2025-06-30 | Delivery Ops | FE |  |  |  | Matthew Vaupel | Added from 11Feb25 Intake Review meeting. Request #13489715328 09Jun25-Pending inputs from Aero Quality Manager - may be delayed if not received soon. 25June25-Moved to August, still pending inputs from Aero Quality Manager 11Aug25-Have the inputs from Quality Manager, need to verify timing for loading into Xyleme. 2Sept25-Pushed to end of September to accommodate Xyleme loading 18Sept25-Pushed to end of October to allow more time to finalize. | https://gevernova.box.com/s/4tl19nsasj466rdymswxasfyircb0hjm | 176d | [6 empty] | Yes | 2025-03-01 | 2025-10-31 | 2025-02-11 10:17 | jennifer.b.wright@ge.com
AP-0466 | Customer Profibus & Modbus Training |  | AP-0466 | Customer Profibus & Modbus TrainingAP-0466 | #INVALID COLUMN VALUE | Top | 0 | 94 | 1 | 0 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | FFB is currently offered and used in HA turbine along with Modbus for ICS/ECS. Profibus is available with Aero controls and we can develop these modules for customer training if and when we can get some availability from current SME (Doug Wadsworth). Separated Profibus & Modbus from FFB project (AP-179) | In Progress |  |  | 2026-03-01 | 2027-05-31 | 2026-06-30 |  | 2025-10-01 | 2026-06-30 | Customer Delivery |  |  |  | Other |  | 2/12/25-Separated Profibus & Modbus scope from AP-179. Per Mohammed, plan a start date of Q4 2025 and end date to be Q2 2026 as we really don’t have urgent need/demand for this content. 31Mar26-added sub-tasks and pushed to 1H 2027 because we're still waiting for the cabinet to arrive in order to develop the training. |  | 327d | [6 empty] | Yes | 2026-03-01 | 2027-05-31 | 2025-02-12 13:29 | jennifer.b.wright@ge.com
AP-0466-1 | Receive Profibus & Modbus Cabinet |  | AP-0849 | Receive Profibus & Modbus CabinetAP-0849 | AP-0466 | AP-0466 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development |  | In Progress | TRUE |  | 2026-03-01 | 2026-09-30 |  |  | 2026-03-01 | 2026-09-30 | [8 empty] | 154d | [6 empty] | Yes | 2026-03-01 | 2026-09-30 | 2026-03-31 15:58 | jennifer.b.wright@gevernova.com
AP-0466-2 | Develop Profibus & Modbus Course Materials & Identify Target Instructor(s) |  | AP-0848 | Develop Profibus & Modbus Course Materials & Identify Target Instructor(s)AP-0848 | AP-0466 | AP-0466 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development |  | Not Started | TRUE |  | 2027-01-01 | 2027-03-31 |  |  | 2027-01-01 | 2027-03-31 | [8 empty] | 64d | [6 empty] | Yes | 2027-01-01 | 2027-03-31 | 2026-03-31 15:58 | jennifer.b.wright@gevernova.com
AP-0466-3 | Load Profibus & Modbus course into our relevant systems |  | AP-0847 | Load Profibus & Modbus course into our relevant systemsAP-0847 | AP-0466 | AP-0466 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2027-04-01 | 2027-05-31 |  |  | 2027-04-01 | 2027-05-31 | [8 empty] | 43d | [6 empty] | Yes | 2027-04-01 | 2027-05-31 | 2026-03-31 15:58 | jennifer.b.wright@gevernova.com
AP-0467 | Pre-hiring Assessment |  | AP-0467 | Pre-hiring AssessmentAP-0467 | #INVALID COLUMN VALUE | Top | 0 | 95 | 0 | 0 | luca.martino@gevernova.com | andrew.samples@gevernova.com, Michael Randolph | michele.alcantar@gevernova.com | Operational Simplification | Creation of a pre-hiring assessment to submit by the recruiting team, to all craft technicians that are in the process to be interviewed for hiring, in order to target their real competency level and HR level. | Complete |  | On Track | 2025-03-01 | 2025-03-31 |  |  | 2025-03-01 | 2025-03-31 | Internal Programs & Competency | Craft | [5 empty] | https://gevernova.box.com/s/qzklkj3m8r8j3m07kfthchl3fv66zpy8 | 22d | [6 empty] | No | 2025-03-01 | 2025-03-31 | 2025-02-21 08:14 | jennifer.b.wright@ge.com
AP-0468 | Update ICS Level 2 course |  | AP-0468 | Update ICS Level 2 courseAP-0468 | #INVALID COLUMN VALUE | Top | 0 | 96 | 0 | 0 | mohammed.nizami@gevernova.com | Carla Martinez Borbolla | jim.rosen@gevernova.com | Content Development | We will review our current content for ICS level 2 and level 3 with help of SME from C&C team. They have specific learning objectives for these courses and provided a list of topics. We will evaluate our current content and propose development of new content (if needed) to deliver this course per C&C team needs and requirements. First pilot course is tentatively scheduled for Late Aug/Early Sep and will be delivered by C&C SME with support from controls instructor at HLC. | Complete |  | On Track | 2025-02-25 | 2026-04-30 | 2026-03-31 |  | 2025-02-25 | 2025-08-29 | Delivery Internal Ops | FE |  |  | Intake Review | Toni Mounder Maalouf | Added from 25Feb25 Intake Review meeting. Request #13553908409 15Aug15-We’re currently waiting on the I&C team to assist with content development for ICS Level 2. Carla has already proposed a plan for this course, and Tony Maalouf’s team needs to identify new SMEs to help develop training on the requested topics. Since there are no plans to deliver this course this year, moving to Dec 22Dec25-Content is 90% developed, pending SME review. Pilot course cancelled in Dec 2025. Plan to pilot Level 2 in Feb 2026. TBD if Level 3 will be updated. 10Feb26-Removed Level 3 course from this AP scope. Will be addressed via separate AP 26Mar26-Moved to April since Mohammed is sick today | https://gevernova.ent.box.com/file/2214713731049 | 308d | [6 empty] | Yes | 2025-02-25 | 2026-04-30 | 2025-02-25 10:12 | jennifer.b.wright@ge.com
AP-0469 | Develop Feedback Method for OJT |  | AP-0469 | Develop Feedback Method for OJTAP-0469 | #INVALID COLUMN VALUE | Top | 0 | 97 | 1 | 0 | mouna.boucherka@gevernova.com | alyssa.mays@gevernova.com, brenda.romanvalle@gevernova.com, howayda.sabrymaher@gevernova.com, paula.pedrozanino@gevernova.com, philip.ganssmann@gevernova.com, siawwei.tan@gevernova.com | leonardo.monzo1@gevernova.com | Content Quality & Improvements | Investigate & Develop new method for gathering feedback on OJT performance | In Progress |  |  | 2025-03-01 | 2026-06-30 | 2026-04-30 |  | 2025-03-01 | 2025-08-29 | Internal Ops | Craft FE OSS |  |  | Other |  | Opened as follow up to AP-198 since FPS can't be used for OJT assignments | n/a-parent row | 348d |  |  | TRUE |  |  |  | No | 2025-03-01 | 2026-06-30 | 2025-02-26 12:14 | jennifer.b.wright@ge.com
AP-0469-1 | Investigate & Select OJT Feedback method |  | AP-0470 | Investigate & Select OJT Feedback methodAP-0470 | AP-0469 | AP-0469 | 1 | 1 | 0 | 1 | shaimaa.galal@gevernova.com |  | leonardo.monzo1@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-03-01 | 2025-05-30 |  |  | 2025-03-01 | 2025-05-30 | Internal Ops | Craft FE OSS | [5 empty] | https://gevernova.box.com/s/jo28g8pywf1fezocm2zqo0c8wvvk7ll4 | 66d | [6 empty] | No | 2025-03-01 | 2025-05-30 | 2025-02-28 09:43 | jennifer.b.wright@ge.com
AP-0469-2 | Implement OJT Feedback method |  | AP-0471 | Implement OJT Feedback methodAP-0471 | AP-0469 | AP-0469 | 1 | 2 | 0 | 1 | mouna.boucherka@gevernova.com |  | leonardo.monzo1@gevernova.com | Content Quality & Improvements | Develop survey from OJT Plan Smartsheet. | In Progress |  | Delayed | 2025-06-02 | 2026-06-30 | 2026-04-30 |  | 2025-06-02 | 2025-08-29 | Internal Ops | Craft FE OSS |  |  | Other |  | 30June25-re-assigned to Mouna and moved close to October due to role changes 27Oct25-Moved to November to allow time to implement solution 10Nov25-Reviewing existing FPS OJT process to see how/if it's working for all regions. May add/extend depending on results of review 26Nov25-Moved to Feb to accommodate SMax adjustments 09Feb26-Call with Chris later this week to determine timeline for Smax implementation. 19Feb26-delayed to April due to due to SMax load & issues in the Craft OJT WOs to enable FPS triggering 08Apr26-push back to June to allow time to implement new WO #s and logic change. |  | 282d | 303 | TRUE | TRUE |  |  |  | No | 2025-06-02 | 2026-06-30 | 2025-02-28 09:43 | jennifer.b.wright@ge.com
AP-0474 | Develop Generator High Hydrogen Consumption Training |  | AP-0474 | Develop Generator High Hydrogen Consumption TrainingAP-0474 | #INVALID COLUMN VALUE | Top | 0 | 98 | 0 | 0 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop pressure decay test guidelines content for use in Commissioning training and potentially other courses. Focus on classroom content & investigate potential cost for developing a VR-based simulation for "hands-on" training. | Cancelled |  |  | 2025-10-01 | 2026-03-31 |  |  | 2025-10-01 | 2025-12-31 | Delivery Internal | FE |  |  | Intake Review | howayda.sabrymaher@gevernova.com | 11Mar25-Created from Intake Tracker Request #13717990976 05Dec25-Pushed to March. Will be part of TDI/Commissioning Materials Update 09Mar26-It’s not doable in any of our training Centers unless we acquire a new equipment (Generator in a good working condition) or create some VR simulation software, and both don’t seem achievable in the short term. Therefore this training is advisable to be performed on site as OJT. This was communicated to the requester (Howayda) |  | 130d | [6 empty] | Yes | 2025-10-01 | 2026-03-31 | 2025-03-11 16:18 | jennifer.b.wright@ge.com
AP-0475 | Develop Aero E-Tools Training |  | AP-0475 | Develop Aero E-Tools TrainingAP-0475 | #INVALID COLUMN VALUE | Top | 0 | 99 | 0 | 0 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop E-Tools training module for Aero, should cover IPR - can use existing content in PowerNow | Complete |  | On Track | 2025-07-01 | 2026-04-30 |  |  | 2025-07-01 | 2025-12-31 | Delivery Internal | FE |  |  | Intake Review | leonardo.monzo1@gevernova.com | 11Mar25-Created from Intake Tracker Request #13330179062 15Dec25-Move to Feb to complete materials 09Feb26-May be at risk due to SME availability, but not yet confirmed delayed 23Feb26-Moved to April due to SME availability | https://gevernova.ent.box.com/file/2213649988473 | 218d | [6 empty] | Yes | 2025-07-01 | 2026-04-30 | 2025-03-11 16:24 | jennifer.b.wright@ge.com
AP-0476 | Modify Customer OJT Checklists |  | AP-0476 | Modify Customer OJT ChecklistsAP-0476 | #INVALID COLUMN VALUE | Top | 0 | 100 | 1 | 0 | Jennifer Wright | Johann Josef Daxer, Michele Alcantar, Mohammed Nizami, sherif.khalifa@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | Need to fix OJT checklists to reflect activities that could be performed by our instructors during the Commissioning phase. | Complete |  | On Track | 2025-03-01 | 2025-12-31 |  |  | 2025-03-01 | 2025-12-31 | Customer Delivery |  |  |  |  | Jennifer Wright | 11Mar25-Created from Intake Tracker Request #13686539304 | n/a-parent row | 219d | [6 empty] | No | 2025-03-01 | 2025-12-31 | 2025-03-11 16:31 | jennifer.b.wright@ge.com
AP-0476-1 | Update Customer OJT Checklists, Outlines & Supporting Documents required for Nhon Trach delivery |  | AP-0477 | Update Customer OJT Checklists, Outlines & Supporting Documents required for Nhon Trach deliveryAP-0477 | AP-0476 | AP-0476 | 1 | 1 | 0 | 1 | Jennifer Wright | Johann Josef Daxer, Michele Alcantar, Mohammed Nizami, sherif.khalifa@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | For Controls, Excitation & GT OJT courses: 1. Update Checklists & Course Outline Activities 2. Review any discrepancies vs. as-sold outlines 3. Build critical supporting documentation (work orders, presentations, etc.) to support checklist activities | Complete |  | On Track | 2025-03-01 | 2025-05-30 |  |  | 2025-03-01 | 2025-05-30 | Customer Delivery | [6 empty] | https://gevernova.ent.box.com/file/1876085389777 | 66d | [6 empty] | No | 2025-03-01 | 2025-05-30 | 2025-03-11 16:43 | jennifer.b.wright@ge.com
AP-0476-2 | Finalize all Future Customer OJT Supporting Documentation & Qualified Instructors |  | AP-0478 | Finalize all Future Customer OJT Supporting Documentation & Qualified InstructorsAP-0478 | AP-0476 | AP-0476 | 1 | 2 | 0 | 1 | Jennifer Wright | Johann Josef Daxer, Michele Alcantar, Mohammed Nizami, sherif.khalifa@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | For Controls, Excitation & GT OJT courses: 1. Update Outlines & Checklists based on feedback from Nhon Trach delivery 2. Finalize any remaining documentation 3. Identify target instructors to be qualified for future delivery & develop qualification plan (as needed) 4. Review remaining as-sold/scheduled OJT deliveries to ensure instructors are qualified & aware of new content | Complete |  | On Track | 2025-06-02 | 2025-12-31 |  |  | 2025-06-02 | 2025-12-31 | Customer Delivery | [6 empty] | https://gevernova.ent.box.com/file/2079076726956 | 153d | 308 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-12-31 | 2025-03-11 16:43 | jennifer.b.wright@ge.com
AP-0476-3 | Update Customer OJT Checklists, Outlines & Supporting Documents required for ST Ops & Maint |  | AP-0479 | Update Customer OJT Checklists, Outlines & Supporting Documents required for ST Ops & MaintAP-0479 | AP-0476 | AP-0476 | 1 | 3 | 0 | 1 | Jennifer Wright | Johann Josef Daxer, Pablo Schibli | jim.rosen@gevernova.com | Content Quality & Improvements | For ST OJT courses: 1. Update Checklists & Course Outline Activities 2. Review any discrepancies vs. as-sold outlines 3. Build critical supporting documentation (work orders, presentations, etc.) to support checklist activities 4. Identify target instructors to be qualified for future delivery & develop qualification plan (as needed) | Complete |  | On Track | 2025-06-02 | 2025-12-31 |  |  | 2025-06-02 | 2025-12-31 | Customer Delivery | [6 empty] | https://gevernova.ent.box.com/file/2079076726956 | 153d | 308 | TRUE |  |  |  |  | No | 2025-06-02 | 2025-12-31 | 2025-03-11 16:43 | jennifer.b.wright@ge.com
AP-0491 | Develop Pixaera Advance Lifting Training |  | AP-0491 | Develop Pixaera Advance Lifting TrainingAP-0491 | #INVALID COLUMN VALUE | Top | 0 | 101 | 0 | 0 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Content Development | A need for an advanced course in rigging, focused on rotor lifting has been highlighted and all material has been collected by quality team (videos, pictures and script). Team is ready to start working with Pizaera, just waiting for the approval on budget. During the discussion it emerged that a 3D solution is not really necessary and a normal 2D can be an alternative. The training team proposed as an addendum or as a plan B (so a stand alone solution) a decision making, critical thinking WBT using the storytelling technique | Complete |  | On Track | 2025-04-01 | 2026-01-30 |  |  | 2025-04-01 | 2025-11-28 | Delivery Internal Ops | Craft EHS |  |  | Intake Review | Anna Katrina Tan | 25Mar25-Added from March 25 Intake Review Request #13659758636 3Nov25-Pending target completion date from Vendor & EHS team. May push out. 10Nov25-Moved to Dec 05Dec25-move to January 2026. All modules are developed but Quality team asked the vendor to review the quiz (again) and there is Christmas. I feel more confident in having this in January 2026 | https://gevernova.box.com/s/zejcgqwpr9emurhf9uo8ix804uoml0lx | 219d | [6 empty] | No | 2025-04-01 | 2026-01-30 | 2025-03-25 09:48 | jennifer.b.wright@ge.com
AP-0492 | Winder ramp up |  | AP-0492 | Winder ramp upAP-0492 | #INVALID COLUMN VALUE | Top | 0 | 102 | 1 | 0 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Competitiveness & Growth | NAM OSS is being asked to hire/train an additional 200 winders in the next 18 months in NAM | Complete |  | On Track | 2025-03-26 | 2025-12-31 |  |  | 2025-03-26 | 2025-10-30 | Delivery Internal Ops Programs & Competency | [6 empty] | https://gevernova.box.com/s/oi93soc8skiv9yif46lzhxa2ouincqmw | 201d | [6 empty] | No | 2025-03-26 | 2025-12-31 | 2025-03-26 14:34 | philip.ganssmann@ge.com
AP-0492-1 | Create Winder Ramp Up Training Program |  | AP-0493 | Create Winder Ramp Up Training ProgramAP-0493 | AP-0492 | AP-0492 | 1 | 1 | 0 | 1 | harry.hanson@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competitiveness & Growth | Create program similar to Craft Accelerate Program for Winders. List Instructor needs, consumable needs etc | Complete | TRUE |  | 2025-03-26 | 2025-08-01 |  |  | 2025-03-26 | 2025-04-30 | Delivery | [5 empty] | 24Apr25-Moved to September to verify intent & demand for this program | Report out at Parent level | 93d | [6 empty] | Yes | 2025-03-26 | 2025-08-01 | 2025-03-26 14:34 | philip.ganssmann@ge.com
AP-0492-2 | Calculate Winder Ramp Up Regional Budget need |  | AP-0494 | Calculate Winder Ramp Up Regional Budget needAP-0494 | AP-0492 | AP-0492 | 1 | 2 | 0 | 1 | marcela.bohorquez1@gevernova.com |  | michele.alcantar@gevernova.com | Competitiveness & Growth | Calculate cost for one student to complete the program | Cancelled | TRUE |  | 2025-08-04 | 2025-09-02 |  |  | 2025-10-01 | 2025-10-30 | Internal | [6 empty] | Report out at Parent level? | 22d | 313 | [5 empty] | No | 2025-08-04 | 2025-09-02 | 2025-03-26 14:34 | philip.ganssmann@ge.com
AP-0492-3 | Calculate Winder Ramp up HQ Budget need |  | AP-0495 | Calculate Winder Ramp up HQ Budget needAP-0495 | AP-0492 | AP-0492 | 1 | 3 | 0 | 1 | philip.ganssmann@gevernova.com |  | michele.alcantar@gevernova.com | Competitiveness & Growth | Calculate cost for one class to be conducted | Cancelled | TRUE |  | 2025-08-04 | 2025-09-02 |  |  | 2025-10-01 | 2025-10-30 | Ops | [6 empty] | Report out at Parent level? | 22d | 313 | [5 empty] | No | 2025-08-04 | 2025-09-02 | 2025-03-26 14:34 | philip.ganssmann@ge.com
AP-0492-4 | Specify Winder Ramp Up Logistical needs |  | AP-0496 | Specify Winder Ramp Up Logistical needsAP-0496 | AP-0492 | AP-0492 | 1 | 4 | 0 | 1 | harry.hanson@gevernova.com | Andrew Ruch, Jennifer Wright, marisol.guidry1@gevernova.com, nelsa1.bernal@gevernova.com | michele.alcantar@gevernova.com | Competitiveness & Growth | Build schedule for new class with resource requirements (instructor & tooling). Provide to Andrew for loading into Scheduling tool | Complete | TRUE |  | 2025-08-04 | 2025-09-30 |  |  | 2025-08-01 | 2025-08-29 | Ops | [5 empty] | 3Sept25-switched Lead to Harry to develop the full resource schedule and provide to Andrew (Instructor & Equipment) | Report out at Parent level | 42d | 313 | [5 empty] | Yes | 2025-08-04 | 2025-09-30 | 2025-03-26 14:38 | philip.ganssmann@ge.com
AP-0492-5 | Review and implement Kahuna competences for OSS Winder entry role |  | AP-0585 | Review and implement Kahuna competences for OSS Winder entry roleAP-0585 | AP-0492 | AP-0492 | 1 | 5 | 0 | 1 | luca.martino@gevernova.com | dan1.hogan@gevernova.com, Harry Hanson | michele.alcantar@gevernova.com | Competitiveness & Growth | Build competency map for this entry level role of OSS Winder | Cancelled | TRUE |  | 2025-10-15 | 2025-12-31 |  |  | 2025-10-15 | 2025-12-31 | Programs & Competency | Craft OSS |  |  |  |  | 05Dec25-Replaced by AP-196 |  | 56d | [6 empty] | No | 2025-10-15 | 2025-12-31 | 2025-08-06 04:59 | luca.martino@ge.com
AP-0520 | Develop Xyleme Governance |  | AP-0520 | Develop Xyleme GovernanceAP-0520 | #INVALID COLUMN VALUE | Top | 0 | 103 | 0 | 0 | Jennifer Wright | James Rosen, Lee Fielding, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Develop guidelines/structure for how Xyleme templates, processes, etc. are managed and updated | Not Started |  | Delayed | 2026-05-01 | 2026-07-31 | 2026-02-27 |  | 2025-10-01 | 2025-12-31 | Delivery Ops |  | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 24Nov25-moved to Feb due to higher priorities 9Feb26-Move to July due to higher priroities | https://gevernova.ent.box.com/file/2126885843771 | 66d |  |  |  | TRUE |  |  | No | 2026-05-01 | 2026-07-31 | 2025-03-20 11:20 | jennifer.b.wright@ge.com
AP-0521 | Steam Turbine Controls TDI Training Program |  | AP-0521 | Steam Turbine Controls TDI Training ProgramAP-0521 | #INVALID COLUMN VALUE | Top | 0 | 104 | 1 | 0 | ankita.gupta@gevernova.com | Mohammed Nizami | michele.alcantar@gevernova.com | Content Development | Develop ALT or Cross-Over course to take someone qualified in MK VIe & FFB and develop them for Steam Turbine Controls TDI. Modify ST Ops & add 2nd course for ST Controls Installation. | In Progress |  | Delayed | 2025-06-01 | 2026-09-30 | 2026-03-31 |  | 2025-06-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review | Rami Alshamali | 15Apr25-Created from Intake Request #13826949775 | n/a-parent row | 349d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2026-09-30 | 2025-04-15 10:23 | jennifer.b.wright@ge.com
AP-0521-1 | Define ST Controls TDI Program Outline |  | AP-0522 | Define ST Controls TDI Program OutlineAP-0522 | AP-0521 | AP-0521 | 1 | 1 | 0 | 1 | ankita.gupta@gevernova.com | Mohammed Nizami | michele.alcantar@gevernova.com | Content Development | Define what tops/content is needed, what needs to be modified in the existing ST Ops course & what should be included in the ST Controls Course. | Complete |  | On Track | 2025-06-01 | 2025-07-31 |  |  | 2025-06-01 | 2025-06-30 | Delivery Internal Ops Programs & Competency | FE |  |  |  |  | SME proposed to attend an active class (Jul 7-18) which has delayed the overall delivery of the Outline. | https://gevernova.ent.box.com/file/1941210669183 | 45d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-07-31 | 2025-04-15 10:26 | jennifer.b.wright@ge.com
AP-0521-2 | Develop ST Controls TDI Program Content |  | AP-0523 | Develop ST Controls TDI Program ContentAP-0523 | AP-0521 | AP-0521 | 1 | 2 | 0 | 1 | ankita.gupta@gevernova.com | Mohammed Nizami | michele.alcantar@gevernova.com | Content Development | Develop List of relevant Competencies & identify which can be delivered via training vs. OJT/other Develop course content / storyboard (not formatting) | In Progress | TRUE | Delayed | 2025-08-01 | 2026-07-31 | 2026-05-29 | TRUE | 2025-07-01 | 2025-11-28 | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 11Dec25-Moved to Dec. No report out required 09Feb26-first draft of content was created on time. We have expanded the group (involved PLL & few more SMEs who have provided additional inputs) & hence we need more time to incorporate everything. 9Mar26-Moved to May to allow full time to develop & review content Pilot delivery is targeted for August 11May26-Just lost SME to support this. Have escalated to Mac to get SME - Risk for Target August delivery. 20May26-New SME identified but schedule is delayed. Moved to July |  | 261d | 320 |  |  | TRUE |  |  | No | 2025-08-01 | 2026-07-31 | 2025-04-15 10:26 | jennifer.b.wright@ge.com
AP-0521-3 | Finalize ST Controls TDI Program Materials |  | AP-0524 | Finalize ST Controls TDI Program MaterialsAP-0524 | AP-0521 | AP-0521 | 1 | 3 | 0 | 1 | ankita.gupta@gevernova.com | Lee Fielding, Mohammed Nizami | michele.alcantar@gevernova.com | Content Development | Work with PLLs to finalise the content | Not Started | TRUE | Delayed | 2026-01-01 | 2026-08-31 | 2026-02-27 |  | 2025-12-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 23Jan26-Moved to Feb 09Feb26-Moved back due to delay for previous task 20May26-Moved back due to delay for previous task |  | 173d | [6 empty] | No | 2026-01-01 | 2026-08-31 | 2025-04-15 10:26 | jennifer.b.wright@ge.com
AP-0521-4 | Ensure ST Controls competencies are reflected in Kahuna |  | AP-0729 | Ensure ST Controls competencies are reflected in KahunaAP-0729 | AP-0521 | AP-0521 | 1 | 4 | 0 | 1 | ankita.gupta@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Content Development | Work with Kelly on updating Kahuna | Cancelled |  |  | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 11Dec25-Added to accommodate new training development rigor. Linked to overall TDI Competency Project 09Mar26-cancelled. Duplicate of AP-214 |  | 64d | [6 empty] | No | 2026-01-01 | 2026-03-31 | 2025-12-11 09:56 | jennifer.b.wright@ge.com
AP-0521-5 | Load ST Controls course into our relevant systems |  | AP-0730 | Load ST Controls course into our relevant systemsAP-0730 | AP-0521 | AP-0521 | 1 | 5 | 0 | 1 | ankita.gupta@gevernova.com | Lee Fielding, Mohammed Nizami | michele.alcantar@gevernova.com | Content Development | MM & Xyleme | Not Started |  | Delayed | 2026-01-01 | 2026-08-31 | 2026-03-31 |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 11Dec25-Added to acccommodate new training development rigor. Work with Lee & Team to determine timeline for loading materials into Xyleme 09Feb26-Moved back due to delay for previous task 20May26-Moved back due to delay for previous task |  | 173d | [6 empty] | No | 2026-01-01 | 2026-08-31 | 2025-12-11 09:56 | jennifer.b.wright@ge.com
AP-0521-6 | First ST Controls Pilot session in summer |  | AP-0731 | First ST Controls Pilot session in summerAP-0731 | AP-0521 | AP-0521 | 1 | 6 | 0 | 1 | ankita.gupta@gevernova.com | Mohammed Nizami | michele.alcantar@gevernova.com | Content Development | Work with PLLs to identify/qualify Instructors & update Kahuna accordingly | Not Started |  |  | 2026-01-01 | 2026-09-30 |  |  | 2026-01-01 |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 11Dec25-Added to acccommodate new training development rigor. Timeline to be linked to blueprint'26 |  | 195d | [6 empty] | No | 2026-01-01 | 2026-09-30 | 2025-12-11 09:56 | jennifer.b.wright@ge.com
AP-0544 | Assemble Annual Export Control Compliance Training |  | AP-0544 | Assemble Annual Export Control Compliance TrainingAP-0544 | #INVALID COLUMN VALUE | Top | 0 | 105 | 0 | 0 | brenda.romanvalle@gevernova.com |  | leonardo.monzo1@gevernova.com | Content Development | Work with Digital Technology and/or Compliance/Legal team to get training on Export Controls Compliance for Controls TFAs . Since they are the "owners" of the content, they should prepare the training and provide it to us (we should not be developing the content). | Complete |  | At Risk | 2025-05-01 | 2026-02-27 |  |  | 2025-05-01 | 2025-08-29 | Internal | FE |  |  | Intake Review | brenda.romanvalle@gevernova.com | 20May25-Created from Intake Request #13775557721 5Aug25-Moved to Nov due to other priorities. 10Nov25-May get delayed if SME determines existing training is not sufficient 18Nov25-Moved to Jan because existing training is not sufficient. Will need to be redeveloped. 22Jan26-Moved to Feb to allow time to complete materials, load in LMS & confirm ongoing update process. | https://gevernova.ent.box.com/file/2136817492038 | 217d | [6 empty] | No | 2025-05-01 | 2026-02-27 | 2025-05-20 09:59 | jennifer.b.wright@ge.com
AP-0545 | Add Borescope to ST Assessment training |  | AP-0545 | Add Borescope to ST Assessment trainingAP-0545 | #INVALID COLUMN VALUE | Top | 0 | 106 | 0 | 0 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Primarily an ILES role, but will adapt FE ALT Assessment training to build familiarity with handling & arranging Borescope equipment, not qualification for using it. Target having it ready for delivery in July Course Duration will not change but will increase the cost of the course delivery to add the tooling rental. Need to get approval for cost increase when determined | Complete |  |  | 2025-05-01 | 2025-08-29 |  |  | 2025-05-01 | 2025-07-31 | Delivery Internal Ops | FE |  |  |  | joni.tavares@gevernova.com | 20May25-Created from Intake Request #13689645326 14July25-Material is ready but can't test yet until Borescope equipment is available. Will try for training in Week of August 18 | https://gevernova.ent.box.com/file/1972067564507 | 87d | [6 empty] | Yes | 2025-05-01 | 2025-08-29 | 2025-05-20 13:33 | jennifer.b.wright@ge.com
AP-0546 | "Entry Level" Alstom Controls Training |  | AP-0546 | "Entry Level" Alstom Controls TrainingAP-0546 | #INVALID COLUMN VALUE | Top | 0 | 107 | 0 | 0 | pablo.schibli@gevernova.com | andrew.ruch@gevernova.com, philip.ganssmann@gevernova.com | jim.rosen@gevernova.com | Content Development | Incorporate EHS training at the beginning of the COMET training pathway & modify the content of the COMET, GT & ST EXPERT, and Advant / Alspa training courses to ensure the material is more fundamental, clear, and easy to follow. Content adjustments & addition of EHS training have already been confirmed for July pilot. This item is to track the success of the pilot and develop standard approach (i.e. new course?) for future delivery. | Complete |  | On Track | 2025-05-01 | 2025-07-31 |  |  | 2025-05-01 | 2025-07-31 | Delivery Internal Ops | FE |  |  |  | brenda.romanvalle@gevernova.com | 20May25-Created from Intake Request #13775524111 | https://gevernova.ent.box.com/file/1941521176559 | 66d | [6 empty] | Yes | 2025-05-01 | 2025-07-31 | 2025-05-20 13:43 | jennifer.b.wright@ge.com
AP-0547 | Gen Spec Program Changes |  | AP-0547 | Gen Spec Program ChangesAP-0547 | #INVALID COLUMN VALUE | Top | 0 | 108 | 1 | 0 | Benjamin Smith | Kelly Kirby | jim.rosen@gevernova.com | Content Quality & Improvements | Update Competencies & training programs to better align with Business/field needs | In Progress |  |  | 2025-12-01 | 2026-08-31 |  |  | 2025-08-01 | 2026-06-30 |  |  |  |  | Intake Review |  |  | n/a-parent row | 196d | [6 empty] | No | 2025-12-01 | 2026-08-31 | 2025-05-29 07:32 | jennifer.b.wright@ge.com
AP-0547-1 | Gen Spec Competencies Review |  | AP-0548 | Gen Spec Competencies ReviewAP-0548 | AP-0547 | AP-0547 | 1 | 1 | 1 | 1 | kelly.kirby@gevernova.com | Michele Alcantar | michele.alcantar@gevernova.com | Competencies | Review and update the competencies in Kahuna to better reflect what is needed in the field. Some competencies that are still stored in the Legacy Workflow system (TN344) have not yet been added to Kahuna. These should be reviewed and considered for inclusion. This process will also help determine whether it is truly necessary to maintain both a testing role and a maintenance role for this skill. | In Progress |  |  | 2025-12-01 | 2026-08-31 | 2026-05-29 |  | 2025-08-01 | 2025-12-31 | Delivery Internal Programs & Competency | FE |  |  | Intake Review | brenda.romanvalle@gevernova.com | 29May25-Created from Intake Request #13986892694 4Nov25- Moved to Feb to accommodate SME schedules 23Apr26-Pushed due to other priories |  | 196d | [6 empty] | No | 2025-12-01 | 2026-08-31 | 2025-05-29 07:35 | jennifer.b.wright@ge.com
AP-0547-1-1 | Develop Gen Spec Competency Maps |  | AP-0668 | Develop Gen Spec Competency MapsAP-0668 | AP-0547-1 | AP-0548 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | In Progress | TRUE | Delayed | 2025-12-01 | 2026-06-30 | 2026-05-29 | [7 empty] | Intake Review |  | 26Feb25-Moved to April due to SME availability to review 23Apr26-Pushed to May due to other priories 11May26-Moved to June |  | 152d |  |  | TRUE |  |  |  | No | 2025-12-01 | 2026-06-30 | 2025-11-06 13:14 | jennifer.b.wright@ge.com
AP-0547-1-2 | Import & Configure System for Gen Spec Maps |  | AP-0666 | Import & Configure System for Gen Spec MapsAP-0666 | AP-0547-1 | AP-0548 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | In Progress | TRUE | Delayed | 2026-02-02 | 2026-07-31 | 2026-05-29 | [7 empty] | Intake Review |  | 26Feb25-Moved to April due to SME availability to review 23Apr26-Pushed to May due to other priories 11May26-Moved to July due to above delay |  | 130d |  |  |  | TRUE |  |  | No | 2026-02-02 | 2026-07-31 | 2025-11-06 13:14 | jennifer.b.wright@ge.com
AP-0547-1-3 | Baseline & Load Gen Spec User Assignments |  | AP-0667 | Baseline & Load Gen Spec User AssignmentsAP-0667 | AP-0547-1 | AP-0548 | 2 | 3 | 0 | 1 | kelly.kirby@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | Not Started | TRUE | Delayed | 2026-08-03 | 2026-08-31 | 2026-06-30 | [7 empty] | Intake Review |  | 23Apr26-Pushed to May due to delay in previous steps 11May26-Moved to Aug due to above delay |  | 21d | 332 | [5 empty] | No | 2026-08-03 | 2026-08-31 | 2025-11-06 13:14 | jennifer.b.wright@ge.com
AP-0547-2 | Gen Spec Training Program Changes |  | AP-0549 | Gen Spec Training Program ChangesAP-0549 | AP-0547 | AP-0547 | 1 | 2 | 0 | 1 | Benjamin Smith | Kelly Kirby | jim.rosen@gevernova.com | Content Development | Based on above updates to competencies, modify existing GST program (22 weeks) into a two part program. Phase one (ELT) focus on T&I, Phase two (ALT) focus on Repairs. OJT is required after each phase. Phase one is a pre-req to phase two. Business is asking to have billable by 365, this will enable candidates to be billable for T&I within a year. | On Hold |  |  | 2025-12-01 | 2026-06-30 |  |  | 2025-12-01 | 2026-06-30 | Delivery Internal | FE |  |  | Intake Review | michele.alcantar@gevernova.com | 29May25-Created from Intake Request #13845359829 13Feb26-TBD if this is still needed. Kelly & Michele to connect once Competency Review is complete to determine how/if the training program needs to be modified. |  | 152d |  |  | TRUE |  |  |  | No | 2025-12-01 | 2026-06-30 | 2025-05-29 07:37 | jennifer.b.wright@ge.com
AP-0570 | Move MM Outline function to Xyleme & Smartsheet |  | AP-0570 | Move MM Outline function to Xyleme & SmartsheetAP-0570 | #INVALID COLUMN VALUE | Top | 0 | 109 | 1 | 0 | Jennifer Wright | Lee Fielding, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Determine how/if current MM functionality could be implemented in Xyleme and corresponding cost/timeline/etc. | In Progress |  | On Track | 2025-06-01 | 2026-06-30 | 2026-04-30 |  | 2025-06-01 | 2025-09-30 | Customer Delivery Internal Ops Programs & Competency |  | OFS-Cost-Cost-Gross Margin | C | Other |  | 24Sept25-updated to include sub-tasks for completion migration | n/a-parent row | 283d |  | TRUE | TRUE |  |  |  | No | 2025-06-01 | 2026-06-30 | 2025-06-11 09:51 | jennifer.b.wright@ge.com
AP-0570-1 | Investigate Moving MM functionality into SS/Xyleme |  | AP-0634 | Investigate Moving MM functionality into SS/XylemeAP-0634 | AP-0570 | AP-0570 | 1 | 1 | 0 | 1 | Jennifer Wright | Lee Fielding, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Determine how/if current MM functionality could be implemented in Xyleme and corresponding cost/timeline/etc. | Complete |  | On Track | 2025-06-01 | 2025-09-30 |  |  | 2025-06-01 | 2025-09-30 | Customer Delivery Internal Ops Programs & Competency | [6 empty] | https://gevernova.ent.box.com/file/1995604477965 | 88d |  | TRUE |  |  |  |  | No | 2025-06-01 | 2025-09-30 | 2025-09-24 09:54 | jennifer.b.wright@ge.com
AP-0570-2 | Build SS & Xyleme Course DB/Outline functionality |  | AP-0635 | Build SS & Xyleme Course DB/Outline functionalityAP-0635 | AP-0570 | AP-0570 | 1 | 2 | 0 | 1 | Jennifer Wright | Lee Fielding, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Jen to build SS functionality Lee to build Xyleme functionality | Complete |  | On Track | 2025-10-01 | 2026-03-31 |  |  | 2025-10-01 | 2026-01-30 | Customer Delivery Internal Ops Programs & Competency |  | OFS-Cost-Cost-Gross Margin | C | Other |  | 12Jan26-Move to Feb to incorporate new categories, etc. 25Feb26-Development still underway due to extra complexities from new categories & program designations. Still on track to switch to new solution by end of April. | https://gevernova.ent.box.com/file/2176320265688 | 130d | [6 empty] | No | 2025-10-01 | 2026-03-31 | 2025-09-24 09:56 | jennifer.b.wright@ge.com
AP-0570-3 | Review Categories & Naming Conventions with stakeholders |  | AP-0636 | Review Categories & Naming Conventions with stakeholdersAP-0636 | AP-0570 | AP-0570 | 1 | 3 | 0 | 1 | Jennifer Wright | andrew.ruch@gevernova.com, lee.s.fielding@gevernova.com, philip.ganssmann@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Address discrepancies between how courses are categorized & named in the Blueprint vs. MM | Complete |  | On Track | 2025-10-01 | 2026-01-30 |  |  | 2025-10-01 | 2026-01-30 | Delivery Internal Ops |  | OFS-Quality-Customer Escapes-% of CX Surveys <=3 OFS-Quality-Customer Escapes-Quality Severe Events (SE) | Q | Other |  |  | https://gevernova.ent.box.com/file/2116794563299 | 88d | [6 empty] | No | 2025-10-01 | 2026-01-30 | 2025-09-24 09:56 | jennifer.b.wright@ge.com
AP-0570-4 | Finalize New Course DB Testing & Freeze updates in MM |  | AP-0869 | Finalize New Course DB Testing & Freeze updates in MMAP-0869 | AP-0570 | AP-0570 | 1 | 4 | 0 | 1 | Jennifer Wright |  | philip.ganssmann@gevernova.com | Operational Simplification | Finalize testing & functionality of all request workflows Freeze changes in MM & request full course extract from MM | Complete |  | On Track | 2026-03-01 | 2026-04-30 |  |  | 2026-03-01 | 2026-04-30 | Delivery Internal Ops | [5 empty] | 07Apr26-New sub tasks to cover final testing and MM requirements | https://gevernova.ent.box.com/file/2213656955672 | 45d | [6 empty] | No | 2026-03-01 | 2026-04-30 | 2026-04-07 13:54 | jennifer.b.wright@gevernova.com
AP-0570-5 | Migrate MM data into Smartsheet & Xyleme & switch from MM |  | AP-0637 | Migrate MM data into Smartsheet & Xyleme & switch from MMAP-0637 | AP-0570 | AP-0570 | 1 | 5 | 0 | 1 | Jennifer Wright | Lee Fielding, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Lee is working on getting Customer Training outlines loaded in Xyleme by the end of 2025. TBD when/how to load the internal outlines. | In Progress |  | On Track | 2026-03-01 | 2026-06-30 | 2026-05-29 | TRUE | 2026-02-01 | 2026-04-30 | Customer Delivery Internal Ops Programs & Competency |  | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 07Apr26-Moved to May with new sub-task 20May26-Moved to June due to MM data extract delays |  | 88d |  |  | TRUE |  |  |  | No | 2026-03-01 | 2026-06-30 | 2025-09-24 10:00 | jennifer.b.wright@ge.com
AP-0591 | Competency map for Advanced Alstom Gen Mechanical Specialization Role |  | AP-0591 | Competency map for Advanced Alstom Gen Mechanical Specialization RoleAP-0591 | #INVALID COLUMN VALUE | Top | 0 | 110 | 1 | 0 | tamara.biediger@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies | Create new competency map for advanced role for Alstom Gen Mechanical specialization. Currently, we have a small number of people who can perform this skill and most knowledge is tribal. There is a danger of losing a critical aspect of the Alstom maintenance business. Requirements to perform this skill are well documented in field procedures and only need to be developed into a competency model to prove competency and tracking both internally and to customers. | Complete |  | On Track | 2025-09-01 | 2025-12-31 |  |  | 2025-08-01 | 2025-12-31 | Internal Programs & Competency | FE RM |  |  |  | scot.bragg@gevernova.com | 12Aug25-Created from Intake Request #14300164530. SME budget of 35 hours approved. 28Oct25-Split into sub tasks with updated dates | https://gevernova.ent.box.com/file/2096020688690 | 88d | [6 empty] | No | 2025-09-01 | 2025-12-31 | 2025-08-12 09:15 | jennifer.b.wright@ge.com
AP-0591-1 | Create Advanced Alstom Gen Mechanical Specialization competency map |  | AP-0651 | Create Advanced Alstom Gen Mechanical Specialization competency mapAP-0651 | AP-0591 | AP-0591 | 1 | 1 | 0 | 1 | tamara.biediger@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE | On Track | 2025-09-01 | 2025-10-15 |  |  | 2025-09-01 | 2025-10-15 | Internal Programs & Competency | FE RM | [5 empty] | Report at Parent Level | 33d | [6 empty] | No | 2025-09-01 | 2025-10-15 | 2025-10-28 08:53 | jennifer.b.wright@ge.com
AP-0591-2 | Identify and submit candidates for baselining as Assessors in new role to Kahuna Manager |  | AP-0652 | Identify and submit candidates for baselining as Assessors in new role to Kahuna ManagerAP-0652 | AP-0591 | AP-0591 | 1 | 2 | 0 | 1 | tamara.biediger@gevernova.com | Kelly Kirby | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE | On Track | 2025-09-01 | 2025-10-31 |  |  | 2025-09-01 | 2025-10-31 | Internal Programs & Competency | FE RM | [5 empty] | Report at Parent Level | 45d | [6 empty] | No | 2025-09-01 | 2025-10-31 | 2025-10-28 08:53 | jennifer.b.wright@ge.com
AP-0591-3 | Import & Configure system for Advanced Alstom Gen Mechanical Specialization Role |  | AP-0650 | Import & Configure system for Advanced Alstom Gen Mechanical Specialization RoleAP-0650 | AP-0591 | AP-0591 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE | On Track | 2025-11-01 | 2025-11-28 |  |  | 2025-11-01 | 2025-11-28 | Internal Programs & Competency | FE RM | [5 empty] | Report at Parent Level | 21d | [6 empty] | No | 2025-11-01 | 2025-11-28 | 2025-10-28 08:53 | jennifer.b.wright@ge.com
AP-0591-4 | Load Advanced Alstom Gen Mechanical Specialization User Assignments |  | AP-0669 | Load Advanced Alstom Gen Mechanical Specialization User AssignmentsAP-0669 | AP-0591 | AP-0591 | 1 | 4 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Competencies |  | Complete | TRUE | On Track | 2025-12-01 | 2025-12-31 |  |  |  |  | Internal Programs & Competency | FE RM | [5 empty] | Report at Parent Level | 23d | [6 empty] | No | 2025-12-01 | 2025-12-31 | 2025-11-06 13:21 | jennifer.b.wright@ge.com
AP-0592 | Enhance Generator Retaining Ring Removal Training in Birr |  | AP-0592 | Enhance Generator Retaining Ring Removal Training in BirrAP-0592 | #INVALID COLUMN VALUE | Top | 0 | 111 | 0 | 0 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop a standalone training program that can serve as a follow-up to the existing RRR training. The primary target audience for this program would be SPS personnel. Currently, for retaining ring removal tasks, we provide training using tools supplied on-site by FC. However, SPS has requested that we also include instruction on the proper use of specialized tools for larger-diameter generators, particularly those installed in nuclear power plants, and with other special equipment. This can be achieved using our training rotor, as these specialized tools can be adapted to the generator dimensions available at BLC. Additionally, they utilize the same ring locking system, the Bayonet-type system. | Complete |  | On Track | 2025-10-01 | 2025-11-28 |  |  | 2025-10-01 | 2025-11-28 | Delivery Internal Ops | FE RM |  |  |  | Julia Netschajewa-Byrne | 12Aug25-Created from Intake Request # 14285177108. Budget to be covered by SPS team. | https://gevernova.ent.box.com/file/2056690400869 | 43d | [6 empty] | Yes | 2025-10-01 | 2025-11-28 | 2025-09-02 14:05 | jennifer.b.wright@ge.com
AP-0593 | Work Force Readiness Phase 1 – Immediate Priorities |  | AP-0593 | Work Force Readiness Phase 1 – Immediate PrioritiesAP-0593 | #INVALID COLUMN VALUE | Top | 0 | 112 | 1 | 0 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete |  | On Track | 2025-09-01 | 2025-10-31 |  |  | 2025-09-01 | 2025-10-31 | [7 empty] | https://gevernova.ent.box.com/file/2029923354367 | 45d | [6 empty] | Yes | 2025-09-01 | 2025-10-31 | 2025-09-03 13:38 | jennifer.b.wright@ge.com
AP-0593-1 | WFR-Establish ISD partnerships and launch Advisory Council |  | AP-0594 | WFR-Establish ISD partnerships and launch Advisory CouncilAP-0594 | AP-0593 | AP-0593 | 1 | 1 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | Alief, Channelview, Deer Park | Complete | TRUE | On Track | 2025-09-01 | 2025-10-31 |  |  | 2025-09-01 | 2025-10-31 | Delivery Internal Ops | [6 empty] | https://gevernova.box.com/s/o2erxaxjkusogxcpiwgbt603fhqt9pv7 | 45d | [6 empty] | Yes | 2025-09-01 | 2025-10-31 | 2025-09-03 13:40 | jennifer.b.wright@ge.com
AP-0593-2 | WFR-Secure Creative Services time |  | AP-0596 | WFR-Secure Creative Services timeAP-0596 | AP-0593 | AP-0593 | 1 | 2 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | for promo video, one-pager, publish Linkedin and YouTube | Complete | TRUE | On Track | 2025-09-01 | 2025-10-31 |  |  | 2025-09-01 | 2025-10-31 | Delivery Internal Ops | [6 empty] | https://gevernova.box.com/s/o2erxaxjkusogxcpiwgbt603fhqt9pv7 | 45d | [6 empty] | Yes | 2025-09-01 | 2025-10-31 | 2025-09-03 13:42 | jennifer.b.wright@ge.com
AP-0593-3 | WFR-Develop “Demo-in-a-Box” |  | AP-0597 | WFR-Develop “Demo-in-a-Box”AP-0597 | AP-0593 | AP-0593 | 1 | 3 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | Day in the Life concept, completed presented to 150 students including pelican box with hands on equipment for demonstration | Complete | TRUE | On Track | 2025-09-01 | 2025-10-31 |  |  | 2025-09-01 | 2025-10-31 | Delivery Internal Ops | [6 empty] | https://gevernova.box.com/s/o2erxaxjkusogxcpiwgbt603fhqt9pv7 | 45d | [6 empty] | Yes | 2025-09-01 | 2025-10-31 | 2025-09-03 13:42 | jennifer.b.wright@ge.com
AP-0593-4 | WFR-Begin NCCER vetting and review incoming content modules |  | AP-0598 | WFR-Begin NCCER vetting and review incoming content modulesAP-0598 | AP-0593 | AP-0593 | 1 | 4 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | continual meetings to align competencies with possible national programs for easy deployment | Complete | TRUE | On Track | 2025-09-01 | 2025-10-31 |  |  | 2025-09-01 | 2025-10-31 | Delivery Internal Ops | [6 empty] | https://gevernova.box.com/s/o2erxaxjkusogxcpiwgbt603fhqt9pv7 | 45d | [6 empty] | Yes | 2025-09-01 | 2025-10-31 | 2025-09-03 13:42 | jennifer.b.wright@ge.com
AP-0599 | Work Force Readiness Phase 2 – Program Design |  | AP-0599 | Work Force Readiness Phase 2 – Program DesignAP-0599 | #INVALID COLUMN VALUE | Top | 0 | 113 | 1 | 0 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete |  | On Track | 2025-09-01 | 2025-12-31 |  |  | 2025-11-01 | 2025-12-31 | [7 empty] | https://gevernova.ent.box.com/file/2095820749230 | 88d | [6 empty] | Yes | 2025-09-01 | 2025-12-31 | 2025-09-03 13:42 | jennifer.b.wright@ge.com
AP-0599-1 | WFR-Build student application and HR/Resource vetting process |  | AP-0600 | WFR-Build student application and HR/Resource vetting processAP-0600 | AP-0599 | AP-0599 | 1 | 1 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete | TRUE | On Track | 2025-11-01 | 2025-11-28 |  |  | 2025-11-01 | 2025-11-28 | Delivery Internal Ops | [6 empty] | report out at parent level | 21d | [6 empty] | Yes | 2025-11-01 | 2025-11-28 | 2025-09-03 13:45 | jennifer.b.wright@ge.com
AP-0599-2 | WFR-Align curriculum to MA competencies and document gaps vs. ISD programs |  | AP-0602 | WFR-Align curriculum to MA competencies and document gaps vs. ISD programsAP-0602 | AP-0599 | AP-0599 | 1 | 2 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete | TRUE | On Track | 2025-11-01 | 2025-11-28 |  |  | 2025-11-01 | 2025-11-28 | Delivery Internal Ops | [6 empty] | report out at parent level | 21d | [6 empty] | Yes | 2025-11-01 | 2025-11-28 | 2025-09-03 13:45 | jennifer.b.wright@ge.com
AP-0599-3 | WFR-Develop comms package |  | AP-0603 | WFR-Develop comms packageAP-0603 | AP-0599 | AP-0599 | 1 | 3 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | flyers, FAQs, parent/ISD presentations | Complete | TRUE | On Track | 2025-11-01 | 2025-12-31 |  |  | 2025-11-01 | 2025-12-31 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 44d | [6 empty] | Yes | 2025-11-01 | 2025-12-31 | 2025-09-03 13:45 | jennifer.b.wright@ge.com
AP-0599-4 | WFR-Complete Legal review |  | AP-0595 | WFR-Complete Legal reviewAP-0595 | AP-0599 | AP-0599 | 1 | 4 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | DOL internship compliance, liability waivers, visitor coverage | Complete | TRUE | On Track | 2025-09-01 | 2025-12-31 |  |  | 2025-09-01 | 2025-10-31 | Delivery Internal Ops |  |  |  | Other |  | 23Oct25-moved to Phase 2 due to delays with Legal team. | report out at parent level | 88d | [6 empty] | Yes | 2025-09-01 | 2025-12-31 | 2025-09-03 13:40 | jennifer.b.wright@ge.com
AP-0604 | Work Force Readiness Program Phase 3 – Medium-Term Buildout |  | AP-0604 | Work Force Readiness Program Phase 3 – Medium-Term BuildoutAP-0604 | #INVALID COLUMN VALUE | Top | 0 | 114 | 1 | 0 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete |  | On Track | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 |  |  |  |  | Other |  |  | https://gevernova.ent.box.com/file/2176408926728 | 64d | [6 empty] | Yes | 2026-01-01 | 2026-03-31 | 2025-09-03 13:46 | jennifer.b.wright@ge.com
AP-0604-1 | WFR-Finalize MOUs with ISDs |  | AP-0605 | WFR-Finalize MOUs with ISDsAP-0605 | AP-0604 | AP-0604 | 1 | 1 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | student participation, TEKS/IBC alignment, liability | Complete | TRUE | On Track | 2026-01-01 | 2026-01-30 |  |  | 2026-01-01 | 2026-01-30 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 22d | [6 empty] | Yes | 2026-01-01 | 2026-01-30 | 2025-09-03 13:49 | jennifer.b.wright@ge.com
AP-0604-2 | WFR-Confirm certification pathways |  | AP-0606 | WFR-Confirm certification pathwaysAP-0606 | AP-0604 | AP-0604 | 1 | 2 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | OSHA-10, SACA, NCCER, others | Complete | TRUE | On Track | 2026-01-01 | 2026-01-30 |  |  | 2026-01-01 | 2026-01-30 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 22d | [6 empty] | Yes | 2026-01-01 | 2026-01-30 | 2025-09-03 13:49 | jennifer.b.wright@ge.com
AP-0604-3 | WFR-Engage GHP for workforce alignment |  | AP-0607 | WFR-Engage GHP for workforce alignmentAP-0607 | AP-0604 | AP-0604 | 1 | 3 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | UpSkill Houston, One Houston Together | Complete | TRUE | On Track | 2026-01-01 | 2026-02-27 |  |  | 2026-01-01 | 2026-02-27 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 42d | [6 empty] | Yes | 2026-01-01 | 2026-02-27 | 2025-09-03 13:49 | jennifer.b.wright@ge.com
AP-0604-4 | WFR-Develop CTE branding and outreach design |  | AP-0608 | WFR-Develop CTE branding and outreach designAP-0608 | AP-0604 | AP-0604 | 1 | 4 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | using GE Vernova standards | Complete | TRUE | On Track | 2026-01-01 | 2026-02-27 |  |  | 2026-01-01 | 2026-02-27 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 42d | [6 empty] | Yes | 2026-01-01 | 2026-02-27 | 2025-09-03 13:49 | jennifer.b.wright@ge.com
AP-0604-5 | WFR-Publish 2026 marketing/outreach calendar |  | AP-0609 | WFR-Publish 2026 marketing/outreach calendarAP-0609 | AP-0604 | AP-0604 | 1 | 5 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete | TRUE | On Track | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 64d | [6 empty] | Yes | 2026-01-01 | 2026-03-31 | 2025-09-03 13:49 | jennifer.b.wright@ge.com
AP-0610 | Work Force Readiness Program Phase 4 – Outreach & Readiness |  | AP-0610 | Work Force Readiness Program Phase 4 – Outreach & ReadinessAP-0610 | #INVALID COLUMN VALUE | Top | 0 | 115 | 1 | 0 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | In Progress |  |  | 2026-04-01 | 2026-06-30 |  |  | 2026-04-01 | 2026-06-30 |  |  |  |  | Other |  |  |  | 65d |  |  | TRUE |  |  |  | Yes | 2026-04-01 | 2026-06-30 | 2025-09-03 13:50 | jennifer.b.wright@ge.com
AP-0610-1 | WFR-Deliver student/parent outreach toolkit |  | AP-0611 | WFR-Deliver student/parent outreach toolkitAP-0611 | AP-0610 | AP-0610 | 1 | 1 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | presentations, handouts, videos | Complete | TRUE | On Track | 2026-04-01 | 2026-04-30 |  |  | 2026-04-01 | 2026-04-30 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 22d | [6 empty] | Yes | 2026-04-01 | 2026-04-30 | 2025-09-03 13:52 | jennifer.b.wright@ge.com
AP-0610-2 | WFR-Launch digital/print outreach materials for HLC tours & recruiting |  | AP-0612 | WFR-Launch digital/print outreach materials for HLC tours & recruitingAP-0612 | AP-0610 | AP-0610 | 1 | 2 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete | TRUE | On Track | 2026-04-01 | 2026-04-30 |  |  | 2026-04-01 | 2026-04-30 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 22d | [6 empty] | Yes | 2026-04-01 | 2026-04-30 | 2025-09-03 13:52 | jennifer.b.wright@ge.com
AP-0610-3 | WFR-Propose teacher externship/train-the-trainer model for scaling |  | AP-0613 | WFR-Propose teacher externship/train-the-trainer model for scalingAP-0613 | AP-0610 | AP-0610 | 1 | 3 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete | TRUE | On Track | 2026-04-01 | 2026-05-29 |  |  | 2026-04-01 | 2026-05-29 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 43d |  |  |  |  | TRUE |  | Yes | 2026-04-01 | 2026-05-29 | 2025-09-03 13:52 | jennifer.b.wright@ge.com
AP-0610-4 | WFR-Define instructor support model for after-school/apprenticeship delivery |  | AP-0615 | WFR-Define instructor support model for after-school/apprenticeship deliveryAP-0615 | AP-0610 | AP-0610 | 1 | 4 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth |  | Complete | TRUE | On Track | 2026-04-01 | 2026-05-29 |  |  | 2026-04-01 | 2026-05-29 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 43d |  |  |  |  | TRUE |  | Yes | 2026-04-01 | 2026-05-29 | 2025-09-03 13:52 | jennifer.b.wright@ge.com
AP-0610-5 | WFR-Finalize reporting framework |  | AP-0614 | WFR-Finalize reporting frameworkAP-0614 | AP-0610 | AP-0610 | 1 | 5 | 0 | 1 | linda.nelson@gevernova.com |  | jim.rosen@gevernova.com | Competitiveness & Growth | readiness, assessment, remediation | Not Started | TRUE |  | 2026-04-01 | 2026-06-30 |  |  | 2026-04-01 | 2026-06-30 | Delivery Internal Ops |  |  |  | Other |  |  | report out at parent level | 65d |  |  | TRUE |  |  |  | Yes | 2026-04-01 | 2026-06-30 | 2025-09-03 13:52 | jennifer.b.wright@ge.com
AP-0616 | Develop & Launch 5S Program at HLC |  | AP-0616 | Develop & Launch 5S Program at HLCAP-0616 | #INVALID COLUMN VALUE | Top | 0 | 116 | 0 | 0 | andrew.samples@gevernova.com | andrew.ruch@gevernova.com, jim.rosen@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Improve the 5S program structure and execution method to drive a cultural change and elevate our training centers globally. | Complete |  | On Track | 2025-09-01 | 2026-02-27 |  |  | 2025-09-01 | 2025-12-31 | Customer Delivery Internal Ops Programs & Competency | [5 empty] | 08Dec25-Moved to January to include first 5S Session in January 29Jan26-completed in Jan, but will present in Feb since Andrew couldn't attend Jan AP call | https://gevernova.ent.box.com/file/2095934787798 | 130d | [6 empty] | No | 2025-09-01 | 2026-02-27 | 2025-09-04 12:21 | jennifer.b.wright@ge.com
AP-0618 | Aero Maintenance Practices Training |  | AP-0618 | Aero Maintenance Practices TrainingAP-0618 | #INVALID COLUMN VALUE | Top | 0 | 117 | 0 | 0 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop an online training module covering Maintenance Practices from Chapter 11 of the Aero O&M manual. This training will provide structured, accessible, and standardized guidance for technicians and operators, ensuring alignment with best practices and supporting both safety and reliability objectives. Greg's SME will develop materials, Vendor can help load content into Xyleme. | In Progress |  | Delayed | 2025-10-01 | 2026-06-30 | 2026-05-29 | TRUE | 2025-10-01 | 2026-01-30 | Delivery Internal Ops | FE |  |  | Intake Review | Leonel Wanko | 09Sept25-Created from Intake Request # 14373310551. 12Jan26-Moved to March due to other projects 23Feb26-Moved to May due to SME availability 11May26-Need to confirm availability for Xyleme team to process & publish this. 21May26-Moved to June to allow Xyleme team time & more images. Pending actual target dates from Xyleme team. |  | 195d |  |  | TRUE |  |  |  | Yes | 2025-10-01 | 2026-06-30 | 2025-09-09 13:16 | jennifer.b.wright@ge.com
AP-0619 | Aero Woodward Controller Training |  | AP-0619 | Aero Woodward Controller TrainingAP-0619 | #INVALID COLUMN VALUE | Top | 0 | 118 | 1 | 0 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Develop instructor-led module covering Woodward valves and drivers to be incorporated into the existing Woodward Controls Operation, Maintenance, and Troubleshooting course (I-AER30801). This addition will provide FSEs with the critical knowledge and experience needed to perform calibrations, troubleshooting, and maintenance with greater confidence and consistency, reducing reliance on informal methods and external support. Full scope is contingent on 2026 budget approval for 10k for hardware (included in CapEx budget requested for 2026). Could do partial scope without simulations if no equipment is approved. | In Progress |  |  | 2026-01-01 | 2026-10-30 |  |  | 2026-02-01 | 2026-07-31 | Delivery Internal Ops | FE |  |  | Intake Review | Ana Cristina Najera Primera | 09Sept25-Created from Intake Request # 14226749146. 24Feb26-Added subtasks with updated dates |  | 217d | [6 empty] | Yes | 2026-01-01 | 2026-10-30 | 2025-09-09 13:21 | jennifer.b.wright@ge.com
AP-0619-1 | Develop/Review List of Aero Woodward Controller Competencies & identify which can be delivered via training vs. OJT/other |  | AP-0829 | Develop/Review List of Aero Woodward Controller Competencies & identify which can be delivered via training vs. OJT/otherAP-0829 | AP-0619 | AP-0619 | 1 | 1 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Coordinated with PLL, SMEs & Program Mgr | In Progress | TRUE |  | 2026-01-01 | 2026-06-30 |  |  | 2026-01-01 | 2026-06-30 | [8 empty] | 129d |  |  | TRUE |  |  |  | Yes | 2026-01-01 | 2026-06-30 | 2026-02-24 13:35 | jennifer.b.wright@ge.com
AP-0619-2 | Ensure Aero Woodward Controller competencies are reflected in Kahuna |  | AP-0828 | Ensure Aero Woodward Controller competencies are reflected in KahunaAP-0828 | AP-0619 | AP-0619 | 1 | 2 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to Coordinated with Program Manager, Kelly, SMEs | Not Started | TRUE |  | 2026-07-01 | 2026-07-31 |  |  | 2026-07-01 | 2026-07-31 | [8 empty] | 23d |  |  |  | TRUE |  |  | Yes | 2026-07-01 | 2026-07-31 | 2026-02-24 13:35 | jennifer.b.wright@ge.com
AP-0619-3 | Update Aero Woodward Controller Course Materials & Identify Target Instructor(s) |  | AP-0827 | Update Aero Woodward Controller Course Materials & Identify Target Instructor(s)AP-0827 | AP-0619 | AP-0619 | 1 | 3 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-08-01 | 2026-09-30 |  |  | 2026-08-01 | 2026-09-30 | [8 empty] | 44d | [6 empty] | Yes | 2026-08-01 | 2026-09-30 | 2026-02-24 13:35 | jennifer.b.wright@ge.com
AP-0619-4 | Update Aero Woodward Controller course in our relevant systems |  | AP-0826 | Update Aero Woodward Controller course in our relevant systemsAP-0826 | AP-0619 | AP-0619 | 1 | 4 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-09-01 | 2026-09-30 |  |  | 2026-09-01 | 2026-09-30 | [8 empty] | 22d | [6 empty] | Yes | 2026-09-01 | 2026-09-30 | 2026-02-24 13:35 | jennifer.b.wright@ge.com
AP-0619-5 | Deliver Updated Aero Woodward Controller Pilot session |  | AP-0825 | Deliver Updated Aero Woodward Controller Pilot sessionAP-0825 | AP-0619 | AP-0619 | 1 | 5 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2026-10-01 | 2026-10-30 |  |  | 2026-10-01 | 2026-10-30 | [8 empty] | 22d | [6 empty] | Yes | 2026-10-01 | 2026-10-30 | 2026-02-24 13:35 | jennifer.b.wright@ge.com
AP-0620 | Develop Internal Translation Process |  | AP-0620 | Develop Internal Translation ProcessAP-0620 | #INVALID COLUMN VALUE | Top | 0 | 119 | 0 | 0 | philip.ganssmann@gevernova.com | Konstantina Georga | philip.ganssmann@gevernova.com | Operational Simplification | Develop process for requesting/tracking/using new AI Translation tool | Complete |  | On Track | 2025-10-01 | 2026-01-30 |  |  | 2025-10-01 | 2025-12-31 | Customer Delivery Internal Ops Programs & Competency |  |  |  | Other |  | 7Jan26-Moved to end of Jan due to end-of-year priorities 12Jan26-Move to Feb | https://gevernova.ent.box.com/file/2114232992975 | 88d | [6 empty] | No | 2025-10-01 | 2026-01-30 | 2025-09-11 13:43 | jennifer.b.wright@ge.com
AP-0621 | Switch to using Xyleme for Exams |  | AP-0621 | Switch to using Xyleme for ExamsAP-0621 | #INVALID COLUMN VALUE | Top | 0 | 120 | 1 | 0 | jim.rosen@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification |  | In Progress |  |  | 2026-01-01 | 2027-07-05 |  |  | 2026-01-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 393d | [6 empty] | Yes | 2026-01-01 | 2027-07-05 | 2025-09-23 13:04 | jennifer.b.wright@ge.com
AP-0621-1 | Migrate Exams into Xyleme |  | AP-0622 | Migrate Exams into XylemeAP-0622 | AP-0621 | AP-0621 | 1 | 1 | 1 | 1 | jim.rosen@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Includes review of exam content (i.e. good question, etc.) | In Progress |  |  | 2026-01-01 | 2026-12-31 | 2026-06-30 | TRUE | 2026-01-01 | 2026-06-30 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2025-09-23 13:07 | jennifer.b.wright@ge.com
AP-0621-1-1 | Migrate GT Exams into Xyleme |  | AP-0626 | Migrate GT Exams into XylemeAP-0626 | AP-0621-1 | AP-0622 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Includes review of exam content (i.e. good question, etc.) | In Progress | TRUE |  | 2026-01-01 | 2026-12-31 | 2026-06-30 |  | 2026-01-01 | 2026-06-30 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2025-09-23 13:45 | jennifer.b.wright@ge.com
AP-0621-1-2 | Migrate ST Exams into Xyleme |  | AP-0627 | Migrate ST Exams into XylemeAP-0627 | AP-0621-1 | AP-0622 | 2 | 2 | 0 | 1 | pablo.schibli@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Includes review of exam content (i.e. good question, etc.) | In Progress | TRUE |  | 2026-01-01 | 2026-12-31 | 2026-06-30 |  | 2026-01-01 | 2026-06-30 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2025-09-23 13:45 | jennifer.b.wright@ge.com
AP-0621-1-3 | Migrate Ex Exams into Xyleme |  | AP-0623 | Migrate Ex Exams into XylemeAP-0623 | AP-0621-1 | AP-0622 | 2 | 3 | 0 | 1 | Benjamin Smith | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Includes review of exam content (i.e. good question, etc.) | In Progress | TRUE |  | 2026-01-01 | 2026-12-31 | 2026-06-30 |  | 2026-01-01 | 2026-06-30 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 261d | [6 empty] | No | 2026-01-01 | 2026-12-31 | 2025-09-23 13:45 | jennifer.b.wright@ge.com
AP-0621-1-4 | Migrate Aero Exams into Xyleme |  | AP-0624 | Migrate Aero Exams into XylemeAP-0624 | AP-0621-1 | AP-0622 | 2 | 4 | 0 | 1 | gregoryd.walker@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Includes review of exam content (i.e. good question, etc.) | In Progress | TRUE |  | 2026-01-01 | 2026-12-31 | 2026-06-30 |  | 2026-01-01 | 2026-06-30 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2025-09-23 13:45 | jennifer.b.wright@ge.com
AP-0621-1-5 | Migrate Craft/Repairs Exams into Xyleme |  | AP-0625 | Migrate Craft/Repairs Exams into XylemeAP-0625 | AP-0621-1 | AP-0622 | 2 | 5 | 0 | 1 | harry.hanson@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Includes review of exam content (i.e. good question, etc.) | In Progress | TRUE |  | 2026-01-01 | 2026-12-31 | 2026-06-30 |  | 2026-01-01 | 2026-06-30 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2025-09-23 13:45 | jennifer.b.wright@ge.com
AP-0621-2 | Operationalize Exams in Xyleme |  | AP-0628 | Operationalize Exams in XylemeAP-0628 | AP-0621 | AP-0621 | 1 | 2 | 1 | 1 | jim.rosen@gevernova.com | Lee Fielding | jim.rosen@gevernova.com | Operational Simplification | Train instructors, roll out for all courses | Not Started |  |  | 2027-01-01 | 2027-07-05 |  |  | 2026-07-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 132d | [6 empty] | Yes | 2027-01-01 | 2027-07-05 | 2025-09-23 13:46 | jennifer.b.wright@ge.com
AP-0621-2-1 | Operationalize GT Exams in Xyleme |  | AP-0630 | Operationalize GT Exams in XylemeAP-0630 | AP-0621-2 | AP-0628 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Train instructors, roll out for all courses | Not Started | TRUE |  | 2027-01-01 | 2027-07-05 |  |  | 2026-07-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 132d | 380 | [5 empty] | Yes | 2027-01-01 | 2027-07-05 | 2025-09-23 13:46 | jennifer.b.wright@ge.com
AP-0621-2-2 | Operationalize ST Exams in Xyleme |  | AP-0631 | Operationalize ST Exams in XylemeAP-0631 | AP-0621-2 | AP-0628 | 2 | 2 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Train instructors, roll out for all courses | Not Started | TRUE |  | 2027-01-01 | 2027-07-05 |  |  | 2026-07-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 132d | 381 | [5 empty] | Yes | 2027-01-01 | 2027-07-05 | 2025-09-23 13:46 | jennifer.b.wright@ge.com
AP-0621-2-3 | Operationalize Ex Exams in Xyleme |  | AP-0632 | Operationalize Ex Exams in XylemeAP-0632 | AP-0621-2 | AP-0628 | 2 | 3 | 0 | 1 | Benjamin Smith |  | jim.rosen@gevernova.com | Operational Simplification | Train instructors, roll out for all courses | Not Started | TRUE |  | 2027-01-01 | 2027-07-05 |  |  | 2026-07-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 132d | 382 | [5 empty] | No | 2027-01-01 | 2027-07-05 | 2025-09-23 13:46 | jennifer.b.wright@ge.com
AP-0621-2-4 | Operationalize Aero Exams in Xyleme |  | AP-0633 | Operationalize Aero Exams in XylemeAP-0633 | AP-0621-2 | AP-0628 | 2 | 4 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Train instructors, roll out for all courses | Not Started | TRUE |  | 2027-01-01 | 2027-07-05 |  |  | 2026-07-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 132d | 383 | [5 empty] | Yes | 2027-01-01 | 2027-07-05 | 2025-09-23 13:46 | jennifer.b.wright@ge.com
AP-0621-2-5 | Operationalize Craft/Repairs Exams in Xyleme |  | AP-0629 | Operationalize Craft/Repairs Exams in XylemeAP-0629 | AP-0621-2 | AP-0628 | 2 | 5 | 0 | 1 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification | Train instructors, roll out for all courses | Not Started | TRUE |  | 2027-01-01 | 2027-07-05 |  |  | 2026-07-01 | 2026-12-31 | Delivery Internal | Craft FE OSS |  |  | Other |  |  |  | 132d | 384 | [5 empty] | Yes | 2027-01-01 | 2027-07-05 | 2025-09-23 13:46 | jennifer.b.wright@ge.com
AP-0638 | Kahuna Competency Framework Document and Best Practices for Competency Map Creation |  | AP-0638 | Kahuna Competency Framework Document and Best Practices for Competency Map CreationAP-0638 | #INVALID COLUMN VALUE | Top | 0 | 121 | 0 | 0 | kelly.kirby@gevernova.com | Aaron Hayes, ankita.gupta@gevernova.com, Benali Salim Messekine, David Ramey, Julieta Ponce, Luca Martino, Tamara Biediger | michele.alcantar@gevernova.com | Competencies | Develop a Competency Framework document to define a standard approach to Competency Management at OFS. Develop a supporting document detailing the process & procedure for building new competency maps i.e. implementation guide. | Complete |  | On Track | 2025-10-01 | 2025-10-31 |  |  | 2025-10-01 | 2025-10-31 | Internal Programs & Competency | [6 empty] | https://gevernova.ent.box.com/file/2030185960561 | 23d | [6 empty] | No | 2025-10-01 | 2025-10-31 | 2025-10-07 07:29 | jennifer.b.wright@ge.com
AP-0639 | Field Employee Mentorship Program |  | AP-0639 | Field Employee Mentorship ProgramAP-0639 | #INVALID COLUMN VALUE | Top | 0 | 122 | 0 | 0 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Programs | Create a mentoring program suitable for all field employees, independently from their business. | Complete |  | On Track | 2025-11-01 | 2026-04-30 |  |  | 2025-11-01 | 2026-03-31 | Internal Programs & Competency | Craft EHS FE OSS |  |  | Intake Review | luca.martino@gevernova.com | 07Oct25-Created from Intake Request # 14481920998. 09Mar26-Delay to April to implement new TDM communication/involvement approach | https://gevernova.ent.box.com/file/2213534315050 | 130d | [6 empty] | No | 2025-11-01 | 2026-04-30 | 2025-10-07 10:06 | jennifer.b.wright@ge.com
AP-0659 | Consolidate HLC Facilities Maint & Tech Trng Support Request Workflows |  | AP-0659 | Consolidate HLC Facilities Maint & Tech Trng Support Request WorkflowsAP-0659 | #INVALID COLUMN VALUE | Top | 0 | 123 | 0 | 0 | daniel.barrera1@gevernova.com | andrew.ruch@gevernova.com, andrew.samples@gevernova.com, Jennifer Wright, Stephen Urban | philip.ganssmann@gevernova.com | Operational Simplification | Consolidate existing HLC Facilities Maintenance Request and Technical Training Support Request workflows into 1 request form with relevant routing. Confirm what types of requests should be included & how they are routed. Include reporting for metrics for processing/close-out time. | Complete |  | On Track | 2026-01-01 | 2026-05-29 |  |  | 2026-01-01 | 2026-03-31 | Customer Delivery Internal Ops |  | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 30Jan26-Switched to Daniel as lead & Jen as assist 20Feb26-Moved to May due to other priorities & workload | https://gevernova.box.com/s/rcdqcc0uyxlz1hzobsz7aj3teu4rewjc | 107d |  |  |  |  | TRUE |  | No | 2026-01-01 | 2026-05-29 | 2025-10-31 09:27 | jennifer.b.wright@ge.com
AP-0661 | Updating hydraulic bolting curriculum |  | AP-0661 | Updating hydraulic bolting curriculumAP-0661 | #INVALID COLUMN VALUE | Top | 0 | 124 | 0 | 0 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Add new bolting presentation/ discussion/ documentation to bolting lab in Craft ELT program. In addition, provide material to Xyleme team to create a module which can be added to regional bolting training programs (FC.011 Advanced bolting theory & FC-298005 Bolting Mentor Program). Ensure loading into Xyleme is complete before closing this. | Complete |  | On Track | 2025-11-04 | 2026-03-31 |  |  | 2025-11-04 | 2025-12-31 | Delivery Internal | Craft |  |  | Intake Review | Alan Carruth | 04Nov5-Created from Intake Request # 14112830622. 7Jan26-Moved to end of Jan since Harry is out this week 27Jan26-Moved to Feb due to remaining gaps/questions for tests 26Fen260Moved to March due to new content received | https://gevernova.ent.box.com/file/2176353616720 | 106d | [6 empty] | Yes | 2025-11-04 | 2026-03-31 | 2025-11-04 13:42 | jennifer.b.wright@ge.com
AP-0662 | Outage Manager New Hire Curriculum |  | AP-0662 | Outage Manager New Hire CurriculumAP-0662 | #INVALID COLUMN VALUE | Top | 0 | 125 | 1 | 0 | benalisalim.messekine@gevernova.com | howayda.sabrymaher@gevernova.com, tamara.biediger@gevernova.com | michele.alcantar@gevernova.com | Programs | Create an online Program with a list of courses, technical & soft skills to provide a basic knowledge for new OMs. If any of them need further training, they can be part of FEP-A or Crosstraining classes (ST to GT or viceversa). New material development should not be needed. Include content regarding differences for GE vs. Alstom fleet & how it impacts their planning, outage delivery, etc. Also coordinating with Leadership Training to avoid duplicate. Target delivery after August FE Conference | In Progress |  |  | 2025-11-01 | 2026-09-30 | 2026-06-30 |  | 2025-11-04 | 2026-06-30 | Internal Programs & Competency |  |  |  | Intake Review | howayda.sabrymaher@gevernova.com, Klaus Hinteregger | 04Nov5-Created from Intake Request # 14583537968. 13Apr26-Added sub-tasks and updated dates to include pilot delivery in August |  | 239d | [6 empty] | No | 2025-11-01 | 2026-09-30 | 2025-11-04 13:48 | jennifer.b.wright@ge.com
AP-0662-1 | Develop Outage Mgr New Hire Course Materials & Delivery Approach |  | AP-0874 | Develop Outage Mgr New Hire Course Materials & Delivery ApproachAP-0874 | AP-0662 | AP-0662 | 1 | 1 | 0 | 1 | benalisalim.messekine@gevernova.com | howayda.sabrymaher@gevernova.com, tamara.biediger@gevernova.com | michele.alcantar@gevernova.com | Programs | 1.Develop Standard materials 2.Identify Pre-requisite courses 3.Define Target Instructor qualifications/expertise 4.Confirm budget/cost structure 5.Confirm scheduling approach (through Andrew’s team?) | In Progress | TRUE |  | 2025-11-01 | 2026-06-30 |  |  | 2025-11-01 | 2026-06-30 | [8 empty] | 173d |  |  | TRUE |  |  |  | No | 2025-11-01 | 2026-06-30 | 2026-04-13 09:54 | jennifer.b.wright@gevernova.com
AP-0662-2 | Load Outage Mgr New Hire course into our relevant systems |  | AP-0875 | Load Outage Mgr New Hire course into our relevant systemsAP-0875 | AP-0662 | AP-0662 | 1 | 2 | 0 | 1 | benalisalim.messekine@gevernova.com | howayda.sabrymaher@gevernova.com, tamara.biediger@gevernova.com | michele.alcantar@gevernova.com | Programs | 1.Course outline in MM (will feed to UDC & Xyleme) 2.Course Schedule Template loaded into UDC (work with Scheduler) (if applicable) 3.Course Materials loaded in shared Box (may add to Xyleme later) | Not Started | TRUE |  | 2026-07-01 | 2026-07-31 |  |  | 2026-07-01 | 2026-07-31 | [8 empty] | 23d |  |  |  | TRUE |  |  | No | 2026-07-01 | 2026-07-31 | 2026-04-13 09:54 | jennifer.b.wright@gevernova.com
AP-0662-3 | Deliver Outage Mgr New Hire Pilot session |  | AP-0873 | Deliver Outage Mgr New Hire Pilot sessionAP-0873 | AP-0662 | AP-0662 | 1 | 3 | 0 | 1 | benalisalim.messekine@gevernova.com | howayda.sabrymaher@gevernova.com, tamara.biediger@gevernova.com | michele.alcantar@gevernova.com | Programs | Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2026-08-01 | 2026-09-30 |  |  | 2026-08-01 | 2026-09-30 | [8 empty] | 44d | [6 empty] | No | 2026-08-01 | 2026-09-30 | 2026-04-13 09:54 | jennifer.b.wright@gevernova.com
AP-0691 | HLC Crane Support Processes |  | AP-0691 | HLC Crane Support ProcessesAP-0691 | #INVALID COLUMN VALUE | Top | 0 | 126 | 1 | 0 | andrew.samples@gevernova.com | andrew.ruch@gevernova.com, Jennifer Wright | philip.ganssmann@gevernova.com | Operational Simplification |  | In Progress |  | On Track | 2026-01-01 | 2026-10-30 |  |  | 2026-01-01 | 2026-10-30 |  |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback | n/a-parent row | 217d | [6 empty] | No | 2026-01-01 | 2026-10-30 | 2025-11-07 09:32 | jennifer.b.wright@ge.com
AP-0691-1 | Analysis of Crane Support Capacity Needs |  | AP-0692 | Analysis of Crane Support Capacity NeedsAP-0692 | AP-0691 | AP-0691 | 1 | 1 | 0 | 1 | andrew.samples@gevernova.com |  | philip.ganssmann@gevernova.com | Operational Simplification | Verify if we have enough crane support resources to meet the typical crane demand throughout the year | Complete |  | On Track | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 |  |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable | cathal.mcginley@gevernova.com |  | https://gevernova.ent.box.com/file/2166757209261 | 64d | [6 empty] | No | 2026-01-01 | 2026-03-31 | 2025-11-07 09:34 | jennifer.b.wright@ge.com
AP-0691-2 | Handling Shared Crane Support |  | AP-0693 | Handling Shared Crane SupportAP-0693 | AP-0691 | AP-0691 | 1 | 2 | 0 | 1 | andrew.samples@gevernova.com |  | philip.ganssmann@gevernova.com | Operational Simplification | Develop process for handling shared crane support resources on a given day (i.e. how much notice needed, handling conflicts, etc.) | Cancelled |  | Not Started | 2026-03-01 | 2026-05-29 |  |  | 2026-03-01 | 2026-05-29 |  |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable | cathal.mcginley@gevernova.com | 11May26-Cancelled - already addressed by hiring new crane operators. Will focus on next sub task |  | 66d |  |  |  |  | TRUE |  | No | 2026-03-01 | 2026-05-29 | 2025-11-07 09:48 | jennifer.b.wright@ge.com
AP-0691-3 | Crane Support Forecast & Scheduling Process |  | AP-0694 | Crane Support Forecast & Scheduling ProcessAP-0694 | AP-0691 | AP-0691 | 1 | 3 | 0 | 1 | andrew.samples@gevernova.com | andrew.ruch@gevernova.com, Jennifer Wright | philip.ganssmann@gevernova.com | Operational Simplification | Develop robust crane support forecast & scheduling process, leveraging UDC system | Not Started |  | Not Started | 2026-05-01 | 2026-10-30 |  |  | 2026-05-01 | 2026-10-30 |  |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable | cathal.mcginley@gevernova.com |  |  | 131d | [6 empty] | No | 2026-05-01 | 2026-10-30 | 2025-11-07 09:48 | jennifer.b.wright@ge.com
AP-0696 | Dashboard for EU Legislative Training |  | AP-0696 | Dashboard for EU Legislative TrainingAP-0696 | #INVALID COLUMN VALUE | Top | 0 | 127 | 0 | 0 | iuliia.zgonnik@gevernova.com | andrew.ruch@gevernova.com, daniel.barrera1@gevernova.com, Jennifer Wright, Sian La-Borde | philip.ganssmann@gevernova.com | Operational Simplification | Develop dashboard for summary views of EU legislative trainings, dates, volume, students trained, etc. Additionally, show key metrics around this training process (i.e. OTD and short cycle requests, etc.) | On Hold |  | Delayed | 2026-01-01 | 2026-06-30 | 2026-03-31 |  | 2026-01-01 | 2026-03-31 | Internal Ops |  | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 19Mar26-Moved to June 2026 as a rough estimate to allow enough time for the SMax fields update to be implemented and for Daniel to support in the context of his other active projects |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-11-14 09:45 | jennifer.b.wright@ge.com
AP-0697 | Build Process for Identifying & Scheduling extra prep time for customer instructor Visas |  | AP-0697 | Build Process for Identifying & Scheduling extra prep time for customer instructor VisasAP-0697 | #INVALID COLUMN VALUE | Top | 0 | 128 | 0 | 0 | nelsa1.bernal@gevernova.com | andrew.ruch@gevernova.com, Jennifer Wright, philip.ganssmann@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Some visa’s require additional travel time to go to the embassy to apply for and/or pick up the visa, etc. Also may require the Instructor to turn in their passport (so they can’t do other travel in the meantime) Build process for connecting with Immigration to identify which instructors will need this time, will to give up passport etc. so it can be incorporated into their schedule accordingly. Goal = Use existing weekly call with Immigration & build a SMax report/view with Immigration Request data to show upcoming potential needs for discussion with Immigration. | In Progress |  | On Track | 2026-01-01 | 2026-06-30 | 2026-05-29 | TRUE | 2026-01-01 | 2026-03-31 | Customer Delivery Ops |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback 09Mar26-Moved to April. Waiting on UDC to implement the new immigration activity types 08Apr26-Need to determine UDC team timeline for new "no passport" activities 15Apr26-Moved to May to accommodate UDC implementation of "no passport" activities 26May26-Moved to June to allow full alignment on process & roles now that tools are in place |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-11-17 09:54 | jennifer.b.wright@ge.com
AP-0698 | Craft I&C Skills Training |  | AP-0698 | Craft I&C Skills TrainingAP-0698 | #INVALID COLUMN VALUE | Top | 0 | 129 | 1 | 0 | luca.martino@gevernova.com | Harry Hanson, Mouna Boucherka | michele.alcantar@gevernova.com | Content Development | Build in-house capability to deliver Craft I&C Skills Training. | In Progress |  |  | 2025-12-01 | 2026-10-30 |  |  | 2025-12-01 | 2026-08-31 | Delivery Internal Ops Programs & Competency | Craft |  |  | Intake Review | mouna.boucherka@gevernova.com | 18Nov5-Created from Intake Request # 14748597488. 13Jan26-Added new standard Content Development sub tasks |  | 240d | [6 empty] | No | 2025-12-01 | 2026-10-30 | 2025-11-18 09:39 | jennifer.b.wright@ge.com
AP-0698-1 | Identify which Craft I&C Competencies can be delivered via training vs. OJT/other |  | AP-0753 | Identify which Craft I&C Competencies can be delivered via training vs. OJT/otherAP-0753 | AP-0698 | AP-0698 | 1 | 1 | 0 | 1 | luca.martino@gevernova.com | Harry Hanson, Mouna Boucherka | michele.alcantar@gevernova.com | Content Development | -define content of internal training according to job descriptions, competency mapping | In Progress | TRUE | At Risk | 2025-12-01 | 2026-05-29 | 2026-03-31 |  |  |  | Delivery Internal Ops Programs & Competency | Craft |  |  | Intake Review |  | 09Feb26-Delay until March to allow time to build SME team and review with other regions 02Apr26-moved to May due to delays with SME reveiw |  | 130d |  |  |  |  | TRUE |  | No | 2025-12-01 | 2026-05-29 | 2026-01-13 15:33 | jennifer.b.wright@ge.com
AP-0698-2 | Ensure Craft I&C competencies are adjusted in Kahuna as needed |  | AP-0754 | Ensure Craft I&C competencies are adjusted in Kahuna as neededAP-0754 | AP-0698 | AP-0698 | 1 | 2 | 0 | 1 | luca.martino@gevernova.com | Harry Hanson, Mouna Boucherka | michele.alcantar@gevernova.com | Content Development | -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to -adjust competency mapping as needed | Not Started | TRUE |  | 2026-06-01 | 2026-07-31 | 2026-04-30 |  |  |  | Delivery Internal Ops Programs & Competency | Craft |  |  | Intake Review |  | 02Apr26-moved to July due to above item delayed |  | 45d |  | TRUE |  | TRUE |  |  | No | 2026-06-01 | 2026-07-31 | 2026-01-13 15:33 | jennifer.b.wright@ge.com
AP-0698-3 | Develop Craft I&C Course Materials & Identify Target Instructor(s) |  | AP-0755 | Develop Craft I&C Course Materials & Identify Target Instructor(s)AP-0755 | AP-0698 | AP-0698 | 1 | 3 | 0 | 1 | luca.martino@gevernova.com | Harry Hanson, Mouna Boucherka | michele.alcantar@gevernova.com | Content Development | -collect training content from vendors on all regions -develop content | In Progress | TRUE |  | 2026-03-01 | 2026-06-30 |  |  |  |  | Delivery Internal Ops Programs & Competency | Craft |  |  | Intake Review |  |  |  | 88d |  |  | TRUE |  |  |  | No | 2026-03-01 | 2026-06-30 | 2026-01-13 15:33 | jennifer.b.wright@ge.com
AP-0698-4 | Load Craft I&C course into our relevant systems |  | AP-0751 | Load Craft I&C course into our relevant systemsAP-0751 | AP-0698 | AP-0698 | 1 | 4 | 0 | 1 | luca.martino@gevernova.com | Harry Hanson, Mouna Boucherka | michele.alcantar@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-07-01 | 2026-07-31 |  |  |  |  | Delivery Internal Ops Programs & Competency | Craft |  |  | Intake Review |  |  |  | 23d |  |  |  | TRUE |  |  | No | 2026-07-01 | 2026-07-31 | 2026-01-13 15:33 | jennifer.b.wright@ge.com
AP-0698-5 | Deliver Craft I&C Pilot session |  | AP-0752 | Deliver Craft I&C Pilot sessionAP-0752 | AP-0698 | AP-0698 | 1 | 5 | 0 | 1 | luca.martino@gevernova.com | Harry Hanson, Mouna Boucherka | michele.alcantar@gevernova.com | Content Development | -deliver pilot September 2026 in MEA Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2026-10-30 | 2026-10-30 |  |  |  |  | Delivery Internal Ops Programs & Competency | Craft |  |  | Intake Review |  |  |  | 1d | [6 empty] | No | 2026-10-30 | 2026-10-30 | 2026-01-13 15:33 | jennifer.b.wright@ge.com
AP-0699 | Update e-tools Training |  | AP-0699 | Update e-tools TrainingAP-0699 | #INVALID COLUMN VALUE | Top | 0 | 130 | 0 | 0 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | E-tools training needs to be updated currently has a lot of obsolete material | Complete |  | On Track | 2026-01-01 | 2026-03-31 |  |  | 2026-01-01 | 2026-03-31 | Delivery Internal | FE |  |  | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback | https://gevernova.ent.box.com/file/2176348151352 | 64d | [6 empty] | Yes | 2026-01-01 | 2026-03-31 | 2025-11-18 14:22 | jennifer.b.wright@ge.com
AP-0700 | Improve Tooling Alignment |  | AP-0700 | Improve Tooling AlignmentAP-0700 | #INVALID COLUMN VALUE | Top | 0 | 131 | 1 | 0 | andrew.samples@gevernova.com | Cathal McGinley, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Better alignment with tooling so we don’t have obsolete tools or get missed when there are modifications | Complete |  | On Track | 2026-01-01 | 2026-03-31 |  |  |  |  | Delivery Ops |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback | https://gevernova.ent.box.com/file/2166855918650 | 64d | [6 empty] | No | 2026-01-01 | 2026-03-31 | 2025-11-18 14:25 | jennifer.b.wright@ge.com
AP-0700-1 | Investigate Tooling Alignment Cause & potential Solutions |  | AP-0702 | Investigate Tooling Alignment Cause & potential SolutionsAP-0702 | AP-0700 | AP-0700 | 1 | 1 | 0 | 1 | cathal.mcginley@gevernova.com | andrew.samples@gevernova.com, philip.ganssmann@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Consider using ITM Database from the Tooling Center | Complete | TRUE | On Track | 2026-01-01 | 2026-02-27 |  |  | 2026-01-01 | 2026-02-27 |  |  | OFS-Quality-Customer Escapes-Escapes | Q | Roundtable |  | 25Feb26-no report-out needed. Will report on full project together. | n/a-report at parent level | 42d | [6 empty] | No | 2026-01-01 | 2026-02-27 | 2025-11-18 14:43 | jennifer.b.wright@ge.com
AP-0700-2 | Implement Tooling Alignment Solution |  | AP-0703 | Implement Tooling Alignment SolutionAP-0703 | AP-0700 | AP-0700 | 1 | 2 | 0 | 1 | andrew.samples@gevernova.com | Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Finish TBD, based on solution decision | Complete | TRUE | On Track | 2026-03-01 | 2026-03-31 |  |  | 2026-03-01 | [5 empty] | Roundtable |  | 23Feb26-Set March date as placeholder 26Feb26-Solution confirmed | n/a-report at parent level | 23d | [6 empty] | No | 2026-03-01 | 2026-03-31 | 2025-11-18 14:47 | jennifer.b.wright@ge.com
AP-0701 | Chain Fall Compliance |  | AP-0701 | Chain Fall ComplianceAP-0701 | #INVALID COLUMN VALUE | Top | 0 | 132 | 1 | 0 | andrew.samples@gevernova.com | Cathal McGinley | philip.ganssmann@gevernova.com | Operational Simplification | Still using non-compliant chain falls - do not have safety hook | In Progress |  | Delayed | 2026-01-01 | 2026-10-30 |  |  |  |  | Delivery Ops |  | OFS-Safety-EHS I&I Rate-I&I Rate OFS-Safety-EHS I&I Rate-Life Saving Rules Effectiveness Score | S | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback | n/a-parent row | 217d | [6 empty] | No | 2026-01-01 | 2026-10-30 | 2025-11-18 14:40 | jennifer.b.wright@ge.com
AP-0701-1 | Investigate Chain Fall Issue & potential Solutions |  | AP-0704 | Investigate Chain Fall Issue & potential SolutionsAP-0704 | AP-0701 | AP-0701 | 1 | 1 | 0 | 1 | andrew.samples@gevernova.com | Cathal McGinley | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2026-01-01 | 2026-04-30 | 2026-03-31 |  | 2026-01-01 | 2026-02-27 |  |  | OFS-Safety-EHS I&I Rate-I&I Rate OFS-Safety-EHS I&I Rate-Life Saving Rules Effectiveness Score | S | Roundtable |  | 25Feb26-Moved to March to allow time for Andrew to coordinate full scope of needed improvements with Tooling Center. 17Mar26-Moved to April for more time to get effective partnership (guidance) from the tooling team | https://gevernova.ent.box.com/file/2196710726140 | 86d | [6 empty] | No | 2026-01-01 | 2026-04-30 | 2025-11-18 14:51 | jennifer.b.wright@ge.com
AP-0701-2 | Implement Chain Fall Solution |  | AP-0705 | Implement Chain Fall SolutionAP-0705 | AP-0701 | AP-0701 | 1 | 2 | 0 | 1 | andrew.samples@gevernova.com |  | philip.ganssmann@gevernova.com | Operational Simplification | Ensure solution is implemented in all learning centers (HLC, BLC, KLC) | Not Started |  | Not Started | 2026-03-01 | 2026-10-30 | 2026-05-26 |  | 2026-03-01 | [5 empty] | Roundtable |  | 23Feb26-Set March date as placeholder, actual timing TBD based on results from previous sub-tasks 25Feb26-Moved to May to allow time to implement improvements prior to summer training outages |  | 176d | [6 empty] | No | 2026-03-01 | 2026-10-30 | 2025-11-18 14:51 | jennifer.b.wright@ge.com
AP-0706 | Launch State of Art Seminar for Steam Turbine |  | AP-0706 | Launch State of Art Seminar for Steam TurbineAP-0706 | #INVALID COLUMN VALUE | Top | 0 | 133 | 1 | 0 | nimra.kazmi1@gevernova.com | pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started |  | Delayed | 2026-09-01 | 2027-04-30 | 2026-09-30 |  | 2026-01-01 | 2026-09-30 | Delivery Internal Ops | FE RM |  |  | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback 11May26-Moved to focus for Summer 2027 due to other priorities for Summer 2026. Will assign to TDM as Lead with PLL as support. 13May26-Per discussion with Leo, moved to target delivery in Feb 2027 |  | 174d | [6 empty] | No | 2026-09-01 | 2027-04-30 | 2025-11-18 15:34 | jennifer.b.wright@ge.com
AP-0706-1 | Plan ST Seminar |  | AP-0711 | Plan ST SeminarAP-0711 | AP-0706 | AP-0706 | 1 | 1 | 0 | 1 | nimra.kazmi1@gevernova.com | pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE | Delayed | 2026-09-01 | 2027-01-27 | 2026-05-29 |  | 2026-01-01 | 2026-05-29 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 107d | [6 empty] | No | 2026-09-01 | 2027-01-27 | 2025-11-18 15:38 | jennifer.b.wright@ge.com
AP-0706-2 | Execute ST Seminar |  | AP-0710 | Execute ST SeminarAP-0710 | AP-0706 | AP-0706 | 1 | 2 | 0 | 1 | nimra.kazmi1@gevernova.com | pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE | Delayed | 2027-02-01 | 2027-02-26 | 2026-07-31 |  | 2026-06-01 | 2026-07-31 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 20d | [6 empty] | No | 2027-02-01 | 2027-02-26 | 2025-11-18 15:38 | jennifer.b.wright@ge.com
AP-0706-3 | Review Feedback & Sustainment for ST Seminar |  | AP-0709 | Review Feedback & Sustainment for ST SeminarAP-0709 | AP-0706 | AP-0706 | 1 | 3 | 0 | 1 | nimra.kazmi1@gevernova.com | pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE | Delayed | 2027-03-01 | 2027-04-30 | 2026-09-30 |  | 2026-08-01 | 2026-09-30 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 45d | [6 empty] | No | 2027-03-01 | 2027-04-30 | 2025-11-18 15:38 | jennifer.b.wright@ge.com
AP-0707 | Launch State of Art Seminar for Gas Turbine |  | AP-0707 | Launch State of Art Seminar for Gas TurbineAP-0707 | #INVALID COLUMN VALUE | Top | 0 | 134 | 1 | 0 | paula.pedrozanino@gevernova.com | Sherif Khalifa | jim.rosen@gevernova.com | Content Quality & Improvements |  | In Progress |  | On Track | 2026-01-01 | 2026-07-31 |  |  | 2026-01-01 | 2026-09-30 | Delivery Internal Ops | FE RM |  |  | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback 11May26-Shifted to Paula as Lead with Sherif as Assist & updated dates per current plan |  | 152d |  |  |  | TRUE |  |  | No | 2026-01-01 | 2026-07-31 | 2025-11-18 15:35 | jennifer.b.wright@ge.com
AP-0707-1 | Plan GT Seminar |  | AP-0714 | Plan GT SeminarAP-0714 | AP-0707 | AP-0707 | 1 | 1 | 0 | 1 | paula.pedrozanino@gevernova.com | Sherif Khalifa | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE | On Track | 2026-01-01 | 2026-05-29 |  |  | 2026-01-01 | 2026-05-29 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 107d |  |  |  |  | TRUE |  | No | 2026-01-01 | 2026-05-29 | 2025-11-18 15:41 | jennifer.b.wright@ge.com
AP-0707-2 | Execute GT Seminar |  | AP-0717 | Execute GT SeminarAP-0717 | AP-0707 | AP-0707 | 1 | 2 | 0 | 1 | paula.pedrozanino@gevernova.com | Sherif Khalifa | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-06-01 | 2026-06-30 |  |  | 2026-06-01 | 2026-07-31 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 22d |  | TRUE | TRUE |  |  |  | No | 2026-06-01 | 2026-06-30 | 2025-11-18 15:41 | jennifer.b.wright@ge.com
AP-0707-3 | Review Feedback & Sustainment for GT Seminar |  | AP-0716 | Review Feedback & Sustainment for GT SeminarAP-0716 | AP-0707 | AP-0707 | 1 | 3 | 0 | 1 | paula.pedrozanino@gevernova.com | Sherif Khalifa | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-07-01 | 2026-07-31 |  |  | 2026-08-01 | 2026-09-30 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 23d |  |  |  | TRUE |  |  | No | 2026-07-01 | 2026-07-31 | 2025-11-18 15:41 | jennifer.b.wright@ge.com
AP-0708 | Launch State of Art Seminar for Aero |  | AP-0708 | Launch State of Art Seminar for AeroAP-0708 | #INVALID COLUMN VALUE | Top | 0 | 135 | 1 | 0 | TDM TBD | gregoryd.walker@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started |  | Delayed | 2027-01-01 | 2027-09-30 | 2026-09-30 |  | 2026-01-01 | 2026-09-30 | Delivery Internal Ops | FE RM |  |  | Roundtable | cathal.mcginley@gevernova.com | Added from Oct 2025 Instructor Round Tables feedback 11May26-Moved to focus for Summer 2027 due to other priorities for Summer 2026. Will assign to TDM as Lead with PLL as support. |  | 195d | [6 empty] | No | 2027-01-01 | 2027-09-30 | 2025-11-18 15:36 | jennifer.b.wright@ge.com
AP-0708-1 | Plan Aero Seminar |  | AP-0712 | Plan Aero SeminarAP-0712 | AP-0708 | AP-0708 | 1 | 1 | 0 | 1 | TDM TBD | gregoryd.walker@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE | Delayed | 2027-01-01 | 2027-05-31 | 2026-05-29 |  | 2026-01-01 | 2026-05-29 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 107d | [6 empty] | No | 2027-01-01 | 2027-05-31 | 2025-11-18 15:41 | jennifer.b.wright@ge.com
AP-0708-2 | Execute Aero Seminar |  | AP-0713 | Execute Aero SeminarAP-0713 | AP-0708 | AP-0708 | 1 | 2 | 0 | 1 | TDM TBD | gregoryd.walker@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE | Delayed | 2027-06-01 | 2027-07-30 | 2026-07-31 |  | 2026-06-01 | 2026-07-31 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 44d |  | TRUE |  |  |  |  | No | 2027-06-01 | 2027-07-30 | 2025-11-18 15:41 | jennifer.b.wright@ge.com
AP-0708-3 | Review Feedback & Sustainment for Aero Seminar |  | AP-0715 | Review Feedback & Sustainment for Aero SeminarAP-0715 | AP-0708 | AP-0708 | 1 | 3 | 0 | 1 | TDM TBD | gregoryd.walker@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE | Delayed | 2027-08-01 | 2027-09-30 | 2026-09-30 |  | 2026-08-01 | 2026-09-30 | Delivery Internal Ops | FE RM |  |  | Roundtable |  |  | n/a-report at parent level | 45d | [6 empty] | No | 2027-08-01 | 2027-09-30 | 2025-11-18 15:41 | jennifer.b.wright@ge.com
AP-0718 | Translate Preventing & Resolving Stuck Bolts Training |  | AP-0718 | Translate Preventing & Resolving Stuck Bolts TrainingAP-0718 | #INVALID COLUMN VALUE | Top | 0 | 136 | 0 | 0 | konstantina.georga@gevernova.com |  | philip.ganssmann@gevernova.com | Content Quality & Improvements | Translate CRSE-FC-300054 Preventing and Resolving Stuck Bolts to Croatian, German, Hungarian, Italian, Polish, Spanish, Turkish, Hebrew and assign to all EU OFS mechanics and SPVs in LMS, retrain annually | Complete |  | On Track | 2025-12-01 | 2026-02-23 |  |  | 2025-12-01 | 2026-01-30 | Internal Ops | Craft | OFS-Quality-Customer Escapes-Quality Severe Events (SE) | Q | Intake Review | beyza.yaver@gevernova.com | 02Dec25-Created from Intake Request # 14696030919. 22Jan26-This task will need to be shifted to February 2026 due to ongoing testing of the translated files. | https://gevernova.box.com/s/bja6wxnzh21w7xevj6gd7g5x73zi829w | 61d | [6 empty] | No | 2025-12-01 | 2026-02-23 | 2025-12-02 12:38 | jennifer.b.wright@ge.com
AP-073 | SME Response Time for Non-standard Inquiries | AP-073 | AP-0420 | SME Response Time for Non-standard InquiriesAP-0420 | #INVALID COLUMN VALUE | Top | 0 | 137 | 0 | 0 | jim.rosen@gevernova.com | Johann Josef Daxer, Philip Ganssmann | johann.daxer@gevernova.com | Operational Simplification | Develop process & agree on expectations for processing non-standard quote inquiries & escalation paths | Complete |  | On Track | 2024-10-01 | 2025-01-31 |  |  | 2024-10-01 | 2025-01-31 | Customer Delivery | [6 empty] | https://gevernova.box.com/s/pr52cc7xb3mkeq5g74hagnppile3ud7s | 89d | [6 empty] | Yes | 2024-10-01 | 2025-01-31 | 2024-12-16 09:28 | jennifer.b.wright@ge.com
AP-093 | Scheduling Tool Phase 1 Development | AP-093 | 56 | Scheduling Tool Phase 1 Development56 | #INVALID COLUMN VALUE | Top | 0 | 138 | 1 | 0 | andrew.ruch@gevernova.com | UDC-Team | philip.ganssmann@gevernova.com | Operational simplification |  | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Customer Ops | n/a | [5 empty] | https://gevernova.box.com/s/oa3i696xyhsc8zvg1wcziihkttmib417 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2024-11-13 07:42 | jennifer.b.wright@ge.com
AP-093 | User Interface design of OFS Scheduler | AP-093 | 57 | User Interface design of OFS Scheduler57 | AP-093 | AP-093 | 1 | 1 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Overall solution design | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Customer Ops | n/a | [5 empty] | Will be reported with AP-093 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-093-2 | Activity window Upper Layout & Bottom Layout |  | AP-0501 | Activity window Upper Layout & Bottom LayoutAP-0501 | AP-093 | AP-093 | 1 | 2 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Activity Window Module | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [6 empty] | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2025-03-31 15:54 | andrew.ruch@ge.com
AP-093-3 | Catalogue Modules - Courses, Instructors, Rooms, Tooling, Equipment, Vendors, Calendars |  | AP-0498 | Catalogue Modules - Courses, Instructors, Rooms, Tooling, Equipment, Vendors, CalendarsAP-0498 | AP-093 | AP-093 | 1 | 3 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Catalogue Module - Courses, Instructors, Rooms, Tooling, Equipment, Vendors, Calendars | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-094 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2025-03-31 14:03 | andrew.ruch@ge.com
AP-093-4 | Template list user interface |  | AP-0500 | Template list user interfaceAP-0500 | AP-093 | AP-093 | 1 | 4 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Project Module | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-094 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2025-03-31 14:03 | andrew.ruch@ge.com
AP-093-5 | Custom Course demand |  | AP-0499 | Custom Course demandAP-0499 | AP-093 | AP-093 | 1 | 5 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Project Module | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-095 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2025-03-31 14:03 | andrew.ruch@ge.com
AP-093-6 | Tool Security & Access management |  | AP-0503 | Tool Security & Access managementAP-0503 | AP-093 | AP-093 | 1 | 6 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Access management | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [6 empty] | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2025-03-31 15:54 | andrew.ruch@ge.com
AP-093-7 | Schedule Engine logic design & development |  | AP-0502 | Schedule Engine logic design & developmentAP-0502 | AP-093 | AP-093 | 1 | 7 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Scheduling Engine | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [6 empty] | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2025-03-31 15:54 | andrew.ruch@ge.com
AP-094 | Database Structure | AP-094 | 58 | Database Structure58 | AP-093 | AP-093 | 1 | 8 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Overall solution design | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-093 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-095 | Customer demand request form | AP-095 | 59 | Customer demand request form59 | AP-093 | AP-093 | 1 | 9 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Project Module | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-093 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-096 | Class List user interface | AP-096 | 60 | Class List user interface60 | AP-093 | AP-093 | 1 | 10 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Project Module | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-093 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-098 | Project Auto creation | AP-098 | 61 | Project Auto creation61 | AP-093 | AP-093 | 1 | 11 | 0 | 1 | andrew.ruch@gevernova.com | Jennifer Wright, marisol.guidry1@gevernova.com, nelsa.bernal@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Project Module | Complete |  |  | 2024-02-01 | 2025-02-14 |  |  | 2024-02-01 | 2025-02-14 | Ops | n/a | [5 empty] | Will be reported with AP-093 | 272d | [6 empty] | No | 2024-02-01 | 2025-02-14 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-111 | Legislative Training Tracking | AP-111 | 65 | Legislative Training Tracking65 | #INVALID COLUMN VALUE | Top | 0 | 139 | 0 | 0 | diana.torres1@gevernova.com | TDMs | philip.ganssmann@gevernova.com | Operational simplification | How to handle legislative training in the system and the different Country versions | Complete |  | On Track | 2024-02-01 | 2025-05-30 |  |  | 2024-02-01 | 2025-03-31 | Internal Ops | RM TDC |  |  |  |  | 3/28/24-extended to April to accommodate unanticiapted work to update all existing courses Dependancy on stakeholder to confirm accuracy of version and naming convention. Manual effort to update in LMS. 7/31/24-Moved to Oct to accommodate new changes (see slide) 10/21/24-Move to 2025 to allow more time to complete cleanup & additions | https://gevernova.ent.box.com/file/1444525606823 | 347d | [6 empty] | No | 2024-02-01 | 2025-05-30 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-113 | Tooling - Tech support | AP-113 | 66 | Tooling - Tech support66 | #INVALID COLUMN VALUE | Top | 0 | 140 | 1 | 0 | andrew.samples@gevernova.com | andrew.ruch@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification |  | Complete |  |  | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-04-01 | Delivery Ops | n/a | [5 empty] | n/a-parent row | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-113-1 | Define and implement process for utilization of Tooling - Tech support |  | AP-0453 | Define and implement process for utilization of Tooling - Tech supportAP-0453 | AP-113 | AP-113 | 1 | 1 | 0 | 1 | andrew.samples@gevernova.com | andrew.ruch@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | Delivery | n/a | [5 empty] | https://gevernova.ent.box.com/file/1813705079804 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2025-01-31 09:56 | philip.ganssmann@ge.com
AP-113-2 | Onboard and train Lab Technicians |  | AP-0258 | Onboard and train Lab TechniciansAP-0258 | AP-113 | AP-113 | 1 | 2 | 0 | 1 | andrew.samples@gevernova.com | andrew.ruch@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Train and integrate new lab technicians into HLC operations | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-04-30 | Delivery | n/a | [5 empty] | https://gevernova.ent.box.com/file/1848502970310 | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-21 08:37 | jennifer.b.wright@ge.com
AP-121 | Working Instructions for content creation and update in LCMS | AP-121 | 67 | Working Instructions for content creation and update in LCMS67 | #INVALID COLUMN VALUE | Top | 0 | 141 | 0 | 0 | lee.s.fielding@gevernova.com | PLLs | philip.ganssmann@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2024-12-01 | 2025-02-28 |  |  | 2024-12-01 | 2025-02-28 | Delivery Internal Ops P&C | n/a |  |  |  |  | Creation / review / Final BOXES? 2024-05-27 waiting on final LCMS decission 2024-06-27: Awaiting on LCMS decision/set-up - moved to Oct to align with LCMS implementation schedule 2024-09-05 - adjusted schedule to continue into 2025 | https://gevernova.box.com/s/9eheigd8pk2w8h7wtw8yczxs4exougsn | 66d | [6 empty] | No | 2024-12-01 | 2025-02-28 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-122 | Develop Content Structure/Course Setup/standard templates in LCMS | AP-122 | AP-0409 | Develop Content Structure/Course Setup/standard templates in LCMSAP-0409 | #INVALID COLUMN VALUE | Top | 0 | 142 | 0 | 0 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex | philip.ganssmann@gevernova.com | Content Quality & Improvements | Includes standard template/output for printed ppt note pages for printed customer manuals | Complete |  | On Track | 2024-12-01 | 2025-03-31 |  |  | 2024-12-01 | 2025-01-31 | Delivery Ops | [5 empty] | Depends on timing of Xyleme "Create" training completion. 1/13/25-Moved to Feb completion due to Xyleme training schedule 02/25/2025: Moved to end of March as Xyleme publishing templates currently WIP with Xyleme. | https://gevernova.box.com/s/z7u84ag12pbnwnrvgjd509cnl3wwh1gw | 87d | [6 empty] | No | 2024-12-01 | 2025-03-31 | 2024-12-11 07:11 | jennifer.b.wright@ge.com
AP-126 | Modernization & LCMS implementation for "Big 6" courses | AP-126 | AP-0113 | Modernization & LCMS implementation for "Big 6" coursesAP-0113 | #INVALID COLUMN VALUE | Top | 0 | 143 | 1 | 0 | lee.s.fielding@gevernova.com | J. Rosen / PLLs | philip.ganssmann@gevernova.com | Content Quality & Improvements | GT Ops, GT Maint, ST Ops, ST Maint, EX2100e, GT ELT In conjunction with moving into Xyleme | In Progress |  |  | 2025-01-01 | 2028-12-29 |  |  | 2025-01-01 | 2025-03-31 | Delivery | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 2024-05-27 waiting on prottype development Complete in 2025 | n/a-parent row | 1043d | [6 empty] | No | 2025-01-01 | 2028-12-29 | 2024-11-18 07:18 | philip.ganssmann@ge.com
AP-126-1 | High-level analysis of course content/modules for Modernization/LCMS Implementation |  | AP-0275 | High-level analysis of course content/modules for Modernization/LCMS ImplementationAP-0275 | AP-126 | AP-126 | 1 | 1 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, Michele Alcantar, Pablo Schibli, sherif.khalifa@gevernova.com | philip.ganssmann@gevernova.com | Content Quality & Improvements | Do we have the content? What are the modules? What courses does each module apply to, where is there overlap? | Complete |  | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-01-31 | Delivery | n/a |  |  |  |  | 1/13/25-waiting on gathering current content for Big 6. moved to Feb completion 2/10/25-ST Ops expected to be available this week, believe ST Maint is available. Need timeline from Sherif for GT Ops & Maint. Then Lee & team can determine new target timeline for Analysis 2/25/25-Still waiting for some material, moved target completion from Feb to March 10Mar25-Made progress but still missing info, likely to move out, new date TBD 24Mar25-Move to April since still missing GT ELT content | https://gevernova.box.com/s/julxpbq6zw7q87o0p4eow9um0qxlljjn | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-21 10:43 | jennifer.b.wright@ge.com
AP-126-2 | Build Plan for completing high priority topics for each big 6 course for Modernization & LCMS Implementation |  | AP-0276 | Build Plan for completing high priority topics for each big 6 course for Modernization & LCMS ImplementationAP-0276 | AP-126 | AP-126 | 1 | 2 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex | philip.ganssmann@gevernova.com | Content Quality & Improvements | Define target completion dates for each course. Completion would be for high priority modules (3+ from analysis) Use standard assumptions for modules with no material Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | Complete |  | On Track | 2025-05-01 | 2025-05-29 |  |  | 2025-03-03 | 2025-03-31 | Delivery | n/a |  |  |  |  | 7May25-scope updated based on output from AP-126-1 | https://gevernova.box.com/s/wuwz82nvofwlzbbhcjefv1u202zg6vwv | 21d | 451 | [5 empty] | No | 2025-05-01 | 2025-05-29 | 2024-11-21 10:43 | jennifer.b.wright@ge.com
AP-126-3 | Publish EX2100e to LCMS |  | AP-0274 | Publish EX2100e to LCMSAP-0274 | AP-126 | AP-126 | 1 | 3 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, Michele Alcantar | philip.ganssmann@gevernova.com | Content Quality & Improvements | Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | Complete |  |  | 2025-05-30 | 2025-06-30 |  |  | 2025-04-01 |  | Delivery | n/a |  |  |  |  | End date TBD based on scope/output from AP-126-2 | https://gevernova.box.com/s/0hmoxco4pva9hauycoy1fq4ku02wjidp | 22d | 452 | [5 empty] | No | 2025-05-30 | 2025-06-30 | 2024-11-21 10:43 | jennifer.b.wright@ge.com
AP-126-4 | Publish GT Maint to LCMS |  | AP-0273 | Publish GT Maint to LCMSAP-0273 | AP-126 | AP-126 | 1 | 4 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, sherif.khalifa@gevernova.com | philip.ganssmann@gevernova.com | Content Quality & Improvements | Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | In Progress |  | Delayed | 2025-05-01 | 2026-12-31 | 2026-07-15 |  | 2025-05-01 | 2026-02-27 | Delivery | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 2026-FEB-06: In alignment with PG - moved out from Feb 27th 2026 till Jul 15th 2026 due to challenges receiving training material. Task ongoing. 2026-MAR-12: Current Finish moved out to Sep 25th 2026 due to lack of SME input and support. 2026-MAR-23: Current Finish moved to 31-Dec-2026 (speculation only) due to lack of content delivered from SME. |  | 436d | [6 empty] | No | 2025-05-01 | 2026-12-31 | 2024-11-21 10:43 | jennifer.b.wright@ge.com
AP-126-5 | Publish GT Ops to LCMS |  | AP-0271 | Publish GT Ops to LCMSAP-0271 | AP-126 | AP-126 | 1 | 5 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, sherif.khalifa@gevernova.com | philip.ganssmann@gevernova.com | Content Quality & Improvements | Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | Not Started |  |  | 2026-12-31 | 2027-12-31 |  |  |  |  | Delivery | n/a |  |  | Other |  | Timing TBD based on lessons from AP-126-4 2026-MAR-23: Start and Finish dates entered (speculation only) due to lack of content delivered from SME. |  | 262d | [6 empty] | No | 2026-12-31 | 2027-12-31 | 2024-11-21 10:43 | jennifer.b.wright@ge.com
AP-126-6 | Publish GT ELT to LCMS |  | AP-0571 | Publish GT ELT to LCMSAP-0571 | AP-126 | AP-126 | 1 | 6 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, sherif.khalifa@gevernova.com | philip.ganssmann@gevernova.com | Content Quality & Improvements | Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | Not Started |  |  | 2027-12-31 | 2028-12-29 | [8 empty] | Other |  | Timing TBD based on lessons from AP-126-4 2026-MAR-23: Speculated start and finish dates given. |  | 261d | [6 empty] | No | 2027-12-31 | 2028-12-29 | 2025-06-12 07:45 | jennifer.b.wright@ge.com
AP-126-7 | Publish ST Ops to LCMS |  | AP-0572 | Publish ST Ops to LCMSAP-0572 | AP-126 | AP-126 | 1 | 7 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, Pablo Schibli | philip.ganssmann@gevernova.com | Content Quality & Improvements | Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | Not Started |  |  | 2026-12-31 | 2028-06-30 | [8 empty] | Other |  | Timing TBD based on lessons from AP-126-4 2026-MAR-23: Start and Finish dates entered (speculation only) due to lack of content delivered from SME and GT-MM - GT-OP priorities. |  | 392d | [6 empty] | No | 2026-12-31 | 2028-06-30 | 2025-06-12 07:45 | jennifer.b.wright@ge.com
AP-126-8 | Publish ST Maint to LCMS |  | AP-0573 | Publish ST Maint to LCMSAP-0573 | AP-126 | AP-126 | 1 | 8 | 0 | 1 | lee.s.fielding@gevernova.com | Konstantina Georga, Laura Bettex, Pablo Schibli | philip.ganssmann@gevernova.com | Content Quality & Improvements | Schedule: https://app.smartsheet.com/reports/XrFhM5Qmx4H8P83qFH98Qh7FC627mJwf2W5r9XM1?view=gantt | In Progress |  |  | 2026-01-01 | 2028-06-30 | [8 empty] | Other |  | Timing TBD based on lessons from AP-126-4 2026-MAR-23: Start and Finish dates entered (speculation only) due to lack of content delivered from SME and GT-MM - GT-OP priorities. |  | 652d | [6 empty] | No | 2026-01-01 | 2028-06-30 | 2025-06-12 07:45 | jennifer.b.wright@ge.com
AP-130 | Develop Customer-facing VR Tours for Learning Centers (for marketing) | AP-130 | AP-0116 | Develop Customer-facing VR Tours for Learning Centers (for marketing)AP-0116 | #INVALID COLUMN VALUE | Top | 0 | 144 | 0 | 0 | lee.s.fielding@gevernova.com |  | philip.ganssmann@gevernova.com | Content Quality & Improvements |  | In Progress |  | Delayed | 2024-04-01 | 2026-07-31 |  |  | 2024-04-01 |  | Customer Internal | n/a | OFS-Cost-Cost-Gross Margin | C | Other |  | 4/8/24-Moved to June due to other priorities 2024-06-27: Request completion moved to September due to focus on AP-127 (Upgrade Customer Courseware) 2024-09-30: Will move this one to 2025 due to other priorities, on hold for now." 2025-06-10: LSF - shifted to end of year due to rebranding of HLC and new 360 image requirements. 03Dec25 - to be moved to 2026 now that HLC reno is complete. new date July 2026 | https://gevernova.box.com/s/26431h1wg2uhzs738rh216wrn2vc9xiy | 610d |  |  |  | TRUE |  |  | No | 2024-04-01 | 2026-07-31 | 2024-11-18 07:18 | philip.ganssmann@ge.com
AP-148 | Define & Develop EHS Technician Career Progression Program | AP-148 | AP-0426 | Define & Develop EHS Technician Career Progression ProgramAP-0426 | #INVALID COLUMN VALUE | Top | 0 | 145 | 0 | 0 | tamara.biediger@gevernova.com | EHS SME | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2024-02-01 | 2025-01-31 |  |  | 2024-02-01 | 2025-01-31 | Internal Programs & Competency | EHS |  |  |  |  | Continued from 2024 to allow time to review progression now that Competency Map is in Kahuna | https://gevernova.ent.box.com/file/1763174774169 | 262d | [6 empty] | No | 2024-02-01 | 2025-01-31 | 2024-12-19 10:11 | jennifer.b.wright@ge.com
AP-156 | Instructor Feedback Survey for Course Logistics/Support | AP-156 | AP-0115 | Instructor Feedback Survey for Course Logistics/SupportAP-0115 | #INVALID COLUMN VALUE | Top | 0 | 146 | 0 | 0 | Jennifer Wright |  | philip.ganssmann@gevernova.com | Operational simplification | Plan is to design the survey content (what questions do we want to ask) then we can build the survey system. Plan to use a Smartsheet form for input and build automation for sending surveys to instructors. Automation could potentially be based on the course completion data available in the Internal Training Dashboard sheet from the Training Certificate Creator, but would need to investigate further & determine how/if to coordinate with Customer Training Instructor survey. May need to wait to release until UDC scheduling tool is available - TBD. Then instructor feedback could be reviewed/cross-referenced in conjunction with the monthly NPS reviews & shared with TDMs/RMs as applicable | Not Started |  | Delayed | 2026-05-01 | 2026-08-31 | 2026-06-30 | TRUE | 2025-04-01 | 2025-06-30 | Customer Delivery Ops | n/a | OFS-Quality-Customer Escapes-Escapes | Q | Other |  | 7/28/24-moved remaining activity to 2025 to coordinate with updated scheduling tool plan Questions are drafted. Implementation is dependent on Scheduling Tool deployment schedule. Will want to use data from scheduling tool to automate instructor survey request. 22Apr25-Moved to start in July due to modified Scheduling Tool Deployment schedule 30June25-Moved to Sept start & Dec end to accommodate delayed scheduling tool. 24Nov25-moved to Feb due to schedule tool delays 9Feb26-Move to June due to higher priorities & stabilization of UDC 9Jun26-Moved to Aug due to higher priorities and pending new survey tool | https://gevernova.ent.box.com/file/2126890004411 | 87d | [6 empty] | No | 2026-05-01 | 2026-08-31 | 2024-11-18 07:18 | philip.ganssmann@ge.com
AP-167 | Roll out NPI & PLL Connection Process to all product lines | AP-167 | 54 | Roll out NPI & PLL Connection Process to all product lines54 | #INVALID COLUMN VALUE | Top | 0 | 147 | 1 | 0 | n/a- See Child Leads | TBD | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete |  |  | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 |  |  |  |  | Other |  | Added on 5/30/24 as output from AP-039. To be started in 2025 | n/a-parent row | 108d | [6 empty] | No | 2025-01-01 | 2025-05-30 | 2024-11-08 13:06 | jennifer.b.wright@ge.com
AP-167-1 | ST NPI & PLL Connection |  | AP-0264 | ST NPI & PLL ConnectionAP-0264 | AP-167 | AP-167 | 1 | 1 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Cancelled |  |  | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [6 empty] | 1May25-Put on hold to realign scope & prioritize with other work 14Oct25-Confirmed to stay on hold for now 11/18/25-Replaced with AP-0706 - ST Seminar |  | 108d | [6 empty] | Yes | 2025-01-01 | 2025-05-30 | 2024-11-21 08:50 | jennifer.b.wright@ge.com
AP-167-2 | Generator and Excitation NPI & PLL Connection |  | AP-0261 | Generator and Excitation NPI & PLL ConnectionAP-0261 | AP-167 | AP-167 | 1 | 2 | 0 | 1 | michele.alcantar@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [7 empty] | https://gevernova.ent.box.com/file/1768332390277 | 108d | [6 empty] | Yes | 2025-01-01 | 2025-05-30 | 2024-11-21 08:50 | jennifer.b.wright@ge.com
AP-167-3 | GT NPI & PLL Connection |  | AP-0260 | GT NPI & PLL ConnectionAP-0260 | AP-167 | AP-167 | 1 | 3 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Cancelled |  |  | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [6 empty] | 1May25-Put on hold to realign scope & prioritize with other work 14Oct25-Confirmed to stay on hold for now 11/18/25-Replaced with AP-0707 - GT Seminar |  | 108d | [6 empty] | Yes | 2025-01-01 | 2025-05-30 | 2024-11-21 08:50 | jennifer.b.wright@ge.com
AP-167-4 | Aero NPI & PLL Connection |  | AP-0263 | Aero NPI & PLL ConnectionAP-0263 | AP-167 | AP-167 | 1 | 4 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete |  | On Track | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [7 empty] | https://gevernova.ent.box.com/file/1875892722424 | 108d | [6 empty] | Yes | 2025-01-01 | 2025-05-30 | 2024-11-21 08:50 | jennifer.b.wright@ge.com
AP-167-5 | Craft/Repairs NPI & PLL Connection |  | AP-0262 | Craft/Repairs NPI & PLL ConnectionAP-0262 | AP-167 | AP-167 | 1 | 5 | 0 | 1 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Cancelled |  |  | 2025-01-01 | 2025-05-30 |  |  | 2025-01-01 | 2025-05-30 | [6 empty] | 1May25-Cancelled - NPI connection will flow thru GT/ST/Gen product lines, not directly |  | 108d | [6 empty] | Yes | 2025-01-01 | 2025-05-30 | 2024-11-21 08:50 | jennifer.b.wright@ge.com
AP-174 | Improve GT ELT-A Program | AP-174 | AP-0114 | Improve GT ELT-A ProgramAP-0114 | #INVALID COLUMN VALUE | Top | 0 | 148 | 1 | 0 | Sherif.Khalifa@gevernova.com | J. Capps | jim.rosen@gevernova.com | Content Development |  | In Progress |  |  | 2024-07-01 | 2026-10-30 |  |  | 2024-07-01 | 2025-10-31 |  |  |  |  | Other |  | To be completed in 2025 | n/a-parent row | 610d | [6 empty] | Yes | 2024-07-01 | 2026-10-30 | 2024-11-18 07:18 | philip.ganssmann@ge.com
AP-174 | Develop/Revise GT ELT-A1 & ELT-A2 materials & exams | AP-174 | 73 | Develop/Revise GT ELT-A1 & ELT-A2 materials & exams73 | AP-174 | AP-174 | 1 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | J. Capps | jim.rosen@gevernova.com | Content Development |  | Complete |  | On Track | 2024-07-01 | 2025-08-29 |  |  | 2024-07-01 | 2025-07-31 | [6 empty] | 30Jul25-Moved to Aug to incorporate adjustments from pilot session 11Aug25-Pilot session was switched to full ELT. Will close this item because content is ready. Pilot will be delivered in 2026. | https://gevernova.ent.box.com/file/1974453295149 | 305d | [6 empty] | Yes | 2024-07-01 | 2025-08-29 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-175 | Pilot GT ELT-A1 & ELT-A2 session | AP-175 | 74 | Pilot GT ELT-A1 & ELT-A2 session74 | AP-174 | AP-174 | 1 | 2 | 0 | 1 | Sherif.Khalifa@gevernova.com | J. Capps | jim.rosen@gevernova.com | Content Development |  | Not Started |  |  | 2026-07-01 | 2026-10-30 |  |  | 2025-07-01 | 2025-10-31 |  |  |  |  | Other |  | 11Aug25-Pushed to 2026 since 2025 session was reverted to full ELT program |  | 88d | [6 empty] | Yes | 2026-07-01 | 2026-10-30 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-179 | Foundation Fieldbus Training | AP-179 | 78 | Foundation Fieldbus Training78 | #INVALID COLUMN VALUE | Top | 0 | 149 | 0 | 0 | mohammed.nizami@gevernova.com | Carla Martinez Borbolla, Yegor Spencer | jim.rosen@gevernova.com | Content Development |  | Complete |  | On Track | 2024-06-01 | 2026-02-27 |  |  | 2024-06-01 | 2025-02-28 | Customer Delivery |  |  |  | Other |  | 2/11/25-We need to separate this improvement into two steps FFB content and rest of digital bus content. Due to higher demand of FFB and limited availability of SME and FFB equipment we are focusing only on FFB content. Doug will work on this in March and goal is to finish this content by end of March so extend close/complete date to end of April 2025. Updated delivery date to setup equipment access at KLC. 21Apr25-postponed till end of June as we're trying to setup access to hardware in Kuwait 09Jun25-Postponed to August due to ongoing access issues in Kuwait & hardware limitations - exploring other solutions 15Aug25-The scope of this AP has evolved. We’re now updating all Foundation Fieldbus content—both internal and customer-facing—and developing new material to incorporate TFA feedback, NPIs, and customer concerns raised during seminars and the HA user conferences. This is high priority project going up to Jim Vono level. Postponing to Dec 22Dec25-Customer is done & piloted, Internal pilot in Jan 2026. | https://gevernova.ent.box.com/file/2146588122276 | 456d |  | TRUE |  |  |  |  | Yes | 2024-06-01 | 2026-02-27 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-180 | Controls Server troubleshooting training / Thin Client training | AP-180 | 79 | Controls Server troubleshooting training / Thin Client training79 | #INVALID COLUMN VALUE | Top | 0 | 150 | 0 | 0 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development | Connected with engineering team responsible for Controls Server product line to help rebuilt our control server equipment @ HLC (old equipment) and increase class capacity from 4 student to 8. Also seeking help to test Controls Server virtualization efforts on Skytap with Aaron Hayes. This project if successful will help deliver Control Server to customers with more hands on experience. Currently pending quote for engineering hours from projects team for these above items. | Complete |  | On Track | 2024-06-01 | 2025-02-28 |  |  | 2024-06-01 | 2025-02-28 | Customer Delivery | [5 empty] | Had moved back to Jan - but reset to Feb to include time to review feedback from pilot session | https://gevernova.ent.box.com/file/1787866683684 | 196d |  | TRUE |  |  |  |  | Yes | 2024-06-01 | 2025-02-28 | 2024-11-14 14:38 | jennifer.b.wright@ge.com
AP-181 | Customer Opflex Course for combined cycle plants | AP-181 | 80 | Customer Opflex Course for combined cycle plants80 | #INVALID COLUMN VALUE | Top | 0 | 151 | 1 | 0 | mohammed.nizami@gevernova.com | martin.acosta1@gevernova.com | jim.rosen@gevernova.com | Content Development | We currently have 4 courses on GT related to OP Flex which are similar and need to be consolidated. We need to develop a new course with help of engineering to delivery OP Flex for ST and CCPP (includes HRSG, BOP, and DCS). This development will require time and funds, but tentatively we can deliver it sometime next year 2025. Needs to include Autotune for 7HA.03 as well. | In Progress |  | Delayed | 2026-01-01 | 2026-11-30 | 2026-05-31 |  | 2024-06-01 | 2025-02-28 |  |  |  |  | Other |  | 2/11/25- I have very limited availability for Doug Wadsworth who is SME for these courses. We will develop a plan to consolidate these Op flex courses along with DLN courses (total of 13 course offering) during Service week and deliver this project by end of 2025. 22Dec25-Have not been able to get SME help. Targeting working with Martin Acosta in March/April to be ready for mid-year customer catalog release 31Mar26-Added subtasks & adjusted finish to include potential pilot delivery |  | 238d | [6 empty] | Yes | 2026-01-01 | 2026-11-30 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-181-1 | Develop Opflex Course Materials & Identify Target Instructor(s) |  | AP-0851 | Develop Opflex Course Materials & Identify Target Instructor(s)AP-0851 | AP-181 | AP-181 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com | martin.acosta1@gevernova.com | jim.rosen@gevernova.com | Content Development |  | On Hold | TRUE | Delayed | 2026-01-01 | 2026-05-29 |  |  | 2026-01-01 | 2026-05-29 | [6 empty] | 10Jun26-On Hold, pending discussion regarding how to handle duration variability |  | 107d |  |  |  |  | TRUE |  | Yes | 2026-01-01 | 2026-05-29 | 2026-03-31 16:11 | jennifer.b.wright@gevernova.com
AP-181-2 | Load Opflex course into our relevant systems |  | AP-0850 | Load Opflex course into our relevant systemsAP-0850 | AP-181 | AP-181 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com | martin.acosta1@gevernova.com | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | On Hold | TRUE | Delayed | 2026-04-01 | 2026-05-29 |  |  | 2026-04-01 | 2026-05-29 | [6 empty] | 10Jun26-On Hold, pending discussion regarding how to handle duration variability |  | 43d |  |  |  |  | TRUE |  | Yes | 2026-04-01 | 2026-05-29 | 2026-03-31 16:11 | jennifer.b.wright@gevernova.com
AP-181-3 | Deliver Opflex Pilot session |  | AP-0852 | Deliver Opflex Pilot sessionAP-0852 | AP-181 | AP-181 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com | james.easley@gevernova.com, michael.sanders@gevernova.com | jim.rosen@gevernova.com | Content Development | Possibly E-CON23409 for PPC Megalopolis (26-1100) Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2026-10-01 | 2026-11-30 |  |  | 2026-10-01 | 2026-11-30 | [8 empty] | 43d | [6 empty] | Yes | 2026-10-01 | 2026-11-30 | 2026-03-31 16:11 | jennifer.b.wright@gevernova.com
AP-184 | Controls HMI (Cimplicity) Operation class (NU - GT/ST/CC/DCS) | AP-184 | 81 | Controls HMI (Cimplicity) Operation class (NU - GT/ST/CC/DCS)81 | #INVALID COLUMN VALUE | Top | 0 | 152 | 1 | 0 | mohammed.nizami@gevernova.com | pablo.schibli@gevernova.com, Santosh Kumar, Sherif Khalifa | jim.rosen@gevernova.com | Content Development | Problem: The level of HMI detail in the GT / ST / CC Ops classes is not what the customer is looking for and the GT/ST Ops instructors are not able to cover what the customer is looking for. Goal: Offer a new HMI Operations course that covers more detail on the HMI topics for Operators. Mohammed has a plan to combine the following courses into 1 HMI Operations course (target 3-days), which should be targeted at Operators & generic for ActivePoint/Advance Viewer -E-CON10801 Control System - ActivePoint™ HMI Operation Familiarization -E-CON33402 Control System - Proficy CIMPLICITY™ for Turbine Controls (Advanced) When designing the new course, need to understand: -What are the missing HMI Operations topics that are not in the existing GT Ops, ST Ops, CC Ops & DCS classes? (Santosh has insight here from his recent experience) -What topics are already addressed in the existing Operations courses? | Not Started |  | Delayed | 2026-10-01 | 2026-12-31 |  |  | 2025-01-01 | 2025-06-30 | Customer Delivery Ops |  |  |  | Other |  | 11Jun25-Updated Improvement title, description & target dates per discussion with Anna & Mohammed 22Dec25-Will plan to fit this into Q4 2026 open timeslots to have ready for Jan 2027 catalog release. 31Mar26-Added sub-tasks |  | 66d | [6 empty] | Yes | 2026-10-01 | 2026-12-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-184-1 | Develop Controls HMI Course Materials & Identify Target Instructor(s) |  | AP-0856 | Develop Controls HMI Course Materials & Identify Target Instructor(s)AP-0856 | AP-184 | AP-184 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com | pablo.schibli@gevernova.com, Santosh Kumar, Sherif Khalifa | jim.rosen@gevernova.com | Content Development |  | Not Started | TRUE |  | 2026-10-01 | 2026-12-31 |  |  | 2026-10-01 | 2026-12-31 | [8 empty] | 66d | [6 empty] | Yes | 2026-10-01 | 2026-12-31 | 2026-03-31 16:43 | jennifer.b.wright@gevernova.com
AP-184-2 | Load Controls HMI course into our relevant systems |  | AP-0857 | Load Controls HMI course into our relevant systemsAP-0857 | AP-184 | AP-184 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com | pablo.schibli@gevernova.com, Santosh Kumar, Sherif Khalifa | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-11-01 | 2026-12-31 |  |  | 2026-11-01 | 2026-12-31 | [8 empty] | 45d | [6 empty] | Yes | 2026-11-01 | 2026-12-31 | 2026-03-31 16:43 | jennifer.b.wright@gevernova.com
AP-186 | Bucket Tech and Blader Entry level consolidation / harmonization | AP-186 | 82 | Bucket Tech and Blader Entry level consolidation / harmonization82 | #INVALID COLUMN VALUE | Top | 0 | 153 | 0 | 0 | shaimaa.galal@gevernova.com | Luca Martino, Michael Randolph | jim.rosen@gevernova.com | Content Development | Recommendation is to accept the proposed blending of Bucket Techs and Blader career paths, creating a more competent and successful workforce. Estimated training duration includes ILT & OJT time. This estimate will vary depending on the creation of the new training path. | Complete |  | On Track | 2024-06-01 | 2025-01-31 |  |  | 2024-06-01 | 2025-01-31 | [6 empty] | Due Date Jan 2025 | https://gevernova.ent.box.com/file/1744596273596 | 176d |  | TRUE |  |  |  |  | No | 2024-06-01 | 2025-01-31 | 2024-11-14 14:38 | jennifer.b.wright@ge.com
AP-188 | GT13 C-Inspection Training | AP-188 | AP-0432 | GT13 C-Inspection TrainingAP-0432 | #INVALID COLUMN VALUE | Top | 0 | 154 | 0 | 0 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Training needed for the EU region. Several C-inspection planned for the 2025 | Complete |  | On Track | 2024-08-01 | 2025-02-28 |  |  | 2024-08-01 | 2025-02-28 | Delivery Internal Ops | FE RM |  |  |  |  | Continued from 2024 to include pilot session 2/10/25-Pilot is underway, expect feedback & updates if needed | https://gevernova.ent.box.com/file/1771742531806 | 152d | [6 empty] | Yes | 2024-08-01 | 2025-02-28 | 2024-12-19 12:12 | jennifer.b.wright@ge.com
AP-189 | ALT Networks (Controls) | AP-189 | 83 | ALT Networks (Controls)83 | #INVALID COLUMN VALUE | Top | 0 | 155 | 1 | 0 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development | Post discussion with Todd Ashley in the engineering team, need was identified to create an ALT on Networks under the Controls PLL due to new products coming to market. | In Progress |  |  | 2026-04-01 | 2027-08-31 | 2025-12-31 |  | 2025-01-01 | 2025-06-30 |  |  |  |  | Other |  | Need to allocate time for SME to develop this content. 22Dec25- On hold, pending final product available from controls team then need to determine expected TFA skills/competencies 31Mar26-Added Sub-tasks and adjusted dates for 2027 delivery |  | 370d | [6 empty] | Yes | 2026-04-01 | 2027-08-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-189-1 | Develop List of Networks Competencies & identify which can be delivered via training vs. OJT/other |  | AP-0861 | Develop List of Networks Competencies & identify which can be delivered via training vs. OJT/otherAP-0861 | AP-189 | AP-189 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development | Coordinated with PLL, SMEs & Program Mgr | In Progress | TRUE |  | 2026-04-01 | 2026-06-30 |  |  | 2026-04-01 | 2026-06-30 | [8 empty] | 65d |  |  | TRUE |  |  |  | Yes | 2026-04-01 | 2026-06-30 | 2026-03-31 16:48 | jennifer.b.wright@gevernova.com
AP-189-2 | Ensure Networks competencies are reflected in Kahuna |  | AP-0862 | Ensure Networks competencies are reflected in KahunaAP-0862 | AP-189 | AP-189 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to Coordinated with Program Manager, Kelly, SMEs | Not Started | TRUE |  | 2026-07-01 | 2026-08-31 |  |  | 2026-07-01 | 2026-08-31 | [8 empty] | 44d | [6 empty] | Yes | 2026-07-01 | 2026-08-31 | 2026-03-31 16:48 | jennifer.b.wright@gevernova.com
AP-189-3 | Develop Networks Course Materials & Identify Target Instructor(s) |  | AP-0858 | Develop Networks Course Materials & Identify Target Instructor(s)AP-0858 | AP-189 | AP-189 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development |  | Not Started | TRUE |  | 2027-01-01 | 2027-03-31 |  |  | 2027-01-01 | 2027-03-31 | [8 empty] | 64d | [6 empty] | Yes | 2027-01-01 | 2027-03-31 | 2026-03-31 16:48 | jennifer.b.wright@gevernova.com
AP-189-4 | Load Networks course into our relevant systems |  | AP-0859 | Load Networks course into our relevant systemsAP-0859 | AP-189 | AP-189 | 1 | 4 | 0 | 1 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2027-04-01 | 2027-05-31 |  |  | 2027-04-01 | 2027-05-31 | [8 empty] | 43d | [6 empty] | Yes | 2027-04-01 | 2027-05-31 | 2026-03-31 16:48 | jennifer.b.wright@gevernova.com
AP-189-5 | Deliver Networks Pilot session |  | AP-0860 | Deliver Networks Pilot sessionAP-0860 | AP-189 | AP-189 | 1 | 5 | 0 | 1 | mohammed.nizami@gevernova.com | john.doss@gevernova.com, Yegor Spencer | jim.rosen@gevernova.com | Content Development | Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2027-07-01 | 2027-08-31 |  |  | 2027-07-01 | 2027-08-31 | [8 empty] | 44d | [6 empty] | Yes | 2027-07-01 | 2027-08-31 | 2026-03-31 16:48 | jennifer.b.wright@gevernova.com
AP-190 | Senior FE Leadership Training | AP-190 | 84 | Senior FE Leadership Training84 | #INVALID COLUMN VALUE | Top | 0 | 156 | 0 | 0 | tamara.biediger@gevernova.com |  | jim.rosen@gevernova.com | Content Development | This program will fill the need for leadership training for mid-career level employees to develop administrative and leadership competency and capability. | Cancelled |  |  | 2024-07-01 | 2025-07-31 |  |  | 2024-07-01 | 2025-07-31 | [6 empty] | Replaced by AP-0340 |  | 284d | [6 empty] | No | 2024-07-01 | 2025-07-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-191 | OSS LES Global Modal Natural Frequency Training | AP-191 | AP-0385 | OSS LES Global Modal Natural Frequency TrainingAP-0385 | #INVALID COLUMN VALUE | Top | 0 | 157 | 0 | 0 | harry.hanson@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Create a technical training course for OSS LES Specialists on how to execute to procedures to determine natural frequencies, corresponding mode shapes, and the dynamic flexibilities of the stator end windings for the legacy Alstom generator fleet. | Cancelled |  | At Risk | 2024-08-01 | 2026-02-27 |  |  | 2024-08-01 | 2025-12-31 | Delivery Internal Ops | OSS |  |  | Other |  | Continued from 2025 due to SME availability 17Mar25-Lower priority since 2025 class was cancelled. Target completion for delivery of course in 2026 7Jan26-Moved to end of Jan since Harry is out this week 26Jan26-Low priority item - no more demand from region. Harry to discuss cancelling this item with Jim & team. Moved to Feb in the meantime 9Feb26-Harry to actively confirm if there is any demand, if not we can cancel. 25Feb26-Canceled since there's no longer any demand for this course |  | 412d | [6 empty] | Yes | 2024-08-01 | 2026-02-27 | 2024-12-09 10:49 | jennifer.b.wright@ge.com
AP-195 | Develop MS Office Training Curriculum for SUP Leadership Program | AP-195 | AP-0383 | Develop MS Office Training Curriculum for SUP Leadership ProgramAP-0383 | #INVALID COLUMN VALUE | Top | 0 | 158 | 0 | 0 | luca.martino@gevernova.com | Brenda Roman Valle, Michael Randolph | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2024-08-01 | 2025-03-31 |  |  | 2024-08-01 | 2025-03-31 | Internal Programs & Competency | Craft RM | [5 empty] | https://gevernova.box.com/s/bz56jcp6jqpl7r70dwbgvvrzo67q7hff | 173d | [6 empty] | No | 2024-08-01 | 2025-03-31 | 2024-12-06 11:51 | jennifer.b.wright@ge.com
AP-196 | Create OSS Roles & Competencies in Kahuna (Winder/Machinist) | AP-196 | AP-0386 | Create OSS Roles & Competencies in Kahuna (Winder/Machinist)AP-0386 | #INVALID COLUMN VALUE | Top | 0 | 159 | 1 | 0 | luca.martino@gevernova.com | Kelly Kirby, Michael Randolph | michele.alcantar@gevernova.com | Competencies |  | Complete |  | On Track | 2025-11-01 | 2026-02-27 |  |  | 2024-11-01 | 2025-09-30 | Internal Programs & Competency | OSS RM |  |  | Other |  | 10Sept25-Moved to Oct to allow time to connect with OSS team 30Oct25-Delayed & split into sub tasks. | https://gevernova.box.com/s/th8yxl5kgztxz0v6hb1jn3rvyw4dnct3 | 86d | [6 empty] | No | 2025-11-01 | 2026-02-27 | 2024-12-09 11:41 | jennifer.b.wright@ge.com
AP-196-1 | Globalization of the OSS competency map (Winder/Machinist) |  | AP-0653 | Globalization of the OSS competency map (Winder/Machinist)AP-0653 | AP-196 | AP-196 | 1 | 1 | 0 | 1 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | check roles levels GE --> FieldCore, etc Steps 1-5 in Competency Map Checklist | Complete | TRUE | On Track | 2025-11-01 | 2025-11-28 |  |  | 2025-11-01 | 2025-11-28 | Internal Programs & Competency | OSS RM |  |  | Other |  |  | Report at Parent Level | 21d | [6 empty] | No | 2025-11-01 | 2025-11-28 | 2025-10-30 09:23 | jennifer.b.wright@ge.com
AP-196-2 | Import & Configure System for OSS Map (Winder/Machinist) |  | AP-0660 | Import & Configure System for OSS Map (Winder/Machinist)AP-0660 | AP-196 | AP-196 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Complete | TRUE | On Track | 2025-12-01 | 2025-12-15 | [8 empty] | Other |  |  | Report at Parent Level | 11d | [6 empty] | No | 2025-12-01 | 2025-12-15 | 2025-11-04 09:49 | jennifer.b.wright@ge.com
AP-196-3 | Baseline & Load OSS Competency Map (Winder/Machinist) |  | AP-0654 | Baseline & Load OSS Competency Map (Winder/Machinist)AP-0654 | AP-196 | AP-196 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Luca Martino | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Complete | TRUE | On Track | 2025-12-15 | 2026-02-27 |  |  | 2025-12-01 | 2025-12-15 | Internal Programs & Competency | OSS RM |  |  | Other |  | 29Jan26-Delayed until Feb due to delays with OSS team baselining | Report at Parent Level | 55d | [6 empty] | No | 2025-12-15 | 2026-02-27 | 2025-10-30 10:39 | jennifer.b.wright@ge.com
AP-198 | Implement FPS Trigger for FEP OJT Assignments | AP-198 | AP-0425 | Implement FPS Trigger for FEP OJT AssignmentsAP-0425 | #INVALID COLUMN VALUE | Top | 0 | 160 | 0 | 0 | shaimaa.galal@gevernova.com | Leonardo Monzo, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification | Include Field Performance Survey for FEP OJT assignments | Cancelled |  |  | 2024-08-01 | 2025-02-28 |  |  | 2024-08-01 | 2025-01-31 | Internal | Craft FE RM |  |  |  |  | 29Jan25 - Could not be tested in real life, testing in sandbox failed, upon investigation further changes/updates to the WO is needed - moved to Feb finish but pending timeline discussion with SMax team 13Jan25-Should have 2 OJTs completing this month to test that FPS is released as planned. Could maybe use test instance if OJT assignments are delayed Started in 2024, waiting for OJT assignments to test new SMx Changes. Expected in January 10Feb25-FPS trigger won't work due to dates associated with WO, need to investigate another option 26Feb25 - Cancelled this & replace with new AP-0469 | https://gevernova.box.com/s/aeu63ywnbpjqooluescx905jis31if3e | 152d | [6 empty] | No | 2024-08-01 | 2025-02-28 | 2024-12-18 10:53 | jennifer.b.wright@ge.com
AP-201 | Create Student Cost Calculator | AP-201 | AP-0118 | Create Student Cost CalculatorAP-0118 | #INVALID COLUMN VALUE | Top | 0 | 161 | 0 | 0 | philip.ganssmann@gevernova.com | daniel.barrera1@gevernova.com | philip.ganssmann@gevernova.com | Operational simplification | Create a calculator to show the true cost of a student in a class taking things like C&B, T&L, Facility Cost, Instructor Cost etc into consideration | On Hold |  |  | 2025-02-01 | 2025-06-30 |  |  | 2025-02-01 | 2025-05-30 | Internal | n/a |  |  | Other |  | To be completed in 2025 12May25-Move to June 10Jun25-Put on hold, not a priority at the moment 13Oct25-Keep on hold, still not a priority |  | 107d | [6 empty] | No | 2025-02-01 | 2025-06-30 | 2024-11-18 07:30 | philip.ganssmann@ge.com
AP-202 | Tool Handling and Safety of Enerpac | AP-202 | AP-0384 | Tool Handling and Safety of EnerpacAP-0384 | #INVALID COLUMN VALUE | Top | 0 | 162 | 0 | 0 | luca.martino@gevernova.com | andrew.samples@gevernova.com, Michael Randolph | michele.alcantar@gevernova.com | Content Development | This is a request to create an internal certification course for the safe and efficient use of Enerpac hydraulic tensioning tools, this is vital to continue effectively applying live outage technology in our outages | Complete |  | On Track | 2024-10-01 | 2025-05-30 |  |  | 2024-10-01 | 2025-05-30 | Internal | Craft OSS |  |  |  |  | Tied to AP-147 | https://gevernova.box.com/s/ja8nuanaqwoopvvovqhn5rljkowphtek | 174d | [6 empty] | No | 2024-10-01 | 2025-05-30 | 2024-12-06 11:55 | jennifer.b.wright@ge.com
AP-207 | Bolting Mentor Quarterly Newsletter | AP-207 | AP-0111 | Bolting Mentor Quarterly NewsletterAP-0111 | #INVALID COLUMN VALUE | Top | 0 | 163 | 0 | 0 | luca.martino@gevernova.com | Craft TDMs | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2024-12-01 | 2025-04-30 |  |  | 2024-12-01 | 2025-04-30 | Internal Programs & Competency | Craft RM |  |  |  |  | Addition to AP-147 "Communicaiton Campaign" (PM Manually Assigned) To be completed in 2025 | https://gevernova.box.com/s/mojcrntc5en55qywrc913kxz8d3yvtbf | 109d | [6 empty] | No | 2024-12-01 | 2025-04-30 | 2024-11-18 07:18 | philip.ganssmann@ge.com
AP-208 | Run TTT class for Borrowed Instructor Pool | AP-208 | AP-0427 | Run TTT class for Borrowed Instructor PoolAP-0427 | #INVALID COLUMN VALUE | Top | 0 | 164 | 0 | 0 | tamara.biediger@gevernova.com | alyssa.mays@gevernova.com, brenda.romanvalle@gevernova.com | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2024-12-01 | 2025-04-30 |  |  | 2024-12-01 | 2025-02-28 | Customer Delivery Internal Ops Programs & Competency | FE RM |  |  |  |  | Moved from 2024 because Dec TTT course was cancelled due to low enrollment. Next class planned in late Jan 2/10-Jan class didn't happen. Tam to confirm new dates with Brenda and update dates here as needed 2/24/25-Now targeting April delivery of TTT course. Moved Finish to end of April. | https://gevernova.box.com/s/6ipvnbq00tbi0560zddg2ygyxhnu6nwr | 109d | [6 empty] | No | 2024-12-01 | 2025-04-30 | 2024-12-19 10:14 | jennifer.b.wright@ge.com
AP-210 | Develop “Combined Cycle - Simulator based Operator OJT” Customer Training | AP-210 | 90 | Develop “Combined Cycle - Simulator based Operator OJT” Customer Training90 | #INVALID COLUMN VALUE | Top | 0 | 165 | 1 | 0 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com, pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Development | Develop a 10 day SkyTap Simulator hands-on Combined Cycle Operation Customer Training where students spend the entire time practicing on the simulator of the same frame they have, when available on their own plant simulator model. This should be on top of our standard NU CC-Ops, ST Ops and GT Ops courses (= requirement or extensive Ops experience) This offering is intended to be packaged with a subsequent, 3 months Skytap simulator access for the students. Current customer feedback provides evidence that such training is looked for by customers, therefore High ROI expeected. This can be developed with relatively low effort, because such training has already been delivered as non-standard to Dolna Odra and various TPC projects. Note: the 10 day CC-Ops version should include the content of the 5-day GT version as applicable | Not Started |  | Delayed | 2026-08-01 | 2027-01-29 | 2026-03-31 |  | 2025-09-15 | 2025-10-31 | Customer Delivery Ops |  |  |  | Other |  | 10/28/24-SME not available in 2024, all work to be completed in 2025 Analysis & Design in 2024, Development to Continue in 2025 28Jul25-Moved end to Dec per Sherif's request 05Dec25-Moved to March. Engineering is currently working on the simulators. Once AP-211 is complete will re-evaluate timing for this AP 02Mar26-Moved to April, pending new dates & sub-tasks 10Mar26-Added subtasks & updated dates |  | 131d | [6 empty] | Yes | 2026-08-01 | 2027-01-29 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-210-1 | 9HA.02/D650 Single Shaft CC Simulator based Operator OJT Course |  | AP-0887 | 9HA.02/D650 Single Shaft CC Simulator based Operator OJT CourseAP-0887 | AP-210 | AP-210 | 1 | 1 | 1 | 1 | [8 empty] | 2026-08-01 | 2027-01-29 | [12 empty] | 131d | [6 empty] | No | 2026-08-01 | 2027-01-29 | 2026-05-18 14:25 | jennifer.b.wright@gevernova.com
AP-210-1-1 | Develop 9HA.02/D650 Single Shaft CC Sim-based OJT Course Materials & Identify Target Instructor(s) |  | AP-0834 | Develop 9HA.02/D650 Single Shaft CC Sim-based OJT Course Materials & Identify Target Instructor(s)AP-0834 | AP-210-1 | AP-0887 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com, pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Development | Includes simulator readiness | Not Started | TRUE |  | 2026-08-01 | 2026-12-31 |  |  | 2026-08-01 | 2026-12-31 | Customer Delivery Ops | [7 empty] | 110d | [6 empty] | Yes | 2026-08-01 | 2026-12-31 | 2026-03-10 14:26 | jennifer.b.wright@gevernova.com
AP-210-1-2 | Load 9HA.02/D650 Single Shaft CC Sim-based OJT Training course into our relevant systems |  | AP-0835 | Load 9HA.02/D650 Single Shaft CC Sim-based OJT Training course into our relevant systemsAP-0835 | AP-210-1 | AP-0887 | 2 | 2 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com, pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC, Catalog & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-12-01 | 2027-01-29 |  |  | 2026-12-01 | 2027-01-29 | Customer Delivery Ops | [7 empty] | 44d | [6 empty] | Yes | 2026-12-01 | 2027-01-29 | 2026-03-10 14:26 | jennifer.b.wright@gevernova.com
AP-210-2 | TBD CC Sim based Operator OJT Course |  | AP-0890 | TBD CC Sim based Operator OJT CourseAP-0890 | AP-210 | AP-210 | 1 | 2 | 1 | 1 | [20 empty] | Placeholder - scope and dates TBD once previous CC course is done | [8 empty] | No | #INVALID DATA TYPE | #INVALID DATA TYPE | 2026-05-18 14:25 | jennifer.b.wright@gevernova.com
AP-210-2-1 | Develop TBD CC Sim-based OJT Course Materials & Identify Target Instructor(s) |  | AP-0888 | Develop TBD CC Sim-based OJT Course Materials & Identify Target Instructor(s)AP-0888 | AP-210-2 | AP-0890 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com, pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Development | Includes simulator readiness | Not Started | TRUE | [22 empty] | Yes | #INVALID DATA TYPE | #INVALID DATA TYPE | 2026-05-18 14:25 | jennifer.b.wright@gevernova.com
AP-210-2-2 | Load TBD CC Sim-based OJT Training course into our relevant systems |  | AP-0889 | Load TBD CC Sim-based OJT Training course into our relevant systemsAP-0889 | AP-210-2 | AP-0890 | 2 | 2 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com, pablo.schibli@gevernova.com | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC, Catalog & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE | [22 empty] | Yes | #INVALID DATA TYPE | #INVALID DATA TYPE | 2026-05-18 14:25 | jennifer.b.wright@gevernova.com
AP-210-3 | Combine individual CC configuration classes into 1 F-Class & H-Class CC Simulator Based Operator OJT course |  | AP-0891 | Combine individual CC configuration classes into 1 F-Class & H-Class CC Simulator Based Operator OJT courseAP-0891 | AP-210 | AP-210 | 1 | 3 | 0 | 1 |  |  | jim.rosen@gevernova.com | Content Development | Update Course Outline & Instructor Competencies | Not Started | [14 empty] | Dates TBD once full scope of CC configurations is determined | [8 empty] | No | #INVALID DATA TYPE | #INVALID DATA TYPE | 2026-05-18 14:25 | jennifer.b.wright@gevernova.com
AP-211 | Develop “Gas Turbine - Simulator based Operator OJT” Customer Training | AP-211 | 91 | Develop “Gas Turbine - Simulator based Operator OJT” Customer Training91 | #INVALID COLUMN VALUE | Top | 0 | 166 | 1 | 0 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development | Develop a 5 day SkyTap Simulator hands-on Gas Turbine Operation Customer Training where students spend the entire time practicing on the simulator of the same frame they have, when available on their own plant simulator model. This should be on top of our standard 10-day GT Ops course (= requirement or extensive GT Ops experience) This offering is intended to be packaged with a subsequent, 3 months Skytap simulator access for the students. Current customer feedback provides evidence that such training is looked for by customers, therefore High ROI expeected. This can be developed with relatively low effort, because such training has already been delivered as non-standard to Dolna Odra and various TPC projects. | In Progress |  | Delayed | 2026-03-01 | 2026-08-31 | 2026-03-31 |  | 2025-09-01 | 2025-09-30 |  |  |  |  | Other |  | 10/28/24-SME not available in 2024, all work to be completed in 2025 Analysis & Design in 2024, Development to Continue in 2025 28Jul25-Moved end to Dec per Sherif's request 05Dec25-Moved to March. Engineering is currently working on the simulators. 02Mar26-Moved to April, pending new dates & sub-tasks 10Mar26-Added subtasks & updated dates 11May26-Reworked subtasks to track completion of each frame-specific course. Will prioritize F & H-class based on simulator availability and then combine into 1 class when the full scope is available | n/a-parent level | 132d | [6 empty] | Yes | 2026-03-01 | 2026-08-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-211-1 | 7FA.05 Simulator based Operator OJT Course |  | AP-0882 | 7FA.05 Simulator based Operator OJT CourseAP-0882 | AP-211 | AP-211 | 1 | 1 | 1 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development |  | In Progress |  | Delayed | 2026-03-01 | 2026-07-31 | [10 empty] | 27May26-Moved to June since Sherif is OoO |  | 111d |  |  |  | TRUE |  |  | Yes | 2026-03-01 | 2026-07-31 | 2026-05-11 14:19 | jennifer.b.wright@gevernova.com
AP-211-1-1 | Develop 7FA.05 Sim-based OJT Course Materials & Identify Target Instructor(s) |  | AP-0836 | Develop 7FA.05 Sim-based OJT Course Materials & Identify Target Instructor(s)AP-0836 | AP-211-1 | AP-0882 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development | Includes simulator readiness | Complete | TRUE | On Track | 2026-03-01 | 2026-04-30 |  |  | 2026-03-01 | 2026-04-30 | [6 empty] | 08Apr26-Need to set realistic dates based on Engineering & Dave Miller/Sim team availability 15Apr26-Confirmed on track for April completion | n/a-report at parent level | 45d | [6 empty] | Yes | 2026-03-01 | 2026-04-30 | 2026-03-10 14:28 | jennifer.b.wright@gevernova.com
AP-211-1-2 | Load 7FA.05 Sim-based OJT course into our relevant systems |  | AP-0837 | Load 7FA.05 Sim-based OJT course into our relevant systemsAP-0837 | AP-211-1 | AP-0882 | 2 | 2 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC, Catalog & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | In Progress | TRUE | Delayed | 2026-04-01 | 2026-07-31 | 2026-06-30 | TRUE | 2026-04-01 | 2026-05-29 | [6 empty] | 11June26-Moved to July to use new outline tool when implemented | n/a-report at parent level | 88d |  |  |  | TRUE |  |  | Yes | 2026-04-01 | 2026-07-31 | 2026-03-10 14:28 | jennifer.b.wright@gevernova.com
AP-211-2 | 7HA.03 Simulator based Operator OJT Course |  | AP-0883 | 7HA.03 Simulator based Operator OJT CourseAP-0883 | AP-211 | AP-211 | 1 | 2 | 1 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development |  | Not Started |  |  | 2026-06-01 | 2026-08-31 | [10 empty] | 11May26-Placeholder dates entered. To be confirmed |  | 66d |  | TRUE |  |  |  |  | Yes | 2026-06-01 | 2026-08-31 | 2026-05-11 14:19 | jennifer.b.wright@gevernova.com
AP-211-2-1 | Develop 7HA.03 Sim-based OJT Course Materials & Identify Target Instructor(s) |  | AP-0884 | Develop 7HA.03 Sim-based OJT Course Materials & Identify Target Instructor(s)AP-0884 | AP-211-2 | AP-0883 | 2 | 1 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development | Includes simulator readiness | Not Started | TRUE |  | 2026-06-01 | 2026-07-31 | [11 empty] | n/a-report at parent level | 45d |  | TRUE |  | TRUE |  |  | Yes | 2026-06-01 | 2026-07-31 | 2026-05-11 14:28 | jennifer.b.wright@gevernova.com
AP-211-2-2 | Load 7HA.03 Sim-based course into our relevant systems |  | AP-0885 | Load 7HA.03 Sim-based course into our relevant systemsAP-0885 | AP-211-2 | AP-0883 | 2 | 2 | 0 | 1 | Sherif.Khalifa@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC, Catalog & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-08-03 | 2026-08-31 | [11 empty] | n/a-report at parent level | 21d | [6 empty] | Yes | 2026-08-03 | 2026-08-31 | 2026-05-11 14:28 | jennifer.b.wright@gevernova.com
AP-211-3 | Combine individual frame classes into 1 F-Class & H-Class Simulator Based Operator OJT course |  | AP-0886 | Combine individual frame classes into 1 F-Class & H-Class Simulator Based Operator OJT courseAP-0886 | AP-211 | AP-211 | 1 | 3 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Update Course Outline & Instructor Competencies | Not Started | [14 empty] | Dates TBD once full scope of GTs is determined | [8 empty] | Yes | #INVALID DATA TYPE | #INVALID DATA TYPE | 2026-05-11 14:28 | jennifer.b.wright@gevernova.com
AP-212 | Simulator Hands-On Aero GT Operation Customer Training | AP-212 | 92 | Simulator Hands-On Aero GT Operation Customer Training92 | #INVALID COLUMN VALUE | Top | 0 | 167 | 0 | 0 | gregoryd.walker@gevernova.com | aaron.hayes@gevernova.com | jim.rosen@gevernova.com | Content Development | Develop a 5 day SkyTap Simulator hands-on Aero GT Operation Customer Training where students spend the entire time practicing on the simulator of the same frame they have, when available on their own plant simulator model. This should be on top of our standard NU courses (= requirement or extensive GT Ops experience) This offering is intended to be packaged with a subsequent, 3 months Skytap simulator access for the students. Current customer feedback provides evidence that such training is looked for by customers, therefore High ROI expeected. This can be developed with relatively low effort, because such training has already been delivered as non-standard to Biblis projects. | Complete |  |  | 2024-10-01 | 2025-10-31 |  |  | 2024-10-01 | 2025-10-01 | [6 empty] | Analysis & Design in 2024, Development to Continue in 2025 13Oct25-TBD if the new course E-AER10701 meets this need | https://gevernova.box.com/s/bowaduy5fkgz5ln27zlkqd1dv1439cjl | 284d | [6 empty] | Yes | 2024-10-01 | 2025-10-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-214 | HD TFA Competency Mapping | AP-214 | 75 | HD TFA Competency Mapping75 | #INVALID COLUMN VALUE | Top | 0 | 168 | 1 | 0 | ankita.gupta@gevernova.com | PLLs | michele.alcantar@gevernova.com | Programs | Replace Level I-IV TDI Competencies This project is a complete overhaul of the TDI competency model. The goal is to eliminate existing TDI competencies and integrate them to level I-IV Gas Turbine, Steam Turbine, Electrical and Controls primary roles. Additionally, installation advanced skills will be added back to the competency maps to provide TFAs with a path to specialize. •Incorporate the TDI competencies into the level I-IV maps •Ensure level I competencies provide comprehensive installation requirements to add for all courses •Ensure level II competencies provide comprehensive installation requirements to add for all qualification criteria •Add level III and IV installation technical skills to competency maps •Redesign the Installation Advanced Skill requirements By Mar'25, scope of the project was enhanced to all HD TFA skills (Electrical, Controls, GT Mech & ST Mech) i.e. Installation skills as well as Maintenance skills. | In Progress |  |  | 2025-01-01 | 2026-10-30 |  |  | 2025-01-01 | 2025-09-30 |  |  |  |  | Other |  | Complete in 2025. Timeline to be confirmed based on skills/competencies changes identifeid in AP-178 & next ELT delivery for each Product Line 28Apr26-Updated Improvement name to reflect modified scope | n/a-parent row | 478d | [6 empty] | No | 2025-01-01 | 2026-10-30 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-214-1 | Develop Competency Map - Electrical Skills |  | AP-0375 | Develop Competency Map - Electrical SkillsAP-0375 | AP-214 | AP-214 | 1 | 1 | 1 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Revamp overall Electrical Competency Map for HD TFAs | Complete | TRUE | On Track | 2025-01-01 | 2025-04-30 |  |  | 2025-01-01 | 2025-02-28 | [6 empty] | Expect to move out from Feb, pending further discussions to determine new target date 13Mar25-Added sub tasks for each Product Line | n/a-parent row | 86d | [6 empty] | No | 2025-01-01 | 2025-04-30 | 2024-11-27 13:53 | jennifer.b.wright@ge.com
AP-214-1-1 | Electrical Skills - Map Development |  | AP-0485 | Electrical Skills - Map DevelopmentAP-0485 | AP-214-1 | AP-0375 | 2 | 1 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Steps 1-4 in Competency Map Checklist | Complete |  | On Track | 2025-01-01 | 2025-03-31 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 21Mar25-purshed back finish date | https://gevernova.ent.box.com/folder/319108945749 | 64d | [6 empty] | No | 2025-01-01 | 2025-03-31 | 2025-03-13 08:31 | jennifer.b.wright@ge.com
AP-214-1-2 | Electrical Skills - Reviews & Approvals |  | AP-0552 | Electrical Skills - Reviews & ApprovalsAP-0552 | AP-214-1 | AP-0375 | 2 | 2 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Step 5 in Competency Map Checklist | Complete |  | On Track | 2025-04-01 | 2025-04-30 |  |  | 2025-05-01 | 2025-08-29 | [6 empty] | 20Jun25-Adjusted scope & date per discussion with Kelly 29Aug25-Moved to Sept to allow more time to review & finalize | https://gevernova.ent.box.com/file/1995281967925 | 22d | 519 | [5 empty] | No | 2025-04-01 | 2025-04-30 | 2025-06-05 08:45 | jennifer.b.wright@ge.com
AP-214-2 | Develop Competency Map - GT Mechanical Skills |  | AP-0554 | Develop Competency Map - GT Mechanical SkillsAP-0554 | AP-214 | AP-214 | 1 | 2 | 1 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Revamp overall GT Mechanical Competency Map for HD TFAs | Complete | TRUE | On Track | 2025-01-01 | 2025-07-31 |  |  | 2025-01-01 | 2025-09-30 | [7 empty] | n/a-parent row | 152d | [6 empty] | No | 2025-01-01 | 2025-07-31 | 2025-06-05 08:45 | jennifer.b.wright@ge.com
AP-214-2-1 | GT Mechanical Skills - Map Development |  | AP-0486 | GT Mechanical Skills - Map DevelopmentAP-0486 | AP-214-2 | AP-0554 | 2 | 1 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Steps 1-4 in Competency Map Checklist | Complete |  | Delayed | 2025-01-01 | 2025-06-30 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 21Mar25-purshed back finish date | https://gevernova.ent.box.com/folder/319108945749 | 129d | [6 empty] | No | 2025-01-01 | 2025-06-30 | 2025-03-13 08:31 | jennifer.b.wright@ge.com
AP-214-2-2 | GT Mechanical Skills - Reviews & Approvals |  | AP-0553 | GT Mechanical Skills - Reviews & ApprovalsAP-0553 | AP-214-2 | AP-0554 | 2 | 2 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Step 5 in Competency Map Checklist | Complete |  | On Track | 2025-07-01 | 2025-07-31 |  |  | 2025-06-02 | 2025-08-29 | [6 empty] | 20Jun25-Adjusted scope & date per discussion with Kelly 29Aug25-Moved to Sept to allow more time to review & finalize | https://gevernova.ent.box.com/file/1995281967925 | 23d | 522 | [5 empty] | No | 2025-07-01 | 2025-07-31 | 2025-06-05 08:45 | jennifer.b.wright@ge.com
AP-214-3 | Develop Competency Map - Controls Skills |  | AP-0556 | Develop Competency Map - Controls SkillsAP-0556 | AP-214 | AP-214 | 1 | 3 | 1 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Revamp overall Controls Competency Map for HD TFAs | Complete | TRUE | On Track | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-09-30 | [7 empty] | n/a-parent row | 173d | [6 empty] | No | 2025-01-01 | 2025-08-29 | 2025-06-05 08:49 | jennifer.b.wright@ge.com
AP-214-3-1 | Controls Skills - Map Development |  | AP-0483 | Controls Skills - Map DevelopmentAP-0483 | AP-214-3 | AP-0556 | 2 | 1 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Steps 1-4 in Competency Map Checklist | Complete |  | On Track | 2025-01-01 | 2025-07-31 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 21Mar25-purshed back finish date | https://gevernova.ent.box.com/folder/319108945749 | 152d | [6 empty] | No | 2025-01-01 | 2025-07-31 | 2025-03-13 08:31 | jennifer.b.wright@ge.com
AP-214-3-2 | Controls Skills - Reviews & Approvals |  | AP-0560 | Controls Skills - Reviews & ApprovalsAP-0560 | AP-214-3 | AP-0556 | 2 | 2 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Step 5 in Competency Map Checklist | Complete |  | On Track | 2025-08-01 | 2025-08-29 |  |  | 2025-07-01 | 2025-08-29 | [6 empty] | 20Jun25-Adjusted scope & date per discussion with Kelly 29Aug25-Moved to Sept to allow more time to review & finalize | https://gevernova.ent.box.com/file/1995281967925 | 21d | 525 | [5 empty] | No | 2025-08-01 | 2025-08-29 | 2025-06-05 08:49 | jennifer.b.wright@ge.com
AP-214-4 | Develop Competency Map - ST Mechanical Skills |  | AP-0558 | Develop Competency Map - ST Mechanical SkillsAP-0558 | AP-214 | AP-214 | 1 | 4 | 1 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Revamp overall ST Mechanical Competency Map for HD TFAs | Complete | TRUE | On Track | 2025-01-01 | 2025-09-30 |  |  | 2025-01-01 | 2025-09-30 | [7 empty] | n/a-parent row | 195d | [6 empty] | No | 2025-01-01 | 2025-09-30 | 2025-06-05 08:49 | jennifer.b.wright@ge.com
AP-214-4-1 | ST Mechanical Skills - Map Development |  | AP-0484 | ST Mechanical Skills - Map DevelopmentAP-0484 | AP-214-4 | AP-0558 | 2 | 1 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Steps 1-4 in Competency Map Checklist | Complete |  | On Track | 2025-01-01 | 2025-08-29 |  |  | 2025-01-01 | 2025-03-31 | [6 empty] | 21Mar25-pushed back finish date Report out To be combined with Competency Mapping activities for all Skills | https://gevernova.ent.box.com/file/1938965313517 | 173d | [6 empty] | No | 2025-01-01 | 2025-08-29 | 2025-03-13 08:31 | jennifer.b.wright@ge.com
AP-214-4-2 | ST Mechanical Skills - Reviews & Approvals |  | AP-0557 | ST Mechanical Skills - Reviews & ApprovalsAP-0557 | AP-214-4 | AP-0558 | 2 | 2 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Step 5 in Competency Map Checklist | Complete |  | On Track | 2025-09-01 | 2025-09-30 |  |  | 2025-08-01 | 2025-08-29 | [6 empty] | 20Jun25-Adjusted scope & date per discussion with Kelly Combined Report-out with all other "Review with Kelly" Skills items 29Aug25-Moved to Sept to allow more time to review & finalize | https://gevernova.ent.box.com/file/1995281967925 | 22d | 528 | [5 empty] | No | 2025-09-01 | 2025-09-30 | 2025-06-05 08:49 | jennifer.b.wright@ge.com
AP-214-5 | Review of Cross-Functional Skills |  | AP-0574 | Review of Cross-Functional SkillsAP-0574 | AP-214 | AP-214 | 1 | 5 | 0 | 1 | ankita.gupta@gevernova.com | SMEs, K. Kirby, PLLs | michele.alcantar@gevernova.com | Competencies | Review of all 7 Competency maps (Electrical, GT Controls, ST Controls, GT Mech (Install), GT Mech (Maint), ST Mech (Install), ST Mech (Maint) for HD TFAs | Complete | TRUE | On Track | 2025-10-01 | 2025-12-31 |  |  | 2025-09-01 | 2025-09-30 |  |  |  |  | Other |  | 20Jun25-Added per discussion with Kelly 4Dec25-Prep for System inputs - no separate report-out needed. | Report out with 214-6/7/8/9 | 66d | [6 empty] | No | 2025-10-01 | 2025-12-31 | 2025-06-18 13:28 | jennifer.b.wright@ge.com
AP-214-6 | Finalize Electrical Map in Systems |  | AP-0671 | Finalize Electrical Map in SystemsAP-0671 | AP-214 | AP-214 | 1 | 6 | 1 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Prepare system content & roll out Electrical competency map for HD TFAs | Not Started |  |  | 2026-01-01 | 2026-06-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2025-11-06 13:32 | jennifer.b.wright@ge.com
AP-214-6-1 | Import & Configure System for Electrical Map |  | AP-0672 | Import & Configure System for Electrical MapAP-0672 | AP-214-6 | AP-0671 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Complete | TRUE | On Track | 2026-01-01 | 2026-05-29 | 2026-03-31 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 107d | 530 |  |  |  | TRUE |  | No | 2026-01-01 | 2026-05-29 | 2025-11-06 13:32 | jennifer.b.wright@ge.com
AP-214-6-2 | Baseline & Load Electrical User Assignments |  | AP-0670 | Baseline & Load Electrical User AssignmentsAP-0670 | AP-214-6 | AP-0671 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE |  | 2026-06-01 | 2026-06-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 22d | 532 | TRUE | TRUE |  |  |  | No | 2026-06-01 | 2026-06-30 | 2025-11-06 13:32 | jennifer.b.wright@ge.com
AP-214-7 | Finalize GT Mech Map in Systems |  | AP-0576 | Finalize GT Mech Map in SystemsAP-0576 | AP-214 | AP-214 | 1 | 7 | 1 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Prepare system content & roll out GT Mech competency map for HD TFAs | Not Started |  |  | 2026-01-01 | 2026-10-30 | 2026-04-30 |  | 2025-10-01 | 2025-11-28 |  |  |  |  | Other |  | 20Jun25-Added per discussion with Kelly 25Mar26-Shifted to align with other Mapping tasks |  | 217d | [6 empty] | No | 2026-01-01 | 2026-10-30 | 2025-06-20 08:12 | jennifer.b.wright@ge.com
AP-214-7-1 | Import & Configure System for GT Mech Map |  | AP-0577 | Import & Configure System for GT Mech MapAP-0577 | AP-214-7 | AP-0576 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | At Risk | 2026-01-01 | 2026-09-30 | 2026-03-31 |  | 2025-12-01 | 2025-12-31 |  |  |  |  | Other |  | 20Jun25-Added per discussion with Kelly 25Mar26-Shifted to align with other Mapping tasks |  | 195d | 530 | [5 empty] | No | 2026-01-01 | 2026-09-30 | 2025-06-20 08:12 | jennifer.b.wright@ge.com
AP-214-7-2 | Baseline & Load GT Mech User Assignments |  | AP-0686 | Baseline & Load GT Mech User AssignmentsAP-0686 | AP-214-7 | AP-0576 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE |  | 2026-10-01 | 2026-10-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 22d | 535 | [5 empty] | No | 2026-10-01 | 2026-10-30 | 2025-11-06 14:02 | jennifer.b.wright@ge.com
AP-214-8 | Finalize Controls Map in Systems |  | AP-0687 | Finalize Controls Map in SystemsAP-0687 | AP-214 | AP-214 | 1 | 8 | 1 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Prepare system content & roll out Controls competency map for HD TFAs | Not Started |  |  | 2026-01-01 | 2026-10-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 217d | [6 empty] | No | 2026-01-01 | 2026-10-30 | 2025-11-06 14:02 | jennifer.b.wright@ge.com
AP-214-8-1 | Import & Configure System for Controls Map |  | AP-0685 | Import & Configure System for Controls MapAP-0685 | AP-214-8 | AP-0687 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | At Risk | 2026-01-01 | 2026-09-30 | 2026-03-31 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 195d | 530 | [5 empty] | No | 2026-01-01 | 2026-09-30 | 2025-11-06 14:02 | jennifer.b.wright@ge.com
AP-214-8-2 | Baseline & Load Controls User Assignments |  | AP-0684 | Baseline & Load Controls User AssignmentsAP-0684 | AP-214-8 | AP-0687 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE |  | 2026-10-01 | 2026-10-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 22d | 538 | [5 empty] | No | 2026-10-01 | 2026-10-30 | 2025-11-06 14:02 | jennifer.b.wright@ge.com
AP-214-9 | Finalize ST Mech Map in Systems |  | AP-0688 | Finalize ST Mech Map in SystemsAP-0688 | AP-214 | AP-214 | 1 | 9 | 1 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Prepare system content & roll out ST Mech competency map for HD TFAs | Not Started |  |  | 2026-01-01 | 2026-10-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 217d | [6 empty] | No | 2026-01-01 | 2026-10-30 | 2025-11-06 14:03 | jennifer.b.wright@ge.com
AP-214-9-1 | Import & Configure System for ST Mech Map |  | AP-0690 | Import & Configure System for ST Mech MapAP-0690 | AP-214-9 | AP-0688 | 2 | 1 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | At Risk | 2026-01-01 | 2026-09-30 | 2026-03-31 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 195d | 530 | [5 empty] | No | 2026-01-01 | 2026-09-30 | 2025-11-06 14:03 | jennifer.b.wright@ge.com
AP-214-9-2 | Baseline & Load ST Mech User Assignments |  | AP-0689 | Baseline & Load ST Mech User AssignmentsAP-0689 | AP-214-9 | AP-0688 | 2 | 2 | 0 | 1 | kelly.kirby@gevernova.com | ankita.gupta@gevernova.com | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE |  | 2026-10-01 | 2026-10-30 | 2026-04-30 | [7 empty] | Other |  | 25Mar26-Shifted to align with other Mapping tasks |  | 22d | 541 | [5 empty] | No | 2026-10-01 | 2026-10-30 | 2025-11-06 14:03 | jennifer.b.wright@ge.com
AP-216 | Add Vernova Mission & Vision content to Training Programs | AP-216 | 93 | Add Vernova Mission & Vision content to Training Programs93 | #INVALID COLUMN VALUE | Top | 0 | 169 | 0 | 0 | kelly.kirby@gevernova.com | Leonardo Monzo | leonardo.monzo1@gevernova.com | Content Development | Craft and FE Onboarding, TM4 to Supervisor Training and FE leadership training | Complete |  | On Track | 2024-10-01 | 2025-02-28 |  |  | 2024-10-01 | 2025-02-28 | Internal P&C | Craft FE |  |  |  |  | 2/10/25- Mission & Vision ready for Feb. Separated Sustainability to separate item (AP-0461) to align with GEV overall Sustainability content development, targeting June closure | https://gevernova.ent.box.com/file/1787504055983 | 109d | [6 empty] | No | 2024-10-01 | 2025-02-28 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-219 | Aero Engine HPC locking lugs drilling Training | AP-219 | 94 | Aero Engine HPC locking lugs drilling Training94 | #INVALID COLUMN VALUE | Top | 0 | 170 | 0 | 0 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Development | This request is in response to an RCA on locking lugs removal. It would result in adding one day (8 hours) to the LM6000 Level 2 Cold Section course of hands on training. Recommend going forward with this project. | Complete |  | On Track | 2024-12-01 | 2025-03-31 |  |  | 2024-12-01 | 2025-03-31 | [6 empty] | Complete in 2025 | https://gevernova.ent.box.com/file/1813502867155 | 87d | [6 empty] | Yes | 2024-12-01 | 2025-03-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-221 | Learning Space for Asia Craft Training | AP-221 | 95 | Learning Space for Asia Craft Training95 | #INVALID COLUMN VALUE | Top | 0 | 171 | 1 | 0 | luca.martino@gevernova.com |  | michele.alcantar@gevernova.com | Programs |  | Complete |  | On Track | 2024-12-01 | 2025-03-31 |  |  | 2024-12-01 | 2025-03-31 | Delivery Internal Programs & Competency | Craft OSS RM |  |  |  |  | Added to address proposed outcomes from 2024 AP-221 | https://gevernova.box.com/s/n9u92jw9z9zq26sg3y5wirnyumt7y089 | 87d | [6 empty] | No | 2024-12-01 | 2025-03-31 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-221-1 | Retouch of Rayong Training Center |  | AP-0435 | Retouch of Rayong Training CenterAP-0435 | AP-221 | AP-221 | 1 | 1 | 0 | 1 | luca.martino@gevernova.com | Carlo Fabregas | michele.alcantar@gevernova.com | Programs | Implement minimum changes at Rayong shop to improve Training Experience | Complete |  | On Track | 2024-12-01 | 2025-03-31 |  |  | 2024-12-01 | 2025-03-31 | [7 empty] | https://gevernova.ent.box.com/file/1729789072020 | 87d | [6 empty] | No | 2024-12-01 | 2025-03-31 | 2024-12-19 13:26 | jennifer.b.wright@ge.com
AP-221-2 | Analyze alternate Training Locations for Asia Craft |  | AP-0436 | Analyze alternate Training Locations for Asia CraftAP-0436 | AP-221 | AP-221 | 1 | 2 | 0 | 1 | luca.martino@gevernova.com | Carlo Fabregas, Harry Hanson, Philip Ganssmann, sherif.khalifa@gevernova.com | michele.alcantar@gevernova.com | Programs | Investigate cost/needs for alternate locations (Warsaw, BLC, KTC) Consider: -HA equipment (mockup & tooling) costs/availability -Travel/Visa restrictions/costs -local site costs / fees | Complete |  | On Track | 2024-12-01 | 2025-03-31 |  |  | 2024-12-01 | 2025-03-31 | [7 empty] | https://gevernova.ent.box.com/file/1729789072020 | 87d | [6 empty] | No | 2024-12-01 | 2025-03-31 | 2024-12-19 13:26 | jennifer.b.wright@ge.com
AP-222 | Mech Assistant role simplification | AP-222 | 96 | Mech Assistant role simplification96 | #INVALID COLUMN VALUE | Top | 0 | 172 | 0 | 0 | luca.martino@gevernova.com | Craft TDMs | michele.alcantar@gevernova.com | Programs | Implement new roles/job titles in all regions | Complete |  | On Track | 2025-01-01 | 2025-06-30 |  |  | 2025-01-01 | 2025-06-30 | Internal Programs & Competency | Craft RM |  |  |  |  | Complete in 2025 | https://gevernova.box.com/s/2v0si0u9bixb67ax82mmqspes87f8wp9 | 129d | [6 empty] | No | 2025-01-01 | 2025-06-30 | 2024-11-08 13:29 | jennifer.b.wright@ge.com
AP-225 | Add Bearing Inspection Procedures to GT & ST courses | AP-225 | AP-0433 | Add Bearing Inspection Procedures to GT & ST coursesAP-0433 | #INVALID COLUMN VALUE | Top | 0 | 173 | 0 | 0 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Need to add to GT and ST GE Tech Mech courses reference to new on site inspection procedures for tilted 4 pads bearings & elliptical. Check which modules cover bearings and add the reference to the correct field procedures. Ensure instructor awareness of new procedures. | Complete |  | On Track | 2024-11-01 | 2025-03-31 |  |  | 2024-11-01 | 2025-03-31 | Delivery Internal | FE |  |  |  |  | Continued from 2024 to include delivery of pilot session | https://gevernova.ent.box.com/file/1814525433419 | 107d | [6 empty] | Yes | 2024-11-01 | 2025-03-31 | 2024-12-19 12:21 | jennifer.b.wright@ge.com
AP-0732 | Add OJT and Qualification into DLN Tuning Training |  | AP-0732 | Add OJT and Qualification into DLN Tuning TrainingAP-0732 | #INVALID COLUMN VALUE | Top | 0 | 174 | 0 | 0 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop DLN Tuning OJT Course checklist, schedule & outline to add as "add-on" class back-to-back with DLN Tuning Class. Remote Tuning Team Leader Thorsten Thome has confirmed his team’s support for the DLN Tuning courses and the subsequent on-the-job training (OJT) following the class. His team will assist during the course delivery and later during OJT. Additionally, Selton Dunn will have a field tuner from his team available to provide extra support or extend the OJT if needed. | In Progress |  |  | 2026-01-01 | 2026-09-30 | 2026-05-29 |  |  |  | Delivery Internal Ops | FE |  |  | Intake Review | brenda.romanvalle@gevernova.com | 16Dec25-Added from Intake Request 14429210424 31Mar26-Moved to May, pending April 20th discussion to determine how to document/capture/schedule add-on course in our systems 20Apr26-moved to Sept to include feedback pilot delivery in August |  | 195d | [6 empty] | Yes | 2026-01-01 | 2026-09-30 | 2025-12-16 11:17 | jennifer.b.wright@ge.com
AP-0733 | STF Steam Turbine FE Training |  | AP-0733 | STF Steam Turbine FE TrainingAP-0733 | #INVALID COLUMN VALUE | Top | 0 | 175 | 1 | 0 | pablo.schibli@gevernova.com | Tamara Biediger | jim.rosen@gevernova.com | Content Development |  | On Hold |  |  | 2026-01-01 | 2026-10-30 |  |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review | joseph.damato@gevernova.com | 16Dec25-Added from Intake Request # 14792272709 11May26-Moved to On Hold, pending relevant procedures & QCPs from Engineering & Value Stream |  | 217d | [6 empty] | Yes | 2026-01-01 | 2026-10-30 | 2025-12-16 11:25 | jennifer.b.wright@ge.com
AP-0733-1 | Develop List of STF ST Competencies & identify which can be delivered via training vs. OJT/other |  | AP-0734 | Develop List of STF ST Competencies & identify which can be delivered via training vs. OJT/otherAP-0734 | AP-0733 | AP-0733 | 1 | 1 | 0 | 1 | tamara.biediger@gevernova.com | Pablo Schibli | jim.rosen@gevernova.com | Content Development | Coordinated with PLL, SMEs & Program Mgr | On Hold | TRUE | Delayed | 2026-01-01 | 2026-05-29 | 2026-04-30 |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 26Feb26-Delayed to April due to waiting on feedback from Requester 24Apr26-Moved to May due to Pending review of procedures & competencies. Pablo to confirm realistic timeline | report at parent level | 107d |  |  |  |  | TRUE |  | No | 2026-01-01 | 2026-05-29 | 2025-12-16 11:33 | jennifer.b.wright@ge.com
AP-0733-2 | Ensure STF ST competencies are reflected in Kahuna |  | AP-0735 | Ensure STF ST competencies are reflected in KahunaAP-0735 | AP-0733 | AP-0733 | 1 | 2 | 0 | 1 | tamara.biediger@gevernova.com | Kelly Kirby, Pablo Schibli | jim.rosen@gevernova.com | Content Development | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to Coordinated with Program Manager, Kelly, SMEs | On Hold | TRUE | Delayed | 2026-03-01 | 2026-05-29 | 2026-04-30 |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  | 26Feb26-Delayed to April due to waiting on feedback from Requester 24Apr26-Moved to May due to Pending review of procedures & competencies. Pablo to confirm realistic timeline | report at parent level | 66d |  |  |  |  | TRUE |  | No | 2026-03-01 | 2026-05-29 | 2025-12-16 11:33 | jennifer.b.wright@ge.com
AP-0733-3 | Develop STF ST Course Materials & Identify Target Instructor(s) |  | AP-0736 | Develop STF ST Course Materials & Identify Target Instructor(s)AP-0736 | AP-0733 | AP-0733 | 1 | 3 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development |  | On Hold | TRUE | Delayed | 2026-03-01 | 2026-05-29 |  |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  |  | report at parent level | 66d |  |  |  |  | TRUE |  | Yes | 2026-03-01 | 2026-05-29 | 2025-12-16 11:33 | jennifer.b.wright@ge.com
AP-0733-4 | Load STF ST course into our relevant systems |  | AP-0737 | Load STF ST course into our relevant systemsAP-0737 | AP-0733 | AP-0733 | 1 | 4 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | On Hold | TRUE |  | 2026-06-01 | 2026-07-31 |  |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  |  | report at parent level | 45d |  | TRUE |  | TRUE |  |  | Yes | 2026-06-01 | 2026-07-31 | 2025-12-16 11:33 | jennifer.b.wright@ge.com
AP-0733-5 | Deliver STF ST Pilot session |  | AP-0738 | Deliver STF ST Pilot sessionAP-0738 | AP-0733 | AP-0733 | 1 | 5 | 0 | 1 | pablo.schibli@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Based on pilot session feedback, finalize Material and modify outline if needed | On Hold | TRUE |  | 2026-08-01 | 2026-10-30 |  |  |  |  | Delivery Internal Ops Programs & Competency | FE |  |  | Intake Review |  |  | report at parent level | 66d | [6 empty] | Yes | 2026-08-01 | 2026-10-30 | 2025-12-16 11:33 | jennifer.b.wright@ge.com
AP-0740 | Review Aero Site Manager Competencies |  | AP-0740 | Review Aero Site Manager CompetenciesAP-0740 | #INVALID COLUMN VALUE | Top | 0 | 176 | 1 | 0 | tamara.biediger@gevernova.com |  | michele.alcantar@gevernova.com | Competencies |  | Not Started |  | Delayed | 2026-01-01 | 2026-09-30 | 2026-06-30 |  |  |  | Internal Programs & Competency | FE |  |  | Intake Review | Maclain Todd | 16Dec25-Added from Intake Request #14812192177 08Apr26-overall project to be delayed due to Stakeholders. |  | 195d | [6 empty] | No | 2026-01-01 | 2026-09-30 | 2025-12-16 13:14 | jennifer.b.wright@ge.com
AP-0740-1 | Develop Aero Site Mgr Role & Competency Maps |  | AP-0741 | Develop Aero Site Mgr Role & Competency MapsAP-0741 | AP-0740 | AP-0740 | 1 | 1 | 0 | 1 | tamara.biediger@gevernova.com |  | michele.alcantar@gevernova.com | Competencies | Steps 1-5 in Competency Map Checklist Determine which (if any) competencies would need to be developed via training. Assumption is that most (if not all) would be via OJT. Any others, may need separate project to develop training if we can't leverage existing training programs. | Not Started | TRUE | Delayed | 2026-01-01 | 2026-07-31 | 2026-04-30 |  |  |  | Internal Programs & Competency | FE |  |  | Intake Review |  | 08Apr26-overall project to be delayed due to Stakeholders. | report at parent level | 152d |  |  |  | TRUE |  |  | No | 2026-01-01 | 2026-07-31 | 2025-12-16 13:14 | jennifer.b.wright@ge.com
AP-0740-2 | Import & Configure System for Aero Site Mgr Maps |  | AP-0742 | Import & Configure System for Aero Site Mgr MapsAP-0742 | AP-0740 | AP-0740 | 1 | 2 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Competencies | Step 6 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-08-03 | 2026-08-31 | 2026-05-29 |  |  |  | Internal Programs & Competency | FE |  |  | Intake Review |  | 08Apr26-overall project to be delayed due to Stakeholders. | report at parent level | 21d | 558 | [5 empty] | No | 2026-08-03 | 2026-08-31 | 2025-12-16 13:14 | jennifer.b.wright@ge.com
AP-0740-3 | Baseline & Load Aero Site Mgr User Assignments |  | AP-0739 | Baseline & Load Aero Site Mgr User AssignmentsAP-0739 | AP-0740 | AP-0740 | 1 | 3 | 0 | 1 | kelly.kirby@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Competencies | Steps 7-8 in Competency Map Checklist | Not Started | TRUE | Delayed | 2026-09-01 | 2026-09-30 | 2026-06-30 |  |  |  | Internal Programs & Competency | FE |  |  | Intake Review |  | 08Apr26-overall project to be delayed due to Stakeholders. | report at parent level | 22d | 559 | [5 empty] | No | 2026-09-01 | 2026-09-30 | 2025-12-16 13:14 | jennifer.b.wright@ge.com
AP-0743 | Revised DLN Course for Customer Training |  | AP-0743 | Revised DLN Course for Customer TrainingAP-0743 | #INVALID COLUMN VALUE | Top | 0 | 177 | 1 | 0 | mohammed.nizami@gevernova.com | martin.acosta1@gevernova.com | jim.rosen@gevernova.com | Content Development | We currently have multiple courses on GT related to DLN which are similar and need to be consolidated to have 1 course for all versions | In Progress |  | On Track | 2026-01-01 | 2026-12-31 | 2026-07-31 | TRUE | 2025-12-01 | 2026-05-29 |  |  |  |  | Other |  | 22Dec25-Added per discussion with Mohammed to capture ongoing work from his team. Similar to AP-181 31Mar26-Added Content development Sub tasks 27May26-Moved out to accommodate updating scope/sub tasks 10Jun26-Moved to Dec due to other priorities |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2025-12-22 10:52 | jennifer.b.wright@ge.com
AP-0743-1 | Develop DLN Course Materials & Identify Target Instructor(s) |  | AP-0855 | Develop DLN Course Materials & Identify Target Instructor(s)AP-0855 | AP-0743 | AP-0743 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com | martin.acosta1@gevernova.com | jim.rosen@gevernova.com | Content Development |  | In Progress | TRUE | On Track | 2026-01-01 | 2026-12-31 | 2026-05-29 |  | 2026-01-01 | 2026-05-29 | [8 empty] | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2026-03-31 16:37 | jennifer.b.wright@gevernova.com
AP-0743-2 | Load DLN course into our relevant systems |  | AP-0853 | Load DLN course into our relevant systemsAP-0853 | AP-0743 | AP-0743 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com | martin.acosta1@gevernova.com | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | In Progress | TRUE | On Track | 2026-04-01 | 2026-12-31 | 2026-05-29 |  | 2026-04-01 | 2026-05-29 | [8 empty] | 197d | [6 empty] | Yes | 2026-04-01 | 2026-12-31 | 2026-03-31 16:37 | jennifer.b.wright@gevernova.com
AP-0744 | Develop Standard Material for Customer DCS Maintenance Class |  | AP-0744 | Develop Standard Material for Customer DCS Maintenance ClassAP-0744 | #INVALID COLUMN VALUE | Top | 0 | 178 | 1 | 0 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Course is currently delivered without standard course materials (uses combination of materials from other courses) | In Progress |  | On Track | 2025-12-01 | 2026-09-30 | 2026-04-30 |  | 2025-12-01 | 2026-03-31 | Customer Delivery |  |  |  | Other |  | 22Dec25-Added per discussion with Mohammed to capture ongoing work from his team. 26Mar26-Moved to April since Mohammed is sick today 29Apr26 - split into sub-tasks to cover standalone vs. package variations |  | 218d | [6 empty] | Yes | 2025-12-01 | 2026-09-30 | 2025-12-22 10:55 | jennifer.b.wright@ge.com
AP-0744-1 | Develop Standard Material for Standalone Customer DCS Maint Class |  | AP-0879 | Develop Standard Material for Standalone Customer DCS Maint ClassAP-0879 | AP-0744 | AP-0744 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development |  | Complete | TRUE | On Track | 2025-12-01 | 2026-04-30 |  |  |  |  | Customer Delivery |  |  |  | Other |  |  | n/a-report-out at parent level | 109d | [6 empty] | Yes | 2025-12-01 | 2026-04-30 | 2026-04-29 14:22 | jennifer.b.wright@gevernova.com
AP-0744-2 | Develop Modified Standard Material for DCS Maint delivery alongside 10-day MkVIe Maint |  | AP-0878 | Develop Modified Standard Material for DCS Maint delivery alongside 10-day MkVIe MaintAP-0878 | AP-0744 | AP-0744 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Adjust standard material to remove overlaps with std 10-day MkVIe content | Not Started | TRUE |  | 2026-05-01 | 2026-09-30 |  |  |  |  | Customer Delivery |  |  |  | Other |  |  | n/a-report-out at parent level | 109d | [6 empty] | Yes | 2026-05-01 | 2026-09-30 | 2026-04-29 14:22 | jennifer.b.wright@gevernova.com
AP-0745 | Develop Internal HA Advanced Controls Course |  | AP-0745 | Develop Internal HA Advanced Controls CourseAP-0745 | #INVALID COLUMN VALUE | Top | 0 | 179 | 1 | 0 | mohammed.nizami@gevernova.com | Muhammad Ahmed Ijaz | jim.rosen@gevernova.com | Content Development | Develop new course to replace HA Seminar course | In Progress |  |  | 2026-03-01 | 2026-09-30 |  |  | 2025-12-01 | 2026-09-30 |  |  |  |  | Other |  | 22Dec25-Added per discussion with Mohammed to capture ongoing work from his team. 31Mar26-Added Sub-tasks |  | 154d | [6 empty] | Yes | 2026-03-01 | 2026-09-30 | 2025-12-22 10:57 | jennifer.b.wright@ge.com
AP-0745-1 | Develop List of HA Advanced Controls Competencies & identify which can be delivered via training vs. OJT/other |  | AP-0863 | Develop List of HA Advanced Controls Competencies & identify which can be delivered via training vs. OJT/otherAP-0863 | AP-0745 | AP-0745 | 1 | 1 | 0 | 1 | Benali Salim Messekine | mohammed.nizami@gevernova.com, Muhammad Ahmed Ijaz | jim.rosen@gevernova.com | Content Development | Coordinated with PLL, SMEs & Program Mgr | In Progress | TRUE | Delayed | 2026-04-01 | 2026-07-31 | 2026-05-29 | TRUE | 2026-04-01 | 2026-05-29 | [6 empty] | 11May26-this needs to be driven by a Program Manager to ensure competency development & mapping is done correctly. Michele to confirm which PM should lead this task & appropriate target timing. 20May26-Moved to July due to change in Lead & SME |  | 88d |  |  |  | TRUE |  |  | No | 2026-04-01 | 2026-07-31 | 2026-03-31 16:53 | jennifer.b.wright@gevernova.com
AP-0745-2 | Ensure HA Advanced Controls competencies are reflected in Kahuna |  | AP-0865 | Ensure HA Advanced Controls competencies are reflected in KahunaAP-0865 | AP-0745 | AP-0745 | 1 | 2 | 0 | 1 | Benali Salim Messekine | mohammed.nizami@gevernova.com | jim.rosen@gevernova.com | Content Development | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to Coordinated with Program Manager, Kelly, SMEs | Not Started | TRUE |  | 2026-06-01 | 2026-08-31 | 2026-07-31 |  | 2026-06-01 | 2026-07-31 | [6 empty] | 11May26-Switch to Program Mgr to lead this to develop the maps before training is defined. 20May26-Moved to Aug due to change in Lead & SME |  | 66d |  | TRUE |  |  |  |  | No | 2026-06-01 | 2026-08-31 | 2026-03-31 16:57 | jennifer.b.wright@gevernova.com
AP-0745-3 | Develop HA Advanced Controls Course Materials & Identify Target Instructor(s) |  | AP-0866 | Develop HA Advanced Controls Course Materials & Identify Target Instructor(s)AP-0866 | AP-0745 | AP-0745 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com | Muhammad Ahmed Ijaz | jim.rosen@gevernova.com | Content Development |  | In Progress | TRUE |  | 2026-03-01 | 2026-07-31 |  |  | 2026-03-01 | 2026-07-31 | [8 empty] | 111d |  |  |  | TRUE |  |  | Yes | 2026-03-01 | 2026-07-31 | 2026-03-31 16:57 | jennifer.b.wright@gevernova.com
AP-0745-4 | Load HA Advanced Controls course into our relevant systems |  | AP-0867 | Load HA Advanced Controls course into our relevant systemsAP-0867 | AP-0745 | AP-0745 | 1 | 4 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) 3. Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-06-01 | 2026-07-31 |  |  | 2026-06-01 | 2026-07-31 | [8 empty] | 45d |  | TRUE |  | TRUE |  |  | Yes | 2026-06-01 | 2026-07-31 | 2026-03-31 16:57 | jennifer.b.wright@gevernova.com
AP-0745-5 | Deliver HA Advanced Controls Pilot session |  | AP-0864 | Deliver HA Advanced Controls Pilot sessionAP-0864 | AP-0745 | AP-0745 | 1 | 5 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2026-08-01 | 2026-09-30 |  |  | 2026-08-01 | 2026-09-30 | [8 empty] | 44d | [6 empty] | Yes | 2026-08-01 | 2026-09-30 | 2026-03-31 16:57 | jennifer.b.wright@gevernova.com
AP-0747 | Digital Class Photos Display |  | AP-0747 | Digital Class Photos DisplayAP-0747 | #INVALID COLUMN VALUE | Top | 0 | 180 | 1 | 0 | jim.rosen@gevernova.com | daniel.barrera1@gevernova.com, Jennifer Wright, lee.s.fielding@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements | Develop a solution to share Class Photos digitally at the HLC | Complete |  |  | 2026-02-01 | 2026-05-29 |  |  | 2026-02-01 | 2026-06-30 | Customer Delivery Internal Ops Programs & Competency | Craft FE OSS |  |  | Other |  |  | https://gevernova.ent.box.com/file/2248410599273 | 86d |  |  |  |  | TRUE |  | Yes | 2026-02-01 | 2026-05-29 | 2026-01-13 13:18 | jennifer.b.wright@ge.com
AP-0747-1 | Select Digital Class Photos Display Tool/System |  | AP-0748 | Select Digital Class Photos Display Tool/SystemAP-0748 | AP-0747 | AP-0747 | 1 | 1 | 0 | 1 | jim.rosen@gevernova.com | daniel.barrera1@gevernova.com, Jennifer Wright, lee.s.fielding@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE | On Track | 2026-02-01 | 2026-04-30 |  |  | 2026-02-01 | 2026-03-31 | Customer Delivery Internal Ops Programs & Competency | Craft FE OSS |  |  | Other |  | 09Mar26-Move to April to allow time to review & select correct tool | n/a-report at parent level | 65d | [6 empty] | Yes | 2026-02-01 | 2026-04-30 | 2026-01-13 13:20 | jennifer.b.wright@ge.com
AP-0747-2 | Develop Digital Class Photos Display Tool/System & Process |  | AP-0749 | Develop Digital Class Photos Display Tool/System & ProcessAP-0749 | AP-0747 | AP-0747 | 1 | 2 | 0 | 1 | jim.rosen@gevernova.com | daniel.barrera1@gevernova.com, Jennifer Wright, lee.s.fielding@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE | On Track | 2026-04-01 | 2026-05-29 |  |  | 2026-04-01 | 2026-05-29 | Customer Delivery Internal Ops Programs & Competency | Craft FE OSS |  |  | Other |  |  | n/a-report at parent level | 43d |  |  |  |  | TRUE |  | Yes | 2026-04-01 | 2026-05-29 | 2026-01-13 13:20 | jennifer.b.wright@ge.com
AP-0747-3 | Pilot & Sustain Digital Class Photos Display Tool/System |  | AP-0750 | Pilot & Sustain Digital Class Photos Display Tool/SystemAP-0750 | AP-0747 | AP-0747 | 1 | 3 | 0 | 1 | jim.rosen@gevernova.com | daniel.barrera1@gevernova.com, Jennifer Wright, lee.s.fielding@gevernova.com | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE |  | 2026-05-01 | 2026-05-29 |  |  | 2026-06-01 | 2026-06-30 | Customer Delivery Internal Ops Programs & Competency | Craft FE OSS |  |  | Other |  |  | n/a-report at parent level | 21d |  |  |  |  | TRUE |  | Yes | 2026-05-01 | 2026-05-29 | 2026-01-13 13:20 | jennifer.b.wright@ge.com
AP-0756 | Adoption / monitoring / sustainment - Craft |  | AP-0756 | Adoption / monitoring / sustainment - CraftAP-0756 | #INVALID COLUMN VALUE | Top | 0 | 181 | 0 | 0 | erica.peredo@gevernova.com | Beyza Yaver, Carlo Fabregas, Marcela Bohorquez, Mouna Boucherka | leonardo.monzo1@gevernova.com | Develop Standard Work for TDM | Review, update and standardize the Leader Stanrdard Work, gathering feedback from the entire team | Not Started |  |  | 2026-03-01 | 2026-08-31 |  |  |  |  | Internal Ops Programs & Competency | Craft EHS OSS RM |  |  | Other |  |  |  | 132d | [6 empty] | No | 2026-03-01 | 2026-08-31 | 2026-01-15 08:57 | leonardo.monzo1@ge.com
AP-0758 | Repairs Support Consolidation |  | AP-0758 | Repairs Support ConsolidationAP-0758 | #INVALID COLUMN VALUE | Top | 0 | 182 | 1 | 0 | carlo.fabregas@gevernova.com | Beyza Yaver, Erica Mayeli Peredo Vazquez, Marcela Bohorquez, Mouna Boucherka | leonardo.monzo1@gevernova.com | TDM Performance | OSS Development plan, documentation and communication | In Progress |  | Delayed | 2026-02-01 | 2026-06-30 | 2026-05-29 | TRUE |  |  | Internal Ops Programs & Competency | EHS OSS RM |  |  | Other |  | 24Apr26-Moved to May to re-visit scope & add sub-tasks. Pending sub-task scope & target dates 4May26-Added sub tasks with modified dates to clarify scope & split LES vs. OSS |  | 108d |  |  | TRUE |  |  |  | No | 2026-02-01 | 2026-06-30 | 2026-01-15 08:57 | leonardo.monzo1@ge.com
AP-0758-1 | LES/NDT Inspectors Support Consolidation |  | AP-0880 | LES/NDT Inspectors Support ConsolidationAP-0880 | AP-0758 | AP-0758 | 1 | 1 | 0 | 1 | carlo.fabregas@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance | Develop Communication Protocols (Regional Rhythm meetings, Quarterly global segment rhythms) Define TDM KPIs (Fulfillment, Budget, etc?) Update TDM LSW | Complete |  | On Track | 2026-02-01 | 2026-05-22 |  |  |  |  | Internal Ops Programs & Competency | EHS OSS RM |  |  | Other |  |  | https://gevernova.ent.box.com/file/2248781738378 | 81d |  |  |  |  | TRUE |  | No | 2026-02-01 | 2026-05-22 | 2026-05-04 08:30 | jennifer.b.wright@gevernova.com
AP-0758-2 | OSS/Generator Support Consolidation |  | AP-0881 | OSS/Generator Support ConsolidationAP-0881 | AP-0758 | AP-0758 | 1 | 2 | 0 | 1 | carlo.fabregas@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance | Develop Communication Protocols (Regional Rhythm meetings, Quarterly global segment rhythms) Define TDM KPIs (Fulfillment, Budget, etc?) Update TDM LSW | In Progress |  |  | 2026-05-01 | 2026-06-30 |  | TRUE |  |  | Internal Ops Programs & Competency | EHS OSS RM |  |  | Other |  | 4May26-June date is placeholder, pending discussion to confirm scope/complexity |  | 43d |  |  | TRUE |  |  |  | No | 2026-05-01 | 2026-06-30 | 2026-05-04 08:36 | jennifer.b.wright@gevernova.com
AP-0759 | SMAX Reports Consolidation |  | AP-0759 | SMAX Reports ConsolidationAP-0759 | #INVALID COLUMN VALUE | Top | 0 | 183 | 0 | 0 | siawwei.tan@gevernova.com |  | leonardo.monzo1@gevernova.com | TDM Performance | Reports for Craft, FEs, FEPs, etc. | Not started |  |  | 2026-04-01 | 2026-10-30 |  |  |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  |  |  | 153d | [6 empty] | No | 2026-04-01 | 2026-10-30 | 2026-01-15 08:57 | leonardo.monzo1@ge.com
AP-0760 | FEP Tracker KPI (WBT - OJT Assignment) |  | AP-0760 | FEP Tracker KPI (WBT - OJT Assignment)AP-0760 | #INVALID COLUMN VALUE | Top | 0 | 184 | 1 | 0 | howayda.sabrymaher@gevernova.com | alyssa.mays@gevernova.com, brenda.romanvalle@gevernova.com, nimra.kazmi1@gevernova.com, paula.pedrozanino@gevernova.com, siawwei.tan@gevernova.com | leonardo.monzo1@gevernova.com | TDM Performance | Define the best path to track FEP's steps | In Progress |  | On Track | 2026-01-01 | 2026-11-30 | 2026-04-30 |  |  |  | Internal Ops Programs & Competency | FE |  |  | Other |  | 29Apr26-Added sub-tasks and adjusted dates to allow more realistic timeline to implement & pilot |  | 238d | [6 empty] | No | 2026-01-01 | 2026-11-30 | 2026-01-15 08:57 | leonardo.monzo1@ge.com
AP-0760-1 | Develop FEP KPI Reporting Tool, Data Sources & Instructions |  | AP-0877 | Develop FEP KPI Reporting Tool, Data Sources & InstructionsAP-0877 | AP-0760 | AP-0760 | 1 | 1 | 0 | 1 | howayda.sabrymaher@gevernova.com | alyssa.mays@gevernova.com, brenda.romanvalle@gevernova.com, daniel.barrera1@gevernova.com, Jennifer Wright, nimra.kazmi1@gevernova.com, paula.pedrozanino@gevernova.com, siawwei.tan@gevernova.com | leonardo.monzo1@gevernova.com | TDM Performance | Define KPIs, Determine how the KPIs are calculated, how the FEPs can find the data, where the reporting tool lives & document standard work | In Progress |  | Delayed | 2026-01-01 | 2026-07-31 |  |  |  |  | Internal Ops Programs & Competency | FE |  |  | Other |  |  |  | 152d |  |  |  | TRUE |  |  | No | 2026-01-01 | 2026-07-31 | 2026-04-29 12:38 | jennifer.b.wright@gevernova.com
AP-0760-2 | Pilot FEP KPI Reporting Tool |  | AP-0876 | Pilot FEP KPI Reporting ToolAP-0876 | AP-0760 | AP-0760 | 1 | 2 | 0 | 1 | howayda.sabrymaher@gevernova.com | alyssa.mays@gevernova.com, brenda.romanvalle@gevernova.com, nimra.kazmi1@gevernova.com, paula.pedrozanino@gevernova.com, siawwei.tan@gevernova.com | leonardo.monzo1@gevernova.com | TDM Performance | Pilot with FEPs | Not Started |  |  | 2026-07-01 | 2026-11-30 |  |  |  |  | Internal Ops Programs & Competency | FE |  |  | Other |  |  |  | 109d | [6 empty] | No | 2026-07-01 | 2026-11-30 | 2026-04-29 12:38 | jennifer.b.wright@gevernova.com
AP-0757 | Field & Region to Global Training Connection / Feedback |  | AP-0757 | Field & Region to Global Training Connection / FeedbackAP-0757 | #INVALID COLUMN VALUE | Top | 0 | 185 | 0 | 0 | marcela.bohorquez1@gevernova.com | Howayda Sabry Maher, Nimra Kazmi, Paula Andrea Pedroza Nino | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | Identify the best way to connect with Staff to improve communication, resources identification and news | In Progress |  | Delayed | 2026-02-01 | 2026-06-30 | 2026-05-29 | TRUE |  |  | Customer Delivery Internal Ops Programs & Competency |  |  |  | Other |  | 28May26-Moved out to re-vamp the plan & add subtasks (TBD) |  | 108d |  |  | TRUE |  |  |  | No | 2026-02-01 | 2026-06-30 | 2026-01-15 08:57 | leonardo.monzo1@ge.com
AP-0762 | Tools definition for each Training - Craft |  | AP-0762 | Tools definition for each Training - CraftAP-0762 | #INVALID COLUMN VALUE | Top | 0 | 186 | 0 | 0 | mouna.boucherka@gevernova.com | andrew.samples@gevernova.com, beyza.yaver@gevernova.com, carlo.fabregas@gevernova.com, erica.peredo@gevernova.com, harry.hanson@gevernova.com, luca.martino@gevernova.com, marcela.bohorquez1@gevernova.com | leonardo.monzo1@gevernova.com | Operational Simplification | Review our Internal Catalog, standardize and define what tools are needed to delivery each training session | Complete |  | On Track | 2026-01-01 | 2026-04-30 |  |  |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  | 09Mar26-moved to April for Mouna's availability. | https://gevernova.ent.box.com/file/2214525042795 | 86d | [6 empty] | No | 2026-01-01 | 2026-04-30 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0763 | Standardize Vendor Certificate (Welders, etc.) |  | AP-0763 | Standardize Vendor Certificate (Welders, etc.)AP-0763 | #INVALID COLUMN VALUE | Top | 0 | 187 | 0 | 0 | mouna.boucherka@gevernova.com | Beyza Yaver, Carlo Fabregas, Erica Mayeli Peredo Vazquez, Luca Martino, Marcela Bohorquez | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | Review our Internal Catalog, standardize and define what tools are needed to delivery each training session | Not started |  |  | 2026-02-01 | 2026-06-30 |  |  |  |  | Internal Ops Programs & Competency |  |  |  | Other |  |  |  | 108d |  |  | TRUE |  |  |  | No | 2026-02-01 | 2026-06-30 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0764 | Steam Turbine State of the Art |  | AP-0764 | Steam Turbine State of the ArtAP-0764 | #INVALID COLUMN VALUE | Top | 0 | 188 | 0 | 0 | nimra.kazmi1@gevernova.com | alyssa.mays@gevernova.com, howayda.sabrymaher@gevernova.com, pablo.schibli@gevernova.com, paula.pedrozanino@gevernova.com | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | State of the Art Seminar for Steam Turbine FEs | Not started |  |  | 2026-02-01 | 2026-07-31 |  |  |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  |  |  | 131d |  |  |  | TRUE |  |  | No | 2026-02-01 | 2026-07-31 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0766 | Competency FE Electrical/Excitation in Kahuna L1 |  | AP-0766 | Competency FE Electrical/Excitation in Kahuna L1AP-0766 | #INVALID COLUMN VALUE | Top | 0 | 189 | 0 | 0 | paula.pedrozanino@gevernova.com |  | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | Review Electrical/Excitation Competency Role to clarify expectations for Level 1 | Not started |  |  | 2026-04-01 | 2026-09-30 |  |  |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  |  |  | 131d | [6 empty] | No | 2026-04-01 | 2026-09-30 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0767 | Gas Turbine State of the Art |  | AP-0767 | Gas Turbine State of the ArtAP-0767 | #INVALID COLUMN VALUE | Top | 0 | 190 | 0 | 0 | paula.pedrozanino@gevernova.com | Alyssa Mays, Howayda Sabry Maher, Nimra Kazmi, sherif.khalifa@gevernova.com | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | State of the Art Seminar for Gas Turbine FEs | Not started |  |  | 2026-04-01 | 2026-09-30 |  |  |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  |  |  | 131d | [6 empty] | No | 2026-04-01 | 2026-09-30 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0761 | New Pacing Process Implementation |  | AP-0761 | New Pacing Process ImplementationAP-0761 | #INVALID COLUMN VALUE | Top | 0 | 191 | 0 | 0 | nimra.kazmi1@gevernova.com | alyssa.mays@gevernova.com, philip.ganssmann@gevernova.com, siawwei.tan@gevernova.com | leonardo.monzo1@gevernova.com | Define KPIs and DM for TDM team | Review, update and standardize the Pacing rhythm and tools across all regions | Not started |  |  | 2026-03-01 | 2026-06-30 |  |  |  |  | Internal Ops Programs & Competency |  |  |  | Other |  |  |  | 88d |  |  | TRUE |  |  |  | No | 2026-03-01 | 2026-06-30 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0768 | Competency Craft Review in Kahuna |  | AP-0768 | Competency Craft Review in KahunaAP-0768 | #INVALID COLUMN VALUE | Top | 0 | 192 | 0 | 0 | erica.peredo@gevernova.com | Beyza Yaver, Carlo Fabregas, Harry Hanson, Kelly Kirby, Luca Martino, Marcela Bohorquez, Mouna Boucherka | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | Review Craft Competency Roles to identify opportunities to redistribute task | Cancelled |  |  | 2026-02-01 | 2026-06-30 |  |  |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  | 17Apr26-Cancelled since this duplicates AP-0379 Review TM I-IV Competencies & AP-0380 Review Supervisor I & II Competencies |  | 108d |  |  | TRUE |  |  |  | No | 2026-02-01 | 2026-06-30 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0765 | Competency FE Controls in Kahuna L1 |  | AP-0765 | Competency FE Controls in Kahuna L1AP-0765 | #INVALID COLUMN VALUE | Top | 0 | 193 | 0 | 0 | brenda.romanvalle@gevernova.com | Howayda Sabry Maher, Mohammed Nizami, Nimra Kazmi, Paula Andrea Pedroza Nino, Siaw Wei Tan | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | Review Controls Competency Role to clarify expectations for Level 1 | Cancelled |  |  | 2026-02-01 | 2026-07-31 |  | TRUE |  |  | Delivery Internal Ops Programs & Competency |  |  |  | Other |  | 14May26-Cancelled. Scope is already covered by AP-214-3 Develop Competency Map - Controls Skills |  | 131d |  |  |  | TRUE |  |  | No | 2026-02-01 | 2026-07-31 | 2026-01-15 09:19 | leonardo.monzo1@ge.com
AP-0774 | Recertification tracker for Craft |  | AP-0774 | Recertification tracker for CraftAP-0774 | #INVALID COLUMN VALUE | Top | 0 | 194 | 0 | 0 | beyza.yaver@gevernova.com | Carlo Fabregas, Erica Mayeli Peredo Vazquez, Harry Hanson, Marcela Bohorquez, Mouna Boucherka | leonardo.monzo1@gevernova.com | Develop Standard Work for TDM | Create and standardize a tracker to plan and execute recertification | In Progress |  | Delayed | 2026-02-01 | 2026-06-30 | 2026-05-29 |  |  |  | Internal Ops Programs & Competency | [5 empty] | 11May26-Pending support from D&A Team. Moved to end of June. |  | 108d |  |  | TRUE |  |  |  | No | 2026-02-01 | 2026-06-30 | 2026-01-26 08:04 | leonardo.monzo1@ge.com
AP-0769 | Adoption / monitoring / sustainment - TDM |  | AP-0769 | Adoption / monitoring / sustainment - TDMAP-0769 | #INVALID COLUMN VALUE | Top | 0 | 195 | 0 | 0 | howayda.sabrymaher@gevernova.com | Brenda Roman Valle, Erica Mayeli Peredo Vazquez, Nimra Kazmi, Paula Andrea Pedroza Nino, Siaw Wei Tan | leonardo.monzo1@gevernova.com | Develop Standard Work for TDM | Review, update and standardize the Leader Stanrdard Work, gathering feedback from the entire team | Not started |  |  | 2026-03-01 | 2026-08-31 | [12 empty] | 132d | [6 empty] | No | 2026-03-01 | 2026-08-31 | 2026-01-26 08:04 | leonardo.monzo1@ge.com
AP-0770 | Training Team Alignment |  | AP-0770 | Training Team AlignmentAP-0770 | #INVALID COLUMN VALUE | Top | 0 | 196 | 0 | 0 | alyssa.mays@gevernova.com | James Rosen, michele.alcantar@gevernova.com, Philip Ganssmann | leonardo.monzo1@gevernova.com | Develop Standard Work for TDM | Create a schedule/plan/process to be informed, aligned and up to date with the other Training Teams (Delivery, P&D, Ops) | Not started |  |  | 2026-01-01 | 2026-06-30 | [12 empty] | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2026-01-26 08:04 | leonardo.monzo1@ge.com
AP-0771 | Feedback after 1 year promotion from FEP |  | AP-0771 | Feedback after 1 year promotion from FEPAP-0771 | #INVALID COLUMN VALUE | Top | 0 | 197 | 0 | 0 | alyssa.mays@gevernova.com | Howayda Sabry Maher, Paula Andrea Pedroza Nino, Siaw Wei Tan | leonardo.monzo1@gevernova.com | Field Feedback Loop (Quality / EHS) | Retrieve feedback from FEPs after 1 year billable in the field, to improve the learning experience | Not started |  | Delayed | 2026-01-01 | 2026-06-30 | 2026-03-31 | [9 empty] | 3/16/26-Moved to June to potentially use new Survey tool |  | 129d |  |  | TRUE |  |  |  | No | 2026-01-01 | 2026-06-30 | 2026-01-26 08:04 | leonardo.monzo1@ge.com
AP-0772 | Legislative Training in EU - Cost tracking |  | AP-0772 | Legislative Training in EU - Cost trackingAP-0772 | #INVALID COLUMN VALUE | Top | 0 | 198 | 0 | 0 | beyza.yaver@gevernova.com | Iuliia Zgonnik, Nimra Kazmi, Sian La-Borde | leonardo.monzo1@gevernova.com | Define KPIs and DM for TDM team | Consolidate the best tools to track and review the training costs associated to Legislative Trainings in EU, with the possibility to expand to other regions in the future | Complete |  | On Track | 2026-01-01 | 2026-04-30 | [11 empty] | https://gevernova.ent.box.com/file/2206272889952 | 86d | [6 empty] | No | 2026-01-01 | 2026-04-30 | 2026-01-26 08:04 | leonardo.monzo1@ge.com
AP-0775 | OFS Evaluation Gradebook |  | AP-0775 | OFS Evaluation GradebookAP-0775 | #INVALID COLUMN VALUE | Top | 0 | 199 | 1 | 0 | philip.ganssmann@gevernova.com | James Rosen | jim.rosen@gevernova.com | Operational Simplification |  | Complete |  | On Track | 2026-02-27 | 2026-03-31 |  |  |  |  | Customer Delivery Internal | [6 empty] | https://gevernova.ent.box.com/file/2176263376159 | 23d | [6 empty] | No | 2026-02-27 | 2026-03-31 | 2026-01-29 03:33 | philip.ganssmann@ge.com
AP-0775-1 | Create a Gradebook version to be tested; version will include Roll Call and Gradebook |  | AP-0776 | Create a Gradebook version to be tested; version will include Roll Call and GradebookAP-0776 | AP-0775 | AP-0775 | 1 | 1 | 0 | 1 | philip.ganssmann@gevernova.com | James Rosen | jim.rosen@gevernova.com | Operational Simplification |  | Complete | TRUE | On Track | 2026-02-27 | 2026-03-31 | [10 empty] | 26Feb26-Moved to March since Philip is OoO |  | 23d | [6 empty] | No | 2026-02-27 | 2026-03-31 | 2026-01-29 03:43 | philip.ganssmann@ge.com
AP-0775-2 | Collect and implement Gradebook feedback |  | AP-0777 | Collect and implement Gradebook feedbackAP-0777 | AP-0775 | AP-0775 | 1 | 2 | 0 | 1 | jim.rosen@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification |  | Complete | TRUE | On Track | 2026-03-01 | 2026-03-31 | [12 empty] | 23d | [6 empty] | Yes | 2026-03-01 | 2026-03-31 | 2026-01-29 03:43 | philip.ganssmann@ge.com
AP-0775-3 | Add LCMS links and statistics to Gradebook |  | AP-0778 | Add LCMS links and statistics to GradebookAP-0778 | AP-0775 | AP-0775 | 1 | 3 | 0 | 1 | philip.ganssmann@gevernova.com |  | jim.rosen@gevernova.com | Operational Simplification |  | Complete | TRUE | On Track | 2026-03-01 | 2026-03-31 | [12 empty] | 23d | [6 empty] | No | 2026-03-01 | 2026-03-31 | 2026-01-29 03:43 | philip.ganssmann@ge.com
AP-0779 | Develop e4 Point Training |  | AP-0779 | Develop e4 Point TrainingAP-0779 | #INVALID COLUMN VALUE | Top | 0 | 200 | 1 | 0 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Add e4 Point Training to our scope. Content is available from SMEs, need to incorporate into our offerings as standalone plus build into ELT program. Instead of buying equipment for all turbines, can we get testing rig from MRT instead? And we already have a rotating device planned for 7E. Can we use rented tooling for now until most people are trained and tooling is fully utilized in the field. Need to be able to deliver this training this summer. | In Progress |  |  | 2026-02-10 | 2026-07-31 |  |  | 2026-02-10 | 2026-07-31 | Delivery Internal Ops | FE |  |  | Intake Review | Dave Runkel | 10Feb26-Added from Intake Request # 13482094884 |  | 124d |  |  |  | TRUE |  |  | Yes | 2026-02-10 | 2026-07-31 | 2026-02-10 09:15 | jennifer.b.wright@ge.com
AP-0779-1 | Develop List of e4 Point Competencies & identify which can be delivered via training vs. OJT/other |  | AP-0780 | Develop List of e4 Point Competencies & identify which can be delivered via training vs. OJT/otherAP-0780 | AP-0779 | AP-0779 | 1 | 1 | 0 | 1 | ankita.gupta@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Coordinated with PLL, SMEs & Program Mgr | Complete | TRUE | On Track | 2026-02-10 | 2026-05-29 | 2026-03-31 |  | 2026-02-10 | 2026-03-31 | Delivery Internal Ops | FE |  |  |  |  | 19May26-Reopened and moved to May to allow team to finalize details. Changed Lead to Ankita |  | 79d |  |  |  |  | TRUE |  | No | 2026-02-10 | 2026-05-29 | 2026-02-10 09:25 | jennifer.b.wright@ge.com
AP-0779-2 | Ensure e4 Point competencies are reflected in Kahuna |  | AP-0781 | Ensure e4 Point competencies are reflected in KahunaAP-0781 | AP-0779 | AP-0779 | 1 | 2 | 0 | 1 | ankita.gupta@gevernova.com | Sherif.Khalifa@gevernova.com | jim.rosen@gevernova.com | Content Development | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to Coordinated with Program Manager, Kelly, SMEs | In Progress | TRUE | At Risk | 2026-03-01 | 2026-06-30 | 2026-05-29 | TRUE | 2026-03-01 | 2026-04-30 | Delivery Internal Ops | FE |  |  |  |  | 30Apr26-Moved to May to allow time to coordinate with Kelly 11May26-this needs to be driven by a Program Manager to ensure competency mapping is done correctly. Michele to confirm which PM should lead this task & appropriate target timing. 19May26-Confirmed Ankita as Lead and tentatively moved to June |  | 88d |  |  | TRUE |  |  |  | No | 2026-03-01 | 2026-06-30 | 2026-02-10 09:25 | jennifer.b.wright@ge.com
AP-0779-3 | Assemble/Develop e4 Point Course Materials & Identify Target Instructor(s) |  | AP-0782 | Assemble/Develop e4 Point Course Materials & Identify Target Instructor(s)AP-0782 | AP-0779 | AP-0779 | 1 | 3 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Core content should be available from SMEs | Complete | TRUE | On Track | 2026-02-10 | 2026-04-30 |  |  | 2026-02-10 | 2026-04-30 | Delivery Internal Ops | FE | [6 empty] | 58d | [6 empty] | Yes | 2026-02-10 | 2026-04-30 | 2026-02-10 09:25 | jennifer.b.wright@ge.com
AP-0779-4 | Load e4 Point course into our relevant systems |  | AP-0783 | Load e4 Point course into our relevant systemsAP-0783 | AP-0779 | AP-0779 | 1 | 4 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | 1. Standalone Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies (update outline for ELT too?) 2. Standalone Course Schedule Template loaded into UDC (work with Scheduler) & ELT schedule updated too? 3. Standalone Course added to target instructor competencies 4. Standalone Course Materials loaded in Xyleme & ELT Materials updated? | In Progress | TRUE | On Track | 2026-05-01 | 2026-05-29 |  |  | 2026-05-01 | 2026-05-29 | Delivery Internal Ops | FE | [6 empty] | 21d |  |  |  |  | TRUE |  | Yes | 2026-05-01 | 2026-05-29 | 2026-02-10 09:25 | jennifer.b.wright@ge.com
AP-0779-5 | Deliver e4 Point Pilot session |  | AP-0784 | Deliver e4 Point Pilot sessionAP-0784 | AP-0779 | AP-0779 | 1 | 5 | 0 | 1 | Sherif.Khalifa@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Based on pilot session feedback, finalize Material and modify outline if needed | Cancelled | TRUE |  | 2026-06-01 | 2026-07-31 |  |  | 2026-06-01 | 2026-07-31 | Delivery Internal Ops | FE |  |  |  |  | 11May26-cancelled. No pilot to be delivered at this time |  | 45d |  | TRUE |  | TRUE |  |  | Yes | 2026-06-01 | 2026-07-31 | 2026-02-10 09:25 | jennifer.b.wright@ge.com
AP-0785 | Revamp ICS-3 Course |  | AP-0785 | Revamp ICS-3 CourseAP-0785 | #INVALID COLUMN VALUE | Top | 0 | 201 | 1 | 0 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Develop advanced-level ICS training that will serve as the next step beyond our current ICS Level II program (which we plan to rename to ICS Level I for clarity). The new course will focus on more advanced concepts, including comprehensive plant‑wide system tuning and operational strategies. | Not Started |  |  | 2026-07-01 | 2026-10-30 |  |  |  |  | Delivery Internal Ops | FE |  |  | Intake Review | Toni Mounder Maalouf | 10Feb26-Added from Intake Request # 15084088355 |  | 88d | [6 empty] | Yes | 2026-07-01 | 2026-10-30 | 2026-02-10 09:33 | jennifer.b.wright@ge.com
AP-0785-1 | Develop List of ICS-3 Competencies & identify which can be delivered via training vs. OJT/other |  | AP-0786 | Develop List of ICS-3 Competencies & identify which can be delivered via training vs. OJT/otherAP-0786 | AP-0785 | AP-0785 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Coordinated with PLL, SMEs & Program Mgr | Not Started | TRUE |  | 2026-07-01 | 2026-07-31 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 23d |  |  |  | TRUE |  |  | Yes | 2026-07-01 | 2026-07-31 | 2026-02-10 09:37 | jennifer.b.wright@ge.com
AP-0785-2 | Ensure ICS-3 competencies are reflected in Kahuna |  | AP-0787 | Ensure ICS-3 competencies are reflected in KahunaAP-0787 | AP-0785 | AP-0785 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to Coordinated with Program Manager, Kelly, SMEs | Not Started | TRUE |  | 2026-08-01 | 2026-08-31 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 22d | [6 empty] | Yes | 2026-08-01 | 2026-08-31 | 2026-02-10 09:37 | jennifer.b.wright@ge.com
AP-0785-3 | Assemble/Develop ICS-3 Course Materials & Identify Target Instructor(s) |  | AP-0788 | Assemble/Develop ICS-3 Course Materials & Identify Target Instructor(s)AP-0788 | AP-0785 | AP-0785 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development |  | Not Started | TRUE |  | 2026-08-01 | 2026-08-31 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 22d | [6 empty] | Yes | 2026-08-01 | 2026-08-31 | 2026-02-10 09:37 | jennifer.b.wright@ge.com
AP-0785-4 | Load ICS-3 course into our relevant systems |  | AP-0789 | Load ICS-3 course into our relevant systemsAP-0789 | AP-0785 | AP-0785 | 1 | 4 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | 1. Update Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Update Course Schedule Template in UDC (work with Scheduler) 3. Ensure Course added to target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-08-01 | 2026-08-31 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 22d | [6 empty] | Yes | 2026-08-01 | 2026-08-31 | 2026-02-10 09:37 | jennifer.b.wright@ge.com
AP-0785-5 | Deliver ICS-3 Pilot session |  | AP-0790 | Deliver ICS-3 Pilot sessionAP-0790 | AP-0785 | AP-0785 | 1 | 5 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Development | Based on pilot session feedback, finalize Material and modify outline if needed | Not Started | TRUE |  | 2026-09-01 | 2026-10-30 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 44d | [6 empty] | Yes | 2026-09-01 | 2026-10-30 | 2026-02-10 09:37 | jennifer.b.wright@ge.com
AP-0791 | Build Integrated Finance Pacing Dashboard |  | AP-0791 | Build Integrated Finance Pacing DashboardAP-0791 | #INVALID COLUMN VALUE | Top | 0 | 202 | 1 | 0 | daniel.barrera1@gevernova.com | András Pintér, Jennifer Wright, philip.ganssmann@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification | Develop a simplified solution to integrate Budget, Forecast & Actual data from various data sources for improved pacing awareness | In Progress |  |  | 2026-02-01 | 2026-09-30 |  |  |  |  | Customer Delivery Internal Ops Programs & Competency |  | OFS-Cost-Cost-Gross Margin | C |  |  |  |  | 174d | [6 empty] | No | 2026-02-01 | 2026-09-30 | 2026-02-17 14:55 | jennifer.b.wright@ge.com
AP-0791-1 | Assemble & Sort data sources & owners for all relevant budget categories |  | AP-0792 | Assemble & Sort data sources & owners for all relevant budget categoriesAP-0792 | AP-0791 | AP-0791 | 1 | 1 | 0 | 1 | daniel.barrera1@gevernova.com | András Pintér, Jennifer Wright, philip.ganssmann@gevernova.com | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete | TRUE | On Track | 2026-02-01 | 2026-04-30 | 2026-03-31 |  |  |  | Customer Delivery Internal Ops Programs & Competency | [5 empty] | 25Mar26-Moved to April to accommodate more time for understanding the data sources & relationships |  | 65d | [6 empty] | No | 2026-02-01 | 2026-04-30 | 2026-02-17 14:59 | jennifer.b.wright@ge.com
AP-0791-2 | Design solution for Budget Pacing & Tracking |  | AP-0793 | Design solution for Budget Pacing & TrackingAP-0793 | AP-0791 | AP-0791 | 1 | 2 | 0 | 1 | daniel.barrera1@gevernova.com | Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification |  | Complete | TRUE | On Track | 2026-04-01 | 2026-04-30 |  |  |  |  | Customer Delivery Internal Ops Programs & Competency | [7 empty] | 22d | [6 empty] | No | 2026-04-01 | 2026-04-30 | 2026-02-17 14:59 | jennifer.b.wright@ge.com
AP-0791-3 | Build solution for Budget Pacing & Tracking |  | AP-0794 | Build solution for Budget Pacing & TrackingAP-0794 | AP-0791 | AP-0791 | 1 | 3 | 0 | 1 | daniel.barrera1@gevernova.com | Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification |  | Not Started |  |  | 2026-05-01 | 2026-06-30 |  |  |  |  | Customer Delivery Internal Ops Programs & Competency | [7 empty] | 43d | 617 |  | TRUE |  |  |  | No | 2026-05-01 | 2026-06-30 | 2026-02-17 14:59 | jennifer.b.wright@ge.com
AP-0791-4 | Pilot & Track effectiveness of Finance Dashboard & Process |  | AP-0795 | Pilot & Track effectiveness of Finance Dashboard & ProcessAP-0795 | AP-0791 | AP-0791 | 1 | 4 | 0 | 1 | daniel.barrera1@gevernova.com | Jennifer Wright, Philip Ganssmann | philip.ganssmann@gevernova.com | Operational Simplification |  | Not Started |  |  | 2026-07-01 | 2026-09-30 |  |  |  |  | Customer Delivery Internal Ops Programs & Competency | [7 empty] | 66d | 618 | [5 empty] | No | 2026-07-01 | 2026-09-30 | 2026-02-17 14:59 | jennifer.b.wright@ge.com
AP-0796 | Spares for Mk VIe Panels in Birr |  | AP-0796 | Spares for Mk VIe Panels in BirrAP-0796 | #INVALID COLUMN VALUE | Top | 0 | 203 | 0 | 0 | pablo.schibli@gevernova.com | Mohammed Nizami | jim.rosen@gevernova.com | Content Quality & Improvements | Acquire spares for Mark VIe panels at the BLC | In Progress |  |  | 2026-02-01 | 2026-06-30 |  |  |  |  | Customer Delivery |  |  |  | NPS Review | johann.daxer@gevernova.com | 17Feb26-Added as result of Issues from January Customer NPS review |  | 108d |  |  | TRUE |  |  |  | Yes | 2026-02-01 | 2026-06-30 | 2026-02-17 15:58 | jennifer.b.wright@ge.com
AP-0805 | Improve Controls Rooms Setup & Hardware |  | AP-0805 | Improve Controls Rooms Setup & HardwareAP-0805 | #INVALID COLUMN VALUE | Top | 0 | 204 | 1 | 0 | mohammed.nizami@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Content Quality & Improvements | Address NPS complaints about computers, hardware, infrastructure. | In Progress |  |  | 2026-02-01 | 2026-06-30 |  |  | 2026-02-01 | 2026-06-30 | Customer Delivery Internal |  |  |  | NPS Review | johann.daxer@gevernova.com | 18Feb26-Added as result of Issues from January Customer NPS review |  | 108d |  |  | TRUE |  |  |  | Yes | 2026-02-01 | 2026-06-30 | 2026-02-18 13:22 | jennifer.b.wright@ge.com
AP-0805-1 | Investigate issues and options for improving Controls room setup (3209), incl. hardware, cabling, etc. |  | AP-0806 | Investigate issues and options for improving Controls room setup (3209), incl. hardware, cabling, etc.AP-0806 | AP-0805 | AP-0805 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE |  | 2026-02-01 | 2026-02-27 |  |  | 2026-02-01 | 2026-02-27 | Customer Delivery Internal | [7 empty] | 21d | [6 empty] | Yes | 2026-02-01 | 2026-02-27 | 2026-02-18 13:26 | jennifer.b.wright@ge.com
AP-0805-2 | Develop budget for potential Controls Room (3209) improvement solutions & review options with Leadership |  | AP-0807 | Develop budget for potential Controls Room (3209) improvement solutions & review options with LeadershipAP-0807 | AP-0805 | AP-0805 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE | On Track | 2026-03-01 | 2026-03-31 |  |  | 2026-03-01 | 2026-03-31 | Customer Delivery Internal | [7 empty] | 23d | [6 empty] | Yes | 2026-03-01 | 2026-03-31 | 2026-02-18 13:26 | jennifer.b.wright@ge.com
AP-0805-3 | Implement Controls Rooms improvements |  | AP-0808 | Implement Controls Rooms improvementsAP-0808 | AP-0805 | AP-0805 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com | Stephen Urban | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-04-01 | 2026-06-30 |  |  | 2026-04-01 | 2026-06-30 | Customer Delivery Internal | [5 empty] | Timing TBD based on results from above task |  | 65d |  |  | TRUE |  |  |  | Yes | 2026-04-01 | 2026-06-30 | 2026-02-18 13:26 | jennifer.b.wright@ge.com
AP-0809 | Improve Entry Level Gas Turbine Mark Vle |  | AP-0809 | Improve Entry Level Gas Turbine Mark VleAP-0809 | #INVALID COLUMN VALUE | Top | 0 | 205 | 1 | 0 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Standardize schedule and content so any instructor can deliver. Current material lives in Box; focus is content quality, not formatting. Target: stabilize content by end of current ELT, then hand off to Xyleme team. | In Progress |  |  | 2026-02-01 | 2026-12-31 | 2026-08-31 |  | 2026-02-01 | 2026-08-31 | Delivery Internal Ops | FE |  |  | NPS Review |  | 19Feb26-Added as result of Issues from January Internal NPS review 2Apr26-Moved back to ID improvements in Spring/Summer session and pilot in Summer/Fall session |  | 240d | [6 empty] | Yes | 2026-02-01 | 2026-12-31 | 2026-02-18 13:38 | jennifer.b.wright@ge.com
AP-0809-1 | Review GT MkVIe ELT content to identify improvements |  | AP-0810 | Review GT MkVIe ELT content to identify improvementsAP-0810 | AP-0809 | AP-0809 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | In Progress | TRUE | Delayed | 2026-02-01 | 2026-07-31 | 2026-03-31 |  | 2026-02-01 | 2026-03-31 | Delivery Internal Ops | FE |  |  |  |  | 2Apr26-Moved back to ID improvements in Spring/Summer session and pilot in Summer/Fall session |  | 131d |  |  |  | TRUE |  |  | Yes | 2026-02-01 | 2026-07-31 | 2026-02-19 12:23 | jennifer.b.wright@ge.com
AP-0809-2 | Develop & Pilot Improvements in next ELT |  | AP-0811 | Develop & Pilot Improvements in next ELTAP-0811 | AP-0809 | AP-0809 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-04-01 | 2026-11-30 | 2026-07-31 |  | 2026-04-01 | 2026-07-31 | Delivery Internal Ops | FE |  |  |  |  | 2Apr26-Moved back to ID improvements in Spring/Summer session and pilot in Summer/Fall session |  | 174d | [6 empty] | Yes | 2026-04-01 | 2026-11-30 | 2026-02-19 12:23 | jennifer.b.wright@ge.com
AP-0809-3 | Update Course info in relevant systems, as applicable |  | AP-0812 | Update Course info in relevant systems, as applicableAP-0812 | AP-0809 | AP-0809 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | 1. Update Course outline in MM (will feed to UDC & Xyleme) 2. Update Course Schedule Template in UDC (work with Scheduler) 3. Ensure Course added to all target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-08-01 | 2026-12-31 | 2026-08-31 |  | 2026-08-01 | 2026-08-31 | Delivery Internal Ops | FE |  |  |  |  | 2Apr26-Moved back to ID improvements in Spring/Summer session and pilot in Summer/Fall session |  | 110d | [6 empty] | Yes | 2026-08-01 | 2026-12-31 | 2026-02-19 12:23 | jennifer.b.wright@ge.com
AP-0813 | Standardize Internal Control Server Thin Client course |  | AP-0813 | Standardize Internal Control Server Thin Client courseAP-0813 | #INVALID COLUMN VALUE | Top | 0 | 206 | 1 | 0 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Class expanding to a 10-day format to increase hands-on time. (I-CON23403). Need to review & update content with engineering to ensure it is correct & standardized | In Progress |  |  | 2026-02-01 | 2026-08-31 |  |  | 2026-02-01 | 2026-08-31 | Delivery Internal Ops | FE |  |  | NPS Review |  | 19Feb26-Added as result of Issues from January Internal NPS review |  | 152d | [6 empty] | Yes | 2026-02-01 | 2026-08-31 | 2026-02-19 12:29 | jennifer.b.wright@ge.com
AP-0813-1 | Review Internal Control Server Thin Client Content with Engineering |  | AP-0814 | Review Internal Control Server Thin Client Content with EngineeringAP-0814 | AP-0813 | AP-0813 | 1 | 1 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Complete | TRUE | On Track | 2026-02-01 | 2026-03-31 |  |  | 2026-02-01 | 2026-03-31 | Delivery Internal Ops | FE | [6 empty] | 43d | [6 empty] | Yes | 2026-02-01 | 2026-03-31 | 2026-02-19 12:42 | jennifer.b.wright@ge.com
AP-0813-2 | Update/Standardize Content |  | AP-0815 | Update/Standardize ContentAP-0815 | AP-0813 | AP-0813 | 1 | 2 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-04-01 | 2026-06-30 |  |  | 2026-04-01 | 2026-06-30 | Delivery Internal Ops | FE | [6 empty] | 65d |  |  | TRUE |  |  |  | Yes | 2026-04-01 | 2026-06-30 | 2026-02-19 12:42 | jennifer.b.wright@ge.com
AP-0813-3 | Pilot updated materials |  | AP-0816 | Pilot updated materialsAP-0816 | AP-0813 | AP-0813 | 1 | 3 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-06-01 | 2026-07-31 |  |  | 2026-06-01 | 2026-07-31 | Delivery Internal Ops | FE | [6 empty] | 45d |  | TRUE |  | TRUE |  |  | Yes | 2026-06-01 | 2026-07-31 | 2026-02-19 12:42 | jennifer.b.wright@ge.com
AP-0813-4 | Update Course info in relevant systems, as applicable |  | AP-0817 | Update Course info in relevant systems, as applicableAP-0817 | AP-0813 | AP-0813 | 1 | 4 | 0 | 1 | mohammed.nizami@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | 1. Update Course outline in MM (will feed to UDC & Xyleme) 2. Update Course Schedule Template in UDC (work with Scheduler) 3. Ensure Course added to all target instructor competencies 4. Course Materials loaded in Xyleme | Not Started | TRUE |  | 2026-08-01 | 2026-08-31 |  |  | 2026-08-01 | 2026-08-31 | Delivery Internal Ops | FE | [6 empty] | 22d | [6 empty] | Yes | 2026-08-01 | 2026-08-31 | 2026-02-19 12:42 | jennifer.b.wright@ge.com
AP-0818 | Improve Aero Mark VIe OE Materials & Hardware |  | AP-0818 | Improve Aero Mark VIe OE Materials & HardwareAP-0818 | #INVALID COLUMN VALUE | Top | 0 | 207 | 1 | 0 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | In Progress |  |  | 2026-01-01 | 2026-12-31 |  |  | 2026-01-01 | 2026-12-31 | Customer Delivery Ops |  |  |  | NPS Review | johann.daxer@gevernova.com | 23Feb26-Added as result of Issues from January Customer NPS review |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2026-02-23 10:41 | jennifer.b.wright@ge.com
AP-0818-1 | Update Aero Mark VIe OE Course Materials & Hardware. |  | AP-0819 | Update Aero Mark VIe OE Course Materials & Hardware.AP-0819 | AP-0818 | AP-0818 | 1 | 1 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | Update Aero Mark VIe OE course materials. Purchase & set up improved hardware | In Progress | TRUE |  | 2026-01-01 | 2026-09-30 |  |  | 2026-01-01 | 2026-09-30 | Customer Delivery Ops | [7 empty] | 195d | [6 empty] | Yes | 2026-01-01 | 2026-09-30 | 2026-02-23 10:42 | jennifer.b.wright@ge.com
AP-0818-2 | Update Aero Mark VIe OE course into our relevant systems |  | AP-0820 | Update Aero Mark VIe OE course into our relevant systemsAP-0820 | AP-0818 | AP-0818 | 1 | 2 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements | i.e. outlines, schedules, etc. | Not Started | TRUE |  | 2026-09-01 | 2026-10-30 |  |  | 2026-09-01 | 2026-10-30 | Customer Delivery Ops | [7 empty] | 44d | [6 empty] | Yes | 2026-09-01 | 2026-10-30 | 2026-02-23 10:42 | jennifer.b.wright@ge.com
AP-0818-3 | Deliver Aero Mark VIe OE Pilot session |  | AP-0821 | Deliver Aero Mark VIe OE Pilot sessionAP-0821 | AP-0818 | AP-0818 | 1 | 3 | 0 | 1 | gregoryd.walker@gevernova.com |  | jim.rosen@gevernova.com | Content Quality & Improvements |  | Not Started | TRUE |  | 2026-11-01 | 2026-12-31 |  |  | 2026-11-01 | 2026-12-31 | Customer Delivery Ops | [7 empty] | 45d | [6 empty] | Yes | 2026-11-01 | 2026-12-31 | 2026-02-23 10:42 | jennifer.b.wright@ge.com
AP-0823 | Welding & Pipefitting Training & Career Progression Framework |  | AP-0823 | Welding & Pipefitting Training & Career Progression FrameworkAP-0823 | #INVALID COLUMN VALUE | Top | 0 | 208 | 0 | 0 | luca.martino@gevernova.com | Harry Hanson, Michael Randolph | michele.alcantar@gevernova.com | Programs | Development of competencies & maps is being addressed by AP-0293. This Project would cover the research of global requirements for the role, definition of corresponding training path, and updates to existing maps as needed. Scope is not likely to develop new training material. Just defining which available vendor trainings are required. | Not Started |  |  | 2026-05-01 | 2026-12-31 |  |  | 2026-05-01 | 2026-12-31 | Internal Programs & Competency | Craft |  |  | Intake Review | Michael Randolph | 23Feb26-Added from Intake Review # 15094732721 |  | 175d | [6 empty] | No | 2026-05-01 | 2026-12-31 | 2026-02-24 12:45 | jennifer.b.wright@ge.com
AP-0824 | Craft E&I/I&C Training and Career Progression Framework |  | AP-0824 | Craft E&I/I&C Training and Career Progression FrameworkAP-0824 | #INVALID COLUMN VALUE | Top | 0 | 209 | 0 | 0 | luca.martino@gevernova.com | Harry Hanson, Michael Randolph | michele.alcantar@gevernova.com | Programs | We believe that development of competencies & maps is being addressed by AP-0698, but need to confirm that Craft I&C and E&I are the same roles globally, just different terminology. This Project would cover the research of global requirements for the role, definition of corresponding training path, and updates to existing maps as needed. Scope is not likely to develop new training material. Just defining which available vendor trainings are required. | Not Started |  |  | 2026-05-01 | 2026-12-31 |  |  | 2026-05-01 | 2026-12-31 | Internal Programs & Competency | Craft |  |  | Intake Review | Michael Randolph | 23Feb26-Added from Intake Review # 15094732721 |  | 175d | [6 empty] | No | 2026-05-01 | 2026-12-31 | 2026-02-24 12:56 | jennifer.b.wright@ge.com
AP-0833 | Delivery Load & Variability Visualization |  | AP-0833 | Delivery Load & Variability VisualizationAP-0833 | #INVALID COLUMN VALUE | Top | 0 | 210 | 0 | 0 | jim.rosen@gevernova.com | daniel.barrera1@gevernova.com, Jennifer Wright, philip.ganssmann@gevernova.com | jim.rosen@gevernova.com | Operational Simplification | Explore a simple, shared visualization that answers one question well: “Given what is hitting Delivery today (and what’s coming), how much instability are we asking it to absorb?” Purpose A system-pressure indicator, not a performance or utilization metric. The goal is visibility and shared accountability, not scoring Delivery. View 1: Today’s Delivery Pressure (Snapshot) = A composite pressure score (0–100) per PLL, shown as a thermometer or stacked bar, composed of Baseline Load & Volatility Drivers View 2: Pressure Over Time (Forward-Looking) = A line chart showing the same pressure index over time, comparing Current committed schedule & Forecast including known change orders, APs, and planned hires | Not Started |  |  | 2026-05-01 | 2026-12-31 |  |  | 2026-05-01 | 2026-12-31 | Delivery |  |  |  | Other |  | 10Mar26-Added per Feb emails with Jim & Phlip |  | 175d | [6 empty] | Yes | 2026-05-01 | 2026-12-31 | 2026-03-10 08:15 | jennifer.b.wright@gevernova.com
AP-0844 | Negotiations Training |  | AP-0844 | Negotiations TrainingAP-0844 | #INVALID COLUMN VALUE | Top | 0 | 211 | 0 | 0 | luca.martino@gevernova.com | Tamara Biediger | michele.alcantar@gevernova.com | Content Development | There will be multiple hiring of new project managers (customer facing) in the tendering and Sales team, and there is the need to lay down the negotiations fundamentals for them, support experienced PMs with a structure negotiation frame and provide knowledge and understanding of tariffs mechanism applied by countries. | In Progress |  |  | 2026-02-01 | 2026-09-30 |  |  | 2026-02-01 | 2026-09-30 |  | Other |  |  | Other | Shadi Saleh | 23Mar26-Added per request from Luca & Dave, This is outside OFS scope but they asked for our help in guiding them in the creation of an internal training class to avoid spending a lot of money with an external vendor |  | 174d | [6 empty] | No | 2026-02-01 | 2026-09-30 | 2026-03-23 07:25 | jennifer.b.wright@gevernova.com
AP-0845 | Visual Management Certification Program |  | AP-0845 | Visual Management Certification ProgramAP-0845 | #INVALID COLUMN VALUE | Top | 0 | 212 | 0 | 0 | benalisalim.messekine@gevernova.com |  | michele.alcantar@gevernova.com | Content Development | The Methods team will build the training material that will be used by the vendor to create an online training. They need our support to check the material they developed, PM the vendor training development & LMS implementation.The Method team has the budget to cover the cost for the course development. Consider working with Mediant Labs to develop the course in Xyleme | Not Started |  |  | 2026-05-01 | 2026-09-30 |  |  | 2026-05-01 | 2026-09-30 |  | FE |  |  | Intake Review | Rebecca Messmann | 24Mar26-Added from Intake Review # 15209319019 |  | 109d | [6 empty] | No | 2026-05-01 | 2026-09-30 | 2026-03-24 09:48 | jennifer.b.wright@gevernova.com
AP-0846 | Fast Stator Rewind Hands-on Improvements |  | AP-0846 | Fast Stator Rewind Hands-on ImprovementsAP-0846 | #INVALID COLUMN VALUE | Top | 0 | 213 | 0 | 0 | harry.hanson@gevernova.com |  | James Rosen | Content Quality & Improvements | Develop materials for new/improved hands-on activities and purchase & prepare hands-on equipment by end of May for use in Summer training sessions | In Progress |  | Delayed | 2026-01-01 | 2026-12-31 | 2026-06-30 | TRUE | 2026-01-01 | 2026-05-29 | Delivery | OSS |  |  | NPS Review |  | 22May26-Moved to June due to PO delays. TBD if pilot is scheduled 9Jun26-Moved to Dec. Equipment still not delivered, won't be ready for Summer sessions. May be used for Nov session if it's not cancelled. |  | 261d | [6 empty] | Yes | 2026-01-01 | 2026-12-31 | 2026-03-24 12:29 | jennifer.b.wright@gevernova.com
AP-0868 | Generator Protection Panel (GPP) Training with Relay testing |  | AP-0868 | Generator Protection Panel (GPP) Training with Relay testingAP-0868 | #INVALID COLUMN VALUE | Top | 0 | 214 | 1 | 0 | Benjamin Smith |  | James Rosen | Content Development | Add to our catalog as a course we manage. Delivery will be through Grid at their location. Handle like ECS & IED training. $3600 per person. Handle as Regional Budget cost because "vendor" training or HQ because we set it up? Don't need to develop materials, just get in our systems so we can offer it. | In Progress |  |  | 2026-04-01 | 2026-07-31 | 2026-05-31 |  |  |  | Delivery Internal Ops | FE |  |  | Intake Review | Carlos Morales | 07Apr26-Added from Intake Review # 15233665018 08Apr26-Added subtasks to include completion of pilot session |  | 88d |  |  |  | TRUE |  |  | No | 2026-04-01 | 2026-07-31 | 2026-04-07 13:32 | jennifer.b.wright@gevernova.com
AP-0868-1 | Finalize Budgeting Approach for Grid-delivered GPP training |  | AP-0870 | Finalize Budgeting Approach for Grid-delivered GPP trainingAP-0870 | AP-0868 | AP-0868 | 1 | 1 | 0 | 1 | michele.alcantar@gevernova.com | philip.ganssmann@gevernova.com | James Rosen | Content Development | Does this belong under Region budgets or HQ budget? | Complete | TRUE | On Track | 2026-04-01 | 2026-05-29 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 43d |  |  |  |  | TRUE |  | Yes | 2026-04-01 | 2026-05-29 | 2026-04-08 08:27 | jennifer.b.wright@gevernova.com
AP-0868-2 | Load GPP Training course into our relevant systems (Module matrix, scheduling tool, etc.) |  | AP-0871 | Load GPP Training course into our relevant systems (Module matrix, scheduling tool, etc.)AP-0871 | AP-0868 | AP-0868 | 1 | 2 | 0 | 1 | Benjamin Smith | andrew.ruch@gevernova.com | James Rosen | Content Development | 1. Course outline in MM (will feed to UDC & Xyleme) - Ensure that course objectives align with relevant competencies 2. Course Schedule Template loaded into UDC (work with Scheduler) (is this needed if we’re not using our resources?) | In Progress | TRUE |  | 2026-04-01 | 2026-06-30 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 65d |  |  | TRUE |  |  |  | No | 2026-04-01 | 2026-06-30 | 2026-04-08 08:27 | jennifer.b.wright@gevernova.com
AP-0868-3 | Deliver GPP Training Pilot session |  | AP-0872 | Deliver GPP Training Pilot sessionAP-0872 | AP-0868 | AP-0868 | 1 | 3 | 0 | 1 | Benjamin Smith |  | James Rosen | Content Development | Based on pilot session feedback, finalize Material and modify outline if needed Pilot in June, close in July to incorporate feedback | Not Started | TRUE |  | 2026-06-01 | 2026-07-31 |  |  |  |  | Delivery Internal Ops | FE | [6 empty] | 45d |  | TRUE |  | TRUE |  |  | No | 2026-06-01 | 2026-07-31 | 2026-04-08 08:27 | jennifer.b.wright@gevernova.com
AP-0892 | Develop Lean Tools Training Refresher |  | AP-0892 | Develop Lean Tools Training RefresherAP-0892 | #INVALID COLUMN VALUE | Top | 0 | 215 | 0 | 0 | Benali Salim Messekine |  | Michele Alcantar | Content Development | 1. Course Materials Developed 2.Target Instructor(s) identified 3. Course Materials loaded in Xyleme 4. Course outline added/updated in Course DB (will feed course data to LMS, Kahuna, UDC & Xyleme) 5. Course Schedule Template added/updated in UDC (work with Scheduler) 6. Course added to target instructor competencies in Kahuna (if applicable) | Not Started |  |  | 2026-06-01 | 2026-11-30 |  |  |  |  | Delivery Internal Ops | FE |  |  | Other |  |  |  | 131d |  | TRUE |  |  |  |  | No | 2026-06-01 | 2026-11-30 | 2026-05-29 08:21 | jennifer.b.wright@gevernova.com

## Comments
Row 85 | 01082025 find SME. Ask Tam for I&C | Luca Martino | 01/09/25 2:53 AM
Row 99 | 01082025 Mike to send me list of SME | Luca Martino | 01/09/25 2:53 AM
Row 134 | 01082025 Mike is working with CICB for this. Waiting quotation for TTT and be instructors in Houston LC - instructors need to have master level | Luca Martino | 01/09/25 2:53 AM
Row 135 | 01082025 on hold because you can only do it in Massachussetts | Luca Martino | 01/09/25 2:54 AM
Row 136 | 01082025 include corporate aspects. Talk with the communication team (Lindsay Savage) | Luca Martino | 01/09/25 2:54 AM
Row 275 | Include Jimmy Cahill. Then 1. collect data from Mike and Kelly on competencies - 2. define list of SMEs - 3. define workout dates and location | Luca Martino | 01/09/25 10:00 AM
Row 311 | From Pixaera to normal WBT - Quality expectation is end of June | Luca Martino | 03/27/25 10:15 AM
Row 490 | 01082025 review the content to match the need (that must be defined) - create a lab for intermediate and advanced | Luca Martino | 01/09/25 2:51 AM
Row 491 | 01082025 all in Kahuna Integration GE Star box folder. It is with Kelly | Luca Martino | 01/09/25 2:51 AM
Row 497 | 01082025 (Salim & Beau) to incorporate in the bolting training - create document for recertification | Luca Martino | 01/09/25 2:52 AM
Row 498 | in the box from Mike | Luca Martino | 01/09/25 2:52 AM